## Project List
| Project Description | [31 empty] | Utility ¦CAISO Approval and FERC Rate Cases | [9 empty] | CPUC Permit Status | [9 empty] | Project Status | [7 empty] | Costs | [27 empty] | Notes
1 | 2 | 3a | 3b | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15a | 15b | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40a | 40b | 41a | 41b | 42a | 42b | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Row ¦Line No. | Project Name(s) | Latitude | Longitude | Location2 | Project Description | Project Description - What | Project Description - Action Taken | Project Description - Action Taken (2) | Project Dependencies | Primary Purpose | Secondary Purpose | NERC ¦WECC ¦CAISO Standard ¦Requirement ¦Contingency | NERC ¦WECC ¦CAISO Standard ¦Requirement ¦Contingency (2) | Last Inspection | Age of Asset | Types of Analyses | Alternative Solutions and Costs - Solutions | Alternative Solutions and Costs - Costs | CPUC Fire Threat Zone ¦Rating | Wildfire Related | RAMP | Other Environmental Factors | Project Manager | Transmission Project Size (length in miles) | Substation Project Footprint (acres) | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA and ¦or kV) | Utility Prioritization Ranking | Utility Unique ID #1 (Most Specific) | Utility Unique ID #2 (Less Specific) | Utility Unique ID #3 (Least Specific) | Changes in Unique IDs | Utility Approval | Year of Internal Utility Approval | Process(es) for Utility Approval | Long term Transmission Investment Plan Inclusion | CAISO Year | TPP Phase 3 | Year(s) when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project has been considered, approved, and ¦or expected to be considered | GIDAP-Related | CEQA Status | CEQA Status - Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status - Year | Project Status | AACE Class | Construction Start Date | Original Planned In-Service Date | Current Projected or Actual In-Service Date | Reason for Change in In-Service Date | Reason for Change in In-Service Date (2) | In-Flight Projects | Original Projected Cost or Cost Range ($000) | Cost Cap ($000) | Current Projected Total or Actual Final Cost ($000) | Actual Capital Expenditures 2019 ($000) | Actual Capital Expenditures 2020 ($000) | Actual Capital Expenditures 2021 ($000) | Actual Capital Expenditures 2022 ($000) | Actual Capital Expenditures 2023 ($000) | Actual and Forecast Capital Expenditures 2024 ($000) | Projected Capital Expenditures 2025 ($000) | Projected Capital Expenditures 2026 ($000) | Projected Capital Expenditures 2027 ($000) | Projected Capital Expenditures 2028 ($000) | Construction Work in Progress ($000) | Accrued Overhead ($000) | Accrued AFUDC ($000) | FERC: Year(s) | Dollars Put into FERC Rate Base 2020 ($000) | Dollars Put into FERC Rate Base 2021 ($000) | Dollars Put into FERC Rate Base 2022 ($000) | Dollars Put into FERC Rate Base 2023 ($000) | Dollars Put into FERC Rate Base 2024 ($000) | Percentage of Bid | Percentage and Value ($000) of Work Requested by Others Passed onto Ratepayers | Cost-Benefit Analysis | FERC Incentives | Percentage of Cost in High Voltage TAC | Percentage of Cost in Low Voltage TAC | Notes
1 | Electric Transmission Line Reliability Projects |  |  | NA | Reliability-based electric transmission projects forecasted to be less than $2M budget are included in this budget. Capital projects forecasted to be greater than $2M typically receive their own unique project-specific budget code. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 1.2 | 100 | Multiple | QB00007 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 942.6256 | 57.9682 | 167.706 | 20.266 | 1.0532 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 341.334 | 1.8306 | 0 | 0 | 0 | 0% | NA | NA | NA | 21% | 79%
2 | Transmission Substation Reliability Projects |  |  | NA | This budget is set based on historical averages and is financially authorized on an annual basis. This annual authorization requires a new funding request at the beginning of the year, which must be internally approved in order to be included within the Five-year Plan. The budget is then adjusted throughout the year to address safety and failure related issues. This budget is required to maintain the reliability and integrity of Transmission substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Other [See Notes] | Wires - Minimum Required Scope (spot repair) Alternative | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.1 | 103 | Multiple | QB00012 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 9622.1519 | 6788.9883 | 1369.6965 | 12113.6339 | 1657.1821 | 4272.3354 | 4393.0293 | 4573.0624 | 5373.6637 | 6305.8224 | 6094.1263 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 12306.7238 | 1868.6584 | 12313.7539 | -162.6004 | 2877.0452 | 0% | NA | NA | NA | 21% | 79% | [Types of Analyses] Responsive budget due to reactive work at substation; projects are under blanket budget; [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
3 | Renewal of Electric Transmission Line Easements |  |  | NA | Placeholder. The purpose of this parent work order is to renew various easements and/or permits for transmission rights of way that will expire within the next 5 years. These easements will allow SDGE to install and maintain electric transmission facilities across public and private lands. These transmission lines are an integral part of our electric transmission system. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | NA | 104 | Multiple | QB00008 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 316.0454 | 64.5809 | 30.5755 | 504.7364 | 622.3588 | 1808.5333 | 771.2197 | 777.0259 | 783.0498 | 789.2673 | 1189.4606 | NA | NA | 2020 ¦ 2021 ¦ 2023 ¦ 2024 | 559.1767 | 30.8162 | 0 | 0 | 1889.427 | 0% | NA | NA | NA | 21% | 79% | [Primary Purpose] Easement review [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
4 | Governmental Electric Transmission Line Relocations |  |  | NA | Government Electric Transmission Relocation Projects. This Budget provides funds for engineering and construction activities associated with transmission facility conflicts identified as part of Government projects. | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 3.3 | 105 | Multiple | QB00160 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1197.9294 | 83.9077 | -2.0837 | 38.0194 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 57.6932 | -1.391 | 25.387 | 0 | 0 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
5 | Distribution Substation Reliability |  |  | NA | This budget is required to maintain the reliability and integrity of distribution substations. The specific work is required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Other [See Notes] | Wires - Minimum Required Scope (spot repair) Alternative | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 4.1 | 203 | Multiple | QB00030 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 63.9288 | 512.6508 | 206.333 | 108.2515 | 1.3029 | 0 | 0 | 0 | 0 | 0 | 704.2944 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 | 38.6693 | 0 | 81.0123 | 0.63813 | -16.2655 | 0% | NA | NA | NA | 0% | 100% | [Types of Analyses] Responsive budget due to reactive work at substation; projects are under blanket budget [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
6 | Electric Distribution Tools & Equipment |  |  | NA | This blanket budget provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. | Other | New | NA | NA | Safety | Automation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | TRUE | NA |  | NA | NA | 69 | NA | NA | 206 | Multiple | QB00028 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 301.9877 | 439.5359 | 547.7187 | 196.3277 | 67.2152 | 315.8955 | 326.4499 | 334.6123 | 342.9779 | 351.5518 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 336.7511 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes; Budget supports new tools and equipment throughout the distribution system [CPUC Status] NA
7 | City of San Diego Surcharge Program (20SD) |  |  | NA | This authorization is for all work on Budget 213. Work is mandated by franchise agreement with the city of San Diego, and is 100% billable. All work orders will be estimated by DPSS and will be approved individually | Transmission Line - Underground | Relocate | NA | NA | Work requested by others | Facility Relocation | Other [See Notes] | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | NA | 69 | NA | 3.2 | 213 | Multiple | QB00029 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | Other | Other | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5684.5728 | -5031.061 | -889.38 | -331.599 | 341.509 | -13.743 | 0 | 0 | 0 | 0 | 965.446 | NA | NA | 2020 ¦ 2021 ¦ 2023 | 987.7077 | 146.3419 | 0 | -51.2275 | 0 | 0% | NA | NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] required by City of San Diego to perform work. [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA; City of San Diego is lead agency
8 | Telecommunication asset projects |  |  | NA | This is a blanket budget to support all IT Telecommunication asset projects | Other - IT | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | 925 | Multiple | QB00114 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3185.025 | 4701.039 | 3140.628 | 2251.068 | 1542.612 | 1762.809 | 259.945 | 107.682 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 1147.0951 | 1.3369 | 0 | 0 | 0 | 0% | NA | NA | NA | NA | NA
9 | Transmission Obsolete Equipment |  |  | NA | The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or which poses a safety risk will be replaced. Each year the average age of all substation equipment increases, with the oldest transformer currently 60+ years old. The ranking of substation equipment is an ongoing process and involves identifying equipment that presents a significant risk to the system. Based on the cost availability of raw materials and global demand, the lead times for major substation equipment have increased to 6 months for breakers and at least 1.5 years for transformers. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.1 | 1145 | Multiple | QBL0003 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 12591.1143 | 10255.4012 | 6162.4376 | 6689.3799 | 6559.6327 | 6372.3512 | 5646.7984 | 5874.2425 | 6101.5832 | 6392.1241 | 12885.8916 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 15523.0623 | 10296.9357 | 5823.316 | 6189.251 | 6291.3079 | 0% | NA | NA | NA | 21% | 79%
10 | Transmission System Automation |  |  | NA | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. The budget also allows us to enable remote event retrieval in non-Medium Impact substations to significantly reduce the time it takes to obtain event records and situational awareness during system disturbances. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NERC CIP Compliance | NA | NA | NA* see notes | Other [See Notes] | Other - Status Quo | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | 373MVA | 4.3 | 3171 | Multiple | QBL0001 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3777.8453 | 3694.7636 | 7014.3563 | 8073.6062 | 4722.7067 | 4338.3835 | 1250.1414 | 1366.1268 | 1610.011 | 1430.2177 | 14421.6172 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 161.0225 | 251.9798 | 11400.0098 | 4773.1216 | 14505.3557 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [Types of Analyses] Information security [CPUC Status] NA
11 | Ocean Ranch Substation |  |  | Oceanside, San Diego | Install a new 69/12kV substation in the North Vista/Oceanside area. Current substations that support this load (Melrose, Morro Hill, Oceanside, and San Luis Rey) are expected to be at 85% aggregate loading in 2016 and 96% in 2021. | Substation - Multiple | New | NA | NA | Load Growth | New Substation | Other [See Notes] | NA | 2023-09-21 07:40 | NA* see notes | Other [See Notes] | Wires - New Substation Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 1.0084 | 69 | 69kV | 4.2 | 5253 | 2014-00047-ZZ | TBD | NA | FALSE | 2014-02-25 | Work Order Authorization | 2010 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2017-10-02 | IS/MND | NA | CPUC | NA | PTC | 2017-03-06 | Approved | 2017 | Operational | NA | 2018-01-22 | 2019-06-01 | 2019-02-07 | Completed Early | NA | FALSE | 54404 | NA | 28413.0071 | 9263.7246 | 317.3437 | 4.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 264.5629 | 2.3943 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] Load growth in the area (Distribution Planning load forecast driver) [Age of Asset] New Substation [Types of Analyses] Distribution Planning
12 | South Orange County Reliability Enhancement |  |  | San Juan Capistrano, Orange ¦ San Clemente, Orange | To rebuild the existing Capistrano Substation, which is currently a 138/12kV distribution substation to a 230/138/12kV. Remove TL13835 (SMO-LNL) between Talega Substation and Capistrano Substation. Open TL23007 (SONGS-TA) at Talega Substation and loop into Capistrano Substation two new 230kV' TLs (SONGS-CP230kV & CP-TA 230kV). Re-arrange 138kV TL's 13833, 138736, and 13812 bay positions at Talega to allow for the termination of TL13835 (SMO-TA) at Talega Substation. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Load Growth | Substation Capacity | NERC TPL Standards | NA | 2023-10-27 13:18 | 55; 62; 52;56; 54; 19 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Transmission Foundations At Talega Canyon Containing High Levels Of Sulfate. Mitigated By Installing Cmp To Protect Concrete Foundations |  | 9.1339 | 6 | 230 | 230kV | 2.1 | 6129 | 2014-00068-ZZ | 2066680, 2651832, 2652342, 2651833, 2652278, 5983099, 5050193, 5983101, 5983102, 5983103, 5983104, 5983105, 5983106, 5983107, 5983836, 5983837, 2800095, 2455441, 5984480, 5984481, 2389801, 2652340 | NA | FALSE | 2017-06-01 | Work Order Authorization | 2006 | 2011 | FALSE | 2009 ¦ 2010 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-04-25 | EIR | NA | CPUC | NA | CPCN | 2012-05-18 | Approved | 2016 | Construction (over 75%) | NA | 2018-06-29 | 2015-05-18 | 2024-11-01 | Construction Delays | Construction Delays | TRUE | 381000 | 419,100 ¦ CPCN | 381000 | 0 | 0 | 0 | 0 | 32236.7226 | 10088.2024 | 0 | 0 | 0 | 0 | 34782.5986 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 78952.2982 | 129188.5734 | 5201.7747 | 91820.4274 | 41225.1162 | 0% | NA | NA | NA | 100% | 0% | [Alternative Solutions and Costs - Solutions] [Alternative Solutions and Costs - Costs] SOCRUP Alternative 1: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and build a new Escondido to Capistrano 230 kV line using existing right-of-way. Estimated cost for this alternative is $454.8 million. 2. SOCRUP Alternative 2: Rebuild Capistrano 138kV substation (aging infrastructure maintenance project), reconductor 138kV lines – Talega – Pico, Talega – Laguna Niguel, Talega – Trabuco, Capistrano – Trabuco, Talega – Rancho Mission Viejo, and upgrade SONGS – Talega 230 kV lines. Upgrade two 230/138 kV transformer banks at Talega. Estimated cost for this alternative is $347.6 million. 3. SOCRUP Alternative 3: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and tap off a 230 kV line to Capistrano from existing Escondido – Talega 230 kV line. Estimated cost for this alternative is $364.8 million. Approved Alternative
13 | Emergency Transformer & Switchgear |  |  | NA | This budget supports the restoration of service to our distribution customers following outages caused by equipment failure by purchasing additional emergency spare and mobile equipment. Spare equipment is necessary to provide construction and operations with the appropriate spares to replacement equipment under failure conditions. Spare equipment is typically use for critical situations and the stock must be kept up to date to minimize chances for mismatch in field. | Substation - Multiple | Replace | NA | NA | Reliability | Substation Reliability | NERC TPL Standards | NA | NA | NA* see notes | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 | 28MVA | 4.1 | 6254 | Multiple | QBL0024 | NA | TRUE | 2016-05-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 375.7862 | 288.8328 | 987.1972 | 277.6598 | 266.417 | 1544.4427 | 487.3079 | 499.4632 | 510.3523 | 521.2302 | 431.1484 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 521.1663 | 1171.5107 | 333.7874 | 266.4452 | 148.2544 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
14 | Fiber Build Initiative |  |  | NA | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. 2020 has (20) active projects at various stages of engineering and construction. All projects to date are exempt from CPUC permitting. | Other | New | NA | NA | Reliability | NERC CIP Compliance | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 4.3 | 7144 | Multiple | QBL0025 | NA | TRUE | 2016-09-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 4055.5234 | 4950.4495 | 5415.5568 | 6205.0808 | 5536.0709 | 8160.7856 | 8112.2365 | 9632.1247 | 9823.5818 | 10322.6232 | 29636.4761 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4896.5473 | 704.6285 | 4239.7195 | 44.6794 | 2735.3451 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes. Program consists of multiple same scope projects per transmission line with separate environmental permits. [CPUC Status] NA
15 | Cleveland National Forest (CNF) |  |  | Julian, San Diego ¦ Alpine, San Diego ¦ Pine Valley, San Diego ¦ San Diego, San Diego County | These projects involve fire hardening five 69kV transmission lines (TL625, TL6931, 629, 682 and 6923) and segments of seven distribution lines (C78, C79, C222, C157, C440, C442 and C449) which traverse in and out of the Cleveland National Forest (CNF). In addition to wood to steel conversion, TL626 will be removed from service and approximately 27 miles of overhead 12kV distribution will be converted to underground. The project also includes attaining a Master Special Use Permit from the US Forest Service to replace over 70 expired Special Use Permits for existing SDG&E facilities on the CNF. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-02-07 ¦ 2023-07-01 ¦ 2023-09-07 ¦ 2021-02-09 ¦ 2021-04-13 | NA ¦ NA ¦ NA ¦ NA ¦ 27 * see notes | NA | NA | NA | HFTD Tier 3 ¦ Zone 1 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 224.33 | NA | 69 | NA | 1.1 | 8165 | 2014-00071-ZZ | 2052282, 2505207, 2587013, 2596316, 2650658, 2651101, 2651102, 2651103, 2651104, 2651107, 2651115, 2651116, 2651275, 2651276, 2651305, 2651306, 2651307, 2651308, 2651309, 2651345, 2651347, 2651348, 2651349, 2651350, 2651352, 2651572, 2651573, 2651770, 2901463, 2901472, 2901492, 2901493, 2901660, 2902561, 2983110, 2986990, 2986991, 2986994, 2989040 | NA | TRUE | 2016-05-10 | Work Order Authorization | 2008 | NA | FALSE | NA | NA | NA | FALSE | NA | 2016-01-01 | EIR | EIS | CPUC | FOREST SERVICE | PTC | 2012-10-17 | Approved | 2016 | Construction (over 75%) | NA | 2016-09-30 | 2020 | 2021-10-01 | Permitting | Permitting | TRUE | 680000 | NA | 423532.1888 | 69122 | 107278 | 12697 | 1535 | 1338 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 151423.1757 | 14320.6991 | 684.165 | -0.30186 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] asset age data discrepancy being corrected for future submission
16 | TL6926 - Wood to Steel |  |  | Valley Center, San Diego | Fire harden a portion of TL6926 by replacing approximately 50 wood poles with equivalent steel poles in the high fire threat and wind-prone areas. TL6926 is a single circuit 69 kV transmission line located between the Valley Center Substation and the Rincon Substation. Approximately one mile of the line will be reconductored. The line will be fire hardened between poles Z12820 and Z114811, with the exception of the portion located adjacent to Valley Center Road near the Rincon Casino. Approximately one mile of the transmission line will be reconductored. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-09-01 | 45 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 4.6374 | NA | 69 | NA | 1.1 | 9132 | 2014-00061-ZZ | 2902140, 2652399 | NA | TRUE | 2011-06-15 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2019-11-13 | Approved | 2020 | Operational | NA | 2020-10-19 | 2020-10-31 | 2023-06-30 | Permitting | NA | TRUE | 19559.489 | NA | 102428.8017 | 1115.9209 | 16086.0507 | 54034.4148 | 10288.0922 | 2723.7517 | 726.0646 | 1834.8836 | 0 | 0 | 0 | 119.9926 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 100051.9875 | 2291.9576 | 653.5931 | 0% | NA | NA | NA | 0% | 100% | [CPUC Filing Type] Advice Letter/ Project Completed with temporary shoo-fly configuration
17 | TL649 - Wood to Steel - Otay-San Ysidro-Border |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | A portion of TL649 is within the fire and wind prone area. Replace a portion of TL649 with steel poles in order to maintain existing electric transmission in high fire threat & wind prone areas in SDG&E territory. TL649 is a 69 kV single-circuit transmission line located between pole Z188714 & pole Z31758. The proposed project consists of the following components: Replace approximately 116 existing wood power line and interest distribution line poles with galvanized steel structures. Approx. half of the replacement poles will be direct buried with the other half being engineered foundations (pier & micropile).Reroute approximately 130 feet of existing underground distribution lines. Conduct overhead work on one existing pole and transfer existing power line conductors to the new steel poles. Replace the existing distribution conductor with new ACSR distribution conductor. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-09-18 | 34 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.7111 | NA | 69 | NA | 1.1 | 9137 | 2017-0120 | TBD | NA | TRUE | 2019-07-12 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | NA | IS/MND | NA | CPUC | NA | PTC | 2015-08-10 | Approved | 2019 | Operational | NA | 2019-07-11 | NA | 2020-02-22 | NA | NA | FALSE | 42500 | NA | 29685.145 | 19546.9482 | 6117.3729 | 64.463 | 1.3955 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 29658.6315 | 54.952 | 1.1916 | 0 | 0 | 0% | NA | NA | NA | 0% | 100%
18 | TL686 Wood-to-Steel/Reliability Upgrades |  |  | San Diego County | TL686 Wood-to-Steel will include the replacement of 182 wood and wood equivalent steel (SW) poles with 120 new poles. Scope includes the reconductoring of 14.6 miles of 69kV transmission and associated 12kV distribution underbuild (where underbuild is present) from Warners substation to just outside the Tier 2 HFTD (ending at structure Z118409). All replacements will be either direct-buried SW poles or foundation steel poles. Direct-buried transmission SW and distribution SW Round (SWR) poles shall be backfilled with concrete and gravel. Engineered steel poles shall have either drilled pier or micropile foundations. Per SDG&E’s fire hardening standards, traditional 69 kV design and construction standards with additional phase spacing and insulation shall be used and guy anchors shall be avoided. Shield wire with a fiber (OPGW) will be added to protect phase conductors from lightning damage. All transmission conductors in this project shall be reconductored. All poles will be designed to accommodate one level of third-party communication. | Transmission Line - Pole/Tower | Replace | Removal | 23126 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-01-27 | 45 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 24.6759 | NA | 69 | NA | 1.1 | 9142 | 2018-0161 | 2984061 | NA | TRUE | 2019-01-01 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | NA | BLM | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-10-31 | 2024-09-30 | 2027-04-21 | Land Rights | Permitting | TRUE | 10181.003 | NA | 15272.6679 | 1138.5509 | 1373.4769 | 1641.5459 | 873.8694 | 672.9783 | 1564.4954 | 29874.0134 | 69848.8954 | 26798.0909 | 0 | 9605.6563 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.62% ¦ Copperleaf | NA | 0% | 100% | [NEPA Document Type] NEPA document/process yet to be finalized with BLM [CPUC Status] NA
19 | TL676 Reconductor (Mission-Mesa Heights) |  |  | San Diego, San Diego | The TL676 project is a reconductor project between Mesa Heights Substation and Mission Substation. It includes reconductoring approx. 4.3 miles of transmission line (TL676) with single 900 ACSS/AW, reconductoring approx. 3.7 miles of distribution underbuild with single 636 ACRS/AW, and converting sections of the 69kV out of both substations with underground getaways. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Age/Condition - Replace Wood Poles | CAISO Requirement | NA | 2023-05-22 | 24 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.9515 | NA | 69 ¦138 | NA | 2.1 | 9153 | 2011-00017-ZZ | 2982360, 2382250, 2382251, 2382252, 2382253 | NA | FALSE | 2016-09-01 | Work Order Authorization | 2011 | 2011 | FALSE | 2010 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2017-07-25 | Approved | 2017 | Operational | NA | 2018-06-24 | 2015-06-01 | 2019-06-07 | Prioritization | NA | FALSE | 45000 | NA | 38557.1668 | 11638.1785 | 361.4143 | 52.1278 | 0.13369 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 3884.255 | 46.9643 | 0.13369 | 0 | 0 | 0% | NA | NA | NA | 0% | 100%
20 | Overstressed Breakers |  |  | NA | Replace overstressed breakers as identified at the following substations : Bay Boulevard, Mission, Sycamore Canyon, San Luis Rey, Miguel | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition | NERC TPL Standards | NA | NA | NA* see notes | Short Circuit Duty Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 138 | Multiple | 2.1 | 9170 | Multiple | QBL0061 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3402.8882 | 1520.5744 | 3349.3163 | 2045.4696 | 472.9499 | 1777.7082 | 3473.9399 | 3654.9542 | 3819.9798 | 3769.4298 | 3207.367 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 | 36.8775 | 0 | 8460.4178 | 109.4131 | 1159.6408 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
21 | Synchrophasors (PMU/WASA) |  |  | NA | This project provides funds for the installation, upgrade, and expansion of SDG&E’s Phasor Measurement Units (PMUs), commonly referred to as Synchronized Phasors or Synchrophasors which will be used for monitoring the health of the Electric System, Wide Area situational Awareness (WASA) and Wide Area Monitoring Protection and Control (WAMPAC). The project will install new PMUs or upgrade existing PMUs and install Phasor Data Concentrators (PDC), hardware, associated communication network, and software. | Substation - Other Equipment | Replace | NA | NA | Reliability | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 4.3 | 10138 | Multiple | QBL0062 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 7200.9894 | 6065.5563 | 6441.7652 | 2415.9565 | 2130.8099 | 3206.5252 | 4224.6563 | 3995.6072 | 3993.7113 | 3806.9681 | 5523.29 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 248.6809 | 23308.7689 | 32.6132 | 1278.6712 | 3231.7266 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
22 | TL690E Reconductor (Camp Pendleton) |  |  | Camp Pendleton, San Diego | Replace approx. 72 wood poles with overhead steel poles and/or underground cabling. Reconductor approx. 5.4 mi from Stuart Tap to Las Pulgas Substation. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2021-05-28 | 60 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 5.3506 | NA | 69 | NA | 1.1 | 10143 | 2014-00050-ZZ | 2981430, 5981369, 5981957 | NA | FALSE | 2020-11-11 | Work Order Authorization | 2012 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Other [See Notes] | NA | Exempted | Other [See Notes] | CPUC | MCBCP | PTC | 2024-12-16 | To be Filed | 2026 | Engineering less than 50% complete | NA | 2027-02-10 | 2015-06-01 | 2028-02-18 | Project Design | Permitting | TRUE | 26232.1568 | NA | 26232.1568 | 920.89 | 1191.9396 | 989.8139 | 1042.8332 | 845.2716 | 523.5006 | 3303.9606 | 850.954 | 19389.0914 | 10132.5725 | 12550.9072 | NA | NA | 2020 ¦ 2023 ¦ 2024 | 0.12957 | 0 | 0 | 0 | 0 | 0% | NA | 2.15% ¦ Copperleaf | NA | 0% | 100% | [CEQA Status] Likely will be CatEx for CPUC; NEPA permit TBD by MCBCP
23 | TL691 Wood to Steel and Reconductor (Avocado - Monserate Camp Pendleton) |  |  | Fallbrook, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL691 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2020-10-10 | 51 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.5485 | NA | 69 | NA | 1.1 | 10144 | 2014-00051-ZZ | 2981470, 5981963 | NA | TRUE | 2020-11-19 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2019-11-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Advice Letter | 2020-12-03 | Approved | 2021 | Construction (25%-50%) | NA | 2023-04-28 | 2024-04-18 | 2024-05-31 | NA | NA | TRUE | 63239.0651 | NA | 63239.0651 | 370.1681 | 1203.3315 | 3504.6217 | 1725.0428 | 16949.5984 | 8699.4186 | 0 | 0 | 0 | 0 | 31979.6034 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 44143.3852 | 0% | NA | 2.61% ¦ Copperleaf | NA | 0% | 100% | [CEQA Status]CPUC CatEx
24 | TL692 Wood to Steel (Camp Pendleton) |  |  | Camp Pendleton, San Diego | This project will replace existing wood poles along TL692 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-06-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.6533 | NA | 69 | NA | 1.1 | 10145 | 2014-00225-ZZ | 2981410, 5981367, 5983108 | NA | TRUE | 2011-01-11 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2019-07-19 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-17 | NA | 2021-11-01 | NA | NA | TRUE | 34365.984 | NA | 17350.09 | 778.7658 | 2900.3357 | 12457.7287 | 1531.8875 | -47.4758 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 16098.9216 | 1298.8384 | -47.67 | 0 | 0% | NA | NA | NA | 0% | 100% | [CEQA Status] CPUC CatEx [CPUC Status] NA
25 | TL695 TL6971 Reconductor (Camp Pendleton) |  |  | San Clemente, Orange | Transmission Planning has identified TL695 as a NERC Category B violation therefore the conductor size must be upgraded to an acceptable capacity. This project will also replace existing wood poles along TL695 within the Fire Threat Zone with new steel poles and associated hardware. Transmission Engineering will double circuit TL695 (and future TL6971) from Basilone Substation to Japanese Mesa Substation, cross the Edison 230kV corridor, travel north along the existing 138kV corridor to Talega Substation. | Transmission Line - Multiple | Replace | New | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2022-09-13 | 55 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.8008 | NA | 69 | NA | 1.1 | 10146 | 2014-00074-ZZ | 2981440, 5981952, 5981987, 5983032 | NA | FALSE | 2020-11-12 | Work Order Authorization | 2012 | 2012 | FALSE | 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | CEQA Draft Published | 2017-07-07 | IS/MND | EA | CPUC | MCBCP | PTC | 2016-04-25 | Approved | 2018 | Permitting | NA | 2024-10-17 | 2016 | 2026-07-23 | Project Design | Permitting | TRUE | 36049.0968 | NA | 36049.0968 | 708.1595 | 913.4336 | 2289.415 | 1541.6075 | 635.8347 | 3810.7685 | 13011.7927 | 10753.4903 | 2009.5082 | 0 | 15743.1039 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 3.06% ¦ Copperleaf | NA | 0% | 100% | [NEPA Document Type] NEPA permit pending
26 | TL6912 Wood to Steel Replacement (Camp Pendleton) |  |  | Oceanside, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL6912 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-07-19 | 30 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.5058 | NA | 69 | NA | 1.1 | 10149 | 2022-3073 | 2981450 | NA | TRUE | 2020-11-02 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2017-12-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-01-27 | NA | 2020-09-04 | NA | NA | TRUE | 25191.7609 | NA | 14098.9451 | 2134.6523 | 9929.1867 | 1277.2013 | -29.4637 | 0 | 84.9 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 13243.6626 | 1223.2109 | -367.9284 | 0 | 76.41 | 0% | NA | NA | NA | 0% | 100% | [CEQA Status] Project complete. Project ID Replaced From 2014-00073 to 2022-3073 [CPUC Status] NA
27 | TL663 Reconductor (Mission-Kearny) |  |  | San Diego, San Diego | Construction of this project provides a long term “wires” mitigation for the identified NERC CAT B reliability criteria indications. Availability of the short term non wires option of depending on the pre contingency dispatch of the Kearny gas turbines to provide loading relief is no longer available after 2013. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | T-Line Capacity | NERC TPL Standards | NA | 2022-08-11 | NA* see notes | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.5902 | NA | 69 | NA | 2.1 | 11126 | 2011-00018-ZZ | 2982340, 2368750, 2368751, 2982341, 2982342, 2982343, 2982344, 2982345, 2982346, 2982347, 2982348, 2982349 | NA | FALSE | 2016-04-01 | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2017-05-31 | Approved | 2017 | Operational | NA | 2017-12-13 | 2015-06-01 | 2020-02-26 | Bundling Dependencies | Permitting | TRUE | 43000 | NA | 39879.8863 | 6333.9957 | 2446.4842 | 545.3879 | 558.5325 | 67.3847 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 38014.0634 | 1215.1722 | 589.0169 | 61.6338 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission
28 | TL644 Reconductor (Bay Blvd - Sweetwater) |  |  | National City, San Diego ¦ Chula Vista, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NERC TPL Standards | NA | 2022-10-19 | NA* see notes | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2.0338 | NA | 69 | NA | 2.1 | 11154 | 2011-00021-ZZ | 2982810 | NA | FALSE | 2018-01-01 | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-15 | 2013-06-01 | 2022-05-15 | Permitting | Prioritization | TRUE | 9464.457 | NA | 10692.0315 | 960.496 | 187.8435 | 2482.2866 | 2407.6727 | 702.5488 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 10022.2501 | 669.7814 | 0 | 0% | NA | NA | NA | 0% | 100% | [Primary Purpose] NERC Category B Criteria [Age of Asset] Asset age data discrepancy being corrected for future submission [CPUC Status] NA
29 | Automated Fault Location (TEAM) |  |  | NA | This project provides funds for installation, upgrade, and expansion of SDG&E's Event Reporting Software and hardware to include Automated Fault Locator. This new system known as TEAM will provide accurate fault location within seconds by measuring the parameters at both ends of the line (multiple ends on multi-terminal lines) and time synchronizing the events with GPS clock. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Other [See Notes] | Automation | NA | NA | NA | NA* see notes | Protection Studies | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 12129 | Multiple | QBL0063 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 448.5463 | 424.6434 | 537.9743 | 82.3357 | 7.0931 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 1456.9706 | 80.6676 | 40.988 | 0 | 0% | NA | NA | NA | 100% | 0% | [Primary Purpose] System Protection [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
30 | Substation SCADA Expansion- Transmission |  |  | NA | The project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at transmission substations. Additionally, this project improves the protection of SDG&E’s transmission system to provide fast isolation for faults and system disturbances. Includes upgrading relays including increased security, differential protection, and traveling wave fault finding technology to reduce restoration times. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Install SCADA/RTU | NERC PRC Compliance | NA | NA | NA* see notes | Protection Studies | Other - Status Quo | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 12132 | Multiple | QBL0064 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 888.666 | 723.9364 | 1268.569 | 1008.3142 | 1181.8055 | 3105.142 | 2786.9594 | 3424.4163 | 3646.5487 | 3707.2472 | 1657.7121 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 2318.2561 | 510.4552 | 756.3739 | 2789.1623 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
31 | TL639 Wood to Steel Replacement |  |  | San Diego, San Diego | The TL639 Fire Hardening and Reconductor Project consists of installing new steel structures along the 69kV tie line between Elliott Substation and Structure Z100981, located inside Sycamore Canyon. The replacement structures from TL639 Elliott to Structure Z379545 will be constructed in conjunction with TL636, since most of the structures in that portion are single pole double circuit. TL639 Wood to Steel will cover pole replacements starting at Sycamore Canyon Substation to Structure Z379545. The project spans approximately 4.8 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2019-11-16 | 44 | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 8.1767 | NA | 69 | NA | 1.1 | 12136 | 2012-00005-ZZ | 2983340, 2983341 | NA | TRUE | 2023-10-04 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-31 | 2026-12-31 | 2023-12-04 | NA | NA | TRUE | 17883.8405 | NA | 17883.8405 | 351.4966 | 475.69 | 838.6306 | 2314.2942 | 5093.5888 | 1113.7353 | 0 | 0 | 0 | 0 | 10444.0574 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 9663.2159 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
32 | TL6916 Wood to Steel Replacement |  |  | San Diego, San Diego | APPROXIMATELY 5 MILES OF FIRE HARDENING ON TL6916 WOOD TO STEEL PROJECT. ALL EXISTING WOOD TRANSMISSION POLES WILL BE REMOVED FROM SERVICE/REPLACED WITH PRE ENGINEERED POLES OR ENGINEERED STEEL POLES AND ASSOCIATED DISTRIBUTION WOOD POLES ON CIR434 AND CIR920 WILL BE REPLACED WITH STEEL POLES. NEW CONDUCTOR 900ACSS WILL REPLACE EXISTING 900ACSS CONDUCTOR DUE TO CONSTRUCTION AND OUTAGE CONSTRAINTS OF EXISTING CONFIGURATION. DISTRIBUTION CONDUCTOR WILL BE UPGRADED TO 636 AND #2 ACSR CONDUCTOR. 1-96CT ADSS WILL BE INSTALLED FROM Z678465 TO Z100980. 31 NEW SW POLES WILL BE INSTALLED ALONG WITH 12 NEW ENGINEERED STEEL POLES. WE PREDICT 9 DRILLED PIER FOUNDATIONS AND 3 NEW MICROPILE FOUNDATIONS WILL BE INSTALLED. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-11-04 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.7679 | NA | 69 | NA | 1.1 | 12137 | 2012-00006-ZZ | 2983350, 2983351 | NA | TRUE | 2018-01-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2026-12-31 | 2022-07-11 | NA | NA | TRUE | 24362.992 | NA | 14436.8476 | 536.7097 | 363.6876 | 1587.8671 | 11993.0233 | 200.154 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 14264.7751 | 172.0725 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
33 | TL615 TL659 Direct Buried Cable Replacement (Cabrillo - Point Loma) |  |  | San Diego, San Diego | Replace approximately six (6) miles of direct buried cable on TL615 and TL659 within the streets of Point Loma into a new double circuit 69kV duct package infrastructure with off-setting substructures in an effort to mitigate reliability issues associated with aging direct buried cable systems. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2022-04-15 | 47 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.7 | NA | 69 | NA | 4.1 | 12138 | 2012-00011-ZZ | QS00068 | NA | TRUE | 2021-09-16 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-04-11 | NA | 2026-09-17 | Permitting | Land Rights | FALSE | 46528 | NA | NA | 2100.0192 | 580.4096 | 13084.0079 | 1012.4843 | 2582.5834 | 11564.1221 | 8190.8722 | 153.693 | 0 | 0 | 28863.733 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] CPUC filing requirements to be determined
34 | TL633 Overhead Reconductor |  |  | San Diego, San Diego | The CAISO has approved this reconductor project, which is required to mitigate a projected overload in 2015. In order to accomplish this, the Project will upgrade TL6913 (Poway - Pomerado) and all associated relay and control equipment to achieve a minimum 148 MVA continuous/emergency rating. By reconductoring the existing wire from 1033.5 ACSR/AW to 900 ACSS/AW, the current line rating of 136MW will improve to 174MW. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Load Growth | Line Reconductoring | NA | NA | 2023-05-02 | 34 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 2.88 | NA | 69 | NA | 2.1 | 12139 | 2012-00028-ZZ | 2982932, 2988470, P650576, 2983360, 2983361, 2983362, 2983363, 2988471 | NA | FALSE | 2016-01-01 | Work Order Authorization | 2012 | 2012 | FALSE | 2011 ¦2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | NA | Advice Letter | 2017-11-15 | Approved | 2017 | Operational | NA | 2019-11-07 | 2015-06-01 | 2019-11-07 | Permitting | Land Rights | FALSE | 46190.46 | NA | 48544.1722 | 19414.3973 | 1254.123 | 71.5639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 48477.913 | 66.2591 | -2.5466e-14 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Wildfire Related] Reconductor HFTD Tier 2
35 | Merchant Switchyard Ownership/NV Energy Vacate Bay |  |  | Boulder City, Clark | On October 1, 2011 SDG&E acquired the desert star energy center (DSEC), A 480 MW Power Plant in Boulder City, Nevada, The adjacent Eldorado-Merchant 230kV transmission line requires upgrades to accommodate the change in boundary authority from NV energy to CAISO. This job will include the design and construction of facilities necessary for SDG&E to gain operational control of merchant. | Other | NA | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-13 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 72.1226 | 230 | NA | 2.1 | 12140 | 2014-00227-ZZ | TBD | NA | TRUE | 2013-05-13 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2014-09-15 | NA | 2015-07-11 | NA | NA | FALSE | 11528.455 | NA | 14927.5086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 14927.5086 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [Last Inspection] Acquisition of Substation in 2011; [CPUC Status] FERC Only
36 | TL636 Wood to Steel Replacement |  |  | San Diego, San Diego | Replacing wood pole with steel equivalent from Northern structure at Z200694 to Elliott Substation. The purpose for this project is for fire hardening of this corridor due to it being within the FTZ and classified as high to extreme fire danger. The project spans approximately 6.07 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2023-03-02 | NA* see notes | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 5.8672 | NA | 69 | NA | 1.1 | 12144 | 2012-00015-ZZ | 2983940, 2983942 | NA | TRUE | 2022-07-07 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-18 | 2026-12-31 | 2022-10-17 | NA | NA | TRUE | 25131.9882 | NA | 21257.1391 | 575.0215 | 996.1296 | 2457.9571 | 15743.3178 | 1644.9849 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 21132.2362 | 124.9029 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
37 | TL694 Wood to Steel |  |  | Fallbrook, San Diego ¦ Oceanside, San Diego | This project replaces 4.8 miles, approximately 80 wood structures, to direct-embed and engineered steel poles and replace the existing 636 ASCR/AW conductor to harden the electric transmission and distribution systems and increase reliability in the region. This project will also mitigate some existing access issues to the structures. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-07-17 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.85 | NA | 69 | NA | 1.1 | 12149 | 2012-00014-ZZ | 2984281, 2984280 | NA | TRUE | 2021-02-09 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-01-05 | 2026-12-31 | 2026-01-13 | NA | NA | TRUE | 36464.0897 | NA | 36464.0897 | 123.3571 | 502.4708 | 598.3269 | 401.3375 | 545.3317 | 3707.8422 | 16867.2352 | 735.7592 | 0 | 0 | 4021.611 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 3288.0369 | 0% | NA | 1.01% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
38 | TL13831 Wood to Steel Replacement (Talega - Rancho Mission Viejo) |  |  | Orange County | The purpose of project is to replace approximately 72 wood poles for steel equivalent from Rancho Mission Viejo to Talega Substation for fire hardening. The project spans approximately 6.46 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-03-18 | 29 | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 6.377 | NA | 138 | NA | 1.1 | 12150 | 2012-00019-ZZ | 2984300, 2984301, 2369410, 2369411 | NA | TRUE | 2018-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-15 | 2026-12-31 | 2023-04-23 | NA | NA | TRUE | 41615.025 | NA | 19904.0839 | 923.1502 | 533.1916 | 2434.0244 | 12550.1509 | 4903.2732 | 0 | 0 | 0 | 0 | 0 | 132.7427 | NA | NA | 2023 | 0 | 0 | 0 | 19904.0839 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
39 | TL13838 Wood to Steel Replacement (Margarita - Rancho Mission Viejo) |  |  | Orange County | This project replaces nine poles with steel, approximately 1.4 miles of 1033.5ACSR/AW, insulators and hardware. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-03-09 | 11 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.6748 | NA | 138 | NA | 1.1 | 12152 | 2012-00020-ZZ | 2984290, 2984291 | NA | TRUE | 2018-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-09-24 | 2026-12-31 | 2022-01-17 | NA | NA | TRUE | 4653.916 | NA | 2573.3341 | 277.5555 | 271.6898 | 1173.2442 | 428.2031 | 245.0556 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 2341.0556 | 232.2785 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
40 | TL600 Reliability Pole Replacements |  |  | San Diego, San Diego | This project replaces an existing 33 (between Phases 1, 2, and 3) transmission structures on TL600. | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | CAISO Requirement | NA | 2023-05-22 | 63 | NA | Wires - Reconductor/Line Rebuild Alternative | $10 Mil -$15 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.9991 | NA | 69 | NA | 4.1 | 12156 | 2012-00023-ZZ | 2984460, 2984461, 2984462, 2306700, 2306701, 2984463 | NA | TRUE | 2020-12-14 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | 2012-01-01 | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2013-02-01 | See Notes | 2022-08-29 | NA | NA | TRUE | 13591.4008 | NA | 7801.1408 | 713.7244 | 1466.0789 | 1956.4616 | 849.8624 | 435.355 | 198.0502 | 0 | 0 | 0 | 0 | 224.1628 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 6109.9589 | 376.9468 | 188.1477 | 0% | NA | NA | NA | 0% | 100% | [CEQA Status] This was a phased project. Different phases had different target completion dates. [CPUC Status] NA
41 | Aerial Marking Implementation (Risk Mgmt and Low Level Safety Flights) |  |  | NA | This project will add aerial marker balls and /or lighting at locations identified by Transmission Engineering, Transmission maintenance personnel, or AL&M support team as safety concerns or necessary for FAA compliance. These locations fall under SDG&E’s expanded aerial lighting and marking policy that seeks to reduce the risk of collisions and improve safety. This will be an ongoing project as Transmission Construction & Maintenance may provide additional locations with safety concerns and for the Aerial Lighting and Marking company initiative. The work includes analyzing current structures for strength and clearance to add marking, replacing structures as necessary, and installing aerial marking and/or lighting. | Transmission Line - Multiple | NA | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.2 | 12159 | Multiple | P162638 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5183.3007 | 4907.7989 | 794.8546 | 123.3039 | 13.8643 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 3236.1865 | 5710.4218 | 125.5466 | 13.395 | 0 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
42 | TL664 Sorrento to Miramar Customer Relocation |  |  | San Diego, San Diego | TL664 Sorrento Miramar Customer Relocation | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2022-07-09 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.19576 | NA | 69 | NA | 3.3 | 13123 | 2021-2082 | TBD | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2024-04-16 | To be Filed | 2024 | On Hold | NA | 2025-01-30 | NA | 2025-04-16 | NA | NA | FALSE | 2312 | NA | 2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] asset age data discrepancy being corrected for future submission [CEQA Status] Project on hold at 60% design milestone. [CEQA Document Type] 100% Customer requested relocation requiring CPUC Advice Letter.
43 | SX-PQ 230kV Transmission Line |  |  | San Diego, San Diego | The Proposed Project includes approximately 16.7 linear miles of transmission line as well as associated access roads and work areas, all of which are located primarily within the City of San Diego, a small portion of the City of Poway, and on the extreme northern portion of Marine Corps Air Station (MCAS) Miramar. The Proposed Project will result in a new 230 kV transmission line that will connect the existing Sycamore Canyon and Peñasquitos Substations through utilization of existing SDG&E facilities, ROWs, and City of San Diego franchise position. Segment A - Construction of approximately 8.31 miles of new 230 kV transmission line on new tubular steel poles all within existing SDG&E ROW located between the existing Sycamore Canyon Substation and Carmel Valley Road Segment B - Install new, approximately 2.84-mile 230 kV underground transmission line in Carmel Valley Road utilizing existing franchise position for almost the entire segment Segment C - Install new 230 kV conductor on the existing 230 kV steel structures and one new tubular steel pole all within existing SDG&E ROW located between Carmel Valley Road and Peñasquitos Junction Segment D - Install new 230 kV conductor on existing double-circuit 230 kV steel lattice towers and relocate two existing 69 kV power lines to new tubular steel poles all within existing SDG&E ROW located between the Peñasquitos Junction and the existing Peñasquitos Substation Minor modifications of the existing Sycamore Canyon and Peñasquitos Substations to allow for connection of the new 230 kV transmission line | Transmission Line - Multiple | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | CAISO Requirement | NA | 2023-06-30 | NA* see notes | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 13.3942 | NA | 230 | NA | 2.1 | 13128 | 2014-00044-ZZ | 2650975 | NA | FALSE | 2016-11-01 | Work Order Authorization | 2013 | 2013 | TRUE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-10-13 | EIR | NA | CPUC | NA | CPCN | 2014-04-07 | Approved | 2016 | Operational | NA | 2017-01-03 | 2017-06-01 | 2018-08-29 | Construction Delays | NA | TRUE | 260000 | 260,000 ¦ CPCN | 255511.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 4034.3556 | 142.2257 | -0.00046 | -5.4001 | 0 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] new transmission line [Alternative Solutions and Costs - Solutions ] Alternatives Analysis listed in FEIR see attached link https://ia.cpuc.ca.gov/Environment/info/panoramaenv/Sycamore_Penasquitos/FEIR.html
44 | DelMar Reconfiguration Project |  |  | Del Mar, San Diego ¦ Solano Beach, San Diego ¦ San Diego, San Diego | Eliminate the need for ongoing O&M work in environmentally sensitive areas (San Dieguito Lagoon, Torrey Pines State Park and Los Penasquitos Lagoon) by removing TL666D from service (Phase IV). Install a new underground 69kV transmission line segment along Via de la Valle, which will provide a new TL connecting the Del Mar Substation to the North City West Substation. This will replace the existing TL 674A tap that will be eliminated in Phase II as part of the Rancho Santa Fe Tap reconfiguration. | Transmission Line - Multiple | Upgrade/Retrofit | Relocate | NA | Reliability | Environmental | NA | NA | 2023-10-10 09:55 | NA* see notes | Steady State Power Flow System Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.2489 | NA | 69 | NA | 2.1 | 13130 | 2013-00010-ZZ | 2985250, 2985251 | NA | FALSE | 2020-12-15 | Work Order Authorization | 2015 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-21 | IS/MND | NA | CPUC | NA | PTC | 2017-06-28 | Approved | 2019 | Operational | NA | 2020-12-30 | 2015-06-01 | 2023-10-12 | NA | NA | TRUE | 48809.816 | NA | 27673.8443 | 695.0528 | 3527.8217 | 3042.0546 | 14720.5483 | 2988.6699 | 538.2414 | 0 | 0 | 0 | 0 | 11585.9192 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 26669.8059 | 1004.0384 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission. Major project construction activities completed on November 15, 2023.
45 | CBM Gas Breakers |  |  | NA | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on approximately 900 Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA* see notes | Other [See Notes] | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.3 | 13139 | Multiple | QS00086 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3370.1517 | 3686.8071 | 4732.6084 | 2049.5418 | 1377.9392 | 643.4388 | 0 | 0 | 0 | 0 | 10318.9377 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 7006.1574 | 3479.4568 | 3687.4675 | 0 | 9826.4356 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
46 | Kearny - Rebuild 69kV/12kV Sub |  |  | San Diego, San Diego | The Kearny Substation rebuild will consist of relocating the existing installation to the west side of the Kearny facility on a larger and more suitable location to accommodate a low profile 120MVA substation. The relocation will be on the existing Kearny facility property zoned for utility use, and therefore will not be subject to any permits. It will be rebuilt on the site once utilized by transformer oil tanks, in the southwest corner of the Kearny facility. This site will allow space for all required expansion to meet existing and projected electric distribution load growth and the ultimate arrangement will allow for feeds to existing generators and proposed battery storage area. It is anticipated that the rebuild will improve Kearny’s reliability by 98%. The ultimate arrangement of the substation will consist of five 69kV bays consisting of five 69 kV TL breakers, one 69kV bus tie breaker, four 69 kV bank breakers, one 69kV ground bank and associated breaker, four 30 MVA 69/12 kV low profile transformers, four ¼ sections of switchgear, four 12 kV capacitors, one new control shelter, new relaying, SCADA, five 69 kV transmission lines, and sixteen distribution circuits. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-09-29 | 20; 59; 54; 59; 55; 54; 55; 40; 55; 20; 20; 15 | Lifecycle Replacement Analysis | Wires - New Substation Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12046 | NA | 69 | 120MVA | 4.1 | 13242 | 2014-00210-ZZ | PSS0028 | NA | TRUE | 2015-09-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-11-06 | NA | 2020-01-10 | NA | NA | FALSE | 47947 | NA | 20430.7246 | 1021.7362 | 222.8276 | 14.8608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 215.4731 | 14.8445 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] The project is completed and was exempt from CPUC filings. No permits were required due to move forward with the project.
47 | Streamview Substation Rebuild |  |  | San Diego, San Diego | Initially expand the existing 69 ¦12 kV substation from two to three banks to increase capacity on the system, with future expansion to four banks. Scope to construct a new 69 kV tie line between the Station F Substation and the Streamview Substation within an existing transmission corridor has been REMOVED. | Transmission Line/Substation | Upgrade/Retrofit | New | NA | Reliability | Age/Condition | NA | NA | 2023-10-16 | 21; 54; 21; 52;6; 2 | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.38816 | 69 | 12kV ¦69kV ¦28MVA | 4.2 | 13244 | 2014-00062-ZZ | 5984765, 5907328 | NA | TRUE | 2021-06-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | NA | PTC | 2020-11-30 | Approved | 2020 | Construction (under 10%) | NA | 2020-03-11 | 2026-07-14 | 2029-01-15 | NA | NA | TRUE | 543 | NA | 83383.2211 | 4106.1362 | 1243.0493 | 482.8375 | 2788.8514 | 1296.8375 | 19456.3952 | 8726.8253 | 7995.5738 | 665.316 | 0 | 14230.1596 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 3622.8086 | 299.6637 | 33.7723 | 149.5358 | 0% | NA | NA | NA | 0% | 100%
48 | Suncrest 230kV 300MVAr Dynamic Reactive Power Support |  |  | San Diego County | In the draft 2013-2014 Transmission Plan, the CAISO has identified a potential policy driven need for installation of a synchronous condenser facility or SVC at the 230kV bus within Suncrest Substation. The preferred alternative will add one +320/-100 MVAr SVC at the Suncrest Substation 230kV bus. SDGE is required to submit a bid to the CAISO by Monday, June 16, 2014 to compete for the right to engineer, procure, and construct an SVC facility connected at the 230kV Suncrest bus. SDGE submitted the bid for Suncrest Substation as requested by the CAISO on June 16, 2014. SDGE submitted a response on July 22, 2014 to the deficiency letter received from the CAISO. An additional follow up request was submitted to the CAISO on August 15, 2014 as part of the CAISO's project qualification process. On September 9, 2014 SDGE was identified by the CAISO as being a qualified project sponsor for the Suncrest policy driven project. | Substation - Voltage Support Equipment | NA | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Load Interconnection | CAISO Requirement | NA | 2023-10-07 13:00 | NA* see notes | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.9412 | 230 | 300MVA | 2.1 | 14126 | 2014-00076-ZZ | TBD | NA | FALSE | 2021-07-03 | Work Order Authorization | 2015 | 2014 | TRUE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | CPCN | 2019-07-12 | Approved | 2018 | Operational | NA | 2019-05-28 | 2017 | 2020-02-24 | Permitting | Land Rights | FALSE | 798 | NA | 3711.61 | 2916.2219 | 470.3467 | 28.9237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 3662.4194 | 28.9193 | 0 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] New substation equipment
49 | 230kV Artesian Substation |  |  | San Diego, San Diego | Per the CAISO 2013-2014 Final Plan, SDG&E will expand the existing 69 ¦12kV Artesian Substation to a 230 ¦69 ¦12kV Substation (Artesian East Substation) to alleviate the existing 69kV congestion at Sycamore Canyon Substation. In addition, the Proposed Project will help mitigate Cat B contingencies and increase reliability to the Poway Area Load Pocket which is expected to grow by as much as 12% in the next 10 years. The Proposed Project will be built on existing SDG&E Artesian Substation land and adjacent land east of the current substation site, also owned by SDG&E (pending final sale negotiations). Transmission work includes the loop-in of TL23051 (SX-PEN), terminating TL616C into the Artesian 69kV substation to form two (2) 69 kV Artesian - Bernardo lines; reconductoring both Artesian - Bernardo lines to achieve a 145 ¦179 rating (TL6939 & segment of TLNew), and replacing underground getaways at Artesian, Bernardo, Rancho Carmel, and Poway to achieve new ratings. Permitting and Environmental will be required for the expanded 230 ¦69 ¦12kV substation, in addition to the reconductor work associated with the project. Requested ISD of the ISO is June 2016, however the team proposes and ISD of December 2018 depending on application filing, and receipt of approval from the Commission. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Capacity | NERC TPL Standards | NA | 2023-10-05 | 21;21;21;15;23;15;23;15;23;15;15 | Steady State Power Flow System Analysis | Wires - Bus Upgrade Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.9377 | 230 | 69kV ¦230kV ¦224MVA | 2.1 | 14128 | 2014-00056-ZZ | 5983218, 5984695 | NA | FALSE | 2013-07-01 | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-22 | IS/MND | NA | CPUC | NA | PTC | 2019-10-07 | Approved | 2020 | Operational | NA | 2020-04-17 | 2016-06-01 | 2022-12-04 | Permitting | Construction Delays | TRUE | 17140 | NA | 130112.5516 | 15274.1608 | 0 | 0 | 0 | 0 | 1104.5159 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 50195.6024 | 74458.1935 | 1557.4884 | 1104.5159 | 0% | NA | NA | NA | 100% | 0%
50 | TL6975 San Marcos to Escondido |  |  | San Marcos, San Diego ¦ Carlsbad, San Diego ¦ Lake San Marcos, San Diego ¦ Escondido, San Diego | Segment 1: Rebuild approximately 1.8 miles of an existing 69kV circuit (TL 680C) to create a double circuit from San Marcos Substation to Melrose Tap. Construction at San Marcos Substation including installation of a new circuit breaker par, seven piers, and an A-frame for the new line. Along Segment 1, all wood pole structures would be replaced with steel poles; porcelain insulators would be replaced with polymer insulators. Segment 2: Construct 2.8 miles of new single-circuit 69kV overhead power line on new steel poles in the existing transmission corridor from Melrose Tap to Meadowlark Junction adjacent to existing TL 13811/13825 power line, approximately 50-feet east of the centerline of the existing structures. Segment 3: Transition new line (described under Segment 2, above) and reconductor approximately 7.4 miles of power line; remove and replace existing copper conductors with new 636 ACSS/AW conductors and existing porcelain insulators with polymer insulators; construction at the existing Escondido Substation to accommodate new circuit. | Transmission Line - Multiple | New | NA | NA | Load Growth | New T-Line | NERC TPL Standards | NA | NA* see notes | NA* see notes | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.9036 | NA | 69 | 69kV | 2.1 | 14137 | 2014-00078-ZZ | 2986471 | NA | FALSE | 2022-08-31 | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | PEA Deemed Complete | 2018-03-16 | IS/MND | NA | CPUC | NA | PTC | 2017-11-15 | Approved | 2021 | Operational | NA | 2021-10-19 | 2015-06-01 | 2023-02-28 | Permitting | Land Rights | TRUE | 10,000 ¦ 100,000 | NA | 50158.381 | 1335.1916 | 1477.0226 | 8784.9334 | 32029.5756 | 2197.7199 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 529.1659 | 332.0915 | 49297.1237 | 0 | 0% | NA | NA | NA | 0% | 100% | [Last Inspection] TL energized 2023-02-28 [Age of Asset] new transmission line
51 | TL698 Wood to Steel Replacement (Monserate - Avocado) |  |  | Fallbrook, San Diego | The TL698 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 698 in FTZ from Z10213, north of Monserate Substation, to structure Z293941, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. TL698 is located within existing easements. TL698 will be designed for (3)-636 ACSS/AW conductors and the existing 336 ACSR/AW conductors will be retired. There will be one SDG&E 96-count ADSS and one position for a third party installed along the line from Z10212 to Z293941. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-12-06 | 49 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.2938 | NA | 69 | NA | 1.1 | 14140 | 2014-00009-ZZ | 2271085 | NA | TRUE | 2021-08-31 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2023-10-27 | 2026-12-31 | 2024-08-07 | NA | NA | TRUE | 150 | NA | 41381.4385 | 217.5404 | 492.3221 | 706.465 | 1588.1374 | 2268.5705 | 16676.3412 | 0 | 0 | 0 | 0 | 380.2909 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 1968.6566 | 1246.6941 | 1971.7615 | 15008.707 | 0% | NA | 1.02% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
52 | Poway Substation Rebuild |  |  | Poway, San Diego | The purpose of this project is to rebuild Poway Substation to a low profile distribution substation with an ultimate capacity of 120MVA. The current substation consists of aging infrastructure, no SCADA control, and a control shelter that cannot accommodate new panels for any SCADA upgrades. Adding SCADA control and replacing old equipment will increase the reliability of this sub and allow room for any future expansion. Substation, Transmission, and Distribution work are required for this rebuild. Installing SCADA to Poway Sub will increase reliability by giving Mission Control remote access to operate the equipment. Replacing aging infrastructure also increases reliability. Building a new control shelter allows for any future expansion. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Age/Condition | NA | NA | 2023-09-26 12:00 | 23;30;46;30;47;49 | Lifecycle Replacement Analysis | Wires - Minimum Required Scope (spot repair) Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.36956 | 69 | 120MVA | 4.1 | 14143 | 2017-0095 | 2986910, PSS019 | NA | TRUE | 2015-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2015-10-26 | NA | 2018-11-06 | NA | NA | TRUE | 28839 | NA | 21857.5534 | 416.9023 | 547.4167 | 478.3805 | 914.0113 | 10.3026 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | -40.4736 | 2.4413 | 1398.6141 | 10.3026 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; Project has been completed.
53 | Helicopter Access for Transmission Structures (HATS) Work Release 1 |  |  | San Diego County | Obtain the necessary permits, environmental clearance and regulatory authority for the helicopter landing areas along our transmission system. Relocate approximately 6 existing Sunrise Tower Staging Access Pads (TSAP) to locations that are better suited for TCM's O&M requirements. Build platforms at approximately 12 of the TSAPs and create 8 new TSAPs at tower locations to ensure safer and more secure landing areas for TCM. Establish approximately 15 permanent staging/fly yard locations, one acre or less in size, at locations along Sunrise that will best meet TCM's needs. Many of these will be at the same fly yard locations utilized for construction of Sunrise. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦500 | NA | 1.3 | 14145 | 2014-00060-ZZ | 2686773, 2984870 | NA | TRUE | 2021-09-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-06-24 | 2019-03-01 | 2020-12-28 | Construction Delays | NA | FALSE | 499 | NA | 15071.928 | 3755.8273 | 6293.535 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 11057.0747 | 4215.1246 | -185.8243 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [Primary Purpose] Remote access landing pads for transmission structures [CPUC Status] NA
54 | CAST Security Upgrades |  |  | NA | CAST is an ongoing program that addresses security for critical substation assets. | Substation - Other Equipment | New | NA | NA | Physical Security | Security Upgrades | Multiple Options [See Notes] | Multiple Options [See Notes] | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 ¦500 | 230kV ¦500kV | 1.2 | 15125 | Multiple | QBL0020 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | 42453.867 | NA | 42453.867 | 18495.8021 | 11160.4224 | 35749.7593 | 35347.4351 | 24944.3844 | 42521.4796 | 41980.5287 | 43691.7221 | 33867.2762 | 0 | 26185.3747 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 25943.0437 | 23922.725 | 31572.0836 | 25436.1939 | 55520.414 | 0% | NA | NA | NA | 100% | 0% | [NERC / WECC / CAISO Standard / Requirement / Contingency] NERC CIP Compliance and Security Assessments [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
55 | Rancho Santa Fe - Sub Fire Hardening / Rebuild |  |  | Rancho Santa Fe, San Diego | Replace approximately one (1) mile of direct-buried cable along Old Seaworld Drive to a new 69kV duct package infrastructure relocated onto Sea World Drive. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-09-21 11:28 | 64; 69; 61 | Lifecycle Replacement Analysis | Wires - Minimum Required Scope (spot repair) Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12094 | NA | 69 | 69kV | 1.1 | 15246 | 2014-00289-ZZ | PSS0027 | NA | TRUE | 2015-12-11 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-07-10 | NA | 2020-11-18 | NA | NA | FALSE | 15034 | NA | 7618.3272 | 365.014 | 2684.7836 | 1534.6687 | 8.9299 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 196.0093 | 7250.4838 | 8.6311 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Primary Purpose] Specialized Structure Access [Alternative Solutions and Costs - Solutions] Alternative - run to failure [CPUC Status] NA
56 | Mid-Coast Corridor Transit Project (Relocation) |  |  | San Diego, San Diego | Mid-Coast: As part of SANDAG's Mid Coast Trolley Extension Project, SDG&E will be relocating multiple electric and gas services from the Santa Fe Depot in downtown San Diego to the University City community. | Transmission Line - Multiple | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.2125 | NA | 69 | NA | 3.3 | 15258 | 2015-00016 | 4162439, 4164166, 4176438, 4185920, 4207134, 4227650, 530000163833, 530000196039, 530000196527, 530000197131, 530000200652, 530000211727, 2087844, 2087846, 2087849, 2321276, 2321279, 2356300, 2424730, 2424731, 2424732, 2424733, 2424737, 2424738, 2436614, 2436615, 2470380, 2470383, 2529611, 2529612, 2529614, 2529615, 2529617, 2529619, 1525800, 1525810, 1545577, 2087847, 2321274, 2321278, 2321279, 2424739, 2436610, 2436611, 2436612, 2436613, 2436616, 2470385, 2470386, 2470388, 2470389, 2529613, 2529616, 2529618, 2651341, 2651661, 2652611, 2985650, 2985653, 2985654, 2985656, 2985659, 2986861, 2986862, 2986863 | NA | TRUE | 2015-12-05 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-10-03 | NA | 2022-08-17 | NA | NA | TRUE | 22439 | NA | 7244.0358 | 161.3832 | 652.165 | 1245.3496 | 2165.9791 | 361.4901 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 655.01 | 66.7479 | 3503.5331 | 381.6753 | 0 | 0% | NA | NA | NA | 0% | 100%
57 | Fire Threat Zone Adv Protect & SCADA Upg |  |  | NA | Replaces aging circuit breakers and/or obsolete electromechanical relays, to create a more comprehensive protection system by taking advantage of newer field technologies under installation by the FiRM program, and to create visibility in fire threat areas with installation of Distribution SCADA. Adding distribution SCADA and replacing obsolete distribution relays and aging equipment. Improve distribution reliability and improve fire safety. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NA | NA | NA | NA* see notes | Protection Studies | Other - Status Quo | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 | 120MVA | 1.1 | 15259 | Multiple | QBL0071 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 2034.9499 | 5911.756 | 8689.0565 | 12205.0175 | 11223.936 | 13037.367 | 8496.2469 | 277.9378 | 0 | 0 | 66240.836 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 56.0093 | 4141.1392 | 5161.9731 | 17446.3413 | 14172.9505 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
58 | Substation Security Installations - Under $500k |  |  | NA | This budget is required to maintain the reliability and integrity of the security of electric substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Other - Physical Security | Upgrade/Retrofit | NA | NA | Reliability | Security Upgrades | NERC CIP Compliance | NA | NA | NA* see notes | Lifecycle Replacement Analysis | Wires - New Substation Alternative | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 4.3 | 16126 | Multiple | QBL0002 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1276.2123 | 2362.9201 | 7255.8467 | 6722.4789 | 6014.5782 | 6595.766 | 5678.9784 | 6455.4572 | 6460.2448 | 0 | 4163.9034 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2656.2569 | 269.1069 | 4148.4855 | 13392.1399 | 7672.4313 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [Alternative Solutions and Costs - Costs] Projects are under blanket budget [CPUC Status] NA
59 | Substation Auxiliary Power System |  |  | NA | This project will develop, procure, design, and install three enclosed fuel cell units manufactured by GenCell. One unit will be installed at Descanso Substation, one unit will be installed at Boulevard East Substation, and one unit will be installed at Warners Substation. Each fuel cell will connect to the substation’s DC panel via a DC breaker. | Substation - Multiple | New | NA | NA | Reliability | Emergency Response - Storm Related | NA | NA | NA | NA* see notes | Interconnection System Impact/Facilities Studies | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 138 | Multiple | 4.3 | 16133 | Multiple | QS00137 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1182.9766 | 82.1523 | 7.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 2039.5043 | 7.4317 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
60 | Substation DC Reliability Upgrades |  |  | NA | This project installs new assets in existing substation control shelters to support increased power requirements driven by aging infrastructure replacements of telecommunication hardware. Scope includes installation of new communication racks, upgrades to 125V DC systems for power, adding HVAC in transmission substation control shelters to support equipment environmental control requirements, DC-DC power converters, as well as batteries and Station Light & Power (SL&P) upgrades. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | Other - Status Quo | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 16138 | Multiple | QBL0094 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2017-04-04 | NA | NA | NA | NA | TRUE | NA | NA | NA | 6187.0973 | 5269.0216 | 6210.5463 | 5194.8994 | 3388.8822 | 4397.9529 | 3968.25 | 3890.4601 | 3598.8118 | 2059.482 | 3827.6249 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 8102.4175 | 7533.5637 | 4917.9388 | 3257.5534 | 7835.4562 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
61 | TL23001 TL23004 Wood to Steel Replacement (Mission - San Luis Rey) |  |  | San Diego, San Diego | TL23001 and TL23004 from Mission to San Luis Wood to Steel pole replacement. The scope of work includes replacing 42 existing wood pole structures with engineered steel structures as well as stringing 3.5 miles of new single conductor 1033 ACSR one line of OPGW and one line of 7#8 shield wire for TL23001 and TL23004. | Transmission Line - Conductor | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.9735 | NA | 230 | NA | 1.1 | 16150 | 2014-00016-ZZ | 2982933 | NA | TRUE | 2016-01-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-10-18 | 2026-12-31 | 2020-03-31 | NA | NA | FALSE | 22646.466 | NA | 28842.643 | 16356.2278 | 10219.9705 | 123.9126 | 0.60204 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 28720.3845 | 121.6565 | 0.60204 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
62 | New 2nd Miguel to Bay Blvd. 230 kV Line |  |  | Bonita, San Diego ¦ Chula Vista, San Diego | New 2nd Miguel to Bay Blvd. 230 kV Line | Transmission Line - Conductor | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | NERC TPL Standards | NA | NA | NA | Steady State Power Flow System Analysis | Wires - New T-Line Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 9.8716 | NA | 230 | NA | 2.1 | 16157 | 2015-00021 | TBD | NA | FALSE | 2017-08-31 | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-04-02 | 2018-06-01 | 2019-08-21 | Permitting | Construction Delays | FALSE | 24499.998 | NA | 21457.951 | 12648.4165 | 717.5751 | 40.835 | 0.00798 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 691.3548 | 39.4429 | 0.00759 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] NA
63 | TL605 Reconductor (Silvergate-Urban) |  |  | San Diego, San Diego | Reconductor TL605 with 2-636ACSS (200MVA) or equivalent Note: there is an active project (ID:2015-00013; budget code: 16158) with ISD of 6/26/2024. This new summited cost request is to upgrade the current design line rating from 137 MVA to 200MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Line Reconductoring | NERC TPL Standards | NA | 2023-10-24 | 19 | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.9028 | NA | 69 | NA | 2.1 | 16158 | 2015-00013 | 2988650 | NA | FALSE | 2018-04-01 | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2024-07-01 | 2018-06-01 | 2024-07-01 | Permitting | ISO Action | TRUE | 15676.263 | NA | 34054.1313 | 344.691 | 6.5632 | 5396.2009 | 361.297 | 6603.6531 | 12353.9105 | 0 | 0 | 0 | 0 | 13614.3709 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 26085.913 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
64 | Southwest Powerlink HVDC Conversion |  |  | San Diego County | The scope of this work encompasses all aspects of engineering and design that is required to plan the HVDC conversion of the Southwest Powerlink. The engineering/planning process will also involve exploring feasible alternatives to this proposed project. | Other | NA | NA | NA | Address Results of Power Flow Analysis | System Operations | NA | NA | NA | NA | Steady State Power Flow System Analysis | NA | Over $500 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 85 | NA | 525 | 525kV | 4.2 | 16159 | NA | QS00145 | NA | FALSE | 2017-01-01 | Work Order Authorization | 2017 | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Canceled | NA | NA | NA | NA | NA | NA | FALSE | 1467 | NA | 1226.7107 | 15.2017 | 5.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 1226.7107 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [Alternative Solutions and Costs - Solutions] Project never approved by CAISO. [CPUC Status] NA
65 | San Mateo Substation |  |  | San Clemente, Orange | Rebuild the existing 138/12 kV San Mateo Substation to Enhance reliability and minimize outage impacts in the San Clemente area. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | 17; 17; 17; 8; 52; 43 | Lifecycle Replacement Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 0.542 | 138 | 12kV ¦ 138kV | 4.1 | 16261 | 2017-0160 | QS00149 | NA | TRUE | 2016-08-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | On Hold | NA | NA | NA | NA | NA | NA | FALSE | 1240 | NA | NA | 1803.1812 | 58.4115 | 65.9274 | 75.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 3697.1199 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CEQA Status] TBD. Project is on hold. Project driver is not identified. [CPUC Status] NA
66 | AB2868 Energy Storage |  |  | San Diego County | Placeholder for AB2868 Energy Storage | Other | New | NA | NA | Local Capacity Requirement | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 12 ¦69 | NA | 4.3 | 16276 | 2014-01087-ZZ | TBD | NA | TRUE | 2017-01-03 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 9718.925 | NA | 23081.8816 | 785.9656 | 501.9642 | 100.5682 | 150.6047 | 103.2225 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Physical projects were new construction and moved to different budget codes once approved. [CPUC Status] NA; This budget code was for development of the microgrid program. Once each project received approval, it was assigned an individual budget code and proceeded to design and construction under the new BC. Each project is now at a different status.
67 | TL632A Loop-In (Granite) |  |  | El Cajon, San Diego ¦ Crest, San Diego ¦ Granite Hills, San Diego | Convert TL632 from a tap into Granite Substation to a loop-in. Based on routing study, underground along La Cresta Rd to Granite Substation is most feasible route. 1.9 miles of 69kV underground. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2021-10-20 | NA* see notes | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | $10 Mil -$15 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.1143 | NA | 69 | NA | 2.1 | 17125 | 2015-00005 | 2651507 | NA | FALSE | 2016-12-09 | Work Order Authorization | 2017 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2014-2015TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | NA | NA | NA | 2025-07-28 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2026-10-12 | 2017-06-01 | 2026-10-12 | Permitting | Land Rights | TRUE | 14057.888 | NA | 14057.888 | 389.2903 | 593.8373 | 256.8387 | 494.8968 | 7682.2363 | 550.4755 | 11506.1055 | 24228.2954 | 0 | 0 | 10493.6739 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 12.56% ¦ Copperleaf | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission [Alternative Solutions and Costs - Costs] Reconductor TL631, El Cajon - Los Coches, Cost $17M-$22M. [CPUC Status] CPUC filing requirements to be determined.
68 | TL611 Direct Buried Cable Replacement (Old Town - Point Loma) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 53 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.3221 | NA | 69 | NA | 4.1 | 17127 | 2012-00002-ZZ | 2983120 | NA | TRUE | 2023-11-28 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-06-03 | To be Filed | 2027 | Planning | NA | 2027-12-02 | NA | 2028-04-05 | NA | NA | TRUE | 28043.924 | NA | 28043.9235 | 0 | 0 | 0 | 0 | 0 | 243.8511 | 3259.4219 | 17324.408 | 0 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 29.22% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] TBD
69 | TL603 Loop-in (Sweetwater, National City, and Naval Station Metering) |  |  | National City, San Diego | Open Sweetwater Tap and make TL603D and TL603B one continuous 69kV line from national City to Sweetwater. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2022-02-24 | 36 | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2.5607 | NA | 69 | NA | 2.1 | 17129 | 2015-00066 | 2988754 | NA | FALSE | 2017-04-05 | Work Order Authorization | 2017 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | NA | NA | NA | 2026-07-24 | To be Filed | 2026 | Engineering more than 50% complete | NA | 2027-10-14 | 2017-06-01 | 2027-10-14 | Prioritization | Permitting | TRUE | 13584.367 | NA | 13584.367 | 711.7533 | 36.8697 | 5253.4249 | 179.5665 | 517.2172 | 453.5829 | 8379.9351 | 12677.2264 | 0 | 0 | 8700.7874 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 21.52% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] CPUC filing requirements to be determined. [ ]TL603D (National City – Sweetwater Tap) and TL603B (Sweetwater – Sweetwater Tap) will be made into one continuous line segment running from National City to Sweetwater Substation to achieve a minimum continuous/emergency rating of 102 MVA. The project is expected to cost $10 to $12 million and the expected in-service date is June, 2017.
70 | TL6906 Mesa Rim Rearrangement |  |  | San Diego, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NA | NA | 2021-03-18 | NA* see notes | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 9.1086 | NA | 69 | NA | 2.1 | 17130 | 2014-00207-ZZ | 2983335, 2983334, 2981181, 2985349 | NA | FALSE | 2018-07-25 | Work Order Authorization | 2017 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-05 | 2018-06-01 | 2020-08-05 | Prioritization | Outage | FALSE | 14328.054 | NA | 16547.7654 | 5537.975 | 8379.5009 | 694.1458 | -360.9559 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 16217.1255 | 670.8744 | -340.2346 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Primary Purpose] NERC Category B Criteria, [Age of Asset] asset age data discrepancy being corrected for future submission [Wildfire Related] Reconductor HFTD Tier 2 [CPUC Status] Project was Exempt from CPUC filing per GO-131D
71 | Imperial Valley Substation: Replace Bank 80 |  |  | Imperial County | Install three (3) new 500/230kV 373MVA single phase transformers. Upgrade 12kV tertiary bus to meet the new MVA rating of Bank 80 and adjust firewalls. Replace existing 480/277V SL&P transformers with new 120/208V transformers to provide the required control power for the new BK80. Remove and demo existing three (3) 500/230kV single phase transformers. Demo the existing spare Bank 80 unit. Upgrade the 3.5" AL bus to 2-2500 KCMIL in the 230kV yard to meet TERG requirements, re-ordered few structural BOMs for the 12kV tertiary, added fiberglass grating, and remobilized Siemens onsite during commissioning to assist KY. | Substation - Transformer | Replace | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Transformers | NA | NA | 2023-10-21 13:00 | 40 | Lifecycle Replacement Analysis | Wires - Minimum Required Scope (spot repair) Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500kV | 2.1 | 17138 | 2014-01072-ZZ | QS00161 | NA | TRUE | 2017-05-08 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-10-26 | 2019-05-04 | 2019-05-11 | NA | NA | TRUE | 16986 | NA | 19539.3467 | 7121.3852 | 584.7405 | 4.5065 | 0 | 174.251 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2023 | 559.4154 | 4.5065 | 0 | 174.251 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] Project exempt
72 | TL690 Direct Buried Cable Replacement (Oceanside-Oceanside Tap) |  |  | Oceanside, San Diego ¦ Camp Pendleton South, San Diego | Direct-Buried Cable Replacement (On Hold) (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 45 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.0534 | NA | 69 | NA | 4.1 | 17142 | 2014-00017-ZZ | TBD | NA | TRUE | 2020-08-02 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-06-14 | To be Filed | 2027 | On Hold | NA | 2027-12-08 | NA | 2028-10-17 | NA | NA | TRUE | 905.761 | NA | 905.761 | 62.5408 | 5.3836 | 0 | 0 | 0 | 936.4362 | 938.8785 | 5325.8504 | 10375.7626 | 11047.8985 | 769.7813 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.96% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] TBD
73 | TL628 Direct Buried Cable Replacement (Rancho Del Rey & H St.) |  |  | Chula Vista, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 44 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.63688 | NA | 69 | NA | 4.1 | 17143 | 2017-0021 | TBD | NA | TRUE | NA | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2027-12-02 | NA | 2028-03-17 | NA | NA | FALSE | 20131.87 | NA | 20131.87 | 438.878 | 16.0786 | 15.6756 | 17.3237 | 12.0389 | 2257.3201 | 2261.4796 | 7746.2387 | 12475.533 | 11712.007 | 1308.9815 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 13.56% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
74 | TL698 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Fallbrook, San Diego | This project installs one new engineered steel cable pole and underground facilities to support the replacement of the direct buried cable Getaways of the Avocado Substation on TL698. The underground segment on TL698 is 1500 feet long, a portion of the line will be installed within a double circuit underground duct package, and a single circuit underground duct package. The duct package will be constructed in a franchise position on the north side of Barhaven Lane, crossing Alvarado St. and consists of three conduits for the 69kV segment of cable and one conduits for fiber optic communication. A new steel cable pole (Z293941) will be installed to replace an existing steel cable pole structure (Z713100) on TL698. Time frame for construction is November 2019- March 2020. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2022-08-08 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.23906 | NA | 69 | NA | 4.1 | 17145 | 2017-0026 | 2988759 | NA | TRUE | 2017-06-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-11-22 | NA | 2020-05-01 | NA | NA | FALSE | 3740.94 | NA | 2822.313 | 797.0091 | 1694.7805 | 95.6191 | 4.389 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 2724.071 | 93.9478 | 4.2942 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Asset age data discrepancy being corrected for future submission [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
75 | TL697 Direct Buried Cable Replacement (Oceanside Sub Getaway) |  |  | Oceanside, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 50 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.065771 | NA | 69 | NA | 4.1 | 17147 | 2017-0025 | 2988951 | NA | TRUE | 2020-08-02 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-03-24 | To be Filed | 2027 | On Hold | NA | 2027-12-01 | NA | 2028-04-04 | NA | NA | FALSE | 1500.416 | NA | 1500.416 | 33.0444 | 2.1883 | 0 | 0 | 0 | 437.6027 | 438.2582 | 439.0112 | 6124.6305 | 2256.9186 | 356.2724 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 1.57% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] TBD
76 | TL667 Direct Buried Cable Replacement (El Camino Real) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 39 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.0087 | NA | 69 | NA | 4.1 | 17151 | 2017-0022 | TBD | NA | TRUE | NA | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2024-05-13 | To be Filed | 2024 | On Hold | NA | 2027-05-04 | NA | 2028-01-26 | NA | NA | FALSE | 15490.906 | NA | 15490.905 | 249.1351 | 22.1989 | 23.9228 | 23.2003 | 19.3484 | 1465.166 | 1486.9151 | 1510.6589 | 14054.4385 | 44608.4461 | 1865.4787 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 50.83% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] TBD
77 | TL673 Direct Buried Cable Replacement (Rose Canyon - La Jolla) |  |  | San Diego, San Diego | Currently TL673 consist entirely of aging 69kV direct-buried cable from Rose Canyon to La Jolla substations at approximately three miles. This existing direct-buried cable is of 1967 vintage year and has far exceeded its designed operational expectancy of 30 years. Transmission Engineering anticipates an increase rate in outages caused by failures on this existing aging cable system in the near future. This project will replace all existing direct-buried cable from Rose Canyon to La Jolla substations within a newly constructed underground trench conduit package and substructures which will improve electric transmission reliability to the La Jolla area as well as resolve the ongoing maintenance issue for TL673. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | NA* see notes | 49 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | NA | 69 | NA | 4.1 | 17152 | 2017-0023 | 2652565 | NA | TRUE | 2022-12-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-06-30 | NA | 2023-06-30 | Permitting | Land Rights | TRUE | 2600 | NA | 61380.2794 | 2921.5738 | 8764.3562 | 12974.7047 | 17316.8906 | 11407.7061 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 5800.3575 | -170.835 | 244.5547 | 55506.2023 | 0 | 0% | NA | NA | NA | 0% | 100% | [Last Inspection] UG sections energized 2023-07-25, first inspection due 2024-12-08. [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
78 | Avocado - 69kV Rebuild |  |  | San Diego, San Diego | Substation Rebuild, Transformers, Control Shelter & Relays & CS equipment, expanded the substation, change out 69kV circuit breakers, PT, and disconnects. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-11 09:47 | 49; 49; 60 | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | 1.7192 | 69 | 60MVA | 2.1 | 17153 | 2014-00941-ZZ | PSS0041 | NA | TRUE | 2017-12-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-09-17 | NA | 2020-11-16 | NA | NA | FALSE | 10074 | NA | 16402.6667 | 6666.2445 | 4404.7636 | 2362.503 | 3.3717 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 94.4561 | 16305.0626 | 3.148 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] asset age data discrepancy being corrected for future submission [CPUC Status] NA; Project has been completed.
79 | TL691 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Oceanside, San Diego | This project replaces approximately 900' of direct buried cable on TL698 from Avocado Substation to Structure Z15588 with concrete encased conduit, cable pole and cable. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.15746 | NA | 69 | NA | 4.1 | 17157 | 2017-0027 | 29829260 | NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-11-22 | NA | 2020-11-16 | NA | NA | TRUE | 1947.832 | NA | 2142.2622 | 586.8519 | 1249.7981 | 129.1762 | 79.1442 | 186.6699 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1786.5114 | 116.3664 | 71.2848 | 168.0996 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
80 | San Marcos - 69kV Rebuild & Switchgear Replacement |  |  | San Marcos, San Diego | Upgrade the 69kV bus, replace all 69kV insulators, disconnects, potential transformers, protection and controls. Replace existing control shelter with a new block shelter. Replace Bk 32’s 12kV switchgear with new switchgear (sized to fit on existing foundation) and cutover existing 12kV circuits to new switchgear. Replace and relocate existing 12kV capacitors. Remove and RFS four 69kV oil breakers, two 12kV capacitors, Bk 32's switchgear, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-17 13:15 | 33; 46; 46; 33 | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.5915 | 69 | 60MVA | 4.1 | 17160 | 2014-01062-ZZ | QS00176 | NA | TRUE | 2017-12-15 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2020-02-03 | 2022-10-30 | 2021-06-30 | NA | NA | FALSE | 11114 | NA | 11295 | 421.7658 | 11.6052 | 7.2018 | 7.0906 | 9.142 | 0 | 204.3403 | 3056.9127 | 1698.0505 | 165.9289 | 1339.8547 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Alternative Solutions and Costs - Solutions] Alternative - run to failure . [CPUC Status] NA; Project not yet scheduled.
81 | Escondido - 230kV Yard Rebuild |  |  | Escondido, San Diego | Escondido Substation 230kV Yard Rebuild | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2023-10-09 09:49 | 40; 44; 46; 16; 16; 16; 23; 16; 16; 24; 24 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.6631 | 230 | 230kV | 4.1 | 18127 | 2014-01090-ZZ | TBD | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | 2019-03-01 | NA | 2020-12-24 | NA | NA | FALSE | 982 | NA | 982 | 5.4845 | 1.2231 | 1.3352 | 9.2223 | 27.0328 | 10288.1716 | 33580.8775 | 27853.9038 | 23454.3496 | 17284.8267 | 154.4497 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 3.24% ¦ Copperleaf | NA | 100% | 0% | [CPUC Status] TBD
82 | Mission – Rebuild the 138kV and 69kV bus |  |  | San Diego, San Diego | Install shoo-fly's for TL618, TL663 & TL13822 in conflict with the proposed Mission 69kV GIS | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2023-10-26 09:44 | 51 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 8.9967 | 69 | 69kV | 4.1 | 18128 | 2019-1012 | 5981934 | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2022-12-05 | 2024-09-05 | 2026-06-29 | NA | NA | TRUE | 100,000+ | NA | 118455.4144 | 37.9723 | 5.2979 | 808.8376 | 15737.3522 | 18376.126 | 31450.7427 | 17548.3232 | 10633.1203 | 0 | 0 | 36439.4669 | NA | NA | 2023 | 0 | 0 | 0 | 1.9299 | 0 | 0% | NA | 27.51% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] NA
83 | Oceanside - 69kV Rebuild |  |  | Oceanside, San Diego | Rebuild will consist of relocating and rebuilding the 69kV bus and structures on the newly acquired property using a 69kV GIS design. The new 69kV GIS bus will consist of five (5) 69kV breakers to meet the ultimate layout consisting of two (2) TL’s, two (2) transformer positions, and a disconnect used to serve portable transformers. This project will also rebuild the control shelter to a larger, block control enclosure. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-06 13:37 | 2; 9; 21; 49; 21 | Lifecycle Replacement Analysis | Wires - New Substation Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.22439 | 69 | 69kV | 4.1 | 18130 | 2018-1015 | QS00200 | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2022-07-18 | NA | 2022-10-31 | NA | NA | TRUE | 20779 | NA | 1028.2459 | 209.3632 | 61.8518 | 22.0362 | 140.0388 | 314.2823 | 0 | 497.2929 | 6821.5632 | 6328.5931 | 5832.7155 | NA | NA | NA | 2023 | 0 | 0 | 0 | 1028.2459 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; Alternative - run to failure . Project has completed phase 1 and phase 2 has yet to be scheduled.
84 | SKILLS TRAINING CENTER – TRANSMISSION YARD EXPANSION |  |  | San Diego, San Diego | The purpose of this project is to expand the transmission yard at Skills Training Center for crews to train safely on. A new OH potion will be installed, along with an UG portion, a 500kV Insulator Replica, and an SW pole with a new stepping pattern will be installed. Last phases of construction to begin September 2021, and end before 2022 | Transmission Line - Conductor | Replace | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.076428 | NA | 69 ¦230 | NA | 1.3 | 18136 | 2018-4002 | 2652031UG, 2652032OH | NA | TRUE | 2019-01-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-18 | NA | 2022-04-01 | NA | NA | TRUE | 2475.891 | NA | 1947.832 | 70.8326 | 325.7595 | 923.4068 | 529.1863 | 1.8695 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 1945.9625 | 1.8695 | 0 | 0% | NA | NA | NA | 100% | 0% | [Primary Purpose] Infrastructure not connected to the grid for training purposes. [Age of Asset] Construction of OH/UG transmission training facilities for SDGE line crews to perform construction and maintenance of transmission lines throughout service territory. [CPUC Status] NA
85 | Miguel Substation 230kV Rebuild |  |  | San Diego County | Upgrade relaying for Bk70/71, replace 32 disconnects, replace 32 switch stands to meet our new seismic standards, replace one overstressed breaker, and eight (8) panel changeouts. Remove existing relaying panels #403 & #406 | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | 2023-10-14 12:33 | NA | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 230 | 660MVA | 4.1 | 18139 | 2014-01074-ZZ | QS00350 | NA | TRUE | 2017-07-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-09-23 | 2020-11-12 | 2022-03-23 | NA | NA | TRUE | 10503 | NA | 11537.3734 | 2689.5163 | 2476.4635 | 1694.8201 | 825.6009 | 5.9404 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 11531.433 | 5.9404 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] NA; FERC Only
86 | Mission 230kV Rebuild |  |  | San Diego, San Diego | Rebuilding the Mission Substation, increase 230kV bus rating to 3k Amps. Replacing 230kV disconnects to latest standards. Replacing control shelter and equipment. Equipment was upgraded to meet standards, increase reliability and replace aging infrastructure | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-26 09:44 | NA | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 | Multiple | 4.1 | 18140 | 2014-01071-ZZ | QS00373 | NA | TRUE | 2017-10-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-09-24 | 2020-06-03 | 2021-04-23 | NA | NA | FALSE | 39512 | NA | 35868.2667 | 14051.2405 | 11189.6227 | 3163.2885 | 234.3455 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 | 0 | 26304.3851 | 9563.8816 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] NA; Substation rebuild, see description for upgrades
87 | TL667 San Dieguito Lagoon Customer Relocation |  |  | San Diego, San Diego | Relocate segment of TL666 for wetland mitigation. Still to meet with Caltrans to understand scope | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-02-27 | 2 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.4066 | NA | 69 | NA | 3.3 | 19128 | 2018-0163 | 2989664 | NA | TRUE | 2019-03-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2021-07-14 | Approved | 2021 | Operational | NA | 2023-01-12 | 2022-11-07 | 2023-03-27 | NA | NA | TRUE | 231.968 | NA | 4055.7199 | -141.9394 | 359.3729 | -73.1736 | 891.9402 | 3079.2415 | 0 | 0 | 0 | 0 | 0 | 55.4879 | NA | NA | 2023 | 0 | 0 | 0 | 4055.7199 | 0 | 0% | NA | NA | NA | 0% | 100% | [CEQA Status] Customer requested relocation requiring CPUC Advice Letter.
88 | TL13831 Rancho Mission Viejo Customer Relocation |  |  | Orange County | This project installs two (2) 138kV/12kV engineered steel poles, eight (8) 138kV engineered steel poles, ten (10) 138kV steel pole pier foundations, removes one (1) 138kV steel pole with foundation, remove one (1) 138kV SW pole, removes twelve (12) 138kV wood poles with guys & anchors all in conflict with the County of Orange & Rancho Mission Viejo (RMV) improvements for Cow Camp Road in San Juan Capistrano, California. | Multiple Options [See Notes] | Replace | Relocate | NA | Work Requested by Others | Facility Relocation | NA | NA | 2022-03-18 | 29 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.1496 | NA | 138 | NA | 3.3 | 19129 | 2017-0128 | TBD | NA | TRUE | 2016-10-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2019-10-28 | Approved | 2020 | Operational | NA | 2020-07-13 | 2020-06-01 | 2020-10-09 | Outage | NA | TRUE | 4917.018 | NA | 1024.1871 | 652.7768 | -252.4534 | 878.7057 | 101.9065 | -859.8052 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 3749.4928 | -2792.8948 | 97.1672 | -29.578 | 0 | 0% | NA | NA | NA | 0% | 100%
89 | Trans Fiber Links HFTD |  |  | NA | Install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan | Other | New | NA | NA | Wildfire Mitigation | NERC CIP Compliance | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 1.1 | 19134 | Multiple | QBL0100 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 577.5554 | 2752.7967 | 6699.0187 | 5366.1979 | 9862.0898 | 16280.0786 | 17937.5649 | 18800.2819 | 21522.3993 | 25238.6165 | 35662.4459 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 246.7031 | 123.2414 | 3981.2932 | 1440.719 | 9750.1953 | 0% | NA | NA | NA | 21% | 79% | [CEQA Status] Program consists of multiple same scope projects per transmission line with separate environmental permits. [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
90 | HFTD Undergrounding |  |  | NA | Blanket budget for High Fire Threat District undergrounding work. This is an electric distribution blanket budget. The forecasted costs shown for this project are only the FERC-specific transmission costs. | Transmission Line/Substation | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 19246 | Multiple | QBL0081 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 234.5417 | -649.2265 | 1687.9391 | 0 | 0 | 0 | 0 | 0 | 0 | 147312.9702 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes
91 | Urban Substation - 12kV Switchgear & Capacitor Replacement |  |  | San Diego, San Diego | Urban Substation - 12kV Switchgear & Capacitor Replacement | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2023-09-13 11:17 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.56634 | 69 | 69kV ¦12kV | 4.1 | 19252 | 2021-2065 | TBD | NA | TRUE | 2020-01-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2023-07-13 | 2025-12-05 | 2026-06-05 | NA | NA | FALSE | 27398.203 | NA | 27398.203 | 3.1085 | 212.151 | 284.6278 | 577.7939 | 868.9245 | 12113.1829 | 11863.9847 | 2568.8309 | 0 | 0 | 12190.1342 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; Exempt
92 | Electric Transmission EMS/SCADA Replacement |  |  | NA | Replacement of Energy Management System (EMS) application and supporting infrastructure at Electric Transmission's Mission Control Center and Metro Control Center | Other - Operations Tech | Replace | NA | NA | Reliability | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.2 | 20125 | Multiple | QS00452 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 471.9193 | 536.9977 | 257.1022 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
93 | Transmission CMP Non HFTD |  |  | NA | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.2 | 20126 | Multiple | QBL0098 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 27738.3414 | 40967.5456 | 45918.1862 | 43393.9224 | 36165.2397 | 38966.4509 | 33121.4836 | 31465.4093 | 29892.1392 | 28397.5316 | 22886.6921 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 28766.1064 | 42012.2332 | 38697.1546 | 33147.6278 | 38153.2337 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
94 | Transmission CMP HFTD |  |  | NA | Remediate CMP Issues in the HFTD Zone (Tier 2 & Tier 3) | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | 20127 | Multiple | QBL0092 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 8235.2118 | 16776.9388 | 15808.8961 | 15609.0096 | 16616.7904 | 14545.678 | 13818.394 | 13127.4742 | 12471.1016 | 11847.5462 | 7986.2939 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 12158.8924 | 12767.9645 | 11698.1804 | 17208.0631 | 13397.5931 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
95 | TL610 Tier 2 W2S Project |  |  | San Diego, San Diego | Wood to steel replacement on TL610 less than 2 miles. | Transmission Line - Pole/Tower | Replace | NA | 20133 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-09-11 | 36 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.35 | NA | 69 | NA | 1.1 | 20133 | 2020-0272 | QS00474, 2991115 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | 2024-12-10 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-07-28 | 2026-12-31 | 2025-10-13 | NA | NA | FALSE | 1979.963 | NA | 1979.963 | 0 | 37.3706 | 104.1737 | 95.8615 | 79.0642 | 1540.7013 | 8755.4376 | 0 | 0 | 0 | 358.3638 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
96 | TL627 Wood to Steel |  |  | Rancho San Diego, San Diego ¦ Spring Valley, San Diego | The TL627 Wood-to-Steel project consists of installing new steel pole structures, re-frame existing steel structures, and conductor along the existing 69kV tie line between Structure Z777999 and Structure Z971734 located in Spring Valley. As part of TL627 rebuild, C91 & C524 will be reconductored as well. This project was initiated as part of SDG&E’s continuous effort to improve reliability and reduce fire risks in fire-prone areas. | Multiple Options [See Notes] | Replace | NA | NA | Reliability | Fire Protection | NA | NA | 2022-10-25 | 45 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.1867 | NA | 69 | NA | 1.1 | 20134 | 2019-0257 | 2991116 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-04-24 | 2026-12-31 | 2025-05-21 | NA | NA | TRUE | 1979.963 | NA | 1979.963 | 0 | 69.4797 | 101.8187 | 438.1259 | 390.3154 | 2592.4852 | 6136.8456 | 0 | 0 | 0 | 1083.0724 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.07% ¦ Copperleaf | NA | 0% | 100% | [Project Description - What] Project is both structure and conductor replacement. [CPUC Status] NA
97 | TL649 Wood to Steel |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | 23 wood poles in HFTD2 to be replaced from wood to steel. Two of the poles (Z192597 and Z82136), are multi-transmission wood pole structures (two poles). 1.162 Miles to be re-conductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-09-18 | 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.6826 | NA | 69 | NA | 1.1 | 20135 | 2019-0268 | 2991117, 5438651 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | 2018-10-05 | IS/MND | NA | CPUC | NA | PTC | 2015-08-10 | Approved | NA | Engineering less than 50% complete | NA | 2024-05-13 | NA | 2024-08-06 | NA | NA | TRUE | 1486.209 | NA | 3115.6208 | 0 | 35.898 | 193.974 | 573.3404 | 669.8638 | 7481.7449 | 1010.3542 | 0 | 0 | 0 | 1607.768 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 8253.1878 | 0% | NA | 0.52% ¦ Copperleaf | NA | 0% | 100%
98 | TL13804 Wood to Steel Z95913-Z319244 |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego | Replace 16 existing wood structures (h-frames) with steel structures. Project spans approximately 5 miles of TL13804 and includes ~0.6 miles of reconductoring with transferring of existing conductor and fiber optic cable to new structures for the remainder. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-04-24 | 57 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project In Coastal Zone; Requires Galvanized Steel Poles |  | 16.3749 | NA | 138 | NA | 1.1 | 20136 | 2019-0255 | 2166154 | NA | TRUE | 2020-07-21 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-09-04 | 2024-02-06 | 2024-11-19 | NA | NA | FALSE | 3628.655 | NA | 3628.655 | 0 | 49.6109 | 243.776 | 293.5591 | 384.7675 | 9042.2882 | 70.4304 | 0 | 0 | 0 | 975.3165 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.17% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] NA
99 | TL23001 TL23004 Insulator and Hardware Replacement |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego ¦ Oceanside, San Diego | TL23001 TL23004 Insulator and Hardware Replacement | Transmission Line - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Insulators | NA | NA | 2023-04-20 | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 34.8284 | NA | 230 | NA | 4.1 | 20138 | 2019-4004 | 2991118 | NA | TRUE | 2020-06-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-01 | 2026-12-31 | 2022-10-11 | NA | NA | TRUE | 8040.059 | NA | 10434.997 | 0 | 14.5954 | 3423.4355 | 7062.8838 | 119.8833 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 10354.5758 | 80.4212 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
100 | TL6952 Wood to Steel |  |  | San Diego, San Diego | Replace 10 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.5 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 20139 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-06-07 | 33 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.3391 | NA | 69 | NA | 1.1 | 20139 | 2020-0287 | 2991119 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | 2024-11-08 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-10-13 | 2026-12-31 | 2025-12-31 | NA | NA | FALSE | 1810.588 | NA | 1810.588 | 0 | 13.5935 | 81.2897 | 97.4571 | 72.1732 | 1793.4398 | 7492.021 | 0 | 0 | 0 | 294.9421 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.57% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
101 | TL661 TL664 Wood to Steel |  |  | San Diego, San Diego | Replace 14 double circuit wood pole structures with underground alternative design, based on preliminary environmental scorecard suggesting a PTC would be required. Intercept existing underground ducting outside Penasquitos substation and install new steel double circuit cable pole at Z97272/Z97273. Approximately 3 miles of underground. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-07-09 | 41 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.0313 | NA | 69 | NA | 1.1 | 20140 | 2020-0289 | 2991160 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2024-12-04 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-05-06 | 2026-12-31 | 2025-09-09 | NA | NA | FALSE | 1810.588 | NA | 1810.588 | 0 | 26.003 | 146.3886 | 250.741 | 312.6505 | 5328.125 | 7889.157 | 17583.4066 | 17410.3573 | 13142.854 | 797.4579 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.79% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
102 | TL691 Wood to Steel |  |  | Fallbrook, San Diego ¦, Camp Pendleton North | The TL691 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 691 in FTZ from Z19800, north of Camp Pendleton to structure Z293940, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2020-10-10 | 51 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.1778 | NA | 69 | NA | 1.1 | 20141 | 2019-0269 | 2991163 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-03-12 | 2026-12-31 | 2026-09-16 | NA | NA | TRUE | 1979.963 | NA | 1979.963 | 0 | 44.3341 | 172.0342 | 487.9782 | 321.6839 | 2995.2905 | 19915.2209 | 27.8207 | 0 | 0 | 1121.8213 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2766.162 | 0% | NA | 0.36% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
103 | TL675 Wood to Steel Z138156-Z33075 |  |  | San Diego, San Diego | ​57 poles to be replaced from wood to steel, and 6 miles to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-03-18 | 33 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 5.4503 | NA | 69 | NA | 1.1 | 20142 | 2019-0251 | 2991164 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-07-25 | 2026-12-31 | 2026-07-07 | NA | NA | FALSE | 1979.963 | NA | 1979.963 | 0 | 27.23 | 251.0996 | 273.1235 | 418.8748 | 508.1248 | 21967.4188 | 7907.8521 | 0 | 0 | 1056.2746 | NA | NA | NA | 0 | 0 | 0 | 0 | 510.5689 | 0% | NA | 0.05% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
104 | TL6939 Wood to Steel Z198381-Z611223 |  |  | San Diego, San Diego | 42 poles in HFTD 2 to be replaced from wood to steel, and 2.5 miles to be reconductored. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2021-07-08 | 19 | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 0.9 | NA | 69 | NA | 1.1 | 20143 | 2019-0256 | 2991162 | NA | TRUE | 2020-05-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-06-01 | 2026-12-31 | 2026-06-16 | NA | NA | FALSE | 1973 | NA | 1973.076 | 0 | 0 | 0 | 0 | 237.7891 | 39.339 | 3990.238 | 4.9065 | 0 | 0 | 453.7099 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.89% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
105 | TL6910 Wood to Steel Z257408-Z122122 |  |  | Chula Vista, San Diego | R​eplace 12 wood poles to steel poles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-12-30 | 31 | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 9.0928 | NA | 69 | NA | 1.1 | 20144 | 2019-0254 | 2991161 | NA | TRUE | 2020-05-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-06-01 | 2026-12-31 | 2026-06-16 | NA | NA | FALSE | 1973.076 | NA | 1973.076 | 0 | 0 | 53.8733 | 40.5518 | 68.4187 | 75.766 | 4497.9729 | 36.0546 | 0 | 0 | 179.9048 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 1.66% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
106 | TL13811 Wood to Steel Z312779-Z119763 |  |  | San Marcos San Diego ¦ Encinitas, San Diego ¦ San Diego, San Diego | TL13811 W2S is a hardening project driven by the circuit’s location within the High Fire Threat District (HFTD) Tier 2. This project will replace all transmission structures from Chicarita Sub to Z312843, and then again from Z200897 to North County Metering Station. Throughout these sections (approximately 11.25 miles in length) the 138 kV mainline will be replaced with 636 kcmil 24/7 Strand “Rook” ACSS/AW. 96 Count OPGW will be installed from Z872457 – Z312843 (approximately 10.75 miles in length). Distribution circuits C1101 and C182 that are in the underbuild position of TL13811 will be reconductored with Covered 336.4 kcmil 26/7 Strands “Linnet” ACSR, and covered 1/0 6/1 Strands “Raven” ACSR, respectively. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-04-05 | 62 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.0003 | NA | 138 | NA | 1.1 | 20145 | 2019-0253 | 2652595 | NA | TRUE | 2020-05-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-04-17 | 2027-01-20 | 2025-06-27 | NA | NA | TRUE | 4679.537 | NA | 4679.537 | 0 | 186.1394 | 768.99 | 1402.7343 | 851.0661 | 38811.4223 | 21403.1679 | 7365.0732 | 0 | 0 | 3573.6477 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.07% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] NA
107 | Imperial Valley - Shunt Reactor Replacement |  |  | Imperial County | Replace the existing 500kV shunt reactors at Imperial Valley substation with spares at Miguel substation. | Substation - Reactive Equipment | Replace | NA | NA | Reliability | Age/Condition - Replace Reactors, Age/Condition - Replace Relays | NA | NA | 2023-10-21 13:00 | 40; 40; 40 | Lifecycle Replacement Analysis | Wires - Minimum Required Scope (spot repair) Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.4775 | 500 | 500kV | 4.1 | 20148 | 2021-2176 | 5983271, QS00482 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2022-06-01 | 2022-09-19 | 2024-05-16 | NA | NA | TRUE | 3742.255 | NA | 3742.255 | 0 | 7.7905 | 1496.0401 | 909.6009 | 239.745 | 691.8793 | 18.7768 | 0 | 0 | 0 | 2935.6944 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 681.1162 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] NA; Replacing Shunt reactors with spares from Miguel Substation; reactors are shared assets
108 | TL6920 Wood to Steel |  |  | San Diego, San Diego | 7 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.584 miles of existing 1033.5 ACSR/AW to be reconductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-04-01 | 28 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.28631 | NA | 69 | NA | 1.1 | 20149 | 2020-0286 | 2468788 | NA | TRUE | 2020-07-20 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-05-08 | 2026-12-31 | 2023-08-02 | NA | NA | TRUE | 1959.396 | NA | 4119.7009 | 0 | 0.74495 | 166.8965 | 279.6341 | 3873.0523 | 0.17697 | 0 | 0 | 0 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 4119.7009 | 12.6085 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] Project was Exempt from CPUC filing per GO-131D.
109 | TL690C Wood to steel |  |  | Camp Pendleton South, San Diego | 10 poles in HFTD 2 to be replaced from wood to steel. A total of 0.57 miles of existing 1/0 CU and 336.4 ACSR/AW to be reconductored. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-05-28 | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.49947 | NA | 69 | NA | 1.1 | 20152 | 2020-0273 | 2639298 | NA | TRUE | 2020-11-02 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-03-08 | 2023-12-29 | 2024-06-25 | NA | NA | TRUE | 3977.8055 | NA | 3977.8055 | 0 | 0.85173 | 142.1026 | 211.151 | 260.5752 | 2172.8026 | 216.5237 | 0 | 0 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 609.5016 | 1987.583 | 0% | NA | 118.91% ¦ Copperleaf | NA | 0% | 100% | [CEQA Status] CPUC & NEPA exempt [CPUC Status] NA
110 | TL649 Otay Soleado (Sunroad) Customer Relocation |  |  | San Diego, San Diego | ​​​​​1. Mixed commercial and residential development to be constructed along Harvest Road and Otay Mesa Road. Otay Mesa Road will be widened, and sidewalks will be installed along the alignment, while Harvest Road will have a portion of the road rerouted underneath the existing transmission tieline TL649 with new roads constructed. 2. Relocation of approximately three (3) transmission poles (Z37159, Z37160 and Z31764) which currently exist in the future roadway and must be relocated. The adjacent poles at each relocated structure will need be analyzed and replaced if necessary.​ 3. P6 schedule is pending – see below for an estimated high-level schedule update (preliminary and subject to change based on material lead times, permitting, regulatory approval, etc.) - 30% Design – December 2020- 60% Design - May 2021- 90% Design – July 2021- 100% Design – August 2021-Construction Start – June 2022 | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-09-18 | NA* see notes | NA | NA | NA | HFTD Tier 2 | TURE ¦ TRUE ¦ TRUE | FALSE | NA |  | 0.202 | NA | 69 | NA | 3.3 | 20158 | 2020-0309 | 2023381 | NA | TRUE | 2021-01-11 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2024-07-15 | To be Filed | 2025 | Planning | NA | 2026-01-02 | NA | 2026-05-05 | NA | NA | FALSE | 2892.487 | NA | NA | 0 | 0 | 30.2122 | -31.8574 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] 100% Customer-funded project canceled at customer request.
111 | Torrey Pines - 12kV Reliability Improvements |  |  | San Diego, San Diego | Replacing oil CB with Vacuum CB, removing Oil containment, upgrades to SL&P, and PT. Upgrading (3) 69kV breakers. Aging equipment is going to be replaced to enhance substation reliability and reduce maintenance needs. Work is on-going. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-09-08 09:53 | 18; 31; 30; 22; 22; 31; 31 | Lifecycle Replacement Analysis | Wires - Minimum Required Scope (spot repair) Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.79 | 69 | 69kV | 4.1 | 20242 | 2020-1014 | 5983185, QS00429 | NA | TRUE | 2020-01-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2023-12-18 | 2021-06-11 | 2024-07-26 | NA | NA | TRUE | 2424.176 | NA | 6870.8817 | 0 | 0 | 508.4329 | 471.6835 | 132.1145 | 455.7687 | 0 | 0 | 0 | 0 | 4470.6917 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1575.6924 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; Replacing Oil CB with Vacuum CB; removing oil containment; Upgrade SL&P, PT
112 | Kettner Rebuild |  |  | San Diego, San Diego | Replacement of: (Qty:8) 12kV Circuit Breakers, (Qty:3) 138kV Circuit Breakers, and (Qty:1) 12kV Switchgear at Chicarita Rebuild Substation, (Qty:2) Capacitor Banks and (Qty:1) Control Shelter due to proactively replace aging substation equipment to improve future SAIDI impact, Environmental concerns and Operational concerns | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2023-09-05 10:23 | 42; 42; 25 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.3 | 69 | 30MVA | 4.1 | 20251 | NA | QS00478 | NA | TRUE | 2019-01-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2021-07-01 | 2022-10-27 | 2024-07-02 | Prioritization | Construction Delays | TRUE | 7799 | NA | 718.2827 | 0 | 201.1112 | 1753.3696 | 1254.0029 | 2849.0456 | 1698.6337 | 38.6752 | 0 | 0 | 0 | 7714.1853 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 704.9014 | 13.3813 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA
113 | Aviation Firefighting Program |  |  | El Cajon, San Diego | This is a new project. Purchase, equipping and initial training of a new Sikorsky S-70i Firehawk helicopter. | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 20277 | NA | QS00481 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 1220.0683 | 1791.1333 | 140.06 | 64.6283 | 462.9721 | 0 | 0 | 0 | 0 | 26949.4815 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 3630.3953 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
114 | OH System Traditional Hardening |  |  | NA | This program (i.e., many projects) focuses on projects that replace OH Distribution system in fire prone areas including HFTD Tier 2, Tier 3, and Wildland Urban Interface. In some cases the distribution lines are underbuilt on transmission structures and require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Age/Condition - Replace Conductor | Other [See Notes] | NA | NA | NA* see notes | Other [See Notes] | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | 138 | NA | 1.1 | 20284 | Multiple | QBL0118 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 93.8724 | 563.1244 | 662.4641 | 158.5048 | 39.8415 | 0 | 0 | 0 | 0 | 0 | 0 | 429.8272 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 52.8592 | 0.23892 | 0.62596 | -0.1661 | -0.637 | 0% | NA | NA | NA | 0% | 100% | [NERC / WECC / CAISO Standard / Requirement / Contingency] This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D. [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
115 | Drone Assessments- Tier 2 |  |  | NA | The project was focused on flying and assessing all structures within the HFTD (Tier 2) with the purpose of mitigating any fire-related issues. | Other | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 20286 | Multiple | QBL0124 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 110700 | 0 | 519.6428 | 762.7732 | 1166.501 | 0 | 752.2647 | 488.7519 | 0 | 0 | 0 | 61371.6611 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 752.2647 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
116 | TL651 Relocation (Boundary Street) |  |  | San Diego, San Diego | Relocate Z91972 approximately 50-75 feet south to be outside of the MTS Right-of-Way, in order to avoid any future relocations that may be driven by MTS. The span between Z91972 and Z91973 is currently approximately 1050-feet in length, supported by guyed wood poles on either side (see Z91973-1.jpg for picture of long crossing). By relocating Z91972 to the south, the span will increase in length which will require a detailed review at Z91973 (Last replaced in 2005). Considering that the line is a long span, crosses a railroad, and applying SDGE Std. 12100 Item 1.v (see screenshot below), we propose replacing the two wood poles (Z91972 and Z91973) with two engineered steel poles. The adjacent structure to the south of Z91972, Z91971 is not expected to be replaced, but will be analyzed and if replacement is needed, a separate PCR will need to be submitted. The poles have transmission and communication conductors only. | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-01-19 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.36257 | NA | 69 | NA | 3.3 | 21128 | 2017-0118 | TBD | NA | TRUE | 2022-05-02 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | NA | 2024-08-09 | To be Filed | 2024 | Engineering more than 50% complete | NA | 2025-10-01 | 2025-06-09 | 2025-12-18 | NA | NA | FALSE | 3267.6739 | NA | 3267.6739 | 0 | 0 | 0 | 16.25 | 129.9103 | 1714.9998 | 59.3666 | 0 | 0 | 0 | 135.3521 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] [CEQA Status] Customer requested relocation requiring CPUC Advice Letter.
117 | ELEC TRANS SMALL RELIABILITY - HFTD |  |  | NA | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 1.1 | 21134 | Multiple | QBL0125 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1291.2968 | 3788.5388 | 4061.7335 | 8101.8535 | 9121.4921 | 10401.3673 | 11102.226 | 11557.3094 | 12051.6252 | 12576.4823 | 12304.2256 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1994.9689 | 1774.151 | 5315.7965 | 2689.5639 | 6150.7399 | 0% | NA | NA | NA | 21% | 79%
118 | ELEC TRANS SMALL RELIABILITY – non HFTD |  |  | NA | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the non-HFTD. | Transmission Line - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦230 | NA | 4.1 | 21135 | Multiple | QBL0126 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 2324.793 | 4803.9937 | 3814.9071 | 8598.8551 | 10764.6394 | 13600.2708 | 14368.0943 | 14948.3144 | 15574.5378 | 16239.7677 | 11471.3058 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 4008.8689 | 2789.6572 | 5117.9862 | 4766.2454 | 9081.7798 | 0% | NA | NA | NA | 21% | 79%
119 | TRANSMISSION CONSTRUCTION & MAINT - HFTD |  |  | NA | Transmission jobs in the HFTD to comply with SDG&E's obligation to serve and meet safety requirements. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Construct Roads/Gates/Culverts | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | 21136 | Multiple | QBL0127 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1067.2928 | 1611.3631 | 1284.9574 | 3274.9795 | 2298.6575 | 2927.3357 | 3096.7658 | 3196.0154 | 3359.2591 | 3481.9701 | 3484.2065 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 803.3704 | 1263.927 | 748.7844 | 1394.1046 | 3851.2972 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
120 | Suncrest Tertiary Reactor Replacement |  |  | San Diego County | The BK80/81 tertiary 12kV reactors are failing at a high rate (one in 2016, one in 2020, and two in 2021). Reactors are necessary to allow critical 500kV voltage control for grid operations. Newer, better designed, and insulated reactors are available to replace units that are failing at a quick rate. | Substation - Reactive Equipment | Upgrade/Retrofit | Replace | NA | Safety | Substation Reliability | NA | NA | 2023-10-07 13:00 | 12 | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 500 | 12kV | 4.1 | 21137 | 2021-2012 | QS00580 | NA | TRUE | 2021-05-24 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2022-03-25 | 2023-03-31 | NA | NA | FALSE | 2699 | NA | 2111.8255 | 0 | 16.6645 | 1881.2109 | 158.8877 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 | 0 | 0 | 2111.8255 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [CPUC Status] NA; Equipment failure due to improper rating and high ambient temperatures at substation
121 | HATS |  |  | NA | This project will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints and supporting the latest work practices. The project will provide additional Helicopter Access for Transmission Structures (HATS) that currently have helicopter access constraints. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.3 | 21146 | Multiple | QBL0130 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 11647.5301 | 8788.0858 | 9166.9176 | 9001.4999 | 8343.6527 | 0 | 0 | 0 | 9443.7008 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 11684.9933 | 8457.9153 | 188.8497 | 9161.8684 | 0% | NA | NA | NA | 21% | 79% | [Primary Purpose] Specialized Structure Access [Age of Asset] Unable to provide age of asset for blanket budget codes
122 | TL623C Reconductor Project |  |  | San Diego, San Diego | This project replaces 4/0 B.S. CU Conductor. OH Full Rebuild approx. 1.30 miles from structure Z180990 to Z181008 South of Otay Valley Regional Park Removes 19 existing wood structures. | Transmission Line - Multiple | Replace | NA | NA | Local Capacity Requirement | Fire Protection | NERC TPL Standards | NA | 2023-07-29 | NA* see notes | Steady State Power Flow System Analysis | Wires - Reconductor/Line Rebuild Alternative | $10 Mil -$15 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 3.62 | NA | 69 | NA | 2.1 | 21148 | 2020-0327 | 2473746, QS00634 | NA | FALSE | NA | Work Order Authorization | NA | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | NA | 2018 | 2024-07-01 | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0.57245 | 40.7127 | 3501.1828 | 0 | 0 | 0 | 0 | 37.3902 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 3512.6631 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] Unable to provide age of asset for blanket budget codes [Alternative Solutions and Costs - Solutions] Project ID on TP's records is 2017-0086. Alternative 1: Install a two hour/5 MW battery to mitigate thermal overload ~$13M [CPUC Status] NA
123 | TL6905 Headquarters Point (Underground) Customer Relocation |  |  | San Diego, San Diego | 1. Customer is planning to construct a new office facility with two (2) new buildings on a site located in Sorrento Valley, south of Lusk Boulevard and west of Wateridge Circle. 2. Conversion of approximately 0.21 miles of overhead TL6905 alignment to underground 69 kV transmission line and associated underbuilt telecommunications facilities (scope includes two (2) engineered steel cable poles, duct bank and the splice vault associated with this underground conversion). Structures adjacent to each relocated structure will need to be analyzed and replaced if necessary. 3. Underground conversion of approximately 0.21 of C1448 overhead underbuilt 12 kV distribution line (to be provided by SDG&E Design and Project Management (DPM) or other external customer-engaged Applicant Design resources). 4. Removal of six (6) TL6905 overhead transmission structures (Z96513, Z96512, Z90211, Z90212, Z90213, and Z90429). | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-01-15 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.20594 | NA | 69 | NA | 3.3 | 21149 | 2021-2431 | 2317062 | NA | TRUE | 2021-09-23 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2024-03-04 | To be Filed | 2024 | Engineering less than 50% complete | NA | 2025-09-29 | 2025-12-22 | 2025-12-22 | NA | NA | TRUE | 7066.8 | NA | NA | 0 | 0 | 4.8625 | -361.163 | 241.479 | 3039.8093 | 1618.5621 | 0 | 0 | 0 | -132.7528 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2802.5928 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] [CEQA Status] [CEQA Document Type]100% Customer requested relocation requiring CPUC Advice Letter.
124 | TCM Non-HFTD |  |  | NA | Transmission jobs in the non-HFTD to comply with SDG&E's obligation to serve and meet safety requirements set by General Orders 95,128, and other regulations. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Construct Roads/Gates/Culverts | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.2 | 21150 | Multiple | QBL0135 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5032.359 | 6816.9891 | 8070.7762 | 2671.3126 | 2788.9019 | 3277.4513 | 3502.1517 | 3438.1391 | 3640.8255 | 3803.3312 | 574.8214 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 5227.4964 | 7925.8248 | 2137.4861 | 2362.4937 | 611.5477 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
125 | Generation Interconnection Projects |  |  | NA | This is a blanket authorization for a multitude of CAISO mandated projects. CAISO approval for these projects is made in the form of a Three Party Interconnection Agreement. SDG&E has historically undertaken work for many of these types of projects to enhance and maintain reliability of the transmission grid. These projects are typically Battery Energy Storage (BESS) or other renewable projects from external parties where infrastructure is created in order to connect to SDG&E's grid through genties connecting to one of the company's many existing 69kV and above substations. Typical scope of these projects include the construction of Interconnection Facilities (ICF) which are 100% customer funded as well as Reliability Network Upgrades (RNU's) will be charged to ratepayers. Given the similar nature of many of these projects as well as the fact that the majority of these costs are refundable, our proposal will be to combine the scope of all existing projects with schedules shifting out into next year and future projects into one authorization for 2022 and future years on an annual basis. | Multiple Options [See Notes] | New | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | NA | NA* see notes | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | Multiple | 2.1 | 21156 | Multiple | QBL0141 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | Other [See Notes] | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | 2506.7347 | 7990.7975 | 33438.3876 | 37800.919 | 755.1243 | 7661.878 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4888.0018 | 4777.1189 | 1203.2578 | -2294.0104 | 2605.5714 | 0% | Multiple | NA | NA | 21% | 79% | [Project Description - What] Project scope and description varies for projects; Permitting and CEQA responsibility of 3rd party interconnection customers (not SDG&E); status varies by project [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
126 | Q1166 - Big Rock Solar Farm |  |  |  | The Big Rock Solar Farm project proposes to interconnect at SDG&E’s existing Imperial Valley 500/230 kV Substation located in Imperial County, California. The Project will be capable of generating 200 MW battery energy storage system (“BESS”) at the Point of Interconnection. The Point of Interconnection is the 230 kV bus at SDG&E’s existing 230 kV Imperial Valley (“IV”) Substation. The Point of Change of Ownership is at the PTO’s property line surrounding IV Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 230 | 500kV |  | 21156 | 2016-0045 | 5799545, 5846360, 5294880 | [11 empty] | Other [See Notes] | [9 empty] | Engineering more than 50% complete |  |  |  | 2024-08-01 | [5 empty] | <$1M | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
127 | Q1169 - Fallbrook Energy Storage |  |  |  | Interconnection of 70MW battery energy storage system ("BESS"). Point of interconnection at SDG&E's Avocado Substation; point of change of ownership is where the interconnection customer's 69kV generation tie line corosses the vertical plane of SDG&E's property line surrounding Avocado Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit |  | Generator Interconnection | [15 empty] | 69 |  |  | 21156 | 2014-01085-ZZ | TBD | [11 empty] | Other [See Notes] | [9 empty] | Operational |  |  |  | 2022-07-15 | [5 empty] | 2264500.91 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
128 | Q789 - Rugged Solar |  |  |  | Rugged Solar interconnection project ((Ted.xlsx)) ¦¦ Rugged Solar interconnection project ¦ 72 MW PV interconnection into Boulevard substation; PTO-IF scope includes below grade scope and installation of equipment (circuit breaker, disconnects, surge arrestors) to allow IC to intereconnect at Boulevard sub; includes network upgrades (relays and protection) to allow for interconnection ¦ Rugged Solar interconnection project | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 69 |  |  | 21156 | 2018-3002 | 5983096, 5983094, 5983095 | [11 empty] | Other [See Notes] | [9 empty] | On Hold |  |  |  | N/A | [5 empty] | 2612000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
129 | Q1532 Cluster 11 Kettle Solar One |  |  |  | ​​Uploaded cost estimates and final Appendix A report. ((Ted.xlsx)) ¦¦ ​​Uploaded cost estimates and final Appendix A report. ¦ 90MW BESS and PV interconnection into a new proposed switchyard on the 138kV East County-Boulevard East line. SDG&E/PTO scope includes network upgrades (relays and protection). Interconnection customer is responsible for construction of the new switchyard and 138kV loop-in. ¦ ​​Uploaded cost estimates and final Appendix A report. | Multiple Options [See Notes] | New | New | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 138 |  |  | 21156 | 2019-0227 | 5986306, 5986307, 5986308, 5986309 | [11 empty] | Other [See Notes] | [9 empty] | Engineering less than 50% complete |  |  |  | 2026-08-01 | [5 empty] | 21036140 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | Includes new switchyard and 138kV loop in; All environmental permitting is responsibility of interconnection customer
130 | Q1670 Peregrine Energy Storage |  |  |  | Peregrine Energy Storage - Generation Interconnection Project ((Ted.xlsx)) ¦¦ Peregrine Energy Storage - Generation Interconnection Project ¦ Peregrine Energy Storage - Generation Interconnection Project: The Project is a 200 MW battery energy storage system (“BESS”). The Point of Interconnection is at the 230 kV bus of PTO’s existing Silvergate Substation. Point of Change of Ownership (“POCO”) is located where the IC’s 230 kV generation tie line (“gen-tie”) crosses the vertical plane of the PTO’s property line surrounding the Silvergate Substation. The IC’s Interconnection Facilities include 230 kV underground cable and conduit package from the POCO to the Project’s substation. ¦ Peregrine Energy Storage - Generation Interconnection Project | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 230 | 230kV |  | 21156 | 2021-2091 | 5863218, 5601429 | [11 empty] | CEQA Final Published | 2022-04-05 | EIR | [7 empty] | Construction (under 10%) |  |  |  | 2024-06-01 | [5 empty] | 3369000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | CPUC GO 131-D Section III, Part B, Exemption F: City of San Diego DSD issued a CEQA Section 15162 SEIR and Negative Declarations consistency evaluation for the project on 4/5/2022. The DSD determined that the project is consistent with the Barrio Logan Community Plan Update PEIR, which was previously certified 10/2/2013, confirming no new or additional environmental impacts identified as a result of SDG&E’s scope of work (SCH No. 2009091021).
131 | Q1432 Starlight Solar |  |  |  | Starlight Solar (Q1432) ((Ted.xlsx)) ¦¦ Starlight Solar (Q1432) ¦ Starlight Solar (Q1432) project consists of co-located solar PV and a battery energy storage system producing a maximum output capacity of 20MW at the Point of Interconnection (POI). The Point of Interconnection is the 69 kV bus at the Boulevard East Substation. The Point of Change of Ownership is where the IC’s 69 kV generation tie line (“gen-tie”) crosses the vertical plane of the PTO’s property line surrounding the Boulevard Substation. The IC’s Interconnection Facilities are sole use facilities and consist of all the facilities 4and equipment owned, controlled, or operated by the IC from the Small Generating Facility to the POCO that are required to establish this interconnection. ¦ Starlight Solar (Q1432) | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 69 | 69kV |  | 21156 | 2021-2198 | 5226028, 5559780 | [11 empty] | TBD | [9 empty] | Construction (50%-75%) |  |  |  | 2026-01-30 | [5 empty] | 1447000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA
132 | Q1045 Chula Vista Energy Center 2 |  |  |  | The Chula Vista Energy Center 2 Project is a battery energy storage system (“BESS”) with a net output capacity of 50 MW at the Point of Interconnection (POI). The POI is at the 69kV bus at the existing Otay Substation located in Chula Vista, CA. The Project will utilize an existing generation tie line known as TL6929 which was constructed to accommodate the interconnection of a combustion turbine project now known as the Chula Vista Energy Center project (OY GEN). The POCO is located where TL6929 attaches to OY GEN’s pole TL6929_1. Project requires replacement of existing communication equipment between IC's facility and Otay Substation (POI). Further engineering analyses have determined an engineered steel pole will need to be replaced due to loading conditions with the comms line (fiber) replacement. Project will require replacement of fiber and installation of a new transmission pole due to the new loading conditions of the updated fiber. | Multiple Options [See Notes] | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 69 |  |  | 21156 | 2021-2379 | 5098590, 5400117 | [11 empty] | Other [See Notes] | [9 empty] | On Hold |  |  |  | 2025-04-01 | [5 empty] | 1738900 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | Includes transmission, fiber, and substation work; All environmental permitting is responsibility of interconnection customer
133 | Q1673 Nighthawk Storage |  |  |  | The Nighthawk Storage Project is a 300 MW battery energy storage system located in San Diego, California. This Project’s Point of Interconnection is at the 138 kV bus of the PTO’s existing Sycamore Canyon Substation. The POCO is located where the IC’s 138 kV generation tie line crosses the vertical plane of the PTO’s property line surrounding the Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 138 | 138kV |  | 21156 | 2021-2393 | 5430994, 5548684, 5890206 | [11 empty] | CEQA Draft Published | [9 empty] | Construction (50%-75%) |  |  |  | 2024-11-04 | [5 empty] | 2806000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | GO 131-D Exemption*: Section III, Part C (substation modification)
134 | Q1047 North Johnson Energy Center |  |  |  | The North Johnson Energy Center Project is a 50 MW battery energy storage system (“BESS”), the Project will utilize an existing underground generation tie line (“gen-tie”) known as TL6955. The Point of Interconnection is at the 69 kV bus at the PTO’s existing El Cajon Substation and the Point of Change of Ownership is located where the TL6955 crosses the vertical plane of the PTO’s property line surrounding the Substation. | Substation - Protection Relay | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 69 |  |  | 21156 | 2021-2394 | 5615088 | [11 empty] | Other [See Notes] | [9 empty] | On Hold |  |  |  | 2025-04-01 | [5 empty] | <$1M | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
135 | Q1531 - Bateria Del Sur Phase 2 |  |  |  | CED Solar Development, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Bateria Del Sur (Project) to the CAISO Controlled Grid. The Project is a Battery Energy Storage System (BESS) generating facility with a requested net output of 350 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 230 kV bus at the Imperial Valley Substation. ((Ted.xlsx)) ¦¦ CED Solar Development, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Bateria Del Sur (Project) to the CAISO Controlled Grid. The Project is a Battery Energy Storage System (BESS) generating facility with a requested net output of 350 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 230 kV bus at the Imperial Valley Substation. ¦ RWE Clean Energy, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Bateria Del Sur (Project) to the CAISO Controlled Grid. The Project is a Battery Energy Storage System (BESS) generating facility with a requested net output of 350 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 230 kV bus at the Imperial Valley Substation. ¦ CED Solar Development, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Bateria Del Sur (Project) to the CAISO Controlled Grid. The Project is a Battery Energy Storage System (BESS) generating facility with a requested net output of 350 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 230 kV bus at the Imperial Valley Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 230 | 500kV |  | 21156 | 2021-2432 | 5866223, 5697482, 7146765, 5995864 | [11 empty] | Other [See Notes] | [9 empty] | Engineering more than 50% complete |  |  |  | 2024-08-31 | [5 empty] | <$1M | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
136 | Q1657 - Sandpiper Storage |  |  |  | Falcon Energy Storage Holdings, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Sandpiper Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 200 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 138 kV bus at the Talega substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 138 | 138kV |  | 21156 | 2021-2433 | 5459133, 5509406, 5549148 | [11 empty] | TBD | [9 empty] | Engineering more than 50% complete |  |  |  | 2024-11-01 | [5 empty] | 1997000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA
137 | Q1662 - Ventasso Energy Storage |  |  |  | RWE Solar Development, LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Ventasso Energy Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 50 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 69 kV bus at the El Cajon Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 69 | 69kV |  | 21156 | 2021-2439 | 5559780, 5577688 | [11 empty] | TBD | [9 empty] | Engineering more than 50% complete |  |  |  | 2025-01-01 | [5 empty] | 1836285 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA
138 | Q1669 - Pome BESS |  |  |  | Pome BESS LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator (CAISO) to interconnect Pome BESS (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 100 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 69 kV bus at the Pomerado Substation. ((Ted.xlsx)) ¦¦ Pome BESS LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator (CAISO) to interconnect Pome BESS (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 100 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 69 kV bus at the Pomerado Substation. ¦ Pome BESS LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator (CAISO) to interconnect Pome BESS (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 100 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 69 kV bus at the Pomerado Substation. SDG&E is responsible for below-grade scope (for gen-tie and fiber) and equipment installation within the substation footprint to allow for interconnection as well as network upgrades (relays and protection); interconnection customer is responsible for all other scope items to allow for interconnection. ¦ Pome BESS LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator (CAISO) to interconnect Pome BESS (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 100 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be at the 69 kV bus at the Pomerado Substation. | Substation - Multiple | Upgrade/Retrofit | Upgrade/Retrofit | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | NA |  | FALSE ¦ FALSE ¦ FALSE | [5 empty] | 69 | 69kV |  | 21156 | 2021-2444 | 5268573, 5162830 | [11 empty] | Other [See Notes] | [9 empty] | Engineering more than 50% complete |  |  |  | 2024-05-27 | [5 empty] | 2744000 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA |  |  |  | All environmental permitting is responsibility of interconnection customer
139 | Q1806 - Captiva Energy Storage |  |  |  | BRP CA Holdco II LLC, an Interconnection Customer (IC), submitted a completed Interconnection Request (IR) to the California Independent System Operator Corporation (CAISO) to interconnect Captiva Energy Storage (Project) to the CAISO Controlled Grid. The Project is a battery energy storage system (BESS) generating facility with a requested net output of 250 MW at the Point of Interconnection (POI). The IC requested that the POI for the Project be a loop at the Trabuco - Capistrano 138 kV line. | Multiple Options [See Notes] | Multiple Options [See Notes] | Multiple Options [See Notes] | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA |  |  | Interconnection System Impact/Facilities Studies | Other - Status Quo | [8 empty] | 138 | 138kV |  | 21156 | 2021-2462 | 5502169 | [25 empty] | 2026-01-23 | [5 empty] | 33800842 | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | [13 empty] | 2605.5714 |  |  | NA
140 | Twin Engine Medium Lift Helicopter |  |  | Gillespie Field, San Diego | Purchase of a twin engine, multi­mission, medium lift helicopter for primary use of external load work. The helicopter allows for heavier lift capability for continual distribution and transmission work in the high fire threat district. The helicopter also has fire fighting capabilities | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | 21256 | NA | QS00609 | NA | TRUE | 2023-08-02 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | 21765 | NA | 21764.6864 | 0 | 0 | 368.1651 | 1589.4562 | 202.6745 | 128.0765 | 0 | 0 | 0 | 0 | NA | NA | NA | 2024 | 0 | 0 | 0 | 2160.296 | 128.0765 | 0% | NA | NA | NA | NA | NA | [Primary Purpose] Initial investigation of potential projects. [CPUC Status] NA
141 | Transmission Power Quality |  |  | NA | This project will deploy Power Quality Meters in SDG&E electric substations on transmission circuits to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 22126 | Multiple | QBL0157 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 76.3477 | 20.465 | 23.3508 | 466.9761 | 394.8028 | 2785.5499 | 522.4645 | 529.123 | 535.2935 | 534.8107 | 456.7724 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 701.3254 | 2621.6936 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
142 | Early Fault Detection |  |  | NA | This project will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. The program will also fund various analytical / software tools utilized to aggregate this highly sampled data, analyze it and use it to triangulate the failure locations so crews may be dispatched to proactively inspect / investigate with a goal of preventing significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Automation | NA | NA | NA | NA* see notes | Protection Studies | Other - Status Quo | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 1.1 | 22256 | Multiple | QB00205,QBL0148 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | -1.1914 | 1213.8 | 898.1128 | 99.05 | 457.611 | 457.611 | 0 | 0 | 11546.636 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
143 | Narrows Rebuild |  |  | San Diego County | The Narrows 88/69 kV bank is on Kearny’s “transformer watchlist” and is nearly 100 years old. The transformers are leaking oil and DGA reports indicate increasing furans, poor oil quality, deteriorating insulation, and dielectric breakdown within the transformer. The transformer is also not large enough to carry all load in the area. Grid Ops is operationally limited when using the Narrows interconnection to feed Borrego. Other infrastructure at the site is also well past its useful life. The TL800 circuit breaker is an oil breaker manufactured in 1968. The TL686 circuit breaker recently failed, forcing an unplanned outage, and was replaced with a system spare that has already been in service for 10 years. The steel bus structure likely does not meet seismic requirements, and the brown glass cap and pin insulators are a point of common failure. A TL687 breaker will be added to improve reliability of the connection to Borrego. There is evidence that the ground grid at Narrows is in poor condition. Portions of the ground grid are showing above the finished grade of the site. The grounding grid should be assessed during the design process to ensure that there are no step and touch potential concerns. During construction, any damage found will be repaired. Lastly, an updated fence will be installed to improve site security. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-26 13:00 | 55; 99; 99; 99 | Lifecycle Replacement Analysis | Wires - Replacement Alternative | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.526 | 69 | 69kV | 4.1 | 23126 | NA | QS00722 | NA | TRUE | 2023-11-29 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2026-05-20 | 2026-12-31 | 2026-12-31 | NA | NA | FALSE | 3962 | NA | 3961.6582 | 0 | 0 | 0 | 0 | 0 | 1334.4012 | 7294.6878 | 5437.1184 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 632.87% ¦ Copperleaf | NA | 0% | 100% | [CPUC Status] NA; FERC Only - new project
144 | Preliminary Survey & Investments |  |  | NA | Placeholder for preliminary design and survey work | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | Environmental | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | NA | 99997 | Multiple | NA | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 960.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 2264.5429 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 21% | 79% | [Primary Purpose] Initial investigation of potential projects. [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA
145 | SED Future Rebuilds |  |  | NA | Placeholder for future Substation Projects | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 ¦500 | NA | 4.1 | TBDET002 | Multiple | NA | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 10725.8683 | 38475.2265 | 42684.7653 | 18989.4893 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 21% | 79% | [Age of Asset] Unable to provide age of asset for blanket budget codes [Alternative Solutions and Costs - Costs] Projects are under blanket budget [CPUC Status] NA
146 | 3 Roots Relocation TL6906, TL677 & TL668 (East to West) |  |  | San Diego, San Diego | 3 Roots TL6906, TL677 & TL668 | Transmission Line - Multiple | Relocate | Upgrade/Retrofit | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-03-21 ¦ 2021-04-12 ¦ 2021-02-17 | NA* see notes | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.8 | NA | 69 | NA | 3.3 | 18143 | 2018-0188 | NA | NA | TRUE | 2019-09-09 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2023-12-06 | 2024-06-10 | 2025-12-31 | NA | NA | TRUE | 24662 | NA | 24661.554 | -138.6557 | 544.2273 | -1016.7867 | 312.2283 | 0 | 7232.1829 | 0 | 0 | 0 | 0 | -8085.6692 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 467.3348 | -392.6235 | 29.3604 | 1.4967 | -1977.9527 | 0% | NA | NA | NA | 0% | 100% | [Age of Asset] [CEQA Status] 100% Customer requested relocation requiring CPUC Advice Letter. [CPUC Status] NA
147 | Downtown Substation |  |  | San Diego, San Diego | New Downtown Substation 69 ¦12kV | Substation - Multiple | New | NA | NA | Load Growth | New Substation | NA | NA | NA | NA | Other [See Notes] | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 8 | 4.5 | 12 ¦69 | 12kV ¦69kV | 4.2 | 18251 | 2018-0170 | NA | NA | TRUE | 2020-11-16 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | 2027-11-12 | Land Rights | NA | FALSE | 501 | NA | 2235.5819 | 181.1787 | 51.3482 | 54.0713 | 10.0565 | 0 | 1582.7724 | 874.2597 | 456.0207 | 382.8625 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | NA | NA | [Types of Analyses] Distribution Planning; Load growth in the area (Distribution Planning load forecast driver) [CPUC Status] NA
148 | Granite - 12kV Breaker/Switchgear Replacement |  |  | Granite Hills, San Diego | Rebuild of the 69kV bus reconfiguring it from an ultimate 2 tie line bus to an ultimate 3 tie line substation. Replace all seven (qty: 7) 69kV kV circuit breakers (5 OCB and 2 GCB ¦older style). Install new 69kV Potential Transformers. Replace 12kV open rack bus and (qty. 8) 12kV circuit breakers and (qty:2) 12kV 1 ¦4 section Switchgear at Granite Substation, due to operational problems, again infrastructure, environmental concerns, in addition to meeting current reliability standards. Rebuilding the 69kV bus and rotating the phases at the transmission pole will allow for a third tie line position. Replacing the 12kV open rack will RFS the OCBs and address the some 12kV reliability issues, will update relaying to support WMP initiatives (advance protection). The new control shelter will assist with updating relaying to include TCRI, new 69kV BT, and increase operational ability. | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2023-09-11 13:00 | NA | Lifecycle Replacement Analysis | Wires - Replacement Alternative | $0 Mil – $1 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.38 | 12 ¦69 | 12kV ¦69kV | 4.1 | 20244 | 2021-2405 | QS00430 | NA | TRUE | 2021-07-19 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | 2021-03-19 | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2023-12-06 | 2024-07-22 | 2026-09-30 | NA | NA | FALSE | 20,000 ¦ 30,000 | NA | 21654.0813 | 0 | 0 | 22.6898 | 151.8227 | 0 | 2153.5257 | 669.5404 | 68.1459 | 0 | 0 | 7626.2763 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; Project is in flight.
149 | Chicarita 12kV Breaker |  |  | San Diego, San Diego | Replacement of: (Qty:8) 12kV Circuit Breakers, (Qty:3) 138kV Circuit Breakers, and (Qty:1) 12kV Switchgear at Chicarita Rebuild Substation, (Qty:2) Capacitor Banks and (Qty:1) Control Shelter due to proactively replace aging substation equipment to improve future SAIDI impact, Environmental concerns and Operational concerns | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2023-10-04 09:59 | 50; 30; 50 | Lifecycle Replacement Analysis | Wires - Replacement Alternative | $0 Mil – $1 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.73 | 12 ¦69 | 12kV ¦69kV | 4.1 | 20264 | 2014-00306-ZZ | QS00548 | NA | TRUE | 2021-03-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 10,000 ¦ 20,000 | NA | 9308.4328 | 228.1314 | 56.2689 | 12.9578 | 4.6326 | 0 | 0 | 2586.6256 | 389.8355 | 96.3864 | 0 | 392.4785 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 0% | 100% | [CPUC Status] NA; In Planning; project not yet scheduled; budgeted to design start beyond 2025
150 | Miguel-Sycamore Canyon 230kV Line Loop-in Suncrest |  |  | San Diego, San Diego ¦ Santee, San Diego ¦ Lakeside, San Diego ¦ Rancho San Diego ¦ San Diego ¦ Granite Hills, San Diego | Miguel-Sycamore Canyon 230kV Line Loop-in Suncrest | Transmission Line - Multiple | New | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | NA | NA* see notes | Steady State Power Flow System Analysis | Wires - System Configuration Alternative | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 27.8 | NA | 230 | NA | NA | 23127 | 2018-0199 | NA | NA | TRUE | NA | Work Order Authorization | 2023 | 2023 | FALSE | 2022 ¦ 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2032 | NA | NA | NA | FALSE | 35000 | NA | 35000 | 0 | 0 | 0 | 0 | 0 | 999.5695 | 1999.1329 | 2998.6896 | 119383.2415 | 119383.2215 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | 100% | 0% | [Age of Asset] asset age data discrepancy being corrected for future submission [CPUC Status] NA
151 | Substation External Routable Connectivity (SERC) |  |  | NA | The SERC program deploys secure routable protocol connections providing event retrieval, password management and remote secure event access to all CIP Medium, Low and No Impact substations. It achieves this by deploying Advanced Relay Event Retrieval (ARER) hardware, Siemens Crossbow devices, and deployment of systems in support thereof. The program also analyses and tests emerging ERC technology use cases and solutions. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | System Operations | NA | NA | NA | NA | Protection Studies | Other - Status Quo | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | 23129 | Multiple | QBL0160 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | 3560 | Multiple | 3560.0581 | 0 | 0 | 0 | 0 | 0 | 3431.9576 | 49.6616 | 50.733 | 51.4342 | 4.3181 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | NA | NA | NA | [Age of Asset] Unable to provide age of asset for blanket budget codes [CPUC Status] NA

## 1-2-24-Submission (hidden)
| Project Description | [31 empty] | Utility/CAISO Approval and FERC Rate Cases | [9 empty] | CPUC Permit Status | [9 empty] | Project Status | [7 empty] | Costs | [27 empty] | Notes
1 | 2 | 3a | 3b | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 14 | 15a | 15b | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40a | 40b | 41a | 41b | 42a | 42b | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 60 | 61 | 62 | 63 | 63 | 63 | 63 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Row/Line No. | Project Name(s) | Latitude | Longitude | Location2 | Project Description | Project Description - What | Project Description - Action Taken | Project Description - Action Taken (2) | Project Dependencies | Primary Purpose | Secondary Purpose | NERC/WECC/CAISO Standard/Requirement/Contingency | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Last Inspection | Age of Asset | Types of Analyses | Alternative Solutions and Costs - Solutions | Alternative Solutions and Costs - Costs | CPUC Fire Threat Zone/Rating | Wildfire Related | RAMP | Other Environmental Factors | Project Manager | Transmission Project Size (length in miles) | Substation Project Footprint (acres) | Transmission Voltage Level (kV) | Substation or Transformer Capacity (MVA and/or kV) | Utility Prioritization Ranking | Utility Unique ID #1 (Most Specific) | Utility Unique ID #2 (Less Specific) | Utility Unique ID #3 (Least Specific) | Changes in Unique IDs | Utility Approval | Year of Internal Utility Approval | Process(es) for Utility Approval | Long term Transmission Investment Plan Inclusion | CAISO Year | TPP Phase 3 | Year(s) when considered in CAISO TPP | Year when expected to be considered in CAISO TPP | Link to TPP where project has been considered, approved, and/or expected to be considered | GIDAP-Related | CEQA Status | CEQA Status - Date | CEQA Document Type | NEPA Document Type | CEQA Lead Agency | NEPA Lead Agency | CPUC Filing Type | CPUC Date Filed | CPUC Status | CPUC Status - Year | Project Status | AACE Class | Construction Start Date | Original Planned In-Service Date | Current Projected or Actual In-Service Date | Reason for Change in In-Service Date | Reason for Change in In-Service Date (2) | In-Flight Projects | Original Projected Cost or Cost Range ($000) | Cost Cap ($000) | Current Projected Total or Actual Final Cost ($000) | Actual Capital Expenditures 2019 ($000) | Actual Capital Expenditures 2020 ($000) | Actual Capital Expenditures 2021 ($000) | Actual Capital Expenditures 2022 ($000) | Actual Capital Expenditures 2023 ($000) | Actual and Forecast Capital Expenditures 2024 ($000) | Projected Capital Expenditures 2025 ($000) | Projected Capital Expenditures 2026 ($000) | Projected Capital Expenditures 2027 ($000) | Projected Capital Expenditures 2028 ($000) | Construction Work in Progress ($000) | Accrued Overhead ($000) | Accrued AFUDC ($000) | FERC: Year(s) | Dollars Put into FERC Rate Base 2020 ($000) | Dollars Put into FERC Rate Base 2021 ($000) | Dollars Put into FERC Rate Base 2022 ($000) | Dollars Put into FERC Rate Base 2023 ($000) | Dollars Put into FERC Rate Base 2024 ($000) | Percentage of Bid | Percentage and Value ($000) of Work Requested by Others Passed onto Ratepayers | Cost-Benefit Analysis | FERC Incentives | Percentage of Cost in High Voltage TAC | Percentage of Cost in Low Voltage TAC | Notes
1 | Electric Transmission Line Reliability Projects |  |  | NA | Reliability-based electric transmission projects forecasted to be less than $2M budget are included in this budget. Capital projects forecasted to be greater than $2M typically receive their own unique project-specific budget code. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 1.2 | 100 | Multiple | QB00007 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 942.6256 | 57.9682 | 167.706 | 20.266 | 1.0532 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 341.334 | 1.8306 | 0 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | 7: Project action taken varies under blanket budget activities 13: Unable to provide age of asset for blanket budget codes 45: CPUC status varies under blanket budget activities
2 | Transmission Substation Reliability Projects |  |  | NA | This budget is set based on historical averages and is financially authorized on an annual basis. This annual authorization requires a new funding request at the beginning of the year, which must be internally approved in order to be included within the Five-year Plan. The budget is then adjusted throughout the year to address safety and failure related issues. This budget is required to maintain the reliability and integrity of Transmission substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Other [See Notes] | Other [See Notes] | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 4.1 | 103 | Multiple | QB00012 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1138.5509 | 1373.4769 | 1641.5459 | 873.8694 | 672.9783 | 1564.4954 | 29874.0134 | 69848.8954 | 26798.0909 | 0 | 6094.1263 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 12306.7238 | 1868.6584 | 12313.7539 | -162.6004 | 0 | 0% | NA | NA | No | 21% | 79% | Responsive budget due to reactive work at substation; projects are under blanket budget; 13: Unable to provide age of asset for blanket budget codes 45:NA
3 | Renewal of Electric Transmission Line Easements |  |  | NA | The purpose of this parent work order is to renew various easements and/or permits for transmission rights of way that will expire within the next 5 years. These easements will allow SDGE to install and maintain electric transmission facilities across public and private lands. These transmission lines are an integral part of our electric transmission system. | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | NA | 104 | Multiple | QB00008 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 316.0454 | 64.5809 | 30.5755 | 504.7364 | 622.3588 | 1808.5333 | 771.2197 | 777.0259 | 783.0498 | 789.2673 | 1189.4606 | NA | NA | 2020 ¦ 2021 ¦ 2023 ¦ 2024 | 559.1767 | 30.8162 | 0 | 0 | 1889.427 | 0% | NA | NA | No | 21% | 79% | 9: Easement review. 13: Unable to provide age of asset for blanket budget codes 45:NA
4 | Governmental Electric Transmission Line Relocations |  |  | NA | Government Electric Transmission Relocation Projects. This Budget provides funds for engineering and construction activities associated with transmission facility conflicts identified as part of Government projects. | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 3.3 | 105 | Multiple | QB00160 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1197.9294 | 83.9077 | -2.0837 | 38.0194 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 57.6932 | -1.391 | 25.387 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
5 | Distribution Substation Reliability |  |  | NA | This budget is required to maintain the reliability and integrity of distribution substations. The specific work is required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Substation - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Other [See Notes] | Other [See Notes] | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 4.1 | 203 | Multiple | QB00030 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 63.9288 | 512.6508 | 206.333 | 108.2515 | 1.3029 | 0 | 0 | 0 | 0 | 0 | 704.2944 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 | 38.6693 | 0 | 81.0123 | 0.63813 | -16.2655 | 0% | NA | NA | No | 0% | 100% | Responsive budget due to reactive work at substation; projects are under blanket budget; 13: Unable to provide age of asset for blanket budget codes 45:NA
6 | Electric Distribution Tools & Equipment |  |  | NA | This blanket budget provides funding for new tools and equipment required by field personnel to inspect, operate and maintain the electric distribution system. | Other | New | NA | NA | Safety | Automation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | TRUE | NA |  | NA | NA | 69 | NA | NA | 206 | Multiple | QB00028 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 301.9877 | 439.5359 | 547.7187 | 196.3277 | 67.2152 | 315.8955 | 326.4499 | 334.6123 | 342.9779 | 351.5518 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 336.7511 | 0% | NA | NA | No | 0% | 100% | Budget supports new tools and equipment throughout the distribution system 13: Unable to provide age of asset for blanket budget codes 45:NA
7 | City of San Diego Surcharge Program (20SD) |  |  | NA | This authorization is for all work on Budget 213. Work is mandated by franchise agreement with the city of San Diego, and is 100% billable. All work orders will be estimated by DPSS and will be approved individually | Transmission Line - Underground | Relocate | NA | NA | Work requested by others | Facility Relocation | Other [See Notes] | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | NA | 69 | NA | 3.2 | 213 | Multiple | QB00029 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | Other | Other | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5684.5728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965.446 | NA | NA | 2020 ¦ 2021 ¦ 2023 | 987.7077 | 146.3419 | 0 | -51.2275 | 0 | 0% | NA | NA | No | 0% | 100% | 11: required by City of San Diego to perform work. 42: City of San Diego is lead agency. 13: Unable to provide age of asset for blanket budget codes 45:NA
8 | Telecommunication asset projects |  |  | NA | This is a blanket budget to support all IT Telecommunication asset projects | Other - IT | Multiple Options [See Notes] | NA | NA | Reliability | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | 925 | Multiple | QB00114 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 1147.0951 | 1.3369 | 0 | 0 | 0 | 0% | NA | NA | No | NA | NA | 7: New, replacements, and upgrades 13: Unable to provide age of asset for blanket budget codes 45:NA
9 | Transmission Obsolete Equipment |  |  | NA | The Substation Equipment Assessment Team will develop alternatives to replace or remove obsolete and problematic equipment. A condition assessment process and evaluation criteria have been created using probability and risk analysis, financial impacts and present value analysis to justify projects. Equipment that is truly obsolete such as equipment that cannot be maintained (no spare parts available), or which poses a safety risk will be replaced. Each year the average age of all substation equipment increases, with the oldest transformer currently 60+ years old. The ranking of substation equipment is an ongoing process and involves identifying equipment that presents a significant risk to the system. Based on the cost availability of raw materials and global demand, the lead times for major substation equipment have increased to 6 months for breakers and at least 1.5 years for transformers. | Substation - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 4.1 | 1145 | Multiple | QBL0003 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3402.8882 | 1520.5744 | 3349.3163 | 2045.4696 | 472.9499 | 1777.7082 | 3473.9399 | 3654.9542 | 3819.9798 | 3769.4298 | 12885.8916 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 15523.0623 | 10296.9357 | 5823.316 | 6189.251 | 1159.6408 | 0% | NA | NA | No | 21% | 79% | 7: Projects are under blanket budget 13: Unable to provide age of asset for blanket budget codes 45:NA
10 | Transmission System Automation |  |  | NA | To enhance transmission system reliability, capital projects are required to 1) install new transmission SCADA systems and 2) replace/upgrade existing transmission SCADA systems to provide control and monitoring capability for grid operations. In addition, there is a requirement to install systems to provide monitoring of certain critical substation apparatus to provide data for enhanced scheduling of maintenance. There are also new security requirements based upon NERC guidelines and the SEMPRA Control System security policy, which mandate the need to install equipment to control access to equipment installed in substations. The budget also allows us to enable remote event retrieval in non-Medium Impact substations to significantly reduce the time it takes to obtain event records and situational awareness during system disturbances. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Relay Upgrades | NERC CIP Compliance | NA | NA | NA* see notes | Other [See Notes] | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | 373MVA | 4.3 | 3171 | Multiple | QBL0001 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 7200.9894 | 6065.5563 | 6441.7652 | 2415.9565 | 2130.8099 | 3206.5252 | 4224.6563 | 3995.6072 | 3993.7113 | 3806.9681 | 14421.6172 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 161.0225 | 251.9798 | 11400.0098 | 4773.1216 | 3231.7266 | 0% | NA | NA | No | 21% | 79% | 14: Information security 13: Unable to provide age of asset for blanket budget codes 45:NA
11 | Ocean Ranch Substation |  |  | Oceanside, San Diego | Install a new 69/12kV substation in the North Vista/Oceanside area. Current substations that support this load (Melrose, Morro Hill, Oceanside, and San Luis Rey) are expected to be at 85% aggregate loading in 2016 and 96% in 2021. | Substation - Multiple | New | NA | NA | Load Growth | New Substation | Other [See Notes] | NA | 2023-09-21 07:40 | NA* see notes | Other [See Notes] | Other [See Notes] | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 1.0084 | 69 | 69kV | 4.2 | 5253 | 2014-00047-ZZ | TBD | NA | FALSE | 2014-02-25 | Work Order Authorization | 2010 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2017-10-02 | IS/MND | NA | CPUC | NA | PTC | 2017-03-06 | Approved | 2017 | Operational | NA | 2018-01-22 | 2019-06-01 | 2019-02-07 | Completed Early | NA | FALSE | 54404 | NA | 28413.0071 | 9263.7246 | 317.3437 | 4.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 264.5629 | 2.3943 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Load growth in the area (Distribution Planning load forecast driver) 13: New Substation 14: Distribution Planning
12 | South Orange County Reliability Enhancement |  |  | San Juan Capistrano, Orange ¦ San Clemente, Orange | To rebuild the existing Capistrano Substation, which is currently a 138/12kV distribution substation to a 230/138/12kV. Remove TL13835 (SMO-LNL) between Talega Substation and Capistrano Substation. Open TL23007 (SONGS-TA) at Talega Substation and loop into Capistrano Substation two new 230kV' TLs (SONGS-CP230kV & CP-TA 230kV). Re-arrange 138kV TL's 13833, 138736, and 13812 bay positions at Talega to allow for the termination of TL13835 (SMO-TA) at Talega Substation. | Transmission Line/Substation | Multiple Options [See Notes] | NA | NA | Load Growth | Substation Capacity | NERC TPL Standards | NA | 2023-10-27 13:18 | 55; 62; 52;56; 54; 19 | Steady State Power Flow System Analysis | Multiple Options [See Notes] | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Transmission Foundations At Talega Canyon Containing High Levels Of Sulfate. Mitigated By Installing Cmp To Protect Concrete Foundations |  | 9.1339 | 6 | 230 | 230kV | 2.1 | 6129 | 2014-00068-ZZ | 2066680, 2651832, 2652342, 2651833, 2652278, 5983099, 5050193, 5983101, 5983102, 5983103, 5983104, 5983105, 5983106, 5983107, 5983836, 5983837, 2800095, 2455441, 5984480, 5984481, 2389801, 2652340 | NA | FALSE | 2017-06-01 | Work Order Authorization | 2006 | 2011 | FALSE | 2009 ¦ 2010 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-04-25 | EIR | NA | CPUC | NA | CPCN | 2012-05-18 | Approved | 2016 | Construction (over 75%) | NA | 2018-06-29 | 2015-05-18 | 2024-11-01 | Construction Delays | Construction Delays | TRUE | 381000 | 419,100 ¦ CPCN | 381000 | 0 | 0 | 0 | 16.2501 | 129.9103 | 1714.9998 | 59.3666 | 0 | 0 | 0 | 34782.5986 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 78952.2982 | 129188.5734 | 5201.7747 | 91820.4274 | 0 | 0% | NA | NA | No | 100% | 0% | SOCRUP Alternative 1: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and build a new Escondido to Capistrano 230 kV line using existing right-of-way. Estimated cost for this alternative is $454.8 million. 2. SOCRUP Alternative 2: Rebuild Capistrano 138kV substation (aging infrastructure maintenance project), reconductor 138kV lines – Talega – Pico, Talega – Laguna Niguel, Talega – Trabuco, Capistrano – Trabuco, Talega – Rancho Mission Viejo, and upgrade SONGS – Talega 230 kV lines. Upgrade two 230/138 kV transformer banks at Talega. Estimated cost for this alternative is $347.6 million. 3. SOCRUP Alternative 3: Rebuild Capistrano 230 kV substation, build a new SONGS – Capistrano 230 kV line using existing right-of-way, and tap off a 230 kV line to Capistrano from existing Escondido – Talega 230 kV line. Estimated cost for this alternative is $364.8 million. Approved Alternative
13 | Emergency Transformer & Switchgear |  |  | NA | This budget supports the restoration of service to our distribution customers following outages caused by equipment failure by purchasing additional emergency spare and mobile equipment. Spare equipment is necessary to provide construction and operations with the appropriate spares to replacement equipment under failure conditions. Spare equipment is typically use for critical situations and the stock must be kept up to date to minimize chances for mismatch in field. | Substation - Multiple | Replace | NA | NA | Reliability | Substation Reliability | NERC TPL Standards | NA | NA | NA* see notes | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230 | 28MVA | 4.1 | 6254 | Multiple | QBL0024 | NA | TRUE | 2016-05-10 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 375.7862 | 288.8328 | 987.1972 | 277.6598 | 266.417 | 1544.4427 | 487.3079 | 499.4632 | 510.3523 | 521.2302 | 431.1484 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 521.1663 | 1171.5107 | 333.7874 | 266.4452 | 148.2544 | 0% | NA | NA | No | 100% | 0% | 13: Unable to provide age of asset for blanket budget codes 45:NA
14 | Fiber Build Initiative |  |  | NA | Install ADSS and or OPGW fiber optic cables on existing Transmission overhead structures and build UG facilities as required. 2020 has (20) active projects at various stages of engineering and construction. All projects to date are exempt from CPUC permitting. | Other | New | NA | NA | Reliability | NERC CIP Compliance | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 4.3 | 7144 | Multiple | QBL0025 | NA | TRUE | 2016-09-01 | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1291.2968 | 3788.5388 | 4061.7335 | 8101.8535 | 9121.4921 | 10401.3673 | 11102.226 | 11557.3094 | 12051.6252 | 12576.4823 | 29636.4761 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4896.5473 | 704.6285 | 4239.7195 | 44.6794 | 6150.7399 | 0% | NA | NA | No | 21% | 79% | Program consists of multiple same scope projects per transmission line with separate environmental permits. 13: Unable to provide age of asset for blanket budget codes 45:NA
15 | Cleveland National Forest (CNF) |  |  | Julian, San Diego ¦ Alpine, San Diego ¦ Pine Valley, San Diego ¦ San Diego, San Diego County | These projects involve fire hardening five 69kV transmission lines (TL625, TL6931, 629, 682 and 6923) and segments of seven distribution lines (C78, C79, C222, C157, C440, C442 and C449) which traverse in and out of the Cleveland National Forest (CNF). In addition to wood to steel conversion, TL626 will be removed from service and approximately 27 miles of overhead 12kV distribution will be converted to underground. The project also includes attaining a Master Special Use Permit from the US Forest Service to replace over 70 expired Special Use Permits for existing SDG&E facilities on the CNF. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-02-07 ¦ 2023-07-01 ¦ 2023-09-07 ¦ 2021-02-09 ¦ 2021-04-13 | NA ¦ NA ¦ NA ¦ NA ¦ 27 * see notes | NA | NA | NA | HFTD Tier 3 ¦ Zone 1 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 224.33 | NA | 69 | NA | 1.1 | 8165 | 2014-00071-ZZ | 2052282, 2505207, 2587013, 2596316, 2650658, 2651101, 2651102, 2651103, 2651104, 2651107, 2651115, 2651116, 2651275, 2651276, 2651305, 2651306, 2651307, 2651308, 2651309, 2651345, 2651347, 2651348, 2651349, 2651350, 2651352, 2651572, 2651573, 2651770, 2901463, 2901472, 2901492, 2901493, 2901660, 2902561, 2983110, 2986990, 2986991, 2986994, 2989040 | NA | TRUE | 2016-05-10 | Work Order Authorization | 2008 | NA | FALSE | NA | NA | NA | FALSE | NA | 2016-01-01 | EIR | EIS | CPUC | FOREST SERVICE | PTC | 2012-10-17 | Approved | 2016 | Construction (over 75%) | NA | 2016-09-30 | 2020 | 2021-10-01 | Permitting | Permitting | TRUE | 680000 | NA | 423532.1888 | 0 | 0 | 0 | 0 | 0 | 162.9107 | 162.9107 | 162.9107 | 162.9107 | 162.9107 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 151423.1757 | 14320.6991 | 684.165 | -0.30186 | 0 | 0% | NA | NA | No | 0% | 100% | 13: asset age data discrepancy being corrected for future submission
16 | TL6926 - Wood to Steel |  |  | Valley Center, San Diego | Fire harden a portion of TL6926 by replacing approximately 50 wood poles with equivalent steel poles in the high fire threat and wind-prone areas. TL6926 is a single circuit 69 kV transmission line located between the Valley Center Substation and the Rincon Substation. Approximately one mile of the line will be reconductored. The line will be fire hardened between poles Z12820 and Z114811, with the exception of the portion located adjacent to Valley Center Road near the Rincon Casino. Approximately one mile of the transmission line will be reconductored. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-09-01 | 45 | NA | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 4.6374 | NA | 69 | NA | 1.1 | 9132 | 2014-00061-ZZ | 2902140, 2652399 | NA | TRUE | 2011-06-15 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2019-11-13 | Approved | 2020 | Operational | NA | 2020-10-19 | 2020-10-31 | 2023-06-30 | NA | NA | TRUE | 19559.489 | NA | 102428.8017 | 1115.9209 | 16086.0507 | 54034.4148 | 10288.0922 | 2723.7517 | 726.0646 | 1834.8836 | 0 | 0 | 0 | 119.9926 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 100051.9875 | 2291.9576 | 653.5931 | 0% | NA | NA | No | 0% | 100% | Advice Letter/ Project Completed with temporary shoo-fly configuration
17 | TL649 - Wood to Steel - Otay-San Ysidro-Border |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | A portion of TL649 is within the fire and wind prone area. Replace a portion of TL649 with steel poles in order to maintain existing electric transmission in high fire threat & wind prone areas in SDG&E territory. TL649 is a 69 kV single-circuit transmission line located between pole Z188714 & pole Z31758. The proposed project consists of the following components: Replace approximately 116 existing wood power line and interest distribution line poles with galvanized steel structures. Approx. half of the replacement poles will be direct buried with the other half being engineered foundations (pier & micropile).Reroute approximately 130 feet of existing underground distribution lines. Conduct overhead work on one existing pole and transfer existing power line conductors to the new steel poles. Replace the existing distribution conductor with new ACSR distribution conductor. | Transmission Line - Multiple | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-09-18 | 34 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.7111 | NA | 69 | NA | 1.1 | 9137 | 2017-0120 | TBD | NA | TRUE | 2019-07-12 | Work Order Authorization | 2009 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | NA | IS/MND | NA | CPUC | NA | PTC | 2015-08-10 | Approved | 2019 | Operational | NA | 2019-07-11 | NA | 2020-02-22 | NA | NA | FALSE | 42500 | NA | 29685.145 | 19546.9482 | 6117.3729 | 64.463 | 1.3955 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 29658.6315 | 54.952 | 1.1916 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | No Comments
18 | TL686 Wood-to-Steel/Reliability Upgrades |  |  | San Diego County | TL686 Wood-to-Steel will include the replacement of 182 wood and wood equivalent steel (SW) poles with 120 new poles. Scope includes the reconductoring of 14.6 miles of 69kV transmission and associated 12kV distribution underbuild (where underbuild is present) from Warners substation to just outside the Tier 2 HFTD (ending at structure Z118409). All replacements will be either direct-buried SW poles or foundation steel poles. Direct-buried transmission SW and distribution SW Round (SWR) poles shall be backfilled with concrete and gravel. Engineered steel poles shall have either drilled pier or micropile foundations. Per SDG&E’s fire hardening standards, traditional 69 kV design and construction standards with additional phase spacing and insulation shall be used and guy anchors shall be avoided. Shield wire with a fiber (OPGW) will be added to protect phase conductors from lightning damage. All transmission conductors in this project shall be reconductored. All poles will be designed to accommodate one level of third-party communication. | Transmission Line - Pole/Tower | Replace | Removal | 1044 (Budget Code 23126) | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-01-27 | 45 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 24.6759 | NA | 69 | NA | 1.1 | 9142 | 2018-0161 | 2984061 | NA | TRUE | 2019-01-01 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | NA | BLM | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-10-31 | 2024-09-30 | 2027-04-21 | Land Rights | Permitting | TRUE | 10181.003 | NA | 15272.6679 | 9622.1519 | 6788.9883 | 1369.6965 | 12113.6339 | 1657.1821 | 4272.3354 | 4393.0293 | 4573.0624 | 5373.6637 | 6305.8224 | 9605.6563 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 2877.0452 | 0% | NA | 0.62% ¦ Copperleaf | No | 0% | 100% | NEPA document/process yet to be finalized with BLM 45:NA
19 | TL676 Reconductor (Mission-Mesa Heights) |  |  | San Diego, San Diego | The TL676 project is a reconductor project between Mesa Heights Substation and Mission Substation. It includes reconductoring approx. 4.3 miles of transmission line (TL676) with single 900 ACSS/AW, reconductoring approx. 3.7 miles of distribution underbuild with single 636 ACRS/AW, and converting sections of the 69kV out of both substations with underground getaways. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Age/Condition - Replace Wood Poles | CAISO Requirement | NA | 2023-05-22 | 24 | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.9515 | NA | 69 -138 | NA | 2.1 | 9153 | 2011-00017-ZZ | 2982360, 2382250, 2382251, 2382252, 2382253 | NA | FALSE | 2016-09-01 | Work Order Authorization | 2011 | 2011 | FALSE | 2010 ¦ 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2017-07-25 | Approved | 2017 | Operational | NA | 2018-06-24 | 2015-06-01 | 2019-06-07 | Prioritization | NA | FALSE | 45000 | NA | 38557.1668 | 11638.1785 | 361.4143 | 52.1278 | 0.13369 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 3884.255 | 46.9643 | 0.13369 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | No Comments
20 | Overstressed Breakers |  |  | NA | Replace overstressed breakers as identified at the following substations : Bay Boulevard, Mission, Sycamore Canyon, San Luis Rey, Miguel | Substation - Circuit Breaker | Replace | NA | NA | Reliability | Age/Condition | NERC TPL Standards | NA | NA | NA* see notes | Short Circuit Duty Analysis | Short Circuit Duty Analysis | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 138 | Multiple | 2.1 | 9170 | Multiple | QBL0061 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 2324.793 | 4803.9937 | 3814.9071 | 8598.8551 | 10764.6394 | 13600.2708 | 14368.0943 | 14948.3144 | 15574.5378 | 16239.7677 | 3207.367 | NA | NA | 2020 ¦ 2022 ¦ 2023 ¦ 2024 | 36.8775 | 0 | 8460.4178 | 109.4131 | 9081.7798 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45:NA
21 | Synchrophasors (PMU/WASA) |  |  | NA | This project provides funds for the installation, upgrade, and expansion of SDG&E’s Phasor Measurement Units (PMUs), commonly referred to as Synchronized Phasors or Synchrophasors which will be used for monitoring the health of the Electric System, Wide Area situational Awareness (WASA) and Wide Area Monitoring Protection and Control (WAMPAC). The project will install new PMUs or upgrade existing PMUs and install Phasor Data Concentrators (PDC), hardware, associated communication network, and software. | Substation - Other Equipment | Replace | NA | NA | Reliability | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 4.3 | 10138 | Multiple | QBL0062 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 12591.1143 | 10255.4012 | 6162.4376 | 6689.3799 | 6559.6327 | 6372.3512 | 5646.7984 | 5874.2425 | 6101.5832 | 6392.1241 | 5523.29 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 248.6809 | 23308.7689 | 32.6132 | 1278.6712 | 6291.3079 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
22 | TL690E Reconductor (Camp Pendleton) |  |  | Camp Pendleton, San Diego | Replace approx. 72 wood poles with overhead steel poles and/or underground cabling. Reconductor approx. 5.4 mi from Stuart Tap to Las Pulgas Substation. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2021-05-28 | 60 | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 5.3506 | NA | 69 | NA | 1.1 | 10143 | 2014-00050-ZZ | 2981430, 5981369, 5981957 | NA | FALSE | 2020-11-11 | Work Order Authorization | 2012 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Other [See Notes] | NA | Exempted | Other [See Notes] | CPUC | MCBCP | PTC | 2024-12-16 | To be Filed | 2026 | Engineering less than 50% complete | NA | 2027-02-10 | 2015-06-01 | 2028-02-18 | Project Design | Permitting | TRUE | 26232.1568 | NA | 26232.1568 | 3777.8453 | 3694.7636 | 7014.3563 | 8073.6062 | 4722.7067 | 4338.3835 | 1250.1414 | 1366.1268 | 1610.011 | 1430.2177 | 12550.9072 | NA | NA | 2020 ¦ 2023 ¦ 2024 | 0.12957 | 0 | 0 | 0 | 14505.3557 | 0% | NA | 2.15% ¦ Copperleaf | No | 0% | 100% | Likely will be CatEx for CPUC; NEPA permit TBD by MCBCP
23 | TL691 Wood to Steel and Reconductor (Avocado - Monserate Camp Pendleton) |  |  | Fallbrook, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL691 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2020-10-10 | 51 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.5485 | NA | 69 | NA | 1.1 | 10144 | 2014-00051-ZZ | 2981470, 5981963 | NA | TRUE | 2020-11-19 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2019-11-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Advice Letter | 2020-12-03 | Approved | 2021 | Construction (25%-50%) | NA | 2023-04-28 | 2024-04-18 | 2024-05-31 | NA | NA | TRUE | 63239.0651 | NA | 63239.0651 | 32274.0378 | 84595.1362 | 44416.8091 | 24991.5609 | 32236.7226 | 10088.2024 | 0 | 0 | 0 | 0 | 31979.6034 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 41225.1162 | 0% | NA | 2.61% ¦ Copperleaf | No | 0% | 100% | CPUC CatEx
24 | TL692 Wood to Steel (Camp Pendleton) |  |  | Camp Pendleton, San Diego | This project will replace existing wood poles along TL692 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-06-03 | NA | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.6533 | NA | 69 | NA | 1.1 | 10145 | 2014-00225-ZZ | 2981410, 5981367, 5983108 | NA | TRUE | 2011-01-11 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2019-07-19 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-05-17 | NA | 2021-11-01 | NA | NA | TRUE | 34365.984 | NA | 17350.09 | 778.7658 | 2900.3357 | 12457.7287 | 1531.8875 | -47.4758 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 16098.9216 | 1298.8384 | -47.67 | 0 | 0% | NA | NA | No | 0% | 100% | CPUC CatEx 45:NA
25 | TL695 TL6971 Reconductor (Camp Pendleton) |  |  | San Clemente, Orange | Transmission Planning has identified TL695 as a NERC Category B violation therefore the conductor size must be upgraded to an acceptable capacity. This project will also replace existing wood poles along TL695 within the Fire Threat Zone with new steel poles and associated hardware. Transmission Engineering will double circuit TL695 (and future TL6971) from Basilone Substation to Japanese Mesa Substation, cross the Edison 230kV corridor, travel north along the existing 138kV corridor to Talega Substation. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NERC TPL Standards | NA | 2022-09-13 | 55 | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.8008 | NA | 69 | NA | 1.1 | 10146 | 2014-00074-ZZ | 2981440, 5981952, 5981987, 5983032 | NA | FALSE | 2020-11-12 | Work Order Authorization | 2012 | 2012 | FALSE | 2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | CEQA Draft Published | 2017-07-07 | IS/MND | EA | CPUC | MCBCP | PTC | 2016-04-25 | Approved | 2018 | Permitting | NA | 2024-10-17 | 2016 | 2026-07-23 | Project Design | Permitting | TRUE | 36049.0968 | NA | 36049.0968 | 4055.5234 | 4950.4495 | 5415.5568 | 6205.0808 | 5536.0709 | 8160.7856 | 8112.2365 | 9632.1247 | 9823.5818 | 10322.6232 | 15743.1039 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 2735.3451 | 0% | NA | 3.06% ¦ Copperleaf | No | 0% | 100% | NEPA permit pending
26 | TL6912 Wood to Steel Replacement (Camp Pendleton) |  |  | Oceanside, San Diego ¦ Camp Pendleton North, San Diego | This project will replace existing wood poles along TL6912 within the Fire Threat Zone with new steel poles and associated hardware. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-07-19 | 30 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.5058 | NA | 69 | NA | 1.1 | 10149 | 2022-3073 | 2981450 | NA | TRUE | 2020-11-02 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | 2017-12-01 | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-01-27 | NA | 2020-09-04 | NA | NA | TRUE | 25191.7609 | NA | 14098.9451 | 2134.6523 | 9929.1867 | 1277.2013 | -29.4637 | 0 | 84.9 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 13243.6626 | 1223.2109 | -367.9284 | 0 | 76.41 | 0% | NA | NA | No | 0% | 100% | Project complete. Project ID Replaced From 2014-00073 to 2022-3073 45:NA
27 | TL663 Reconductor (Mission-Kearny) |  |  | San Diego, San Diego | Construction of this project provides a long term “wires” mitigation for the identified NERC CAT B reliability criteria indications. Availability of the short term non wires option of depending on the pre contingency dispatch of the Kearny gas turbines to provide loading relief is no longer available after 2013. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | T-Line Capacity | NERC TPL Standards | NA | 2022-08-11 | NA* see notes | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.5902 | NA | 69 | NA | 2.1 | 11126 | 2011-00018-ZZ | 2982340, 2368750, 2368751, 2982341, 2982342, 2982343, 2982344, 2982345, 2982346, 2982347, 2982348, 2982349 | NA | FALSE | 2016-04-01 | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2017-05-31 | Approved | 2017 | Operational | NA | 2017-12-13 | 2015-06-01 | 2020-02-26 | Bundling Dependencies | Permitting | TRUE | 43000 | NA | 39879.8863 | 6333.9957 | 2446.4842 | 545.3879 | 558.5325 | 67.3847 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 38014.0634 | 1215.1722 | 589.0169 | 61.6338 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Asset age data discrepancy being corrected for future submission
28 | TL644 Reconductor (Bay Blvd - Sweetwater) |  |  | National City, San Diego ¦ Chula Vista, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NERC TPL Standards | NA | 2022-10-19 | NA* see notes | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2.0338 | NA | 69 | NA | 2.1 | 11154 | 2011-00021-ZZ | 2982810 | NA | FALSE | 2018-01-01 | Work Order Authorization | 2012 | 2011 | FALSE | 2011 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2010-2011TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-05-15 | 2013-06-01 | 2022-05-15 | Permitting | Prioritization | TRUE | 9464.457 | NA | 10692.0315 | 960.496 | 187.8435 | 2482.2866 | 2407.6727 | 702.5488 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 10022.2501 | 669.7814 | 0 | 0% | NA | NA | No | 0% | 100% | 9: NERC Category B Criteria 13: asset age data discrepancy being corrected for future submission 45:NA
29 | Automated Fault Location (TEAM) |  |  | NA | This project provides funds for installation, upgrade, and expansion of SDG&E's Event Reporting Software and hardware to include Automated Fault Locator. This new system known as TEAM will provide accurate fault location within seconds by measuring the parameters at both ends of the line (multiple ends on multi-terminal lines) and time synchronizing the events with GPS clock. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Other [See Notes] | Automation | NA | NA | NA | NA* see notes | Protection Studies | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 12129 | Multiple | QBL0063 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 448.5463 | 424.6434 | 537.9743 | 82.3357 | 7.0931 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 1456.9706 | 80.6676 | 40.988 | 0 | 0% | NA | NA | No | 100% | 0% | 9: System Protection 13: Unable to provide age of asset for blanket budget codes 45:NA
30 | Substation SCADA Expansion- Transmission |  |  | NA | The project provides funding for the installation, upgrades, and expansion of the Supervisory Control and Data Acquisition (SCADA) system at transmission substations. Additionally, this project improves the protection of SDG&E’s transmission system to provide fast isolation for faults and system disturbances. Includes upgrading relays including increased security, differential protection, and traveling wave fault finding technology to reduce restoration times. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Install SCADA/RTU | NERC PRC Compliance | NA | NA | NA* see notes | Protection Studies | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 12132 | Multiple | QBL0064 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 695.0528 | 3527.8217 | 3042.0546 | 14720.5483 | 2988.6699 | 538.2414 | 0 | 0 | 0 | 0 | 1657.7121 | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 2318.2561 | 510.4552 | 756.3739 | 0 | 0% | NA | NA | No | 100% | 0% | 13: Unable to provide age of asset for blanket budget codes 45:NA
31 | TL639 Wood to Steel Replacement |  |  | San Diego, San Diego | The TL639 Fire Hardening and Reconductor Project consists of installing new steel structures along the 69kV tie line between Elliott Substation and Structure Z100981, located inside Sycamore Canyon. The replacement structures from TL639 Elliott to Structure Z379545 will be constructed in conjunction with TL636, since most of the structures in that portion are single pole double circuit. TL639 Wood to Steel will cover pole replacements starting at Sycamore Canyon Substation to Structure Z379545. The project spans approximately 4.8 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2019-11-16 | 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 8.1767 | NA | 69 | NA | 1.1 | 12136 | 2012-00005-ZZ | 2983340, 2983341 | NA | TRUE | 2023-10-04 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-10-31 | 2026-12-31 | 2023-12-04 | NA | NA | TRUE | 17883.8405 | NA | 17883.8405 | 351.4966 | 475.69 | 838.6306 | 2314.2942 | 5093.5888 | 1113.7353 | 0 | 0 | 0 | 0 | 10444.0574 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 9663.2159 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
32 | TL6916 Wood to Steel Replacement |  |  | San Diego, San Diego | APPROXIMATELY 5 MILES OF FIRE HARDENING ON TL6916 WOOD TO STEEL PROJECT. ALL EXISTING WOOD TRANSMISSION POLES WILL BE REMOVED FROM SERVICE/REPLACED WITH PRE ENGINEERED POLES OR ENGINEERED STEEL POLES AND ASSOCIATED DISTRIBUTION WOOD POLES ON CIR434 AND CIR920 WILL BE REPLACED WITH STEEL POLES. NEW CONDUCTOR 900ACSS WILL REPLACE EXISTING 900ACSS CONDUCTOR DUE TO CONSTRUCTION AND OUTAGE CONSTRAINTS OF EXISTING CONFIGURATION. DISTRIBUTION CONDUCTOR WILL BE UPGRADED TO 636 AND #2 ACSR CONDUCTOR. 1-96CT ADSS WILL BE INSTALLED FROM Z678465 TO Z100980. 31 NEW SW POLES WILL BE INSTALLED ALONG WITH 12 NEW ENGINEERED STEEL POLES. WE PREDICT 9 DRILLED PIER FOUNDATIONS AND 3 NEW MICROPILE FOUNDATIONS WILL BE INSTALLED. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-11-04 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.7679 | NA | 69 | NA | 1.1 | 12137 | 2012-00006-ZZ | 2983350, 2983351 | NA | TRUE | 2018-01-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2026-12-31 | 2022-07-11 | NA | NA | TRUE | 24362.992 | NA | 14436.8476 | 536.7097 | 363.6876 | 1587.8671 | 11993.0233 | 200.154 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 14264.7751 | 172.0725 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Asset age data discrepancy being corrected for future submission 45: Project was Exempt from CPUC filing per GO-131D.
33 | TL615 TL659 Direct Buried Cable Replacement (Cabrillo - Point Loma) |  |  | San Diego, San Diego | Replace approximately six (6) miles of direct buried cable on TL615 and TL659 within the streets of Point Loma into a new double circuit 69kV duct package infrastructure with off-setting substructures in an effort to mitigate reliability issues associated with aging direct buried cable systems. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2022-04-15 | 47 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.7 | NA | 69 | NA | 4.1 | 12138 | 2012-00011-ZZ | QS00068 | NA | TRUE | 2021-09-16 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-04-11 | NA | 2026-09-17 | Permitting | Land Rights | FALSE | 46528 | NA | NA | 920.89 | 1191.9396 | 989.8139 | 1042.8332 | 845.2716 | 523.5006 | 3303.9606 | 850.954 | 19389.0914 | 10132.5725 | 28863.733 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 45: CPUC filing requirements to be determined.
34 | TL633 Overhead Reconductor |  |  | San Diego, San Diego | The CAISO has approved this reconductor project, which is required to mitigate a projected overload in 2015. In order to accomplish this, the Project will upgrade TL6913 (Poway - Pomerado) and all associated relay and control equipment to achieve a minimum 148 MVA continuous/emergency rating. By reconductoring the existing wire from 1033.5 ACSR/AW to 900 ACSS/AW, the current line rating of 136MW will improve to 174MW. | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Load Growth | Line Reconductoring | NA | NA | 2023-05-02 | 34 | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 2.88 | NA | 69 | NA | 2.1 | 12139 | 2012-00028-ZZ | 2982932, 2988470, P650576, 2983360, 2983361, 2983362, 2983363, 2988471 | NA | FALSE | 2016-01-01 | Work Order Authorization | 2012 | 2012 | FALSE | 2011 ¦2012 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2011-2012TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | CPUC | NA | Advice Letter | 2017-11-15 | Approved | 2017 | Operational | NA | 2019-11-07 | 2015-06-01 | 2019-11-07 | Permitting | Land Rights | FALSE | 46190.46 | NA | 48544.1722 | 19414.3973 | 1254.123 | 71.5639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 48477.913 | 66.2591 | -2.5466e-14 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 17: Reconductor HFTD Tier 2
35 | Merchant Switchyard Ownership/NV Energy Vacate Bay |  |  | Boulder City, Clark | On October 1, 2011 SDG&E acquired the desert star energy center (DSEC), A 480 MW Power Plant in Boulder City, Nevada, The adjacent Eldorado-Merchant 230kV transmission line requires upgrades to accommodate the change in boundary authority from NV energy to CAISO. This job will include the design and construction of facilities necessary for SDG&E to gain operational control of merchant. | Other | NA | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-13 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 72.1226 | 230 | NA | 2.1 | 12140 | 2014-00227-ZZ | TBD | NA | TRUE | 2013-05-13 | Work Order Authorization | 2012 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | 2014-09-15 | NA | 2015-07-11 | NA | NA | FALSE | 11528.455 | NA | 14927.5086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 14927.5086 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 12: Acquisition of Substation in 2011; 45: FERC Only
36 | TL636 Wood to Steel Replacement |  |  | San Diego, San Diego | Replacing wood pole with steel equivalent from Northern structure at Z200694 to Elliott Substation. The purpose for this project is for fire hardening of this corridor due to it being within the FTZ and classified as high to extreme fire danger. The project spans approximately 6.07 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2023-03-02 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 5.8672 | NA | 69 | NA | 1.1 | 12144 | 2012-00015-ZZ | 2983940, 2983942 | NA | TRUE | 2022-07-07 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-18 | 2026-12-31 | 2022-10-17 | NA | NA | TRUE | 25131.9882 | NA | 21257.1391 | 575.0215 | 996.1296 | 2457.9571 | 15743.3178 | 1644.9849 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 21132.2362 | 124.9029 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Asset age data discrepancy being corrected for future submission 45: Project was Exempt from CPUC filing per GO-131D.
37 | TL694 Wood to Steel |  |  | Fallbrook, San Diego ¦ Oceanside, San Diego | This project replaces 4.8 miles, approximately 80 wood structures, to direct-embed and engineered steel poles and replace the existing 636 ASCR/AW conductor to harden the electric transmission and distribution systems and increase reliability in the region. This project will also mitigate some existing access issues to the structures. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-07-17 | 60 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.85 | NA | 69 | NA | 1.1 | 12149 | 2012-00014-ZZ | 2984281, 2984280 | NA | TRUE | 2021-02-09 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-01-05 | 2026-12-31 | 2026-01-13 | NA | NA | TRUE | 36464.0897 | NA | 36464.0897 | 370.1681 | 1203.3315 | 3504.6217 | 1725.0428 | 16949.5984 | 8699.4186 | 0 | 0 | 0 | 0 | 4021.611 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 44143.3852 | 0% | NA | 1.01% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
38 | TL13831 Wood to Steel Replacement (Talega - Rancho Mission Viejo) |  |  | Orange County | The purpose of project is to replace approximately 72 wood poles for steel equivalent from Rancho Mission Viejo to Talega Substation for fire hardening. The project spans approximately 6.46 miles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-03-18 | 29 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 6.377 | NA | 138 | NA | 1.1 | 12150 | 2012-00019-ZZ | 2984300, 2984301, 2369410, 2369411 | NA | TRUE | 2018-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-08-15 | 2026-12-31 | 2023-04-23 | NA | NA | TRUE | 41615.025 | NA | 19904.0839 | 923.1502 | 533.1916 | 2434.0244 | 12550.1509 | 4903.2732 | 0 | 0 | 0 | 0 | 0 | 132.7427 | NA | NA | 2023 | 0 | 0 | 0 | 19904.0839 | 0 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
39 | TL13838 Wood to Steel Replacement (Margarita - Rancho Mission Viejo) |  |  | Orange County | This project replaces nine poles with steel, approximately 1.4 miles of 1033.5ACSR/AW, insulators and hardware. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-03-09 | 11 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.6748 | NA | 138 | NA | 1.1 | 12152 | 2012-00020-ZZ | 2984290, 2984291 | NA | TRUE | 2018-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2021-09-24 | 2026-12-31 | 2022-01-17 | NA | NA | TRUE | 4653.916 | NA | 2573.3341 | 277.5555 | 271.6898 | 1173.2442 | 428.2031 | 245.0556 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 2341.0556 | 232.2785 | 0 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
40 | TL600 Reliability Pole Replacements |  |  | San Diego, San Diego | This project replaces an existing 33 (between Phases 1, 2, and 3) transmission structures on TL600. | Transmission Line - Pole/Tower | Replace | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | CAISO Requirement | NA | 2023-05-22 | 63 | NA | Lifecycle Replacement Analysis | $10 Mil -$15 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.9991 | NA | 69 | NA | 4.1 | 12156 | 2012-00023-ZZ | 2984460, 2984461, 2984462, 2306700, 2306701, 2984463 | NA | TRUE | 2020-12-14 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | 2012-01-01 | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2013-02-01 | See Notes | 2022-08-29 | NA | NA | TRUE | 13591.4008 | NA | 7801.1408 | 713.7244 | 1466.0789 | 1956.4616 | 849.8624 | 435.355 | 198.0502 | 0 | 0 | 0 | 0 | 224.1628 | NA | NA | 2022 ¦ 2023 ¦ 2024 | 0 | 0 | 6109.9589 | 376.9468 | 188.1477 | 0% | NA | NA | No | 0% | 100% | This was a phased project. Different phases had different target completion dates. 45:NA
41 | Aerial Marking Implementation (Risk Mgmt and Low Level Safety Flights) |  |  | NA | This project will add aerial marker balls and /or lighting at locations identified by Transmission Engineering, Transmission maintenance personnel, or AL&M support team as safety concerns or necessary for FAA compliance. These locations fall under SDG&E’s expanded aerial lighting and marking policy that seeks to reduce the risk of collisions and improve safety. This will be an ongoing project as Transmission Construction & Maintenance may provide additional locations with safety concerns and for the Aerial Lighting and Marking company initiative. The work includes analyzing current structures for strength and clearance to add marking, replacing structures as necessary, and installing aerial marking and/or lighting. | Transmission Line - Multiple | NA | NA | NA | Safety | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.2 | 12159 | Multiple | P162638 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5183.3007 | 4907.7989 | 794.8546 | 123.3039 | 13.8643 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 3236.1865 | 5710.4218 | 125.5466 | 13.395 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
42 | TL664 Sorrento to Miramar Customer Relocation |  |  | San Diego, San Diego | TL664 Sorrento Miramar Customer Relocation | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2022-07-09 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.19576 | NA | 69 | NA | 3.3 | 13123 | 2021-2082 | TBD | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2024-04-16 | To be Filed | 2024 | On Hold | NA | 2025-01-30 | NA | 2025-04-16 | NA | NA | FALSE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Project on hold at 60% design milestone. 100% Customer requested relocation requiring CPUC Advice Letter. 13: asset age data discrepancy being corrected for future submission
43 | SX-PQ 230kV Transmission Line |  |  | San Diego, San Diego | The Proposed Project includes approximately 16.7 linear miles of transmission line as well as associated access roads and work areas, all of which are located primarily within the City of San Diego, a small portion of the City of Poway, and on the extreme northern portion of Marine Corps Air Station (MCAS) Miramar. The Proposed Project will result in a new 230 kV transmission line that will connect the existing Sycamore Canyon and Peñasquitos Substations through utilization of existing SDG&E facilities, ROWs, and City of San Diego franchise position. Segment A - Construction of approximately 8.31 miles of new 230 kV transmission line on new tubular steel poles all within existing SDG&E ROW located between the existing Sycamore Canyon Substation and Carmel Valley Road Segment B - Install new, approximately 2.84-mile 230 kV underground transmission line in Carmel Valley Road utilizing existing franchise position for almost the entire segment Segment C - Install new 230 kV conductor on the existing 230 kV steel structures and one new tubular steel pole all within existing SDG&E ROW located between Carmel Valley Road and Peñasquitos Junction Segment D - Install new 230 kV conductor on existing double-circuit 230 kV steel lattice towers and relocate two existing 69 kV power lines to new tubular steel poles all within existing SDG&E ROW located between the Peñasquitos Junction and the existing Peñasquitos Substation Minor modifications of the existing Sycamore Canyon and Peñasquitos Substations to allow for connection of the new 230 kV transmission line | Transmission Line - Multiple | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | CAISO Requirement | NA | 2023-06-30 | NA* see notes | Steady State Power Flow System Analysis | Multiple Options [See Notes] | Multiple Options [See Notes] | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 13.3942 | NA | 230 | NA | 2.1 | 13128 | 2014-00044-ZZ | 2650975 | NA | FALSE | 2016-11-01 | Work Order Authorization | 2013 | 2013 | TRUE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2016-10-13 | EIR | NA | CPUC | NA | CPCN | 2014-04-07 | Approved | 2016 | Operational | NA | 2017-01-03 | 2017-06-01 | 2018-08-29 | Construction Delays | NA | TRUE | 260000 | 260,000 ¦ CPCN | 255511.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 4034.3556 | 142.2257 | -0.00046 | -5.4001 | 0 | 0% | NA | NA | No | 100% | 0% | Alternatives Analysis listed in FEIR see attached link https://ia.cpuc.ca.gov/Environment/info/panoramaenv/Sycamore_Penasquitos/FEIR.html 13: new transmission line
44 | DelMar Reconfiguration Project |  |  | Del Mar, San Diego ¦ Solano Beach, San Diego ¦ San Diego, San Diego | Eliminate the need for ongoing O&M work in environmentally sensitive areas (San Dieguito Lagoon, Torrey Pines State Park and Los Penasquitos Lagoon) by removing TL666D from service (Phase IV). Install a new underground 69kV transmission line segment along Via de la Valle, which will provide a new TL connecting the Del Mar Substation to the North City West Substation. This will replace the existing TL 674A tap that will be eliminated in Phase II as part of the Rancho Santa Fe Tap reconfiguration. | Transmission Line - Multiple | Upgrade/Retrofit | Relocate | NA | Reliability | Environmental | NA | NA | 2023-10-10 09:55 | NA* see notes | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 7.2489 | NA | 69 | NA | 2.1 | 13130 | 2013-00010-ZZ | 2985250, 2985251 | NA | FALSE | 2020-12-15 | Work Order Authorization | 2015 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-21 | IS/MND | NA | CPUC | NA | PTC | 2017-06-28 | Approved | 2019 | Operational | NA | 2020-12-30 | 2015-06-01 | 2023-10-12 | NA | NA | TRUE | 488.098 | NA | 27673.8443 | 708.1595 | 913.4336 | 2289.415 | 1541.6075 | 635.8347 | 3810.7685 | 13011.7927 | 10753.4903 | 2009.5082 | 0 | 11585.9192 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 26669.8059 | 1004.0384 | 0 | 0% | NA | NA | No | 0% | 100% | Major project construction activities completed on November 15, 2023. 13: asset age data discrepancy being corrected for future submission
45 | CBM Gas Breakers |  |  | NA | This project is a continuing effort to sustain GCB SF6 Tracking and implement Condition Based Maintenance by installing monitors on approximately 900 Gas Circuit Breakers (GCBs). | Substation - Circuit Breaker | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | NA | NA* see notes | Other [See Notes] | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 4.3 | 13139 | Multiple | QS00086 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3370.1517 | 3686.8071 | 4732.6084 | 2049.5418 | 1377.9392 | 643.4388 | 0 | 0 | 0 | 0 | 10318.9377 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2024 | 7006.1574 | 3479.4568 | 3687.4675 | 0 | 9826.4356 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
46 | Kearny - Rebuild 69kV/12kV Sub |  |  | San Diego, San Diego | The Kearny Substation rebuild will consist of relocating the existing installation to the west side of the Kearny facility on a larger and more suitable location to accommodate a low profile 120MVA substation. The relocation will be on the existing Kearny facility property zoned for utility use, and therefore will not be subject to any permits. It will be rebuilt on the site once utilized by transformer oil tanks, in the southwest corner of the Kearny facility. This site will allow space for all required expansion to meet existing and projected electric distribution load growth and the ultimate arrangement will allow for feeds to existing generators and proposed battery storage area. It is anticipated that the rebuild will improve Kearny’s reliability by 98%. The ultimate arrangement of the substation will consist of five 69kV bays consisting of five 69 kV TL breakers, one 69kV bus tie breaker, four 69 kV bank breakers, one 69kV ground bank and associated breaker, four 30 MVA 69/12 kV low profile transformers, four ¼ sections of switchgear, four 12 kV capacitors, one new control shelter, new relaying, SCADA, five 69 kV transmission lines, and sixteen distribution circuits. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-09-29 | 20; 59; 54; 59; 55; 54; 55; 40; 55; 20; 20; 15 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12046 | NA | 69 | 120MVA | 4.1 | 13242 | 2014-00210-ZZ | PSS0028 | NA | TRUE | 2015-09-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-11-06 | NA | 2020-01-10 | NA | NA | FALSE | 47947 | NA | 20430.7246 | 1021.7362 | 222.8276 | 14.8608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 215.4731 | 14.8445 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 45: The project is completed and was exempt from CPUC filings. No permits were required due to move forward with the project.
47 | Streamview Substation Rebuild |  |  | San Diego, San Diego | Initially expand the existing 69/12 kV substation from two to three banks to increase capacity on the system, with future expansion to four banks. Scope to construct a new 69 kV tie line between the Station F Substation and the Streamview Substation within an existing transmission corridor has been REMOVED. | Transmission Line/Substation | Multiple Options [See Notes] | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-16 | 21; 54; 21; 52;6; 2 | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.38816 | 69 | 69/12 KV, 28 MVA | 4.2 | 13244 | 2014-00062-ZZ | 5984765, 5907328 | NA | TRUE | 2021-06-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Categorical Exclusion | CPUC | NA | PTC | 2020-11-30 | Approved | 2020 | Construction (under 10%) | NA | 2020-03-11 | 2026-07-14 | 2029-01-15 | NA | NA | TRUE | 543 | NA | 83383.2211 | 4106.1362 | 1243.0493 | 482.8375 | 2788.8514 | 1296.8375 | 19456.3952 | 8726.8253 | 7995.5738 | 665.316 | 0 | 14230.1596 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 3622.8086 | 299.6637 | 33.7723 | 149.5358 | 0% | NA | NA | No | 0% | 100% | Expansion and replacement of existing aging 69/12kV infrastructure at the Streamview Substation. Add (2) new 12kV distribution circuits, C1493 and C1494. Enhance Streamview Substation reliability by rebuilding to current standards. Reduce substation customer per circuit count at Station F and Streamview substation
48 | Suncrest 230kV 300MVAr Dynamic Reactive Power Support |  |  | San Diego County | In the draft 2013-2014 Transmission Plan, the CAISO has identified a potential policy driven need for installation of a synchronous condenser facility or SVC at the 230kV bus within Suncrest Substation. The preferred alternative will add one +320/-100 MVAr SVC at the Suncrest Substation 230kV bus. SDGE is required to submit a bid to the CAISO by Monday, June 16, 2014 to compete for the right to engineer, procure, and construct an SVC facility connected at the 230kV Suncrest bus. SDGE submitted the bid for Suncrest Substation as requested by the CAISO on June 16, 2014. SDGE submitted a response on July 22, 2014 to the deficiency letter received from the CAISO. An additional follow up request was submitted to the CAISO on August 15, 2014 as part of the CAISO's project qualification process. On September 9, 2014 SDGE was identified by the CAISO as being a qualified project sponsor for the Suncrest policy driven project. | Substation - Voltage Support Equipment | NA | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | Load Interconnection | CAISO Requirement | NA | 2023-10-07 13:00 | NA* see notes | Interconnection System Impact/Facilities Studies | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.9412 | 230 | 300MVA | 2.1 | 14126 | 2014-00076-ZZ | TBD | NA | FALSE | 2021-07-03 | Work Order Authorization | 2015 | 2014 | TRUE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | CPCN | 2019-07-12 | Approved | 2018 | Operational | NA | 2019-05-28 | 2017 | 2020-02-24 | Permitting | Land Rights | FALSE | 798 | NA | 3711.61 | 2916.2219 | 470.3467 | 28.9237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 3662.4194 | 28.9193 | 0 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 13: New substation equipment
49 | 230kV Artesian Substation |  |  | San Diego, San Diego | Per the CAISO 2013-2014 Final Plan, SDG&E will expand the existing 69/12kV Artesian Substation to a 230/69/12kV Substation (Artesian East Substation) to alleviate the existing 69kV congestion at Sycamore Canyon Substation. In addition, the Proposed Project will help mitigate Cat B contingencies and increase reliability to the Poway Area Load Pocket which is expected to grow by as much as 12% in the next 10 years. The Proposed Project will be built on existing SDG&E Artesian Substation land and adjacent land east of the current substation site, also owned by SDG&E (pending final sale negotiations). Transmission work includes the loop-in of TL23051 (SX-PEN), terminating TL616C into the Artesian 69kV substation to form two (2) 69 kV Artesian - Bernardo lines; reconductoring both Artesian - Bernardo lines to achieve a 145/179 rating (TL6939 & segment of TLNew), and replacing underground getaways at Artesian, Bernardo, Rancho Carmel, and Poway to achieve new ratings. Permitting and Environmental will be required for the expanded 230/69/12kV substation, in addition to the reconductor work associated with the project. Requested ISD of the ISO is June 2016, however the team proposes and ISD of December 2018 depending on application filing, and receipt of approval from the Commission. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Capacity | NERC TPL Standards | NA | 2023-10-05 | 21;21;21;15;23;15;23;15;23;15;15 | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.9377 | 230 | 230/69kV, 224 MVA | 2.1 | 14128 | 2014-00056-ZZ | 5983218, 5984695 | NA | FALSE | 2013-07-01 | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | Final Certified | 2019-03-22 | IS/MND | NA | CPUC | NA | PTC | 2019-10-07 | Approved | 2020 | Operational | NA | 2020-04-17 | 2016-06-01 | 2022-12-04 | Permitting | Construction Delays | TRUE | 17140 | NA | 130112.5516 | 15274.1608 | 0 | 0 | 0 | 0 | 1104.5159 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 50195.6024 | 74458.1935 | 1557.4884 | 1104.5159 | 0% | NA | NA | No | 100% | 0% | No Comments
50 | TL6975 San Marcos to Escondido |  |  | San Marcos, San Diego ¦ Carlsbad, San Diego ¦ Lake San Marcos, San Diego ¦ Escondido, San Diego | Segment 1: Rebuild approximately 1.8 miles of an existing 69kV circuit (TL 680C) to create a double circuit from San Marcos Substation to Melrose Tap. Construction at San Marcos Substation including installation of a new circuit breaker par, seven piers, and an A-frame for the new line. Along Segment 1, all wood pole structures would be replaced with steel poles; porcelain insulators would be replaced with polymer insulators. Segment 2: Construct 2.8 miles of new single-circuit 69kV overhead power line on new steel poles in the existing transmission corridor from Melrose Tap to Meadowlark Junction adjacent to existing TL 13811/13825 power line, approximately 50-feet east of the centerline of the existing structures. Segment 3: Transition new line (described under Segment 2, above) and reconductor approximately 7.4 miles of power line; remove and replace existing copper conductors with new 636 ACSS/AW conductors and existing porcelain insulators with polymer insulators; construction at the existing Escondido Substation to accommodate new circuit. | Transmission Line - Multiple | New | NA | NA | Load Growth | New T-Line | NERC TPL Standards | NA | NA* see notes | NA* see notes | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 11.9036 | NA | 69 | 69kV | 2.1 | 14137 | 2014-00078-ZZ | 2986471 | NA | FALSE | 2022-08-31 | Work Order Authorization | 2015 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | PEA Deemed Complete | 2018-03-16 | IS/MND | NA | CPUC | NA | PTC | 2017-11-15 | Approved | 2021 | Operational | NA | 2021-10-19 | 2015-06-01 | 2023-02-28 | Permitting | Land Rights | TRUE | 10,000 ¦ 100,000 | NA | 50158.381 | 1335.1916 | 1477.0227 | 8784.9334 | 32029.5756 | 2197.7199 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 ¦ 2023 | 0 | 529.1659 | 332.0915 | 49297.1237 | 0 | 0% | NA | NA | No | 0% | 100% | 12: TL energized 2023-02-28 13: new transmission line
51 | TL698 Wood to Steel Replacement (Monserate - Avocado) |  |  | Fallbrook, San Diego | The TL698 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 698 in FTZ from Z10213, north of Monserate Substation, to structure Z293941, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. TL698 is located within existing easements. TL698 will be designed for (3)-636 ACSS/AW conductors and the existing 336 ACSR/AW conductors will be retired. There will be one SDG&E 96-count ADSS and one position for a third party installed along the line from Z10212 to Z293941. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-12-06 | 49 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 4.2938 | NA | 69 | NA | 1.1 | 14140 | 2014-00009-ZZ | 2271085 | NA | TRUE | 2021-08-31 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (under 10%) | NA | 2023-10-27 | 2026-12-31 | 2024-08-07 | NA | NA | TRUE | 150 | NA | 41381.4385 | 888.666 | 723.9364 | 1268.569 | 1008.3142 | 1181.8055 | 3105.142 | 2786.9594 | 3424.4163 | 3646.5487 | 3707.2472 | 380.2909 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 1968.6566 | 1246.6941 | 1971.7615 | 2789.1623 | 0% | NA | 1.02% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
52 | Poway Substation Rebuild |  |  | Poway, San Diego | The purpose of this project is to rebuild Poway Substation to a low profile distribution substation with an ultimate capacity of 120MVA. The current substation consists of aging infrastructure, no SCADA control, and a control shelter that cannot accommodate new panels for any SCADA upgrades. Adding SCADA control and replacing old equipment will increase the reliability of this sub and allow room for any future expansion. Substation, Transmission, and Distribution work are required for this rebuild. Installing SCADA to Poway Sub will increase reliability by giving Mission Control remote access to operate the equipment. Replacing aging infrastructure also increases reliability. Building a new control shelter allows for any future expansion. | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Age/Condition | NA | NA | 2023-09-26 12:00 | 23;30;46;30;47;49 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.36956 | 69 | 120MVA | 4.1 | 14143 | 2017-0095 | 2986910, PSS019 | NA | TRUE | 2015-04-01 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2015-10-26 | NA | 2018-11-06 | NA | NA | TRUE | 28839 | NA | 21857.5534 | 416.9023 | 547.4167 | 478.3805 | 914.0113 | 10.3026 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | -40.4736 | 2.4413 | 1398.6141 | 10.3026 | 0 | 0% | NA | NA | No | 0% | 100% | Project has been completed. 45:NA
53 | Helicopter Access for Transmission Structures (HATS) Work Release 1 |  |  | San Diego County | Obtain the necessary permits, environmental clearance and regulatory authority for the helicopter landing areas along our transmission system. Relocate approximately 6 existing Sunrise Tower Staging Access Pads (TSAP) to locations that are better suited for TCM's O&M requirements. Build platforms at approximately 12 of the TSAPs and create 8 new TSAPs at tower locations to ensure safer and more secure landing areas for TCM. Establish approximately 15 permanent staging/fly yard locations, one acre or less in size, at locations along Sunrise that will best meet TCM's needs. Many of these will be at the same fly yard locations utilized for construction of Sunrise. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | HFTD Tier 3 ¦ Zone 1 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230-500 | NA | 1.3 | 14145 | 2014-00060-ZZ | 2686773, 2984870 | NA | TRUE | 2021-09-22 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-06-24 | 2019-03-01 | 2020-12-28 | Construction Delays | NA | FALSE | 499 | NA | 15071.928 | 3755.8273 | 6293.535 | 4215.1246 | -185.8243 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 11057.0747 | 4215.1246 | -185.8243 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 9: Remote access landing pads for transmission structures 45: NA
54 | CAST Security Upgrades |  |  | NA | CAST is an ongoing program that addresses security for critical substation assets. | Substation - Other Equipment | New | NA | NA | Physical Security | Security Upgrades | Multiple Options [See Notes] | Multiple Options [See Notes] | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 230-500 | 230kV/500kV | 1.2 | 15125 | Multiple | QBL0020 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 2100.0192 | 580.4096 | 13084.0079 | 1012.4843 | 2582.5834 | 11564.1221 | 8190.8722 | 153.693 | 0 | 0 | 26185.3747 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 25943.0437 | 23922.725 | 31572.0836 | 25436.1939 | 0 | 0% | NA | NA | No | 100% | 0% | 11: NERC CIP Compliance and Security Assessments 13: Unable to provide age of asset for blanket budget codes 45:NA
55 | Rancho Santa Fe - Sub Fire Hardening / Rebuild |  |  | Rancho Santa Fe, San Diego | Replace approximately one (1) mile of direct-buried cable along Old Seaworld Drive to a new 69kV duct package infrastructure relocated onto Sea World Drive. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-09-21 11:28 | 64; 69; 61 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.12094 | NA | 69 | 69kV | 1.1 | 15246 | 2014-00289-ZZ | PSS0027 | NA | TRUE | 2015-12-11 | Work Order Authorization | 2015 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2017-07-10 | NA | 2020-11-18 | NA | NA | FALSE | 15034 | NA | 7618.3272 | 365.014 | 2684.7836 | 1534.6687 | 8.9299 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 196.0093 | 7250.4838 | 8.6311 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Alternative - run to failure 9: Specialized Structure Access 45:NA
56 | Mid-Coast Corridor Transit Project (Relocation) |  |  | San Diego, San Diego | Mid-Coast: As part of SANDAG's Mid Coast Trolley Extension Project, SDG&E will be relocating multiple electric and gas services from the Santa Fe Depot in downtown San Diego to the University City community. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.2125 | NA | 69 | NA | 3.3 | 15258 | 2015-00016 | 4162439, 4164166, 4176438, 4185920, 4207134, 4227650, 530000163833, 530000196039, 530000196527, 530000197131, 530000200652, 530000211727, 2087844, 2087846, 2087849, 2321276, 2321279, 2356300, 2424730, 2424731, 2424732, 2424733, 2424737, 2424738, 2436614, 2436615, 2470380, 2470383, 2529611, 2529612, 2529614, 2529615, 2529617, 2529619, 1525800, 1525810, 1545577, 2087847, 2321274, 2321278, 2321279, 2424739, 2436610, 2436611, 2436612, 2436613, 2436616, 2470385, 2470386, 2470388, 2470389, 2529613, 2529616, 2529618, 2651341, 2651661, 2652611, 2985650, 2985653, 2985654, 2985656, 2985659, 2986861, 2986862, 2986863 | NA | TRUE | 2015-12-05 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | CPUC | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2016-10-03 | NA | 2022-08-17 | NA | NA | TRUE | 22439 | NA | 7244.0358 | 161.3832 | 652.165 | 1245.3496 | 2165.9791 | 361.4901 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 655.01 | 66.7479 | 3503.5331 | 381.6753 | 0 | 0% | NA | NA | No | 0% | 100% | 7: Multiple project relocations, some new construction, some reconstruction, some removal 13: multiple project relocations required by others 45:NA
57 | Fire Threat Zone Adv Protect & SCADA Upg |  |  | NA | Replaces aging circuit breakers and/or obsolete electromechanical relays, to create a more comprehensive protection system by taking advantage of newer field technologies under installation by the FiRM program, and to create visibility in fire threat areas with installation of Distribution SCADA. Adding distribution SCADA and replacing obsolete distribution relays and aging equipment. Improve distribution reliability and improve fire safety. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | SCADA Switch Installation | NA | NA | NA | NA* see notes | Protection Studies | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 | 120MVA | 1.1 | 15259 | Multiple | QBL0071 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 2034.9499 | 5911.756 | 8689.0565 | 12205.0175 | 11223.936 | 13037.367 | 8496.2469 | 277.9378 | 0 | 0 | 66240.836 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 56.0093 | 4141.1392 | 5161.9731 | 17446.3413 | 14172.9505 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45:NA
58 | Substation Security Installations - Under $500k |  |  | NA | This budget is required to maintain the reliability and integrity of the security of electric substations. The specific work required to meet safety requirements, replace obsolete or failed equipment, and make necessary small capital additions is based on requests from Engineering, Planning, Operations, and Maintenance groups. | Other - Physical Security | Multiple Options [See Notes] | NA | NA | Reliability | Security Upgrades | NERC CIP Compliance | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 4.3 | 16126 | Multiple | QBL0002 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 123.3571 | 502.4708 | 598.3269 | 401.3375 | 545.3317 | 3707.8422 | 16867.2352 | 735.7592 | 0 | 0 | 4163.9034 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 2656.2569 | 269.1069 | 4148.4855 | 13392.1399 | 3288.0369 | 0% | NA | NA | No | 21% | 79% | Projects are under blanket budget 13: Unable to provide age of asset for blanket budget codes 45:NA
59 | Substation Auxiliary Power System |  |  | NA | This project will develop, procure, design, and install three enclosed fuel cell units manufactured by GenCell. One unit will be installed at Descanso Substation, one unit will be installed at Boulevard East Substation, and one unit will be installed at Warners Substation. Each fuel cell will connect to the substation’s DC panel via a DC breaker. | Substation - Multiple | New | NA | NA | Reliability | Emergency Response - Storm Related | NA | NA | NA | NA* see notes | Interconnection System Impact/Facilities Studies | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 138 | Multiple | 4.3 | 16133 | Multiple | QS00137 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1182.9766 | 82.1523 | 7.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 | 2039.5043 | 7.4317 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45:NA
60 | Substation DC Reliability Upgrades |  |  | NA | This project installs new assets in existing substation control shelters to support increased power requirements driven by aging infrastructure replacements of telecommunication hardware. Scope includes installation of new communication racks, upgrades to 125V DC systems for power, adding HVAC in transmission substation control shelters to support equipment environmental control requirements, DC-DC power converters, as well as batteries and Station Light & Power (SL&P) upgrades. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 16138 | Multiple | QBL0094 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2017-04-04 | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0.85173 | 142.1026 | 211.151 | 260.5752 | 2172.8026 | 216.5237 | 0 | 0 | 0 | 3827.6249 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 8102.4175 | 7533.5637 | 4917.9388 | 3257.5534 | 1987.583 | 0% | NA | NA | No | 100% | 0% | 13: Unable to provide age of asset for blanket budget codes 45:NA
61 | TL23001 TL23004 Wood to Steel Replacement (Mission - San Luis Rey) |  |  | San Diego, San Diego | TL23001 and TL23004 from Mission to San Luis Wood to Steel pole replacement. The scope of work includes replacing 42 existing wood pole structures with engineered steel structures as well as stringing 3.5 miles of new single conductor 1033 ACSR one line of OPGW and one line of 7#8 shield wire for TL23001 and TL23004. | Transmission Line - Conductor | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 2.9735 | NA | 230 | NA | 1.1 | 16150 | 2014-00016-ZZ | 2982933 | NA | TRUE | 2016-01-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-10-18 | 2026-12-31 | 2020-03-31 | NA | NA | FALSE | 22646.466 | NA | 28842.643 | 16356.2278 | 10219.9705 | 123.9126 | 0.60204 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 28720.3845 | 121.6565 | 0.60204 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 45: Project was Exempt from CPUC filing per GO-131D.
62 | New 2nd Miguel to Bay Blvd. 230 kV Line |  |  | Bonita, San Diego ¦ Chula Vista, San Diego | New 2nd Miguel to Bay Blvd. 230 kV Line | Transmission Line - Conductor | New | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | New T-Line | NERC TPL Standards | NA | NA | NA | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 9.8716 | NA | 230 | NA | 2.1 | 16157 | 2015-00021 | TBD | NA | FALSE | 2017-08-31 | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-04-02 | 2018-06-01 | 2019-08-21 | Permitting | Construction Delays | FALSE | 24499.998 | NA | 21457.951 | 12648.4165 | 717.5751 | 40.835 | 0.00798 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 691.3548 | 39.4429 | 0.00759 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 45:NA
63 | TL605 Reconductor (Silvergate-Urban) |  |  | San Diego, San Diego | Reconductor TL605 with 2-636ACSS (200MVA) or equivalent Note: there is an active project (ID:2015-00013; budget code: 16158) with ISD of 6/26/2024. This new summited cost request is to upgrade the current design line rating from 137 MVA to 200MVA | Transmission Line - Conductor | Upgrade/Retrofit | NA | NA | Local Capacity Requirement | Line Reconductoring | NERC TPL Standards | NA | 2023-10-24 | 19 | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.9028 | NA | 69 | NA | 2.1 | 16158 | 2015-00013 | 2988650 | NA | FALSE | 2018-04-01 | Work Order Authorization | 2017 | 2016 | FALSE | 2016 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2015-2016TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2024-07-01 | 2018-06-01 | 2024-07-01 | Permitting | ISO Action | TRUE | 15676.263 | NA | 34054.1313 | 344.691 | 6.5632 | 5396.2009 | 361.297 | 6603.6531 | 12353.9105 | 0 | 0 | 0 | 0 | 13614.3709 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 26085.913 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
64 | Southwest Powerlink HVDC Conversion |  |  | San Diego County | The scope of this work encompasses all aspects of engineering and design that is required to plan the HVDC conversion of the Southwest Powerlink. The engineering/planning process will also involve exploring feasible alternatives to this proposed project. | Other | NA | NA | NA | Address Results of Power Flow Analysis | System Operations | NA | NA | NA | NA | Steady State Power Flow System Analysis | Other [See Notes] | Over $500 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 85 | NA | 525 | 525kV | 4.2 | 16159 | NA | QS00145 | NA | FALSE | 2017-01-01 | Work Order Authorization | 2017 | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Canceled | NA | NA | NA | NA | NA | NA | FALSE | 1467 | NA | 1226.7107 | 15.2017 | 5.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 1226.7107 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | Project never approved by CAISO. 45:NA
65 | San Mateo Substation |  |  | San Clemente, Orange | Rebuild the existing 138/12 kV San Mateo Substation to Enhance reliability and minimize outage impacts in the San Clemente area. | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | NA | 17; 17; 17; 8; 52; 43 | Lifecycle Replacement Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 0.542 | 138 | 12-138kV | 4.1 | 16261 | 2017-0160 | QS00149 | NA | TRUE | 2016-08-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | On Hold | NA | NA | NA | NA | NA | NA | FALSE | 1240 | NA | NA | 1803.1812 | 58.4115 | 65.9274 | 75.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 3697.1199 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 40a: TBD. Project is on hold. Project driver is not identified. 45:NA
66 | AB2868 Energy Storage |  |  | San Diego County | AB2868 Energy Storage | Other | New | NA | NA | Local Capacity Requirement | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 12-69 | NA | 4.3 | 16276 | 2014-01087-ZZ | TBD | NA | TRUE | 2017-01-03 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 9718.925 | NA | 23081.8816 | 785.9656 | 501.9642 | 100.5682 | 150.6047 | 103.2225 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | This budget code was for development of the microgrid program. Once each project received approval, it was assigned an individual budget code and proceeded to design and construction under the new BC. Each project is now at a different status. 13: Physical projects were new construction and moved to different budget codes once approved. 45:NA
67 | TL632A Loop-In (Granite) |  |  | El Cajon, San Diego ¦ Crest, San Diego ¦ Granite Hills, San Diego | Convert TL632 from a tap into Granite Substation to a loop-in. Based on routing study, underground along La Cresta Rd to Granite Substation is most feasible route. 1.9 miles of 69kV underground. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2021-10-20 | NA* see notes | Steady State Power Flow System Analysis | Multiple Options [See Notes] | $10 Mil -$15 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 2.1143 | NA | 69 | NA | 2.1 | 17125 | 2015-00005 | 2651507 | NA | FALSE | 2016-12-09 | Work Order Authorization | 2017 | 2015 | FALSE | 2015 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2014-2015TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | NA | NA | NA | 2025-07-28 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2026-10-12 | 2017-06-01 | 2026-10-12 | Permitting | Land Rights | TRUE | 14057.888 | NA | 14057.888 | 217.5404 | 492.3221 | 706.465 | 1588.1374 | 2268.5705 | 16676.3412 | 0 | 0 | 0 | 0 | 10493.6739 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 15008.707 | 0% | NA | 12.56% ¦ Copperleaf | No | 0% | 100% | 13: Asset age data discrepancy being corrected for future submission 15B: Reconductor TL631, El Cajon - Los Coches, Cost $17M-$22M. 45: CPUC filing requirements to be determined.
68 | TL611 Direct Buried Cable Replacement (Old Town - Point Loma) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 53 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.3221 | NA | 69 | NA | 4.1 | 17127 | 2012-00002-ZZ | 2983120 | NA | TRUE | 2023-11-28 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-06-03 | To be Filed | 2027 | On Hold | NA | 2027-12-02 | NA | 2028-04-05 | NA | NA | TRUE | NA | NA | 28043.9235 | 18495.8021 | 11160.4224 | 35749.7593 | 35347.4351 | 24944.3844 | 42521.4796 | 41980.5287 | 43691.7221 | 33867.2762 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 55520.414 | 0% | NA | 29.22% ¦ Copperleaf | No | 0% | 100% | 45:TBD
69 | TL603 Loop-in (Sweetwater, National City, and Naval Station Metering) |  |  | National City, San Diego | Open Sweetwater Tap and make TL603D and TL603B one continuous 69kV line from national City to Sweetwater. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | 2022-02-24 | 36 | Steady State Power Flow System Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 2.5607 | NA | 69 | NA | 2.1 | 17129 | 2015-00066 | 2988754 | NA | FALSE | 2017-04-05 | Work Order Authorization | 2017 | 2013 | FALSE | 2013 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2012-2013TransmissionPlanningProcess.aspx | FALSE | TBD | NA | NA | NA | NA | NA | NA | 2026-07-24 | To be Filed | 2026 | Engineering more than 50% complete | NA | 2027-10-14 | 2017-06-01 | 2027-10-14 | Prioritization | Permitting | TRUE | 13584.367 | NA | 13584.367 | 1276.2123 | 2362.9201 | 7255.8467 | 6722.4789 | 6014.5782 | 6595.766 | 5678.9784 | 6455.4572 | 6460.2448 | 0 | 8700.7874 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 7672.4313 | 0% | NA | 21.52% ¦ Copperleaf | No | 0% | 100% | 45: CPUC filing requirements to be determined.¦¦TL603D (National City – Sweetwater Tap) and TL603B (Sweetwater – Sweetwater Tap) will be made into one continuous line segment running from National City to Sweetwater Substation to achieve a minimum continuous/emergency rating of 102 MVA. The project is expected to cost $10 to $12 million and the expected in-service date is June, 2017.
70 | TL6906 Mesa Rim Rearrangement |  |  | San Diego, San Diego | The purpose of the TL644 Reconductor Project is to improve the reliability of the Transmission System by mitigating potential NERC Category B Criteria violations. The Project will increase the ampacity of TL644 to 204MVA (1,708A) by replacing the single-circuit underground 1750kCMIL aluminum cable to a twin-circuit underground 3000kCMIL copper cable system. Upon completion, the upgrades will mitigate overloads on TL644 in the event of an outage on TL642. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | T-Line Capacity | NA | NA | 2021-03-18 | NA* see notes | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 9.1086 | NA | 69 | NA | 2.1 | 17130 | 2014-00207-ZZ | 2983335, 2983334, 2981181, 2985349 | NA | FALSE | 2018-07-25 | Work Order Authorization | 2017 | 2014 | FALSE | 2014 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2013-2014TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-08-05 | 2018-06-01 | 2020-08-05 | Prioritization | Outage | FALSE | 14328.054 | NA | 16547.7654 | 5537.975 | 8379.5009 | 694.1458 | -360.9559 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 16217.1255 | 670.8744 | -340.2346 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 9: NERC Category B Criteria, 17: Reconductor HFTD Tier 2 45: Project was Exempt from CPUC filing per GO-131D. 13: asset age data discrepancy being corrected for future submission
71 | Imperial Valley Substation: Replace Bank 80 |  |  | Imperial County | Install three (3) new 500/230kV 373MVA single phase transformers. Upgrade 12kV tertiary bus to meet the new MVA rating of Bank 80 and adjust firewalls. Replace existing 480/277V SL&P transformers with new 120/208V transformers to provide the required control power for the new BK80. Remove and demo existing three (3) 500/230kV single phase transformers. Demo the existing spare Bank 80 unit. Upgrade the 3.5" AL bus to 2-2500 KCMIL in the 230kV yard to meet TERG requirements, re-ordered few structural BOMs for the 12kV tertiary, added fiberglass grating, and remobilized Siemens onsite during commissioning to assist KY. | Substation - Transformer | Replace | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Transformers | NA | NA | 2023-10-21 13:00 | 40 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.48 | 500 | 500kV | 2.1 | 17138 | 2014-01072-ZZ | QS00161 | NA | TRUE | 2017-05-08 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-10-26 | 2019-05-04 | 2019-05-11 | NA | NA | TRUE | 16986 | NA | 19539.3467 | 7121.3852 | 584.7405 | 4.5065 | 0 | 174.251 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2023 | 559.4154 | 4.5065 | 0 | 174.251 | 0 | 0% | NA | NA | No | 100% | 0% | 45: Project exempt
72 | TL690 Direct Buried Cable Replacement (Oceanside-Oceanside Tap) |  |  | Oceanside, San Diego ¦ Camp Pendleton South, San Diego | Direct-Buried Cable Replacement (On Hold) (Approx. 1-mile trench and substructures) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 45 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.0534 | NA | 69 | NA | 4.1 | 17142 | 2014-00017-ZZ | TBD | NA | TRUE | 2020-08-02 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-06-14 | To be Filed | 2027 | On Hold | NA | 2027-12-08 | NA | 2028-10-17 | NA | NA | TRUE | NA | NA | 905.761 | 6187.0973 | 5269.0216 | 6210.5463 | 5194.8994 | 3388.8822 | 4397.9529 | 3968.25 | 3890.4601 | 3598.8118 | 2059.482 | 769.7813 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 7835.4562 | 0% | NA | 0.96% ¦ Copperleaf | No | 0% | 100% | 45:TBD
73 | TL628 Direct Buried Cable Replacement (Rancho Del Rey & H St.) |  |  | Chula Vista, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 44 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.63688 | NA | 69 | NA | 4.1 | 17143 | 2017-0021 | TBD | NA | TRUE | NA | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | On Hold | NA | 2027-12-02 | NA | 2028-03-17 | NA | NA | FALSE | NA | NA | 20131.87 | 389.2903 | 593.8373 | 256.8387 | 494.8968 | 7682.2363 | 550.4755 | 11506.1055 | 24228.2954 | 0 | 0 | 1308.9815 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 13.56% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
74 | TL698 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Fallbrook, San Diego | This project installs one new engineered steel cable pole and underground facilities to support the replacement of the direct buried cable Getaways of the Avocado Substation on TL698. The underground segment on TL698 is 1500 feet long, a portion of the line will be installed within a double circuit underground duct package, and a single circuit underground duct package. The duct package will be constructed in a franchise position on the north side of Barhaven Lane, crossing Alvarado St. and consists of three conduits for the 69kV segment of cable and one conduits for fiber optic communication. A new steel cable pole (Z293941) will be installed to replace an existing steel cable pole structure (Z713100) on TL698. Time frame for construction is November 2019- March 2020. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | 2022-08-08 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.23906 | NA | 69 | NA | 4.1 | 17145 | 2017-0026 | 2988759 | NA | TRUE | 2017-06-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-11-22 | NA | 2020-05-01 | NA | NA | FALSE | 3740.94 | NA | 2822.313 | 797.0091 | 1694.7805 | 95.6191 | 4.389 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 2724.071 | 93.9478 | 4.2942 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Asset age data discrepancy being corrected for future submission 45: Project was Exempt from CPUC filing per GO-131D.
75 | TL697 Direct Buried Cable Replacement (Oceanside Sub Getaway) |  |  | Oceanside, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 50 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.065771 | NA | 69 | NA | 4.1 | 17147 | 2017-0025 | 2988951 | NA | TRUE | 2020-08-02 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2027-03-24 | To be Filed | 2027 | On Hold | NA | 2027-12-01 | NA | 2028-04-04 | NA | NA | FALSE | NA | NA | 1500.416 | 0 | 0 | 0 | 0 | 0 | 243.8511 | 3259.4219 | 17324.408 | 0 | 0 | 356.2724 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 1.57% ¦ Copperleaf | No | 0% | 100% | 45:TBD
76 | TL667 Direct Buried Cable Replacement (El Camino Real) |  |  | San Diego, San Diego | Direct-Buried Cable Replacement (On Hold) | Transmission Line - Underground | Replace | NA | NA | Reliability | Age/Condition | NA | NA | NA | 39 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 4.0087 | NA | 69 | NA | 4.1 | 17151 | 2017-0022 | TBD | NA | TRUE | NA | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | Advice Letter | 2024-05-13 | To be Filed | 2024 | On Hold | NA | 2027-05-04 | NA | 2028-01-26 | NA | NA | FALSE | NA | NA | 15490.905 | 711.7533 | 36.8697 | 5253.4249 | 179.5665 | 517.2172 | 453.5829 | 8379.9351 | 12677.2264 | 0 | 0 | 1865.4787 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 50.83% ¦ Copperleaf | No | 0% | 100% | 45:TBD
77 | TL673 Direct Buried Cable Replacement (Rose Canyon - La Jolla) |  |  | San Diego, San Diego | Currently TL673 consist entirely of aging 69kV direct-buried cable from Rose Canyon to La Jolla substations at approximately three miles. This existing direct-buried cable is of 1967 vintage year and has far exceeded its designed operational expectancy of 30 years. Transmission Engineering anticipates an increase rate in outages caused by failures on this existing aging cable system in the near future. This project will replace all existing direct-buried cable from Rose Canyon to La Jolla substations within a newly constructed underground trench conduit package and substructures which will improve electric transmission reliability to the La Jolla area as well as resolve the ongoing maintenance issue for TL673. | Transmission Line - Underground | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | NA* see notes | 49 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | NA | 69 | NA | 4.1 | 17152 | 2017-0023 | 2652565 | NA | TRUE | 2022-12-13 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-06-30 | NA | 2023-06-30 | Permitting | Land Rights | TRUE | 2600 | NA | 61380.2794 | 2921.5738 | 8764.3562 | 12974.7047 | 17316.8906 | 11407.7061 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 5800.3575 | -170.835 | 244.5547 | 55506.2023 | 0 | 0% | NA | NA | No | 0% | 100% | 12: UG sections energized 2023-07-25, first inspection due 2024-12-08. 45: Project was Exempt from CPUC filing per GO-131D.
78 | Avocado - 69kV Rebuild |  |  | San Diego, San Diego | Substation Rebuild, Transformers, Control Shelter & Relays & CS equipment, expanded the substation, change out 69kV circuit breakers, PT, and disconnects. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-11 09:47 | 49; 49; 60 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 3.1283 | 1.7192 | 69 | 60MVA | 2.1 | 17153 | 2014-00941-ZZ | PSS0041 | NA | TRUE | 2017-12-01 | Work Order Authorization | 2017 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-09-17 | NA | 2020-11-16 | NA | NA | FALSE | 10074 | NA | 16402.6667 | 6666.2445 | 4404.7636 | 2362.503 | 3.3717 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 | 94.4561 | 16305.0626 | 3.148 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Project has been completed. 13: asset age data discrepancy being corrected for future submission 45:NA
79 | TL691 Direct Buried Cable Replacement (Avocado Sub Getaway) |  |  | Oceanside, San Diego | This project replaces approximately 900' of direct buried cable on TL698 from Avocado Substation to Structure Z15588 with concrete encased conduit, cable pole and cable. | Transmission Line - Conductor | Replace | NA | NA | Reliability | Age/Condition - Replace Underground System | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.15746 | NA | 69 | NA | 4.1 | 17157 | 2017-0027 | 29829260 | NA | TRUE | 2019-02-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-11-22 | NA | 2020-11-16 | NA | NA | TRUE | 1947.832 | NA | 2142.2622 | 586.8519 | 1249.7981 | 129.1762 | 79.1442 | 186.6699 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1786.5114 | 116.3664 | 71.2848 | 168.0996 | 0 | 0% | NA | NA | No | 0% | 100% | 45: Project was exempt from CPUC filing per GO-131D.
80 | San Marcos - 69kV Rebuild & Switchgear Replacement |  |  | San Marcos, San Diego | Upgrade the 69kV bus, replace all 69kV insulators, disconnects, potential transformers, protection and controls. Replace existing control shelter with a new block shelter. Replace Bk 32’s 12kV switchgear with new switchgear (sized to fit on existing foundation) and cutover existing 12kV circuits to new switchgear. Replace and relocate existing 12kV capacitors. Remove and RFS four 69kV oil breakers, two 12kV capacitors, Bk 32's switchgear, and control shelter. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-17 13:15 | 33; 46; 46; 33 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.5915 | 69 | 60MVA | 4.1 | 17160 | 2014-01062-ZZ | QS00176 | NA | TRUE | 2017-12-15 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2020-02-03 | 2022-10-30 | 2021-06-30 | NA | NA | FALSE | 11114 | NA | 11295 | 421.7658 | 11.6052 | 7.2018 | 7.0906 | 9.142 | 0 | 204.3403 | 3056.9127 | 1698.0505 | 165.9289 | 1339.8547 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Alternative - run to failure . Project not yet scheduled. 45:NA
81 | Escondido - 230kV Yard Rebuild |  |  | Escondido, San Diego | Escondido Substation 230kV Yard Rebuild | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2023-10-09 09:49 | 40; 44; 46; 16; 16; 16; 23; 16; 16; 24; 24 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 4.6631 | 230 | 230kV | 4.1 | 18127 | 2014-01090-ZZ | TBD | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | 2019-03-01 | NA | 2020-12-24 | NA | NA | FALSE | 982 | NA | 982 | 62.5408 | 5.3836 | 0 | 0 | 0 | 936.4362 | 938.8785 | 5325.8504 | 10375.7626 | 11047.8985 | 154.4497 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 3.24% ¦ Copperleaf | No | 100% | 0% | 45: TBD
82 | Mission – Rebuild the 138kV and 69kV bus |  |  | San Diego, San Diego | Install shoo-fly's for TL618, TL663 & TL13822 in conflict with the proposed Mission 69kV GIS | Substation - Multiple | Replace | Upgrade/Retrofit | NA | Reliability | Substation Reliability | NA | NA | 2023-10-26 09:44 | 51 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | NA | 8.9967 | 69 | 69kV | 4.1 | 18128 | 2019-1012 | 5981934 | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2022-12-05 | 2024-09-05 | 2026-06-29 | NA | NA | TRUE | 100,000+ | NA | 118455.4144 | 438.878 | 16.0786 | 15.6756 | 17.3237 | 12.0389 | 2257.3201 | 2261.4796 | 7746.2387 | 12475.533 | 11712.007 | 36439.4669 | NA | NA | 2023 | 0 | 0 | 0 | 1.9299 | 0 | 0% | NA | 27.51% ¦ Copperleaf | No | 0% | 100% | 45: NA
83 | Oceanside - 69kV Rebuild |  |  | Oceanside, San Diego | Rebuild will consist of relocating and rebuilding the 69kV bus and structures on the newly acquired property using a 69kV GIS design. The new 69kV GIS bus will consist of five (5) 69kV breakers to meet the ultimate layout consisting of two (2) TL’s, two (2) transformer positions, and a disconnect used to serve portable transformers. This project will also rebuild the control shelter to a larger, block control enclosure. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | 2023-10-06 13:37 | 2; 9; 21; 49; 21 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.22439 | 69 | 69kV | 4.1 | 18130 | 2018-1015 | QS00200 | NA | TRUE | 2018-03-01 | Work Order Authorization | 2018 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2022-07-18 | NA | 2022-10-31 | NA | NA | TRUE | 20779 | NA | 1028.2459 | 33.0444 | 2.1883 | 0 | 0 | 0 | 437.6027 | 438.2582 | 439.0112 | 6124.6305 | 2256.9186 | NA | NA | NA | 2023 | 0 | 0 | 0 | 1028.2459 | 0 | 0% | NA | NA | No | 0% | 100% | Alternative - run to failure . Project has completed phase 1 and phase 2 has yet to be scheduled. 45:NA
84 | SKILLS TRAINING CENTER – TRANSMISSION YARD EXPANSION |  |  | San Diego, San Diego | The purpose of this project is to expand the transmission yard at Skills Training Center for crews to train safely on. A new OH potion will be installed, along with an UG portion, a 500kV Insulator Replica, and an SW pole with a new stepping pattern will be installed. Last phases of construction to begin September 2021, and end before 2022 | Transmission Line - Conductor | Replace | NA | NA | Other [See Notes] | System Operations | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.076428 | NA | 69-230 | NA | 1.3 | 18136 | 2018-4002 | 2652031UG, 2652032OH | NA | TRUE | 2019-01-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2020-05-18 | NA | 2022-04-01 | NA | NA | TRUE | 2475.891 | NA | 1947.832 | 70.8326 | 325.7595 | 923.4068 | 529.1863 | 1.8695 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 1945.9625 | 1.8695 | 0 | 0% | NA | NA | No | 100% | 0% | Construction of OH/UG transmission training facilities for SDGE line crews to perform construction and maintenance of transmission lines throughout service territory. 9: Infrastructure not connected to the grid for training purposes. 45:NA
85 | Miguel Substation 230kV Rebuild |  |  | San Diego County | Upgrade relaying for Bk70/71, replace 32 disconnects, replace 32 switch stands to meet our new seismic standards, replace one overstressed breaker, and eight (8) panel changeouts. Remove existing relaying panels #403 & #406 | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | 2023-10-14 12:33 | NA | Lifecycle Replacement Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 12.37 | 230 | 660MVA | 4.1 | 18139 | 2014-01074-ZZ | QS00350 | NA | TRUE | 2017-07-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2019-09-23 | 2020-11-12 | 2022-03-23 | NA | NA | TRUE | 10503 | NA | 11537.3734 | 2689.5163 | 2476.4635 | 1694.8201 | 825.6009 | 5.9404 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 11531.433 | 5.9404 | 0 | 0% | NA | NA | No | 100% | 0% | FERC Only 45:NA
86 | Mission 230kV Rebuild |  |  | San Diego, San Diego | Rebuilding the Mission Substation, increase 230kV bus rating to 3k Amps. Replacing 230kV disconnects to latest standards. Replacing control shelter and equipment. Equipment was upgraded to meet standards, increase reliability and replace aging infrastructure | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-26 09:44 | NA | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 9 | 230 | Multiple | 4.1 | 18140 | 2014-01071-ZZ | QS00373 | NA | TRUE | 2017-10-10 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2018-09-24 | 2020-06-03 | 2021-04-23 | NA | NA | FALSE | 39512 | NA | 35868.2667 | 14051.2405 | 11189.6227 | 3163.2885 | 234.3455 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2021 ¦ 2022 | 0 | 26304.3851 | 9563.8816 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | Substation rebuild, see description for upgrades 45:NA
87 | TL667 San Dieguito Lagoon Customer Relocation |  |  | San Diego, San Diego | Relocate segment of TL666 for wetland mitigation. Still to meet with Caltrans to understand scope | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-02-27 | 2 | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 1.4066 | NA | 69 | NA | 3.3 | 19128 | 2018-0163 | 2989664 | NA | TRUE | 2019-03-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2021-07-14 | Approved | 2021 | Operational | NA | 2023-01-12 | 2022-11-07 | 2023-03-27 | NA | NA | TRUE | 231.968 | NA | 4055.7199 | -141.9394 | 359.3729 | -73.1736 | 891.9402 | 3079.2415 | 0 | 0 | 0 | 0 | 0 | 55.4879 | NA | NA | 2023 | 0 | 0 | 0 | 4055.7199 | 0 | 0% | NA | NA | No | 0% | 100% | Customer requested relocation requiring CPUC Advice Letter.
88 | TL13831 Rancho Mission Viejo Customer Relocation |  |  | Orange County | This project installs two (2) 138kV/12kV engineered steel poles, eight (8) 138kV engineered steel poles, ten (10) 138kV steel pole pier foundations, removes one (1) 138kV steel pole with foundation, remove one (1) 138kV SW pole, removes twelve (12) 138kV wood poles with guys & anchors all in conflict with the County of Orange & Rancho Mission Viejo (RMV) improvements for Cow Camp Road in San Juan Capistrano, California. | Multiple Options [See Notes] | Replace | Relocate | NA | Work Requested by Others | Facility Relocation | NA | NA | 2022-03-18 | 29 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 1.1496 | NA | 138 | NA | 3.3 | 19129 | 2017-0128 | TBD | NA | TRUE | 2016-10-07 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2019-10-28 | Approved | 2020 | Operational | NA | 2020-07-13 | 2020-06-01 | 2020-10-09 | Outage | NA | TRUE | 4917.018 | NA | 1024.1871 | 652.7768 | -252.4534 | 878.7057 | 101.9065 | -859.8052 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 3749.4928 | -2792.8948 | 97.1672 | -29.578 | 0 | 0% | NA | NA | No | 0% | 100% | NA
89 | Trans Fiber Links HFTD |  |  | NA | Install ADSS and or OPGW on existing Transmission overhead structures to support the Wildfire Mitigation Plan | Other | New | NA | NA | Wildfire Mitigation | NERC CIP Compliance | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 1.1 | 19134 | Multiple | QBL0100 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 249.1351 | 22.1989 | 23.9228 | 23.2003 | 19.3484 | 1465.166 | 1486.9151 | 1510.6589 | 14054.4385 | 44608.4461 | 35662.4459 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 246.7031 | 123.2414 | 3981.2932 | 1440.719 | 0 | 0% | NA | NA | No | 21% | 79% | 40: Program consists of multiple same scope projects per transmission line with separate environmental permits. 13: Unable to provide age of asset for blanket budget codes 45:NA
90 | HFTD Undergrounding |  |  | NA | Blanket budget for High Fire Threat District undergrounding work. This is an electric distribution blanket budget. The forecasted costs shown for this project are only the FERC-specific transmission costs. | Transmission Line/Substation | Upgrade/Retrofit | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 19246 | Multiple | QBL0081 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 234.5417 | -649.2265 | 1687.9391 | 0 | 0 | 0 | 0 | 0 | 0 | 147312.9702 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45:NA
91 | Urban Substation - 12kV Switchgear & Capacitor Replacement |  |  | San Diego, San Diego | Urban Substation - 12kV Switchgear & Capacitor Replacement | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Other Substation Equipment | NA | NA | 2023-09-13 11:17 | NA | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.56634 | 69 | 69kV/12kV | 4.1 | 19252 | 2021-2065 | TBD | NA | TRUE | 2020-01-01 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2023-07-13 | 2025-12-05 | 2026-06-05 | NA | NA | FALSE | 27398.203 | NA | 27398.203 | 3.1085 | 212.151 | 284.6278 | 577.7939 | 868.9245 | 12113.1829 | 11863.9847 | 2568.8309 | 0 | 0 | 12190.1342 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Exempt 45:NA
92 | Electric Transmission EMS/SCADA Replacement |  |  | NA | Replacement of Energy Management System (EMS) application and supporting infrastructure at Electric Transmission's Mission Control Center and Metro Control Center | Other - Operations Tech | Replace | NA | NA | Reliability | NERC CIP Compliance | NERC CIP Compliance | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.2 | 20125 | Multiple | QS00452 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5.4845 | 1.2231 | 1.3352 | 9.2223 | 27.0328 | 10288.1716 | 33580.8775 | 27853.9038 | 23454.3496 | 17284.8267 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
93 | Transmission CMP Non HFTD |  |  | NA | Remediate CMP Issues in the Non-HFTD Zone | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.2 | 20126 | Multiple | QBL0098 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 37.9723 | 5.2979 | 808.8376 | 15737.3522 | 18376.126 | 31450.7427 | 17548.3232 | 10633.1203 | 0 | 0 | 22886.6921 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 28766.1064 | 42012.2332 | 38697.1546 | 33147.6278 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
94 | Transmission CMP HFTD |  |  | NA | Remediate CMP Issues in the HFTD Zone (Tier 2 & Tier 3) | Transmission Line - Pole/Tower | Replace | NA | NA | Asset Condition | Age/Condition | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.1 | 20127 | Multiple | QBL0092 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 209.3632 | 61.8518 | 22.0362 | 140.0388 | 314.2823 | 0 | 497.2929 | 6821.5632 | 6328.5931 | 5832.7155 | 7986.2939 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 12158.8924 | 12767.9645 | 11698.1804 | 17208.0631 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
95 | TL610 Tier 2 W2S Project |  |  | San Diego, San Diego | Wood to steel replacement on TL610 less than 2 miles. | Transmission Line - Pole/Tower | Replace | NA | 2020-0287 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-09-11 | 36 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.35 | NA | 69 | NA | 1.1 | 20133 | 2020-0272 | QS00474, 2991115 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | 2024-12-10 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-07-28 | 2026-12-31 | 2025-10-13 | NA | NA | FALSE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 471.9193 | 536.9977 | 257.1022 | 0 | 0 | 358.3638 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
96 | TL627 Wood to Steel |  |  | Rancho San Diego, San Diego ¦ Spring Valley, San Diego | The TL627 Wood-to-Steel project consists of installing new steel pole structures, re-frame existing steel structures, and conductor along the existing 69kV tie line between Structure Z777999 and Structure Z971734 located in Spring Valley. As part of TL627 rebuild, C91 & C524 will be reconductored as well. This project was initiated as part of SDG&E’s continuous effort to improve reliability and reduce fire risks in fire-prone areas. | Multiple Options [See Notes] | Replace | NA | NA | Reliability | Fire Protection | NA | NA | 2022-10-25 | 45 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 7.1867 | NA | 69 | NA | 1.1 | 20134 | 2019-0257 | 2991116 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-04-24 | 2026-12-31 | 2025-05-21 | NA | NA | TRUE | 1979.963 | NA | 1979.963 | 27738.3414 | 40967.5456 | 45918.1862 | 43393.9224 | 36165.2397 | 38966.4509 | 33121.4836 | 31465.4093 | 29892.1392 | 28397.5316 | 1083.0724 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 38153.2337 | 0% | NA | 0.07% ¦ Copperleaf | No | 0% | 100% | Project is both structure and conductor replacement. 45:NA
97 | TL649 Wood to Steel |  |  | San Diego, San Diego ¦ Chula Vista, San Diego | 23 wood poles in HFTD2 to be replaced from wood to steel. Two of the poles (Z192597 and Z82136), are multi-transmission wood pole structures (two poles). 1.162 Miles to be re-conductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-09-18 | 44 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 1.6826 | NA | 69 | NA | 1.1 | 20135 | 2019-0268 | 2991117, 5438651 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Final Certified | 2018-10-05 | IS/MND | NA | CPUC | NA | PTC | 2015-08-10 | Approved | NA | Engineering less than 50% complete | NA | 2024-05-13 | NA | 2024-08-06 | NA | NA | TRUE | 1486.209 | NA | 3115.6208 | 8235.2118 | 16776.9388 | 15808.8961 | 15609.0096 | 16616.7904 | 14545.678 | 13818.394 | 13127.4742 | 12471.1016 | 11847.5462 | 1607.768 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 13397.5931 | 0% | NA | 0.52% ¦ Copperleaf | No | 0% | 100% | No Comments
98 | TL13804 Wood to Steel Z95913-Z319244 |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego | Replace 16 existing wood structures (h-frames) with steel structures. Project spans approximately 5 miles of TL13804 and includes ~0.6 miles of reconductoring with transferring of existing conductor and fiber optic cable to new structures for the remainder. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-04-24 | 57 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Project In Coastal Zone; Requires Galvanized Steel Poles |  | 16.3749 | NA | 138 | NA | 1.1 | 20136 | 2019-0255 | 2166154 | NA | TRUE | 2020-07-21 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2024-09-04 | 2024-02-06 | 2024-11-19 | NA | NA | FALSE | 3628.655 | NA | 3628.655 | 0 | 37.3706 | 104.1737 | 95.8615 | 79.0642 | 1540.7013 | 8755.4376 | 0 | 0 | 0 | 975.3165 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.17% ¦ Copperleaf | No | 0% | 100% | 45: NA
99 | TL23001 TL23004 Insulator and Hardware Replacement |  |  | Encinitas, San Diego ¦ Rancho Santa Fe, San Diego ¦ Carlsbad, San Diego ¦ San Diego, San Diego ¦ Oceanside, San Diego | TL23001 TL23004 Insulator and Hardware Replacement | Transmission Line - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition - Replace Insulators | NA | NA | 2023-04-20 | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 34.8284 | NA | 230 | NA | 4.1 | 20138 | 2019-4004 | 2991118 | NA | TRUE | 2020-06-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-01 | 2026-12-31 | 2022-10-11 | NA | NA | TRUE | 8040.059 | NA | 10434.997 | 0 | 14.5954 | 3423.4355 | 7062.8838 | 119.8833 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 ¦ 2023 | 0 | 0 | 10354.5758 | 80.4212 | 0 | 0% | NA | NA | No | 100% | 0% | 45: Project was Exempt from CPUC filing per GO-131D.
100 | TL6952 Wood to Steel |  |  | San Diego, San Diego | Replace 10 wood pole structures in HFTD Tier 2 with steel pole structures and transfer approximately 1.5 miles of overhead conductor. | Transmission Line - Pole/Tower | Replace | NA | 2020-0272 | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-06-07 | 33 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.3391 | NA | 69 | NA | 1.1 | 20139 | 2020-0287 | 2991119 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | 2024-11-08 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-10-13 | 2026-12-31 | 2025-12-31 | NA | NA | FALSE | 1810.588 | NA | 1810.588 | 0 | 37.3706 | 104.1737 | 95.8615 | 79.0642 | 1540.7013 | 8755.4376 | 0 | 0 | 0 | 294.9421 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.57% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
101 | TL661 TL664 Wood to Steel |  |  | San Diego, San Diego | Replace 14 double circuit wood pole structures with underground alternative design, based on preliminary environmental scorecard suggesting a PTC would be required. Intercept existing underground ducting outside Penasquitos substation and install new steel double circuit cable pole at Z97272/Z97273. Approximately 3 miles of underground. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2022-07-09 | 41 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 1.0313 | NA | 69 | NA | 1.1 | 20140 | 2020-0289 | 2991160 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Advice Letter | 2024-12-04 | To be Filed | 2025 | Engineering more than 50% complete | NA | 2025-05-06 | 2026-12-31 | 2025-09-09 | NA | NA | FALSE | 1810.588 | NA | 1810.588 | 0 | 69.4797 | 101.8187 | 438.1259 | 390.3154 | 2592.4852 | 6136.8456 | 0 | 0 | 0 | 797.4579 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.79% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
102 | TL691 Wood to Steel |  |  | Fallbrook, San Diego ¦, Camp Pendleton North | The TL691 Fire Hardening & Reconductor Project consists of replacing existing structures and installing new steel structures along the 69kV tie line 691 in FTZ from Z19800, north of Camp Pendleton to structure Z293940, south of Avocado Substation, with new light duty and heavy engineered steel poles. This project is needed to mitigate loss of service due to wildfires by replacing existing wood poles with new steel structures. The new steel poles shall be designed to 138kV specifications and accommodate existing and future 12kV distribution underbuild and communications circuits. | Transmission Line - Pole/Tower | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2020-10-10 | 51 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 6.1778 | NA | 69 | NA | 1.1 | 20141 | 2019-0269 | 2991163 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2026-03-12 | 2026-12-31 | 2026-09-16 | NA | NA | TRUE | 1979.963 | NA | 1979.963 | 0 | 35.898 | 193.974 | 573.3404 | 669.8638 | 7481.7449 | 1010.3542 | 0 | 0 | 0 | 1121.8213 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 8253.1878 | 0% | NA | 0.36% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
103 | TL675 Wood to Steel Z138156-Z33075 |  |  | San Diego, San Diego | ​57 poles to be replaced from wood to steel, and 6 miles to be reconductored. | Transmission Line - Pole/Tower | Replace | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-03-18 | 33 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | Coastal |  | 5.4503 | NA | 69 | NA | 1.1 | 20142 | 2019-0251 | 2991164 | NA | TRUE | 2020-04-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-07-25 | 2026-12-31 | 2026-07-07 | NA | NA | FALSE | 1979.963 | NA | 1979.963 | 0 | 49.6109 | 243.776 | 293.5591 | 384.7675 | 9042.2882 | 70.4304 | 0 | 0 | 0 | 1056.2746 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.05% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
104 | TL6939 Wood to Steel Z198381-Z611223 |  |  | San Diego, San Diego | 42 poles in HFTD 2 to be replaced from wood to steel, and 2.5 miles to be reconductored. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Wood Structure Replacement | NA | NA | 2021-07-08 | 19 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.9 | NA | 69 | NA | 1.1 | 20143 | 2019-0256 | 2991162 | NA | TRUE | 2020-05-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-06-01 | 2026-12-31 | 2026-06-16 | NA | NA | FALSE | 1973 | NA | 1973.076 | 0 | 13.5935 | 81.2897 | 97.4571 | 72.1732 | 1793.4398 | 7492.021 | 0 | 0 | 0 | 453.7099 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 0.89% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
105 | TL6910 Wood to Steel Z257408-Z122122 |  |  | Chula Vista, San Diego | R​eplace 12 wood poles to steel poles. | Multiple Options [See Notes] | Replace | Upgrade/Retrofit | NA | Wildfire Mitigation | Priority 1 Steel Structure Replacement | NA | NA | 2022-12-30 | 31 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 9.0928 | NA | 69 | NA | 1.1 | 20144 | 2019-0254 | 2991161 | NA | TRUE | 2020-05-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | 2025-06-01 | 2026-12-31 | 2026-06-16 | NA | NA | FALSE | 1973.076 | NA | 1973.076 | 0 | 26.003 | 146.3886 | 250.741 | 312.6505 | 5328.125 | 7889.157 | 17583.4066 | 17410.3573 | 13142.854 | 179.9048 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 1.66% ¦ Copperleaf | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
106 | TL13811 Wood to Steel Z312779-Z119763 |  |  | San Marcos San Diego ¦ Encinitas, San Diego ¦ San Diego, San Diego | TL13811 W2S is a hardening project driven by the circuit’s location within the High Fire Threat District (HFTD) Tier 2. This project will replace all transmission structures from Chicarita Sub to Z312843, and then again from Z200897 to North County Metering Station. Throughout these sections (approximately 11.25 miles in length) the 138 kV mainline will be replaced with 636 kcmil 24/7 Strand “Rook” ACSS/AW. 96 Count OPGW will be installed from Z872457 – Z312843 (approximately 10.75 miles in length). Distribution circuits C1101 and C182 that are in the underbuild position of TL13811 will be reconductored with Covered 336.4 kcmil 26/7 Strands “Linnet” ACSR, and covered 1/0 6/1 Strands “Raven” ACSR, respectively. | Transmission Line - Multiple | Replace | Removal | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-04-05 | 62 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 13.0003 | NA | 138 | NA | 1.1 | 20145 | 2019-0253 | 2652595 | NA | TRUE | 2020-05-18 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2025-04-17 | 2027-01-20 | 2025-06-27 | NA | NA | TRUE | 4679.537 | NA | 4679.537 | 0 | 44.3341 | 172.0342 | 487.9782 | 321.6839 | 2995.2905 | 19915.2209 | 27.8207 | 0 | 0 | 3573.6477 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2766.162 | 0% | NA | 0.07% ¦ Copperleaf | No | 0% | 100% | 45: NA
107 | Imperial Valley - Shunt Reactor Replacement |  |  | Imperial County | Replace the existing 500kV shunt reactors at Imperial Valley substation with spares at Miguel substation. | Substation - Reactive Equipment | Replace | NA | NA | Reliability | Age/Condition - Replace Reactors, Age/Condition - Replace Relays | NA | NA | 2023-10-21 13:00 | 40; 40; 40 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 55.4775 | 500 | 500kV | 4.1 | 20148 | 2021-2176 | 5983271, QS00482 | NA | TRUE | 2020-06-15 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2022-06-01 | 2022-09-19 | 2024-05-16 | NA | NA | TRUE | 3742.255 | NA | 3742.255 | 0 | 7.7905 | 1496.0401 | 909.6009 | 239.745 | 691.8793 | 18.7768 | 0 | 0 | 0 | 2935.6944 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 681.1162 | 0% | NA | NA | No | 100% | 0% | Replacing Shunt reactors with spares from Miguel Substation; reactors are shared assets 45:NA
108 | TL6920 Wood to Steel |  |  | San Diego, San Diego | 7 poles in HFTD 2 to be replaced from wood to steel, and a total of 0.584 miles of existing 1033.5 ACSR/AW to be reconductored. | Transmission Line - Pole/Tower | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2023-04-01 | 28 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.28631 | NA | 69 | NA | 1.1 | 20149 | 2020-0286 | 2468788 | NA | TRUE | 2020-07-20 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2023-05-08 | 2026-12-31 | 2023-08-02 | NA | NA | TRUE | 1959.396 | NA | 4119.7009 | 0 | 0.74495 | 166.8964 | 279.6341 | 3873.0523 | 0.17697 | 0 | 0 | 0 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 4119.7009 | 12.6085 | 0% | NA | NA | No | 0% | 100% | 45: Project was Exempt from CPUC filing per GO-131D.
109 | TL690C Wood to steel |  |  | Camp Pendleton South, San Diego | 10 poles in HFTD 2 to be replaced from wood to steel. A total of 0.57 miles of existing 1/0 CU and 336.4 ACSR/AW to be reconductored. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | 2021-05-28 | 20 | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.49947 | NA | 69 | NA | 1.1 | 20152 | 2020-0273 | 2639298 | NA | TRUE | 2020-11-02 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Exempted | Categorical Exclusion | CPUC | MCBCP | Exempt | NA | NA [See Notes] | NA | Permitting | NA | 2024-03-08 | 2023-12-29 | 2024-06-25 | NA | NA | TRUE | 3977.8055 | NA | 3977.8055 | 0 | 27.23 | 251.0996 | 273.1235 | 418.8748 | 508.1248 | 21967.4188 | 7907.8521 | 0 | 0 | NA | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 609.5016 | 510.5689 | 0% | NA | 118.91% ¦ Copperleaf | No | 0% | 100% | CPUC & NEPA exempt 45:NA
110 | TL649 Otay Soleado (Sunroad) Customer Relocation |  |  | San Diego, San Diego | ​​​​​1. Mixed commercial and residential development to be constructed along Harvest Road and Otay Mesa Road. Otay Mesa Road will be widened, and sidewalks will be installed along the alignment, while Harvest Road will have a portion of the road rerouted underneath the existing transmission tieline TL649 with new roads constructed. 2. Relocation of approximately three (3) transmission poles (Z37159, Z37160 and Z31764) which currently exist in the future roadway and must be relocated. The adjacent poles at each relocated structure will need be analyzed and replaced if necessary.​ 3. P6 schedule is pending – see below for an estimated high-level schedule update (preliminary and subject to change based on material lead times, permitting, regulatory approval, etc.) - 30% Design – December 2020- 60% Design - May 2021- 90% Design – July 2021- 100% Design – August 2021-Construction Start – June 2022 | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-09-18 | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.202 | NA | 69 | NA | 3.3 | 20158 | 2020-0309 | 2023381 | NA | TRUE | 2021-01-11 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Advice Letter | 2024-07-15 | To be Filed | 2025 | Planning | NA | 2026-01-02 | NA | 2026-05-05 | NA | NA | FALSE | 2892.487 | NA | NA | 0 | 0 | 30.2122 | -31.8574 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | 100% Customer-funded project canceled at customer request.
111 | Torrey Pines - 12kV Reliability Improvements |  |  | San Diego, San Diego | Replacing oil CB with Vacuum CB, removing Oil containment, upgrades to SL&P, and PT. Upgrading (3) 69kV breakers. Aging equipment is going to be replaced to enhance substation reliability and reduce maintenance needs. Work is on-going. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-09-08 09:53 | 18; 31; 30; 22; 22; 31; 31 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.79 | 69 | 69kV | 4.1 | 20242 | 2020-1014 | 5983185, QS00429 | NA | TRUE | 2020-01-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2023-12-18 | 2021-06-11 | 2024-07-26 | NA | NA | TRUE | 2424.176 | NA | 6870.8817 | 0 | 0 | 508.4329 | 471.6835 | 132.1145 | 455.7687 | 0 | 0 | 0 | 0 | 4470.6917 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 1575.6924 | 0% | NA | NA | No | 0% | 100% | Replacing Oil CB with Vacuum CB; removing oil containment; Upgrade SL&P, PT 45:NA
112 | Kettner Rebuild |  |  | San Diego, San Diego | Replacement of: (Qty:8) 12kV Circuit Breakers, (Qty:3) 138kV Circuit Breakers, and (Qty:1) 12kV Switchgear at Chicarita Rebuild Substation, (Qty:2) Capacitor Banks and (Qty:1) Control Shelter due to proactively replace aging substation equipment to improve future SAIDI impact, Environmental concerns and Operational concerns | Substation - Multiple | Upgrade/Retrofit | Removal | NA | Reliability | Replace Other Substation Equipment | NA | NA | 2023-09-05 10:23 | 42; 42; 25 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.3 | 69 | 30MVA | 4.1 | 20251 | NA | QS00478 | NA | TRUE | 2019-01-01 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (50%-75%) | NA | 2021-07-01 | 2022-10-27 | 2024-07-02 | Prioritization | Construction Delays | TRUE | 7799 | NA | 718.2827 | 0 | 201.1112 | 1753.3696 | 1254.0029 | 2849.0456 | 1698.6337 | 38.6752 | 0 | 0 | 0 | 7714.1853 | NA | NA | 2022 ¦ 2023 | 0 | 0 | 704.9014 | 13.3813 | 0 | 0% | NA | NA | No | 0% | 100% | 45: NA
113 | Aviation Firefighting Program |  |  | El Cajon, San Diego | This is a new project. Purchase, equipping and initial training of a new Sikorsky S-70i Firehawk helicopter. | Other | NA | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 20277 | NA | QS00481 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 1220.0683 | 1791.1333 | 140.06 | 64.6283 | 462.9721 | 0 | 0 | 0 | 0 | 26949.4815 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 3630.3953 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45:NA
114 | OH System Traditional Hardening |  |  | NA | This program (i.e., many projects) focuses on projects that replace OH Distribution system in fire prone areas including HFTD Tier 2, Tier 3, and Wildland Urban Interface. In some cases the distribution lines are underbuilt on transmission structures and require some amount of FERC spend. | Other | Replace | NA | NA | Wildfire Mitigation | Age/Condition - Replace Conductor | Other [See Notes] | NA | NA | NA* see notes | Other [See Notes] | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | TRUE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | 138 | NA | 1.1 | 20284 | Multiple | QBL0118 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | Exempted | Other [See Notes] | CPUC | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 93.8724 | 563.1244 | 662.4641 | 158.5048 | 39.8415 | 0 | 0 | 0 | 0 | 0 | 0 | 429.8272 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 52.8592 | 0.23892 | 0.62596 | -0.1661 | -0.637 | 0% | NA | NA | No | 0% | 100% | This is a distribution hardening program and there is not one single project. The only case where we should charging FERC are when we are dealing with replacing the distribution assets underbuilt on 69kV and 138kV structures, and in the vast majority of cases we do not replace the transmission structure. We also do not go through any permitting with the CPUC as our distribution system upgrades are exempt from GO 131D. 13: Unable to provide age of asset for blanket budget codes 45: NA
115 | Drone Assessments- Tier 2 |  |  | NA | The project was focused on flying and assessing all structures within the HFTD (Tier 2) with the purpose of mitigating any fire-related issues. | Other | Replace | NA | NA | Wildfire Mitigation | Fire Protection | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | 69 | NA | 1.1 | 20286 | Multiple | QBL0124 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 110700 | 0 | 519.6428 | 762.7732 | 1166.501 | 0 | 752.2647 | 488.7519 | 0 | 0 | 0 | 61371.6611 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 0 | 752.2647 | 0% | NA | NA | No | 0% | 100% | 13: Unable to provide age of asset for blanket budget codes 45: NA
116 | TL651 Relocation (Boundary Street) |  |  | San Diego, San Diego | Relocate Z91972 approximately 50-75 feet south to be outside of the MTS Right-of-Way, in order to avoid any future relocations that may be driven by MTS. The span between Z91972 and Z91973 is currently approximately 1050-feet in length, supported by guyed wood poles on either side (see Z91973-1.jpg for picture of long crossing). By relocating Z91972 to the south, the span will increase in length which will require a detailed review at Z91973 (Last replaced in 2005). Considering that the line is a long span, crosses a railroad, and applying SDGE Std. 12100 Item 1.v (see screenshot below), we propose replacing the two wood poles (Z91972 and Z91973) with two engineered steel poles. The adjacent structure to the south of Z91972, Z91971 is not expected to be replaced, but will be analyzed and if replacement is needed, a separate PCR will need to be submitted. The poles have transmission and communication conductors only. | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-01-19 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.36257 | NA | 69 | NA | 3.3 | 21128 | 2017-0118 | TBD | NA | TRUE | 2022-05-02 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | NA | 2024-08-09 | To be Filed | 2024 | Engineering more than 50% complete | NA | 2025-10-01 | 2025-06-09 | 2025-12-18 | NA | NA | FALSE | 3267.6739 | NA | 3267.6739 | 0 | 0 | 0 | 0 | 0 | 39.339 | 3990.238 | 4.9065 | 0 | 0 | 135.3521 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Customer requested relocation requiring CPUC Advice Letter.
117 | ELEC TRANS SMALL RELIABILITY - HFTD |  |  | NA | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the HFTD. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Wildfire Mitigation | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ TRUE ¦ TRUE | FALSE | NA |  | NA | NA | 69-230 | NA | 1.1 | 21134 | Multiple | QBL0125 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 53.8733 | 40.5518 | 68.4187 | 75.766 | 4497.9729 | 36.0546 | 0 | 0 | 12304.2256 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 1994.9689 | 1774.151 | 5315.7965 | 2689.5639 | 0 | 0% | NA | NA | No | 21% | 79% | 7: Project action taken varies under blanket budget activities 13: Unable to provide age of asset for blanket budget codes 45: CPUC status varies under blanket budget activities
118 | ELEC TRANS SMALL RELIABILITY – non HFTD |  |  | NA | This budget code is all Electric Transmission projects under $2M, including shared equipment on the structures for both Transmission and Distribution. The funds are applied to the infrastructure to meet SDGE’s obligation to increase safety and reliability of the electric system. Budget includes proactive system upgrades and reactive projects that include poles, insulators, conductor and other electric infrastructure when reliability issues are identified in the non-HFTD. | Transmission Line - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | T-Line Reliability | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-230 | NA | 4.1 | 21135 | Multiple | QBL0126 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 186.1394 | 768.99 | 1402.7343 | 851.0661 | 38811.4223 | 21403.1679 | 7365.0732 | 0 | 0 | 11471.3058 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 | 4008.8689 | 2789.6572 | 5117.9862 | 4766.2454 | 0 | 0% | NA | NA | No | 21% | 79% | 7: Project action taken varies under blanket budget activities 13: Unable to provide age of asset for blanket budget codes 45: CPUC status varies under blanket budget activities
119 | TRANSMISSION CONSTRUCTION & MAINT - HFTD |  |  | NA | Transmission jobs in the HFTD to comply with SDG&E's obligation to serve and meet safety requirements. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Wildfire Mitigation | Construct Roads/Gates/Culverts | NA | NA | NA | NA* see notes | NA | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.1 | 21136 | Multiple | QBL0127 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 1067.2928 | 1611.3631 | 1284.9574 | 3274.9795 | 2298.6575 | 2927.3357 | 3096.7658 | 3196.0154 | 3359.2591 | 3481.9701 | 3484.2065 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 803.3704 | 1263.927 | 748.7844 | 1394.1046 | 3851.2972 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
120 | Suncrest Tertiary Reactor Replacement |  |  | San Diego County | The BK80/81 tertiary 12kV reactors are failing at a high rate (one in 2016, one in 2020, and two in 2021). Reactors are necessary to allow critical 500kV voltage control for grid operations. Newer, better designed, and insulated reactors are available to replace units that are failing at a quick rate. | Substation - Reactive Equipment | Upgrade/Retrofit | Replace | NA | Safety | Substation Reliability | NA | NA | 2023-10-07 13:00 | 12 | Lifecycle Replacement Analysis | NA | NA | HFTD Tier 3 | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 40.94 | 500 | 12kV | 4.1 | 21137 | 2021-2012 | QS00580 | NA | TRUE | 2021-05-24 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Operational | NA | 2022-03-07 | 2022-03-25 | 2023-03-31 | NA | NA | FALSE | 2699 | NA | 2111.8255 | 0 | 16.6645 | 1881.2109 | 158.8877 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2022 | 0 | 0 | 2111.8255 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | Equipment failure due to improper rating and high ambient temperatures at substation 45:NA
121 | HATS |  |  | NA | This project will facilitate ongoing compliance and safe and efficient operations and maintenance of the transmission system by addressing helicopter access constraints and supporting the latest work practices. The project will provide additional Helicopter Access for Transmission Structures (HATS) that currently have helicopter access constraints. | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.3 | 21146 | Multiple | QBL0130 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 11647.5301 | 8788.0858 | 9166.9176 | 9001.4999 | 8343.6527 | 0 | 0 | 0 | 9443.7008 | NA | NA | 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0 | 11684.9933 | 8457.9153 | 188.8497 | 9161.8684 | 0% | NA | NA | No | 21% | 79% | 9: Specialized Structure Access 13: Unable to provide age of asset for blanket budget codes 45:NA
122 | TL623C Reconductor Project |  |  | San Diego, San Diego | This project replaces 4/0 B.S. CU Conductor. OH Full Rebuild approx. 1.30 miles from structure Z180990 to Z181008 South of Otay Valley Regional Park Removes 19 existing wood structures. | Transmission Line - Multiple | Replace | NA | NA | Local Capacity Requirement | Fire Protection | NERC TPL Standards | NA | 2023-07-29 | NA* see notes | Steady State Power Flow System Analysis | Other [See Notes] | $10 Mil -$15 Mil | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 3.62 | NA | 69 | NA | 2.1 | 21148 | 2020-0327 | 2473746, QS00634 | NA | FALSE | NA | Work Order Authorization | NA | 2018 | FALSE | 2018 | NA | https://www.caiso.com/planning/Pages/TransmissionPlanning/2017-2018TransmissionPlanningProcess.aspx | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Engineering less than 50% complete | NA | NA | 2018 | 2024-07-01 | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0.57245 | 40.7127 | 3501.1828 | 0 | 0 | 0 | 0 | 37.3902 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 3512.6631 | 0% | NA | NA | No | 0% | 100% | Project ID on TP's records is 2017-0086 Alternative 1: Install a two hour/5 MW battery to mitigate thermal overload ~$13M ((Copy of Emeterio Hernandez Data.xlsx)) 13: Unable to provide age of asset for blanket budget codes 45:NA
123 | TL6905 Headquarters Point (Underground) Customer Relocation |  |  | San Diego, San Diego | 1. Customer is planning to construct a new office facility with two (2) new buildings on a site located in Sorrento Valley, south of Lusk Boulevard and west of Wateridge Circle. 2. Conversion of approximately 0.21 miles of overhead TL6905 alignment to underground 69 kV transmission line and associated underbuilt telecommunications facilities (scope includes two (2) engineered steel cable poles, duct bank and the splice vault associated with this underground conversion). Structures adjacent to each relocated structure will need to be analyzed and replaced if necessary. 3. Underground conversion of approximately 0.21 of C1448 overhead underbuilt 12 kV distribution line (to be provided by SDG&E Design and Project Management (DPM) or other external customer-engaged Applicant Design resources). 4. Removal of six (6) TL6905 overhead transmission structures (Z96513, Z96512, Z90211, Z90212, Z90213, and Z90429). | Transmission Line - Pole/Tower | Relocate | NA | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-01-15 | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | 0.20594 | NA | 69 | NA | 3.3 | 21149 | 2021-2431 | 2317062 | NA | TRUE | 2021-09-23 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | Other [See Notes] | NA | NA | NA | Advice Letter | 2024-03-04 | To be Filed | 2024 | Engineering less than 50% complete | NA | 2025-09-29 | 2025-12-22 | 2025-12-22 | NA | NA | TRUE | 7066.8 | NA | NA | 0 | 0 | 4.8625 | -361.163 | 241.479 | 3039.8093 | 1618.5621 | 0 | 0 | 0 | -132.7528 | NA | NA | 2024 | 0 | 0 | 0 | 0 | 2802.5928 | 0% | NA | NA | No | 0% | 100% | 100% Customer requested relocation requiring CPUC Advice Letter.
124 | TCM Non-HFTD |  |  | NA | Transmission jobs in the non-HFTD to comply with SDG&E's obligation to serve and meet safety requirements set by General Orders 95,128, and other regulations. Budget provides resources to provide support to reactive issues that arise such as storm, fire and pole car contact. The majority of the activities that fall under this blanket budget are necessary to comply with Federal, State , and Local regulations. Activities include poles that need to be replaced due to deterioration, capital repairs related to inspections (visual, infrared, LiDAR, etc.), and emergency situations. This work is scheduled and managed by Transmission, Construction & Maintenance. | Transmission Line - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Construct Roads/Gates/Culverts | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.2 | 21150 | Multiple | QBL0135 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 5032.359 | 6816.9891 | 8070.7762 | 2671.3126 | 2788.9019 | 3277.4513 | 3502.1517 | 3438.1391 | 3640.8255 | 3803.3312 | 574.8214 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 5227.4964 | 7925.8248 | 2137.4861 | 2362.4937 | 611.5477 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
125 | Generation Interconnection Projects |  |  | NA | This is a blanket authorization for a multitude of CAISO mandated projects. CAISO approval for these projects is made in the form of a Three Party Interconnection Agreement. SDG&E has historically undertaken work for many of these types of projects to enhance and maintain reliability of the transmission grid. These projects are typically Battery Energy Storage (BESS) or other renewable projects from external parties where infrastructure is created in order to connect to SDG&E's grid through genties connecting to one of the company's many existing 69kV and above substations. Typical scope of these projects include the construction of Interconnection Facilities (ICF) which are 100% customer funded as well as Reliability Network Upgrades (RNU's) will be charged to ratepayers. Given the similar nature of many of these projects as well as the fact that the majority of these costs are refundable, our proposal will be to combine the scope of all existing projects with schedules shifting out into next year and future projects into one authorization for 2022 and future years on an annual basis. | Multiple Options [See Notes] | Multiple Options [See Notes] | NA | NA | Generator Interconnection | Generation Interconnection | CAISO Requirement | NA | NA | NA* see notes | Interconnection System Impact/Facilities Studies | Interconnection System Impact/Facilities Studies | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | Multiple | 2.1 | 21156 | Multiple | QBL0141 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | TRUE | Other [See Notes] | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 3924.7324 | 2738.7667 | 5181.4554 | 1712.94 | -1252.515 | 2506.7347 | 7990.7975 | 33438.3876 | 37800.919 | 755.1243 | 7661.878 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 4888.0018 | 4777.1189 | 1203.2578 | -2294.0104 | 2605.5714 | 0% | Multiple | NA | No | 21% | 79% | Project scope and description varies for projects; Permitting and CEQA responsibility of 3rd party interconnection customers (not SDG&E); status varies by project 13: Unable to provide age of asset for blanket budget codes 45:NA
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140 | Twin Engine Medium Lift Helicopter |  |  | Gillespie Field, San Diego | Purchase of a twin engine, multi­mission, medium lift helicopter for primary use of external load work. The helicopter allows for heavier lift capability for continual distribution and transmission work in the high fire threat district. The helicopter also has fire fighting capabilities | Other | New | NA | NA | Other [See Notes] | Safety - Line Right of Way Access | NA | NA | NA | NA | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | 1.1 | 21256 | NA | QS00609 | NA | TRUE | 2023-08-02 | Work Order Authorization | 2021 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | 21765 | NA | 21764.6864 | 0 | 0 | 368.1651 | 1589.4562 | 202.6745 | 128.0765 | 0 | 0 | 0 | 0 | NA | NA | NA | 2024 | 0 | 0 | 0 | 0 | 128.0765 | 0% | NA | NA | No | NA | NA | 9: Various Aviation applications. 45: NA
141 | Transmission Power Quality |  |  | NA | This project will deploy Power Quality Meters in SDG&E electric substations on transmission circuits to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Replace Other Substation Equipment | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 500 | 373MVA | 4.3 | 22126 | Multiple | QBL0157 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 76.3477 | 20.465 | 23.3508 | 466.9761 | 394.8028 | 2785.5499 | 522.4645 | 529.123 | 535.2935 | 534.8107 | 456.7724 | NA | NA | 2023 ¦ 2024 | 0 | 0 | 0 | 701.3254 | 2621.6936 | 0% | NA | NA | No | 100% | 0% | 13: Unable to provide age of asset for blanket budget codes 45:NA
142 | Early Fault Detection |  |  | NA | This project will deploy Power Quality Meters and advanced Radio Frequency (RF) Sensors in SDG&E electric substations and electric distribution circuits within the High Fire Threat District to enable the collection of time-series analog data used to detect incipient failures of electrical equipment and locate that failing equipment before it can cause significant damage. The program will also fund various analytical / software tools utilized to aggregate this highly sampled data, analyze it and use it to triangulate the failure locations so crews may be dispatched to proactively inspect / investigate with a goal of preventing significant damage. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Automation | NA | NA | NA | NA* see notes | Protection Studies | NA | NA | HFTD Tier 2 ¦ HFTD Tier 3 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | NA | NA | 69-500 | NA | 1.1 | 22256 | Multiple | QB00205,QBL0148 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | -1.1914 | 1213.8 | 898.1128 | 99.05 | 457.611 | 457.611 | 0 | 0 | 11546.636 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | 13: Unable to provide age of asset for blanket budget codes 45:NA
143 | Narrows Rebuild |  |  | San Diego County | The Narrows 88/69 kV bank is on Kearny’s “transformer watchlist” and is nearly 100 years old. The transformers are leaking oil and DGA reports indicate increasing furans, poor oil quality, deteriorating insulation, and dielectric breakdown within the transformer. The transformer is also not large enough to carry all load in the area. Grid Ops is operationally limited when using the Narrows interconnection to feed Borrego. Other infrastructure at the site is also well past its useful life. The TL800 circuit breaker is an oil breaker manufactured in 1968. The TL686 circuit breaker recently failed, forcing an unplanned outage, and was replaced with a system spare that has already been in service for 10 years. The steel bus structure likely does not meet seismic requirements, and the brown glass cap and pin insulators are a point of common failure. A TL687 breaker will be added to improve reliability of the connection to Borrego. There is evidence that the ground grid at Narrows is in poor condition. Portions of the ground grid are showing above the finished grade of the site. The grounding grid should be assessed during the design process to ensure that there are no step and touch potential concerns. During construction, any damage found will be repaired. Lastly, an updated fence will be installed to improve site security. | Substation - Multiple | Upgrade/Retrofit | NA | NA | Reliability | Age/Condition | NA | NA | 2023-10-26 13:00 | 55; 99; 99; 99 | Lifecycle Replacement Analysis | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 0.526 | 69 | 69kV | 4.1 | 23126 | NA | QS00722 | NA | TRUE | 2023-11-29 | Work Order Authorization | 2023 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Planning | NA | 2026-05-20 | 2026-12-31 | 2026-12-31 | NA | NA | FALSE | 3962 | NA | 3961.6582 | 0 | 0 | 0 | 0 | 0 | 1334.4012 | 7294.6878 | 5437.1184 | 0 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | 632.87% ¦ Copperleaf | No | 0% | 100% | FERC Only - new project 45:NA
144 | Preliminary Survey & Investments |  |  | NA | Preliminary design and survey work | Transmission Line - Right of Way | NA | NA | NA | Other [See Notes] | Environmental | NA | NA | NA | NA* see notes | NA | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | NA | 99997 | Multiple | NA | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | 960.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | 2020 | 2264.5429 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | 9: Initial investigation of potential projects. 13: Unable to provide age of asset for blanket budget codes 45: NA
145 | SED Future Rebuilds |  |  | NA | Placeholder for future Substation Projects | Substation - Multiple | Multiple Options [See Notes] | NA | NA | Reliability | Substation Reliability | NA | NA | NA | NA* see notes | Lifecycle Replacement Analysis | NA | Multiple Options [See Notes] | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | 69-500 | NA | 4.1 | TBDET002 | Multiple | NA | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | TRUE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 10725.8683 | 38475.2265 | 42684.7653 | 18989.4893 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 21% | 79% | Projects are under blanket budget 13: Unable to provide age of asset for blanket budget codes 45:NA
146 | 3 Roots Relocation TL6906, TL677 & TL668 (East to West) |  |  | San Diego, San Diego | 3 Roots TL6906, TL677 & TL668 | Transmission Line - Multiple | Relocate | Upgrade/Retrofit | NA | Work Requested by Others | Facility Relocation | NA | NA | 2021-03-21 ¦ 2021-04-12 ¦ 2021-02-17 | NA* see notes | NA | NA | NA | NA | FALSE ¦ TRUE ¦ FALSE | FALSE | NA |  | 0.8 | NA | 69 | NA | 3.3 | 18143 | 2018-0188 | NA | NA | TRUE | 2019-09-09 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | Other [See Notes] | NA | NA | NA | NA | NA | Exempt | NA | NA [See Notes] | NA | Construction (10%-25%) | NA | 2023-12-06 | 2024-06-10 | 2025-12-31 | NA | NA | TRUE | 24662 | NA | 24661.554 | -138.6557 | 544.2273 | -1016.7867 | 312.2283 | -8057.3727 | 7232.1829 | 0 | 0 | 0 | 0 | -8085.6692 | NA | NA | 2020 ¦ 2021 ¦ 2022 ¦ 2023 ¦ 2024 | 0.46733 | -0.39262 | 0.02936 | 0.0014967 | -1977.9527 | 0% | NA | NA | No | 0% | 100% | 100% Customer requested relocation requiring CPUC Advice Letter. 45:NA
147 | Downtown Substation |  |  | San Diego, San Diego | New Downtown Substation 69/12kV | Substation - Multiple | New | NA | NA | Load Growth | New Substation | NA | NA | NA | NA | Other [See Notes] | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | Coastal |  | 8 | 4.5 | 12-69 | 12/69kV | 4.2 | 18251 | 2018-0170 | NA | NA | TRUE | 2020-11-16 | Work Order Authorization | 2019 | NA | FALSE | NA | NA | NA | FALSE | TBD | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | 2027-11-12 | Land Rights | NA | FALSE | 501 | NA | 2235.5819 | 181.1787 | 51.3482 | 54.0713 | 10.0565 | 162.8633 | 1582.7724 | 874.2597 | 456.0207 | 382.8625 | 0 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | NA | NA | Load growth in the area (Distribution Planning load forecast driver); 14: Distribution Planning 45:NA
148 | Granite - 12kV Breaker/Switchgear Replacement |  |  | Granite Hills, San Diego | Rebuild of the 69kV bus reconfiguring it from an ultimate 2 tie line bus to an ultimate 3 tie line substation. Replace all seven (qty: 7) 69kV kV circuit breakers (5 OCB and 2 GCB/older style). Install new 69kV Potential Transformers. Replace 12kV open rack bus and (qty. 8) 12kV circuit breakers and (qty:2) 12kV 1/4 section Switchgear at Granite Substation, due to operational problems, again infrastructure, environmental concerns, in addition to meeting current reliability standards. Rebuilding the 69kV bus and rotating the phases at the transmission pole will allow for a third tie line position. Replacing the 12kV open rack will RFS the OCBs and address the some 12kV reliability issues, will update relaying to support WMP initiatives (advance protection). The new control shelter will assist with updating relaying to include TCRI, new 69kV BT, and increase operational ability. | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2023-09-11 13:00 | NA | Lifecycle Replacement Analysis | Lifecycle Replacement Analysis | $0 Mil – $1 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.38 | 12-69 | 12/69kV | 4.1 | 20244 | 2021-2405 | QS00430 | NA | TRUE | 2021-07-19 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | 2021-03-19 | NA [See Notes] | NA | Engineering more than 50% complete | NA | 2023-12-06 | 2024-07-22 | 2026-09-30 | NA | NA | FALSE | 20,000 ¦ 30,000 | NA | 21654.0813 | 0 | 0 | 22.6898 | 151.8227 | 822.0659 | 2153.5257 | 669.5404 | 68.1459 | 0 | 0 | 7626.2763 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | Project is in flight. 45:NA
149 | Chicarita 12kV Breaker |  |  | San Diego, San Diego | Replacement of: (Qty:8) 12kV Circuit Breakers, (Qty:3) 138kV Circuit Breakers, and (Qty:1) 12kV Switchgear at Chicarita Rebuild Substation, (Qty:2) Capacitor Banks and (Qty:1) Control Shelter due to proactively replace aging substation equipment to improve future SAIDI impact, Environmental concerns and Operational concerns | Substation - Circuit Breaker | Replace | Upgrade/Retrofit | NA | Reliability | Age/Condition - Replace Breakers | NA | NA | 2023-10-04 09:59 | 50; 30; 50 | Lifecycle Replacement Analysis | Lifecycle Replacement Analysis | $0 Mil – $1 Mil | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | 1.73 | 12-69 | 12/69kV | 4.1 | 20264 | 2014-00306-ZZ | QS00548 | NA | TRUE | 2021-03-12 | Work Order Authorization | 2020 | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | NA | NA | NA | NA | FALSE | 10,000 ¦ 20,000 | NA | 9308.4328 | 228.1314 | 56.2689 | 12.9578 | 4.6326 | 3.5594 | 0 | 2586.6256 | 389.8355 | 96.3864 | 0 | 392.4785 | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 0% | 100% | In Planning; project not yet scheduled; budgeted to design start beyond 2025; 45:NA
150 | Miguel-Sycamore Canyon 230kV Line Loop-in Suncrest |  |  | San Diego, San Diego ¦ Santee, San Diego ¦ Lakeside, San Diego ¦ Rancho San Diego ¦ San Diego ¦ Granite Hills, San Diego | Miguel-Sycamore Canyon 230kV Line Loop-in Suncrest | Transmission Line - Multiple | New | Upgrade/Retrofit | NA | Reliability | T-Line Reliability | NERC TPL Standards | NA | NA | NA* see notes | Steady State Power Flow System Analysis | NA | NA | HFTD Tier 2 | FALSE ¦ FALSE ¦ TRUE | FALSE | NA |  | 27.8 | NA | 230 | NA | NA | 23127 | 2018-0199 | NA | NA | TRUE | NA | Work Order Authorization | 2023 | 2023 | FALSE | 2022 ¦ 2023 | NA | https://www.caiso.com/Documents/ISO-Board-Approved-2022-2023-Transmission-Plan.pdf | FALSE | TBD | NA | NA | NA | CPUC | NA | NA | NA | NA [See Notes] | NA | Planning | NA | NA | 2032 | NA | NA | NA | FALSE | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 999.5695 | 1999.1329 | 2998.6896 | 119383.2415 | 119383.2215 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | 100% | 0% | 13: asset age data discrepancy being corrected for future submission 45: NA
151 | Substation External Routable Connectivity (SERC) |  |  | NA | The SERC program deploys secure routable protocol connections providing event retrieval, password management and remote secure event access to all CIP Medium, Low and No Impact substations. It achieves this by deploying Advanced Relay Event Retrieval (ARER) hardware, Siemens Crossbow devices, and deployment of systems in support thereof. The program also analyses and tests emerging ERC technology use cases and solutions. | Substation - Other Equipment | Upgrade/Retrofit | NA | NA | Reliability | System Operations | NA | NA | NA | NA | Protection Studies | NA | NA | NA | FALSE ¦ FALSE ¦ FALSE | FALSE | NA |  | NA | NA | NA | NA | NA | 23129 | Multiple | QBL0160 | NA | TRUE | NA | Work Order Authorization | NA | NA | FALSE | NA | NA | NA | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA [See Notes] | NA | Operational | NA | NA | NA | NA | NA | NA | FALSE | 3560 | Multiple | 3560.0581 | 0 | 0 | 0 | 0 | 0 | 3431.9576 | 49.6616 | 50.733 | 51.4342 | 4.3181 | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0% | NA | NA | No | NA | NA | 13: Unable to provide age of asset for blanket budget codes 45:NA

## Data Fields
Category | Sorting Order | Data Field # | Transmission Project Data Field | Format | Example | Input Terms and Descriptions
Project Description | 1 | 1 | Row/Line No. | Number (whole number) | 4 | Row/line number in spreadsheet. Include separate project lines, as described and required in data fields 26-28, for all subparts, i.e., ID #1 of all FERC-jurisdictional electric transmission projects, including generator interconnection-related network upgrades: 1. the total cost of which At Unique ID #2 will at any point equal or exceed $1 million. In the event that there is no ID#2 to provide, the million-dollar threshold applies to ID #1. and 2. for which there were capital expenditures in the last five years OR for which any capital expenditures are anticipated in the current or next four years, regardless of the actual or anticipated operative date. Each project should have at least one Row/Line No. in this spreadsheet, as subparts of projects will require additional project lines.
Project Description | 2 | 2 | Project Name | Text String, separated by " ¦ " as necessary | Manzanita Substation | Include Project Name at date of report filing. Identify all prior names of the project and other names currently used in different venues, including the name as approved and included in the CAISO's TPP.
Project Description | 3 | 3a | Latitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | 20.234 ¦ 19.983 | Positive number indicates north of equator. Subject to redaction in the public data.
Project Description | 4 | 3b | Longitude | Number (decimal), separated by " ¦ " for multiple locations; NA if no geolocation | -132.018 ¦ -132.231 | Negative number indicates west of Prime Meridian. Subject to redaction in the public data.
Project Description | 5 | 4 | Location 2 | Text String, with comma separator between City and County. Multiple entries separated by " ¦ ". Order of values to be consistent with latitude and longitude values * City1, County1 ¦ City2, County2 | Berkeley, Alameda ¦ Concord, Contra Costa | All Cities and Counties included in the scope of the project.
Project Description | 6 | 5 | Project Description | Text String | This project will repair the transmission line connecting 4th and Townsend to the East Northfork station which failed as consequence of the 2019 San Clemente Hedge Fire. Assets to be replaced include... at ....kV. | General project overview: what, where, and why. Discuss all assets to be installed and include all capacities (MVA) and voltages (kV).
Project Description | 7 | 6 | Project Description - What | Select text from drop-down menu | Substation - Circuit Breaker | Transmission line (new, reconductor, relocation), substation (breaker, transformer relay protection), etc.
Project Description | 8 | 7 | Project Description - Action Taken (2) | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 9 | 7 | Project Description - Action Taken | Select text from drop-down menu(s) | Upgrade/Retrofit | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed.
Project Description | 10 | 8 | Project Dependencies | Number (whole) indicating required project or projects' Unique ID #(s), separated by " ¦ " as necessary | 235435 ¦ 432787 | Identify all other projects (Unique ID #1) in the spreadsheet that this project depends on and/or whose construction will be bundled with this project.
Project Description | 11 | 9 | Primary Purpose | Select text from drop-down menu | Reliability | May include, but not limited to: CAISO Transmission Planning Standards (NERC Compliance and contingency code, WECC Requirement (and the specific requirement)), Reliability, Load Growth, Local Capacity Requirement, Address Results of Power Flow Analysis, Address Results of Protection Studies, Physical Security, Policy, Economic, Generator Interconnection, Work Requested by Others, Age/End of Life, Wildfire Mitigation, Field Test Results, Emergency Event, Location, Environmental Conditions, Safety, Asset Condition, or Other. In the "Notes" data field, please explain a purpose identified as "Other" or provide additional details on the purpose identified.
Project Description | 12 | 10 | Secondary Purpose | Select text from drop-down menu | Age/Condition - Anti Climb Guards | May include, but not limited to: 3rd Party Damage, Age/Condition, Age/Condition - 230/115/70/60 kV Relay Replacement, Age/Condition - 500 kV Relay Replacement, Age/Condition - Anti Climb Guards, Age/Condition - Insulator Replacement - Steel, Age/Condition - Insulator Replacement - Wood, Age/Condition - Raptor Protection - Steel, Age/Condition - Replace 230/115/70/60 kV Breakers, Age/Condition - Replace 230/115/70/60 kV Transformers, Age/Condition - Replace 500 kV Breakers, Age/Condition - Replace 500 kV Transformers, Age/Condition - Replace Boardwalks, Age/Condition - Replace Breakers, Age/Condition - Replace Civil Structures, Age/Condition - Replace Conductor, Age/Condition - Replace Insulators, Age/Condition - Replace Other Substation Equipment, Age/Condition - Replace Other T-Line Equipment, Age/Condition - Replace Reactors, Age/Condition - Replace Relays, Age/Condition - Replace Relays, Age/Condition - Replace SCADA/RTU, Age/Condition - Replace Steel Poles, Age/Condition - Replace Switches, Age/Condition - Replace Transformers, Age/Condition - Replace Underground System, Age/Condition - Replace Wood Poles, Age/Condition - Switch Replacement - Steel, Age/Condition - Switch Replacement - Wood, Age/Condition - Targeted Relay Replacement, Age/Condition - Wood Pole Reframe, Animal Abatement, Automation, Bus Upgrade, Compliance - Remove Idle Facilities, Construct Roads/Gates/Culverts, Emergency Response - Fire Related, Emergency Response - Storm Related, Environmental, Facility Relocation, Fire Protection, Generation Interconnection, GO95 Mitigation - Steel, Install SCADA/RTU, Line Reconductoring, Line Termination, Load Interconnection, Modular Protection and Automation Control, NERC CIP Compliance, NERC Compliance - GO 95, New Substation, New T-Line, Priority 1 Steel Structure Replacement, Priority 1 Wood Structure Replacement, Protection NERC Compliance, Relay Upgrades, Replace Breakers, Replace Other Substation Equipment, Replace Transformers, Safety - Line Right of Way Access, SCADA Emergency Replacement, SCADA Switch Installation, Security Upgrades, Seismic Upgrade - Replace Conductor, Special Protection Scheme, Substation Capacity, Substation Reliability, System Design Upgrade, System Operations, Targeted Line Reliability, T-Line Capacity, T-Line Emergency, T-Line Reliability, Tools, Transformer Addition/Replacement, Underground Emergency, Voltage Conversion, Voltage Support. If the secondary purpose is to comply with a NERC, WECC, or CAISO requirement, list the standard, requirement, and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 13 | 11 | NERC / WECC / CAISO Standard / Requirement / Contingency | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 14 | 11 | NERC/WECC/CAISO Standard/Requirement/Contingency (2) | Select text from drop-down menu(s) | CIP-006 | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If the primary or secondary purpose relates to complying with a NERC, WECC, or CAISO requirement, list the specific standard(s), requirement(s), and/or any contingencies that are being addressed in the "Notes" data field.
Project Description | 15 | 12 | Last Inspection | Date, formatted YYYY-MM-DD if text; NA if not yet inspected | 2019-12-10 | Specific date when the last inspection of the asset being repaired, replaced, or upgraded occurred.
Project Description | 16 | 13 | Age of Asset | Number (whole number) | 12 | Age in years from original in-service date of the asset being repaired, replaced, or upgraded.
Project Description | 17 | 14 | Types of Analyses | Select text from drop-down menu | Load Flow | Types of analyses that have been performed on the asset being repaired, replaced, or upgraded (e.g., load flow, short circuit, corrosion). List all field test and results that indicated the need for the project, and include inspector ID, when available in the "Notes" data field.
Project Description | 18 | 15a | Alternative Solutions and Costs - Solutions | Select text from drop-down menu(s) | Dynamic System Analysis | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. Include all alternative solutions to the project that were considered and the costs of all alternatives considered.
Project Description | 19 | 15b | Alternative Solutions and Costs - Costs | Select text from drop-down menu(s) | $5 Mil - $10 Mil | See drop-down menu for options. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field. If multiple responses as included for the Sulutions and Costs fields, please provide costs in the same order as solutions.
Project Description | 20 | 16 | CPUC Fire Threat Zone/Rating | Text String, separated by " ¦ " as necessary, or NA | HFTD Tier 2 | Indicate whether the project is located in Tier1, Tier 2, or Tier 3 of CPUC's High Fire-Threat Districts (HFTD) or Zone 1 in CalFire/USFS High Hazard Zone (HHZ).
Project Description | 21 | 17 | Wildfire Related | Boolean, TRUE or FALSE, divided by " ¦ " | TRUE ¦ TRUE ¦ FALSE | Indicate whether the project is 1. related to repairing wildfire damage, 2. a measure identified in the Wildfire Mitigation Plan, or 3. is related to wildfire in some other way. If #3, please explain in the "Notes" data field.
Project Description | 22 | 18 | RAMP | Boolean, TRUE or FALSE | TRUE | Indicate whether the project is a proposed mitigation measure in the utility's Risk Assessment & Mitigation Phase (RAMP).
Project Description | 23 | 19 | Other Environmental Factors | Text String, or NA | Project exists in CA Building Climate Zone 3 which presents a high risk of accelerated oxidation or steel structures due to coastal humidity and salt exposure. | Environmental factors in the project's location that may affect the length of the asset's service life.
Project Description | 24 | 20 | Project Manager | Text String: Last, First | Doe, John | Person in charge of the implementation of this project for the Utility.
Project Description | 25 | 21 | Transmission Project Size (length in miles) | Number (decimal), or NA | 42.66 | Miles of transmission power lines included in the project.
Project Description | 26 | 22 | Substation Project Footprint (acres) | Number (decimal), or NA | 12.25 | Acres of substation footprint included in the project.
Project Description | 27 | 23 | Transmission Voltage Level (kV) | Number (whole), or NA | 230 | Use kV for transmission power lines ratings.
Project Description | 28 | 24 | Substation or Transformer Capacity (MVA and/or kV) | Text String, or NA if unrelated | 115kV | Use MVA and/or kV for substations.
Project Description | 29 | 25 | Utility Prioritization Ranking | Number (whole), in reference to ranking system identified in field name | 1 | Using the Utility's prioritization ranking. If multiple metrics are used to prioritize projects, please include a separate data subfield for each. (Sub-columns can be created to accommodate multiple or tiered ranking methodologies.)
Project Description | 30 | 26 | Project ID (Utility Unique ID #1) | Text String | 78493 | Most specific (PG&E = Planning Order, SCE = SCE ID, SDG&E = Project ID)
Project Description | 31 | 27 | Budget Code (Utility Unique ID #2) | Text String | 432 | Less specific (PG&E = T.dot, SCE = Capital Work Breakdown Structure, SDG&E = Budget Code)
Project Description | 32 | 28 | Work Order (Utility Unique ID #3) | Text String | 92 | Least specific (PG&E = Major Work Category, SCE = Project Identification Number , SDG&E = NA)
Project Description | 33 | 29 | Changes in Unique IDs | Date, formatted YYYY-MM-DD, and former identifiers: YYYY-MM-DD ¦ UID1 ¦ UID2 ¦ UID 3 If any components remain unchanged, use NA for those UIDs | 2022-05-05 ¦ NA ¦ NA ¦ 78322 | If any of the Unique IDs above changed at any time, please note the date of change and the former ID.
Utility/CAISO Approval and FERC Rate Cases | 34 | 30 | Utility Approval | Boolean: TRUE or FALSE | TRUE | "TRUE" if the Utility self-approved the project; "FALSE" if not.
Utility/CAISO Approval and FERC Rate Cases | 35 | 31 | Year of Internal Utility Approval | Date, formatted YYYY-MM-DD, or NA | 2022-01-02 | If utility has approved the project, insert first year of internal approval. If not insert "NA."
Utility/CAISO Approval and FERC Rate Cases | 36 | 32 | Process(es) for Utility Approval | Text String, or NA | Annual Capital Operating Plan Process | If utility has approved the project, insert utility approval process for which a description has been provided to the CPUC and Stakeholders.
Utility/CAISO Approval and FERC Rate Cases | 37 | 33 | Long term Transmission Investment Plan Inclusion | Year, formatted YYYY | 2022 | The year in which the project was first included in the utility's long-term transmission investment plan.
Utility/CAISO Approval and FERC Rate Cases | 38 | 34 | CAISO Year | Year, formatted YYYY, or NA | 2019 | Insert the year when approved by CAISO. If not a CAISO-approved project, insert "NA".
Utility/CAISO Approval and FERC Rate Cases | 39 | 35 | Transmission Planning Process ("TPP") Phase 3 | Boolean: TRUE or FALSE | FALSE | Please indicate with "TRUE" if any part of this project was subject to the competitive solicitation process in the TPP. In the "Notes" section briefly describe any portion of the project awarded to another developer and how it relates to the project in this Spreadsheet.
Utility/CAISO Approval and FERC Rate Cases | 40 | 36 | Year(s) when considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2020 ¦ 2021 | Indicate years in which the project was considered in the TPP. If considered in year(s) prior to CAISO approval, please indicate all years.
Utility/CAISO Approval and FERC Rate Cases | 41 | 37 | Year when expected to be considered in CAISO TPP | Years, formatted YYYY and separated by " ¦ ", or NA | 2025 | If not yet considered in the CAISO TPP, indicate the year when it is expected to be considered in the CAISO TPP.
Utility/CAISO Approval and FERC Rate Cases | 42 | 38 | Link to TPP where project has been considered, approved, and/or expected to be considered | URL | http://www.caiso.com/Documents/BoardApproved-2017-2018_Transmission_Plan.pdf | Insert active hyperlink to any TPP where project was considered, including years in which the project was not approved.
Utility/CAISO Approval and FERC Rate Cases | 43 | 39 | Generator Interconnection and Deliverability Allocation Procedures (GIDAP) Related | Boolean: TRUE or FALSE | TRUE | Please indicate with TRUE or FALSE whether this transmission project is a transmission network upgrade related to generator interconnection(s).
CPUC Permit Status | 44 | 40a | CEQA Status | Select text from drop-down menu | Final Certified | See drop-down menu for options. Include one of the following: Expected PEA Completion, PEA Deemed Complete, CEQA Draft Published, CEQA Final Published, Final Certified, TBD, Other [See Notes], or NA.
CPUC Permit Status | 45 | 40b | CEQA Status - Date | Date, formatted YYYY-MM-DD, or NA | 2020-03-29 | Include the date that corresponds with the CEQA status.
CPUC Permit Status | 46 | 41a | CEQA Document Type | Select text from drop-down menu | EIR | Examples include: IS/ND, IS/MND, EIR, Exempted, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 47 | 41b | NEPA Document Type | Select text from drop-down menu | EIS | Examples include: EIS, EA, Categorical Exclusion, Other, or NA (If "Other," include explanation in the "Notes" data field.).
CPUC Permit Status | 48 | 42a | CEQA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | CPUC | Examples include: CPUC, SWRCB, CSLC, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 49 | 42b | NEPA Lead Agency | Text String, separated by " ¦ " as necessary, or NA | USFS | Examples include: USFS, NA etc. If more than two options are required, enter each, pipe-delimited.
CPUC Permit Status | 50 | 43 | CPUC Filing Type | Text String, or NA | PG&E AL 2355-E | NOC Advice Letter (AL), Application for 851, PTC, CPCN, or NA. If an AL, include the number. If an Application, include number.
CPUC Permit Status | 51 | 44 | CPUC Date Filed | Date, formatted YYYY-MM-DD, or NA | 2022-04-08 | The year filed at the CPUC or insert "Not yet filed" with the expected filing date.
CPUC Permit Status | 52 | 45 | CPUC Status | Select text from drop-down menu | Approved | Indicate "Approved", "Rejected", "To be Filed", "Filed and Under Review," "Other," or "NA" (If "Other" or "NA", include explanation in the "Notes" data field.).
CPUC Permit Status | 53 | 46 | CPUC Status: Year | Year, formatted YYYY, or NA | 2019 | Insert the year this CPUC Status was determined.
Project status | 54 | 47 | Project Status | Select text from drop-down menu | Construction (10%-25%) | See drop-down menu for options. Examples include: Planning, Engineering less than 50% complete, Engineering more than 50% complete, Permitting, Construction (include percentage of construction completed at the time this data spreadsheet is provided (i.e., less than 10%, 10%-25%, 25%-50%, 50%-75%, greater than 75%), Operational, On Hold, Canceled, or Abandoned (if On Hold, Canceled, or Abandoned, include explanation in the "Notes" data field.).
Project status | 55 | 48 | AACE Class | Select text from drop-down menu | 3 | The current Estimate Class in AACE International's Cost Estimate Classification System at the time this data spreadsheet is provided.
Project status | 56 | 49 | Construction Start Date | Date, formatted YYYY-MM-DD, or NA | 2025-06-01 | The date on which construction began or is expected to begin.
Project status | 57 | 50 | Original Planned In- Service Date | Date, formatted YYYY-MM-DD, or NA* | 2025-06-01 | What was the expected in-service date when the project was first approved by the CAISO? If not a CAISO-approved project, provide the expected in-service date when the project was approved internally by the Utility.
Project status | 58 | 51 | Current Projected or Actual In-Service Date | Date, formatted YYYY-MM-DD, followed by OAI indicator if applicable (or NA) | 2021-01-01 ¦ NA 2021-01-01 ¦ OAI | At the time the data was extracted from the Utility’s Database(s) as provided in Section 2.1.5 of the Transmission Project Review Process Description. Projects without identified in-service dates that are "Operative as Installed" should be identified as "OAI".
Project status | 59 | 52 | Reason for Change in In- Service Date | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 60 | 52 | Reason for Change in In-Service Date (2) | Select text from drop-down menu(s) | Customer Action | See drop-down menu for options. If the current projected or actual in-service date varies more than six months from the original in-service date, please select all reasons for this change. If more than two options are required, select "Multiple Options" in second column and provide remaining responses, pipe-delimited, in "Notes" data field.
Project status | 61 | 53 | In-Flight Projects | Boolean: TRUE or FALSE | TRUE | For projects with costs expected to go into rate base in the current rate year or in the following rate year at FERC, please indicate with "TRUE." If there will be no additions to rate base in either year, indicate with "FALSE."
Costs | 62 | 54 | Original Projected Cost or Cost Range ($000) | Dollar value, or dollar value range, separated by " ¦ " | 2100 ¦ 2500 | Forecast cost or forecast cost range for Utility Unique ID #2, i.e., the totality of the project, at the earliest of CAISO, CPUC, or utility internal approval.
Costs | 63 | 55 | Cost Cap ($000) | Dollar value and Text String, separated by " ¦ ", or NA | 2500 ¦ CAISO TPP | Insert Cost Cap on project if available, as well as the authority imposing the cost cap. This shall include any maximum cost determined to be reasonable and prudent in a CPUC proceeding or a cost cap set for a competitively bid project in the CAISO's Transmission Planning Process.
Costs | 64 | 56 | Current Projected Total or Actual Final Cost ($000) | Dollar value | 78 | Updated projected fully-loaded total or actual fully loaded final cost of project. Projected total should be the anticipated sum of all capital expenditures, overhead,and AFUDC. Actual cost should be the total expenditures, overhead and AFUDC in the addition to rate base. Operational projects and all data must remain in this report for at least five (5) years after the last of the project's expenditures and capital additions.
Costs | 65 | 57 | 2019 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 66 | 57 B | 2020 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 67 | 57 C | 2021 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 68 | 57 D | 2022 Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 69 | Internal | October 2023 YTD Actual Capital Expenditures ($000) | Dollar value | 12 | Please include separate columns for each of the previous five (5) years and one for actual expenditures for the current year as of the date the data was extracted. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 70 | 58 | Nov & Dec 2023 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 71 | 58 B | 2024 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 72 | 58 C | 2025 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 73 | 58 D | 2026 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 74 | 58 E | 2027 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 75 | 58 F | 2028 Projected Capital Expenditures ($000) | Dollar value | 4650 | For the current year and four (4) future years, provide the year-by-year fully-loaded forecast capital expenditures for the project. Please include separate columns for each year. If these expenditures do not include overheads and AFUDC, please provide those year-by-year.
Costs | 76 | 59 | Construction Work in Progress Expenditures ($000) | Dollar value | 2350 | Total amount of money that has been spent so far for the project through the last calendar year.
Costs | 77 | 60 | Accrued Overhead | Dollar value | 12 | If the capital expenditures provided in Data Field #57 do not include Overhead, please provide the accrued Overhead through the last calendar year.
Costs | 78 | 61 | Accrued AFUDC | Dollar value | 0 | If the capital expenditures provided in Data Field #57 do not include AFUDC, please provide the accrued AFUDC through the last calendar year.
Costs | 79 | 62 | FERC: Year(s) | Years, separated by " ¦ ", or NA | 2023 ¦ 2024 ¦ 2025 ¦ 2026 ¦ 2027 | Insert ALL rate years when any costs of this project went - or are forecast to go - into FERC jurisdictional transmission rate base.
Costs | 80 | 63 | 2020 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2022 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 81 | 63 B | 2021 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2023 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 82 | 63 C | 2022 Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2024 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 83 | 63 D | October 2023 YTD Actual FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2025 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 84 | 63 E | Nov & Dec 2023 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2026 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 85 | 63 F | 2024 Projected FERC Dollars Ratebased ($000) | Dollar Value, per year column e.g., FERC_dollars_in_rate_base_2027 | 500000 | Insert the year(s) and actual dollars added to FERC jursidictional transmission rate base on the project for each of the four prior years and the present year. This should include additional costs added to rate base in years after operation first occurred.
Costs | 86 | 64 | Percentage of Bid | Percentage to two decimals, and Text String, separated by " ¦ " | 33.33% ¦ "SuperPower LLC is developing a third of the project as part of its "TransValley Electrification" project. See http://.... | Percentage (or actual cost) of project implemented by outside developer, as opposed to the incumbent utility. If there is a project being developed by a non-incumbent utility that relates to this project, please indicate the name of the project as approved in the CAISO TPP.
Costs | 87 | 65 | Percentage of Work Requested by Others Passed onto Ratepayers | Percentage to two decimals and/or dollar value. If both, separate by " ¦ ". If either is not provided, please enter NA. | 25.00% ¦ 2300 35% ¦ NA NA ¦ 50000 | If the project is work requested by others or customer-driven, what percentage of the projects costs has been - or is expected to be - passed onto ratepayers? If the dollar amount being passed onto ratepayers is fixed, then this number can be expressed as a dollar amount.
Costs | 88 | 66 | Cost-Benefit Analysis | Percentage to two decimals, and ranking system identifier, separated by " ¦ " | 25.00% ¦ EnergyRank | The Cost-to-Benefit ratio. If the Utility's Cost-Benefit analysis related to its Risk-Based Decision-Making Framework (RDF) has not already been included in the "Utility Prioritization Ranking" data field above, please include it here.
Costs | 89 | 67 | FERC Incentives | Test Strings, separated by " ¦ ", or NA | Abandoned Plant ¦ CWIP | List any project-specific transmission incentives granted under any FERC Orders.
Costs | 90 | 68 | Percentage of Cost in High Voltage TAC | Percentage to two decimals | 23.05% | Insert % of project cost recovered in the high-voltage TAC.
Costs | 91 | 69 | Percentage of Cost in Low Voltage TAC | Percentage to two decimals | 0% | Insert % of project cost recovered in the low-voltage TAC.
Notes | 92 | 70 | Notes | Strings, inclusive of field identifiers in brackets, separated by 3 linebreaks ("\n\n\n"), or NA [ID1] String1 [ID2] String2 | [CEQA/NEPA Document Type] Form STD762 [CPUC Status] Approved in part following bifurcation. Details indeterminate as of 5/6/2024. Expected update and clarification by 8/1/2024. | Any additionally requested information or other needed details about the project that were not otherwise covered.

## Change Log
Change Number | Type | Description | Date Modified
1 | Correction | Field 5: Added "placeholder" to multiple cells. | 2024-01-19
2 | Correction | Field 6 & 7: made multiple changes where "Multiple" was chosen to adhere to more specific descriptors and formatting. | 2024-01-19
3 | Correction | Field 8: Corrected several cells to list Project Dependencies in UID1 value format. | 2024-01-19
4 | Correction | Field 23: Corrected multiple cells with multiple entries to have pipe-delimited (" ¦ ") low¦high format | 2024-01-19
5 | Correction | Field 24: Corrected multiple cells with multiple entries to have a pipe-delimited (" ¦ ") low¦high format | 2024-01-19
6 | Correction | Field 65: Reviewed all work requested by others and confirmed "NA" is appropriate for all projects except one instance of "Multiple" that is not currently feasible to breakout in percentages and dollars. | 2024-01-19
7 | Correction | Field 67: Corrected all cells with "No" to "NA". | 2024-01-19
8 | Correction | Field 70: Corrected all cells to adhere to formatting in Atch B. | 2024-01-19
9 | Correction | Field 15a: Incorrectly listed input options from Field 14. Made the necessary changes to the correct options that applied. | 2024-02-07
10 | Correction | Field 57, 58, & 63: Cost data for roughly half of projects either missing or out of sync due to suspected formula/data validation error prior to release of initial project list. Corrected all instances and tied back to all source data. | 2024-02-27
11 | Correction | Field 57 & 58: Cost data missing for two specific project rows (Line No. 7 and 8). Reason from Business Planning is that the budget codes for these rows were not part of TM1 search query by design as one is an IT project and the other is 100% billable so is modeled differently. Missing cost data obtained and entered into the project list. | 2024-03-01
12 | Correction | Field 54: Cost data for Line No. 44 was manually entered incorrectly as $488 during initial preparation of the project list. Value is updated to $48,810 | 2024-03-05
13 | Correction | Field 54: 'NA' replaced with Original Project Cost amount for Line Nos. 42, 54, 68, 72-73, 75-76, 95, and 136 | 2024-03-06
14 | Correction | Field 56: 'NA' replaced with Current Projected Total amount for Line Nos. 42, 54, 95, and 136 | 2024-03-06
15 | Correction | Field 47: 'On Hold' replaced with 'Planning' for Line No. 68 | 2024-03-07
16 | Correction | Field 63: For 'Dollars Put into FERC Rate Base 2023 ($000)' the amount is updated from zero to $2,160 | 2024-03-08
17 | Correction | Field 57: Cost data is updated from Field 57 (2019-2023 capital expenditures). Fields were originally blank in error. | 2004-03-11
18 | Data Request | Field 9, 15a, 51: Per Data Request 01-61 21156 added rows 130-143 with data added to columns mentioned. | 2024-03-15
19 | Data Request | Field 17: Data Request 01-69: 7 projects changed from FALSE¦FALSE¦FALSE to TRUE¦TRUE¦TRUE | 2024-03-15
20 | Correction | Field 52: Updated to show permitting for UID#1 9132 | 2024-03-18

## Options Lists
06. Project Description - What | 07. Project Description - Action taken | 09. Primary Purpose | 10. Secondary Purpose | 11. NERC/WECC/CAISO Standard/Requirement/Contingency | 14. Types of Analyses | 15a. Alternative Solutions and Costs - Solutions | 15b. Alternative Solutions and Costs - Costs | 40. CEQA Status | 41a. CEQA Document Type | 41b. NEPA Document Type | 45. CPUC Status | 47. Project Status | Column1 | 48. AACE Class | 52. Reason for Change in In-Service Date
Substation - Multiple | New | CAISO Transmission Planning Standards [See Notes for NERC Compliance and contingency code, WECC Requirement (and the specific requirement)] | 3rd Party Damage | NERC CIP Compliance | Lifecycle Replacement Analysis | Wires - System Configuration Alternative | $0 Mil – $1 Mil | Expected PEA Completion | IS/ND | EIS | To be Filed | Planning | planning | 1 | Weather
Substation - Other Equipment | Replace | Reliability | Age/Condition | NERC BAL Compliance | Steady State Power Flow System Analysis | Wires - Location/Route Alternative | $1 Mil - $2 Mil | PEA Deemed Complete | IS/MND | EA | Filed and Under Administrative Review | Engineering less than 50% complete | design | 2 | Permitting
Substation - Transformer | Upgrade/Retrofit | Load Growth | Age/Condition - 230/115/70/60 kV Relay Replacement | NERC FAC Compliance | Dynamic System Analysis | Wires - Reconductor/Line Rebuild Alternative | $2 Mil - $3 Mil | CEQA Draft Published | EIR | Categorical Exclusion | Administratively Complete and Under Technical Review | Engineering more than 50% complete | design, pre-constr | 3 | Clearances
Substation - Circuit Breaker | Relocate | Local Capacity Requirement | Age/Condition - 500 kV Relay Replacement | WECC Audit Findings | Short Circuit Duty Analysis | Wires - Replacement Alternative | $3 Mil -$5 Mil | CEQA Final Published | Exempted | Other [See Notes] | Approved | Permitting | permit | 4 | Material
Substation - Line Termination | Removal | Address Results of Power Flow Analysis | Age/Condition - Anti Climb Guards | NERC PRC Compliance | Protection Studies | Wires - Minimum Required Scope (spot repair) Alternative | $5 Mil - $10 Mil | Final Certified | Other [See Notes] | NA | Rejected | Construction (under 10%) | constr | 5 | Workforce
Substation - Voltage Support Equipment | NA | Address Results of Protection Studies | Age/Condition - Insulator Replacement - Steel | NERC TPL Standards | Interconnection System Impact/Facilities Studies | Wires - Voltage Support/Reactive Support Alternative | $10 Mil -$15 Mil | TBD | NA |  | Advice Letter Filed and In-Process | Construction (10%-25%) | constr | NA | Prioritization
Substation - Bus Arrangement | Multiple Options [See Notes] | Physical Security | Age/Condition - Insulator Replacement - Wood | CAISO Requirement | Other [See Notes] | Wires - New Substation Alternative | $15 Mil - $20 Mil | Other [See Notes] |  |  | Other [See Notes] | Construction (25%-50%) | constr |  | Bundling Dependencies
Substation - Switch |  | Policy | Age/Condition - Raptor Protection - Steel | Other [See Notes] | Multiple Options [See Notes] | Wires - Bus Upgrade Alternative | $20 Mil - $30 Mil | NA |  |  | NA [See Notes] | Construction (50%-75%) | constr |  | Customer Action
Substation - Modular Protection and Automation Control Building |  | Economic | Age/Condition - Replace 230/115/70/60 kV Breakers | NA | NA | Wires - New T-Line Alternative | $30 Mil - $40 Mil |  |  |  |  | Construction (over 75%) | constr |  | ISO Action
Substation - Protection Relay |  | Generator Interconnection | Age/Condition - Replace 230/115/70/60 kV Transformers | Multiple Options [See Notes] |  | Non-Wires - Large Scale Energy Alternative | $40 Mil - $50 Mil |  |  |  |  | Operational | close out, cmplt, |  | Completed Early
Substation - Reactive Equipment |  | Work Requested by Others | Age/Condition - Replace 500 kV Breakers |  |  | Non-Wires - System DER Alternative | $50 Mil – $75 Mil |  |  |  |  | On Hold |  |  | Construction Delays
Substation - Structure |  | Age/End of Life | Age/Condition - Replace 500 kV Transformers |  |  | Other - Status Quo | $75 Mil – $100 Mil |  |  |  |  | Canceled |  |  | Outage
Other - IT |  | Wildfire Mitigation | Age/Condition - Replace Boardwalks |  |  | Other - Deferral | $100 Mil – $125 Mil |  |  |  |  | Abandoned |  |  | Project Design
Other - Physical Security |  | Field Test Results | Age/Condition - Replace Breakers |  |  | TBD | $125 Mil - $150 Mil | [7 empty] | Input Error
Other - Operations Tech |  | Emergency Event | Age/Condition - Replace Civil Structures |  |  | NA | $150 Mil - $175 Mil | [7 empty] | Vendor Quality/Delays
Other - Cybersecurity |  | Location, Environmental Conditions | Age/Condition - Replace Conductor |  |  |  | $175 Mil - $200 Mil | [7 empty] | Scope Change
Other - Remedial Action Scheme/Special Protection Scheme |  | Safety | Age/Condition - Replace Insulators |  |  |  | $200 Mil - $250 Mil | [7 empty] | Land Rights
Other |  | Asset Condition | Age/Condition - Replace Other Substation Equipment |  |  |  | $250 Mil – $300 Mil | [7 empty] | Other [See Notes]
Other - Environmental |  | Other [See Notes] | Age/Condition - Replace Other T-Line Equipment |  |  |  | $300 Mil - $350 Mil | [7 empty] | NA
Other - Civil |  |  | Age/Condition - Replace Reactors, Age/Condition - Replace Relays |  |  |  | $350 Mil – $400 Mil | [7 empty] | Multiple Options [See Notes]
Transmission Line/Substation |  |  | Age/Condition - Replace Relays |  |  |  | $400 Mil - $500 Mil
Transmission Line - Multiple |  |  | Age/Condition - Replace SCADA/RTU |  |  |  | Over $500 Mil
Transmission Line - Switch |  |  | Age/Condition - Replace Steel Poles |  |  |  | Multiple Options [See Notes]
Transmission Line - Underground |  |  | Age/Condition - Replace Switches, Age/Condition - Replace Transformers |  |  |  | NA
Transmission Line - Pole/Tower |  |  | Age/Condition - Replace Underground System
Transmission Line - Conductor |  |  | Age/Condition - Replace Wood Poles
Transmission Line - Other Equipment |  |  | Age/Condition - Switch Replacement - Steel
Transmission Line - Right of Way |  |  | Age/Condition - Switch Replacement - Wood
Multiple Options [See Notes] |  |  | Age/Condition - Targeted Relay Replacement
Age/Condition - Wood Pole Reframe
Animal Abatement
Automation
Bus Upgrade
Compliance - Remove Idle Facilities
Construct Roads/Gates/Culverts
Emergency Response - Fire Related
Emergency Response - Storm Related
Environmental
Facility Relocation
Fire Protection
Generation Interconnection
GO95 Mitigation - Steel
Install SCADA/RTU
Line Reconductoring
Line Termination
Load Interconnection
Modular Protection and Automation Control
NERC CIP Compliance
NERC Compliance - GO 95
New Substation
New T-Line
Priority 1 Steel Structure Replacement
Priority 1 Wood Structure Replacement
Protection NERC Compliance
Relay Upgrades
Replace Breakers
Replace Other Substation Equipment
Replace Transformer
Safety - Line Right of Way Access
SCADA Emergency Replacement
SCADA Switch Installation
Security Upgrades
Seismic Upgrade - Replace Conductor
Special Protection Scheme
Substation Capacity
Substation Reliability
System Design Upgrade
System Operations
Targeted Line Reliability
T-Line Capacity
T-Line Emergency
T-Line Reliability
Tools, Transformer Addition/Replacement
Underground Emergency
Voltage Conversion
Voltage Support