## Cluster 5
2012-07-04 | Cluster 5
2012-09-03 | Milestone |  | GIDAP Tariff Effective Date | Cluster 5 Decision (GIDAP) | Phase I Study | Affidavits |  | Phase I Study Report issued, Customer comment option on Study Report | Phase I Study Results Meeting | Phase I Results Meeting Follow Up Comments to Study Report | Appendix B Submittal & Selection of Options A & B |  | Post Initial Financial Security | Phase II Study | Phase II Study Report issued, Customer comment option on Study Report | Phase II Study Results Meeting | Phase II Results Meeting Follow Up Comments to Study Report | Affidavits |  | Allocations and Reassessment | Allocation Results | Tender Draft GIA | GIA Negotiation | GIA Execution | Post 2nd Financial Security | Post 3rd Financial Security
2012-11-22 | Dates | Start | 2012-07-25 | 2012-07-25 | 2012-07-15 |  |  | 2013-01-31 | [5 empty] | 2013-05-01 | 2013-11-22 |  |  |  |  | 2014-01-05 | 2014-03-14
2012-11-23 |  | End |  | 2012-08-06 | 2013-01-31 | 2012-12-21 | 2013-01-20 | 2013-02-14 | 2013-03-02 | 2013-03-06 | 2013-03-15 |  | 2013-05-01 | 2013-11-22 | 2013-12-10 | 2013-12-22 | 2013-12-26 | 2013-12-20 | 2014-01-20 | 2014-06-30 | 2014-03-21 | 2013-12-22 | 2014-03-22 |  | 2014-05-21 | On or before the start of construction
| Milestone Timeframe |  | July 24: FERC issued order accepting GIDAP Tariff July 25: Effective date of GIDAP Tariff |  | 200 Calendar Days to complete |  |  |  | Within 30 Calendar Days of Issuing Phase I Study Report |  |  |  |  | 205 Calendar Days |  | Within 30 Calendar Days of Issuing Phase II Study Report | [5 empty] | Within 30 Calendar Days after Issuing Final Phase II Study Report | Within 120 Calendar Days after Issuing Final Phase II Study Report
2012-12-25 | Tariff Reference (Section No.) |  |  | FERC filing Transmittal Letter | 6.6 |  |  | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 |  | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.5 | 8.7 | 8.7 | 8.9.2 |  | 8.9 thru 8.9.2 | 8.9.8 (and 8.9.4 thru 8.9.6) | 13.1 | 13.1 | 13.2, 13.3 | 11.3.1 thru 11.3.1.7 | 11.3.2 thru 11.3.2.4
2014-01-01
2013-01-01 | Customer Actions |  |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions
2013-01-21 | Customer Response Timeframe |  |  | Within 10 Calendar Days from Issuance of FERC Approved Order |  |  | Within 30 Calendar Days of Receipt of Affidavits | Within 10 Business Days of Receipt, 3 Business Days Before Phase I Report Meeting |  | Within 3 Business Days after Phase I Report Meeting | Within 10 Business Days after Phase I Results Meeting |  | Within 90 Calendar Days After Final Phase I Study Report |  | Within 10 Business Days of Receipt, 3 Business Days Before Phase II Report Meeting |  | Within 3 Business Days after Phase II Report Meeting |  | Within 30 Calendar Days of Receipt of Affidavits |  | Within 7 Calendar Days of receipt of Notification of Allocation | Within 30 Calendar Days after Receipt of Draft GIA |  |  | 180 Calendar Days after Issuance of Final Phase II Study report | Before Start of Construction
2013-09-02 | Customer Actions |  |  | Provides decision to ISO by 8/6/2012 to Withdraw or Continue (see Section 3.5.1.1 (b) of Tariff, Tariff begins on page 122) (all IR data needs to be valid at this time) |  | Pre-C5 customers Affidavit Form Posted | Pre-C5 customers return completed Affidavits | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Report Meeting | Option to provide further comments on Phase I Study Report | Customer resubmits Appendix B reflecting any allowed modifications to project | Customer selects Option A or B in Appendix B | Post Initial Financial Security |  | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Results Meeting | Option to provide further comments on Phase II Study Report | Receive Affidavit form from ISO | Return Completed Affidavits to ISO |  | Inform ISO of decision based on allocation information received | Provides comments to Draft GIA | Enter GIA negotiations with ISO +PTO |  | Post 2nd Financial Security | Post 3rd Financial Security
| Customer Resources |  | http://elibrary.ferc.gov/idmws/common/OpenNat.asp?fileID=13033536 | http://www.caiso.com/Documents/May252012GIDAPAmendmentER12-1855pdf.pdf |  | <FUTURE: link to Affidavits Process> |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  |  | <FUTURE: link to Appendix B form> | <FUTURE: link to Posting Financial Security> |  |  |  |  | <FUTURE: link to Affidavits Process >
| ISO Actions |  |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions
2013-11-28 | ISO Actions |  |  |  |  | Sends Out Affidavits |  | Issues Report to Customer via E-mail on or before 01/31/2013 | Send out Results Meeting minutes to attendees, including documentation of any action items | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B. If necessary, notifies Customer if modifications require a Material Modification Review |  | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date |  | Issues Report to Customer via E-mail | Send out Results Meeting minutes to attendees, including documentation of any action items | Review all comments and, if necessary, issue addendum or revised Study Report | Sends Out Affidavit forms to Customers | Begin Scoring Projects based on Affidavit Information |  | Provides Allocation Results | (ISO +PTO) Tender Draft GIA Appendices | ISO +PTO enter GIA negotiations with customer | ISO +PTO Provide Final Executed GIA | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date
2013-11-29 | ISO Response Timeframe |  |  | Cut off date for IR withdrawal is COB 8/3/2012 | Approximately 60 Calendar Days After Window Closes |  |  |  | Within 10 Business Days | Within 15 Business Days after results Meeting | Timely manner |  |  |  |  | Within 10 Business Days | Within 15 Business Days after results Meeting |  |  |  | Timely Manner | Within 30 Calendar Days after Issuing Final Phase II Study Report | Within 120 Calendar Days after Issuing Final Phase II Study Report | Within 15 Business Days after completion of negotiation
2013-12-25
2014-01-01
2014-01-20
Formulas:
Cluster 5 Decision (GIDAP) = [GIDAP Tariff Effective Date]
Phase I Study = [Phase I Study, row above]+200
Phase II Study = [Phase II Study, row above]+205
Phase II Study Results Meeting = [Phase II Study]+30
Allocation Results = [Allocation Results, row above]+7

## Cluster 6
2012-07-04 | Cluster 6
2012-09-03 | Milestone |  | IR Open Window Announcement | IR Submittal & Validation |  |  | Issue Study Agreement | Scoping Meeting | Scoping Meeting Minutes |  | Engagement Agreements | Phase I Study | Affidavits |  | Phase I Study Report issued, Customer comment option on Study Report | Phase I Study Results Meeting | Phase I Results Meeting Follow Up Comments to Study Report | Appendix B Submittal & Selection of Options A & B |  | Post Initial Financial Security | Phase II Study | Phase II Study Report issued, Customer comment option on Study Report | Phase II Study Results Meeting | Phase II Results Meeting Follow Up Comments to Study Report | Affidavits |  | Allocations | Allocation Results | Draft GIA | GIA Negotiation | GIA Execution | Post 2nd Financial Security | Post 3rd Financial Security
2014-01-01 | Dates | Start | 2013-03-01 | 2013-04-01 | [7 empty] | 2013-07-01 |  |  | 2013-12-18 | [5 empty] | 2014-05-01 | 2014-11-22 |  |  |  |  | 2015-01-05 | 2015-03-14
2012-11-22 |  | End |  | 2013-04-30 |  | 2013-05-28 | 2013-05-30 | 2013-06-29 | 2013-07-03 |  | 2013-07-29 | 2013-12-18 | 2013-12-20 | 2014-01-20 | 2014-01-03 | 2014-01-17 | 2014-01-23 | 2014-02-03 |  | 2014-03-18 | 2014-11-22 | 2014-12-05 | 2015-01-16 | 2015-01-21 | 2014-12-21 | 2015-01-20 | 2015-06-30 | 2015-03-21 | 2015-01-04 | 2015-04-04 |  | 2015-05-21 | On or before the start of construction
2012-11-23 | Milestone Timeframe |  |  | 30 Calendar Days |  |  | Within 30 Calendar Days After Window Closes | Within 60 Calendar Days After Window Closes |  |  |  | 170 Calendar Days to Complete |  |  |  | Within 30 Calendar Days of Issuing Phase I Study Report |  |  |  |  | 205 Calendar Days |  | Within 30 Calendar Days of Issuing Phase II Study Report | [5 empty] | Within 30 Calendar Days after Issuing Final Phase II Study Report | Within 120 Calendar Days after Issuing Final Phase II Study Report
2013-09-02 | Tariff Reference (Section No.) |  |  | 3.3.1, 3.5.2.1, 3.5.2.2 |  |  | 6.1.1 | 6.1.2 | [6 empty] | 6.7 | 6.7 | 6.7 | 6.7.2.2, 7.1, 7.2 |  | 7.3, 10.1, 10.2, 11.1 thru 11.2.7 | 8.5 | 8.5 | 8.7 | 8.7 | 8.9.2 |  | 8.9 thru 8.9.2 | 8.9.8 (and 8.9.4 thru 8.9.8) | 13.1 | 13.1 | 13.2, 13.3 | 11.3.1 thru 11.3.1.7 | 11.3.2 thru 11.3.2.4
| Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  |  |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions |  | Customer Actions
| Customer Response Timeframe |  |  |  | Within 10 Business Days of Notification | Within 20 Business Days after Window Closes |  |  | Within 3 Business Days after Scoping Meeting |  | Within 30 Calendar Days of Scoping Meeting |  |  | Within 30 Calendar Days of Receipt of Affidavits | Within 10 Business Days of Receipt, 3 Business Days Before Phase I Report Meeting |  | Within 3 Business Days after Phase I Report Meeting | Within 10 Business Days after Phase I Report Meeting |  | Within 90 Calendar Days After Final Phase I Study Report |  | Within 10 Business Days of Receipt, 3 Business Days Before Phase II Report Meeting |  | Within 3 Business Days after Phase II Report Meeting |  | Within 30 Calendar Days of Receipt of Affidavits |  | Within 7 Calendar Days of receipt of Notification of Allocation | Within 30 Calendar Days after Receipt of Draft GIA |  |  | 180 Calendar Days after Issuance of Final Phase II Study report | Before Start of Construction
2013-11-28 | Customer Actions |  |  | Submit: 1) IR 2) Funds 3) Evidence of Site Control Information | *(If Applicable)* Submit Additional Information | *(If Applicable)* Cure Period: Submit Additional Information |  | Attends Scoping Meeting | Specify designation of POI for the Phase I Study |  | Execute and Deliver GISPA to ISO |  | Pre-C6 customers receive Affidavits | Pre-C6 customers return completed Affidavits | Receive Phase I Study Report and Provide Comments in writing to ISO | Attend Phase I Report Meeting | Option to provide initial or further comments on Phase II Study Report | Customer resubmits Appendix B reflecting any allowed modifications to project | Customer selects Option A or B in Appendix B | Post Initial Financial Security |  | Receive Phase II Study Report and Provide Comments in writing to ISO | Attend Phase II Report Meeting | Option to provide initial or further comments on Phase II Study Report | Receive Affidavit form from ISO | Return Completed Affidavits to ISO |  | Inform ISO of decision based on allocation information received | Provides comments to Draft GIA | Enter GIA negotiations with ISO +PTO |  | Post 2nd Financial Security | Post 3rd Financial Security
2013-11-29 | Customer Resources |  | <FUTURE: link to how to become a subscriber> | <FUTURE: link to IR Form> |  |  | <link to GISPA form?> | <FUTURE: link to Scoping Meeting Checklist/What to expect?> | <FUTURE: link to how to designate POI> |  | <FUTURE: link to Withdrawal Process> |  | <FUTURE: link to Affidavits Process> |  | <FUTURE: link to "How to issue comments"?> <link to Options A & B> |  |  |  | <FUTURE: link to Appendix B form> | <FUTURE: link to Posting Financial Security> |  |  |  |  | <FUTURE: link to Affidavits Process > |  | <FUTURE: link to Tariff Section 8.9.2>
2013-12-25
| ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  |  |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions |  | ISO Actions
2014-01-01 | ISO Actions |  | Sends Out Notifications to Subscribers | Notifies Customer if IR is Complete or Deficient | (If Applicable) Notifies if additional Information is Complete or Deficient | (If Applicable) Notifies if IR is Complete or Deficient or Application is Not Valid | (Pending Validity of IR) Issues Pro-Forma Generator Interconnection Study Process Agreement (GISPA) | Contact Customer to set up agreeable date/time for Scoping Meeting | Sends Out Meeting Minutes to Attendees to verify accuracy and receive for Comments | Sends out Final Meeting Minutes | Provide (PTO+ISO) Signed GISPA |  | Sends Out Affidavits |  | Issues Report to Customer via E-mail | Send out Results Meeting minutes to attendees, including documentation of any action items | Review all comments and, if necessary, issue addendum or revised Study Report | Validates Appendix B. If necessary, notifies Customer if modifications require a Material Modification Review |  | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date |  | Issues Report to Customer via E-mail | Send out Results Meeting minutes to attendees, including documentation of any action items | Review all comments and, if necessary, issue addendum or revised Study Report | Sends Out Affidavit forms to Customers | Begin Scoring Projects based on Affidavit Information |  | Provides Allocation Results | (ISO +PTO) Tender Draft GIA Appendices | ISO +PTO enter GIA negotiations with customer | ISO +PTO Provide Final Executed GIA | ISO coordinates with PTO to determine whether each project Posted by each project's Posting due date
2014-01-20 | ISO Response Timeframe |  |  | Within 10 Business Days of Receipt | Within 5 Business Days of Receipt | Within 5 Business Days of Receipt | Within 30 Calendar Days After Window Closes | Within 5 Business Days After Receipt of Valid IR | Within 5 Business Days of Meeting | Within 3 Business Days After Comments | Within 10 Business Days of POI Designation | Approximately 60 Calendar Days After Window Closes |  |  |  | Within 10 Business Days | Within 15 Business Days after results Meeting | Timely manner |  |  |  |  | Within 10 Business Days | Within 15 Business Days after results Meeting |  |  |  | Timely Manner | Within 30 Calendar Days after Issuing Final Phase II Study Report | Within 120 Calendar Days after Issuing Final Phase II Study Report | Within 15 Business Days after completion of negotiation
Formulas:
Issue Study Agreement = [IR Submittal & Validation]+30
Scoping Meeting = [IR Submittal & Validation]+60
Scoping Meeting Minutes = WORKDAY([Scoping Meeting],3,A1:A16)
Engagement Agreements = [Scoping Meeting]+30
Phase I Study = [Phase I Study, row above]+170
Post Initial Financial Security = [Phase I Study]+90
Phase II Study = [Phase II Study, row above]+205
Allocation Results = [Allocation Results, row above]+7