## Response 3
Date SDG&E Informed | Date Safety Issue Occurred | Conductor Voltage | VM Intiative | Description of Safety Issue
2022-07-15 | 2022-07-15 | Secondary | Tree Trimming | A two-man tree crew was trimming a vine in contact with three phase open-wire secondaries. The crew decided to use a pole saw head attached to fiberglass extension poles and trim the vine from the ground. The trimmer (Foreperson) would generally pull the vine down below the lines before cutting it. The trimmer raised the pole saw above the lines and lost control of the tool. The metal head of the pole saw contacted two secondary conductors simultaneously, causing a dead short and opening a fuse on the transformer. This resulted in a crew-caused secondary outage and loss of power to two homes. The utility customer was called, and power was restored with no injuries, fire, or other property damage.
2022-10-19 | 2022-10-19 | Secondary | Tree Trimming | A tree crew was pruning bamboo away from the facilities. As the crew was pruning they accidentally cut the service line which pulled down the weather guard. No injuries were involved and Trouble (Service Dispatch) was immediately notified out to repair the line.

## Response 4
Provide your workplan that describes where and when you will perform system hardening on distribution circuits in 2023. For projects that you expect to partially complete in 2023 (i.e., projects that started before 2023 and are expected to continue in 2023, or projects that are expected to be completed after 2023), please include the project and report the work what you forecast will actually be performed in calendar year 2023.
a) Order number | b) Program | c) Circuit ID number | d) Circuit-segment name or ID number (if the project affects more than one circuit-segment, please identify each one) | e) Relevant wildfire risk score(s) from the wildfire risk model that you are using to estimate distribution risk in your 2023-2025 WMP filing | f) The expected or actual start date of the project (construction start) | g) The expected completion date of the project | h) Length (in circuit miles) of covered conductor to be installed in 2023 | i) Length (in circuit miles) of underground conductor to be installed in 2023 | j) Length (in circuit miles) of overhead conductor to be permanently removed in 2023 and replaced by underground conductor (note that this may differ slightly from the previous item due to differing overhead and underground routes) | k) Length (in circuit miles) of overhead conductor to be permanently removed in 2023 and not replaced with covered conductor or undergrounded) | l) Length (in circuit miles) of any bare-wire overhead system hardening project to be installed in 2023 (if this is greater than zero, please describe the type of system hardening project) | m) Length (in circuit miles) of any other type of system hardening project to be installed in 2023 (if this is greater than zero, please describe the type of system hardening project).
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 230 | Z7218373-Z613000 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.04 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 1235 | Z7218373-Z613000 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.04 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 231 | Z219800-Z219813 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 3.52 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 500 | Z312787-P819071 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 0.03 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 928 | Z171694-Z137563 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 0.27 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 1101 | Z312804-Z312788 | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 2.87 | N/A
2012-00019-ZZ | Transmission Hardening - Distribution Underbuild | 991 |  | Bare OH hardening not currently modeled in WiNGS. | 2022-08-15 | 2023-03-22 | N/A | N/A | N/A | N/A | 2.55 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 231 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 3.22 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 522 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.62 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | 523 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.55 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | FB1 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.27 | N/A
2014-00051-ZZ | Transmission Hardening - Distribution Underbuild | FB2 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-26 | 2023-11-16 | N/A | N/A | N/A | N/A | 0.05 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 500 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 0.03 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 928 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 0.27 | N/A
2020-0286 | Transmission Hardening - Distribution Underbuild | 1101 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-04-03 | 2023-06-19 | N/A | N/A | N/A | N/A | 2.87 | N/A
2021-0388 | Transmission Hardening - Distribution Underbuild | 928 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-09-12 | 2023-11-29 | N/A | N/A | N/A | N/A | 1.3 | N/A
ESH C0073 A SUG | Strategic Underground | 73 | 73-643R, CB 73 | 0.00212616984353637,4.19E-06 | 2023-08-10 | 2023-09-05 |  | 1.84
ESH C0073 C SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2023-12-15 | 2024-01-17 |  | 1.98
ESH C0220 B SUG | Strategic Underground | 220 | 220-288R, 220-294R | 0.000130176258989742, 0.000543919859362151 | 2023-09-11 | 2023-10-20 |  | 3.84
ESH C0221 A SUG | Strategic Underground | 221 | 221-1235F |  | 2023-01-01 | 2023-03-31 |  | 0.94
ESH C0221 B SUG | Strategic Underground | 221 |  |  | 2023-09-11 | 2023-12-05 |  | 6.2
ESH C0221 C SUG | Strategic Underground | 221 |  |  | 2023-08-02 | 2023-10-11 |  | 8.52
ESH C0221 D SUG | Strategic Underground | 221 |  |  | 2023-06-28 | 2023-07-12 |  | 0.24
ESH C0221 DUG 3 SUG | Strategic Underground | 221 | 221-1230F, 222-1364R | 0.000115188843084162, 0.00441813230690826 | 2023-04-04 | 2023-06-20 |  | 6.08
ESH C0222 A SUG | Strategic Underground | 222 | 222-1364R, CB 222 | 0.00441813230690826, 0.0000127588759093363 | 2023-07-31 | 2023-08-04 |  | 0.1
ESH C0222 BB SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2023-12-12 | 2023-12-20 |  | 1.31
ESH C0222 C SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2023-10-09 | 2023-11-17 |  | 2.95
ESH C0222 DD SUG | Strategic Underground | 222 | 222-2013R | 0.0014386 | 2023-08-08 | 2023-09-26 |  | 2.76
ESH C0222 E SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2023-10-02 | 2023-11-07 |  | 3.38
ESH C0222 EE SUG | Strategic Underground | 222 | 222-2013R | 0.0014386 | 2023-07-27 | 2023-09-07 |  | 3.58
ESH C0222 FF SUG | Strategic Underground | 222 | 222-2013R | 0.0014386 | 2023-10-24 | 2023-12-20 |  | 4.01
ESH C0222 H SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2023-12-22 | 2024-01-29 |  | 2.49
ESH C0222 I SUG | Strategic Underground | 222 | 222-1503, 222-1523R | 0.0000614847068957712, 0.00128929523130269 | 2023-09-28 | 2023-10-18 |  | 1.21
ESH C0222 J SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2023-10-02 | 2023-10-20 |  | 1.5
ESH C0222 L SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2023-09-29 | 2023-10-19 |  | 1.26
ESH C0222 N SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2023-08-11 | 2023-08-29 |  | 1.19
ESH C0222 X SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2023-09-01 | 2023-10-18 |  | 3.06
ESH C0358 DUG 2 SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2023-04-20 | 2023-06-01 |  | 2.31
ESH C0445 A SUG | Strategic Underground | 445 | 445-19R, 445-39R | 0.000319236243341737, 0.000320573042022656 | 2023-12-05 | 2024-01-08 |  | 1.35
ESH C0445 B SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2023-08-08 | 2023-09-22 |  | 3.28
ESH C0445 C SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2023-07-25 | 2023-08-23 |  | 2.14
ESH C0445 F SUG | Strategic Underground | 445 | 445-39R | 0.00032057 | 2023-10-23 | 2023-12-19 |  | 3.35
ESH C0445 O SUG | Strategic Underground | 445 | 445-24R, 445-39R, 445-897R | 0.00119535926658874, 0.000320573042022656, 0.00011623549872629 | 2023-12-22 | 2024-01-11 |  | 1.09
ESH C0972 DUG C SUG | Strategic Underground | 972 | 972-8 | 0.00039365 | 2023-04-10 | 2023-05-09 |  | 6.75
ESH C0972 DUG D SUG | Strategic Underground | 972 | 972-8 | 0.00039365 | 2023-08-14 | 2023-08-18 |  | 0.47
ESH C0972 DUG E SUG | Strategic Underground | 972 | 972-8, CB RA2 | 0.000393646469631985,2.34E-05 | 2023-04-24 | 2023-11-22 |  | 1.29
ESH C1458 1B SUG | Strategic Underground | 1458 | 1458-454F | 2.1265e-06 | 2023-05-15 | 2023-05-26 |  | 0.53
ESH COK1 A SUG | Strategic Underground | OK1 | CB OK1 | 0.00023691 | 2023-05-12 | 2023-09-05 |  | 8.36
ESH COK1 B SUG | Strategic Underground | OK1 | CB OK1 | 0.00023691 | 2023-06-21 | 2023-09-14 |  | 5.95
ESH CSL1 B SUG | Strategic Underground | SL1 | CB SL1 | 0.00010054 | 2023-09-07 | 2023-11-15 |  | 7.45
ESH CSL1 C SUG | Strategic Underground | SL1 | CB SL1 | 0.00010054 | 2023-10-10 | 2024-01-05 |  | 5.74
ESH C0073 A SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2023-09-19 | 2023-10-17 |  |  | 1.5465
ESH C0073 A SUG | Strategic Underground | 73 | CB 73 | 4.1907e-06 | 2023-09-19 | 2023-10-17 |  |  | 0.12851
ESH C0445 C SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2023-09-08 | 2023-10-05 |  |  | 1.9241
ESH C0222 X SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2023-11-02 | 2023-12-01 |  |  | 1.2454
ESH C0222 X SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2023-11-02 | 2023-12-01 |  |  | 0.12134
ESH C0445 B SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2023-10-09 | 2023-11-03 |  |  | 1.9169
ESH C0222 N SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2023-10-19 | 2023-11-15 |  |  | 1.0637
0157-Z-CC | Covered Conductor | 157 | 157-273R | 0.00054913 | 2023-02-02 | 2023-03-17 | 1.75
0157-A-CC-2023 | Covered Conductor | 157 | 157-81R | 0.0023888 | 2022-07-29 | 2023-04-05 | 2.83
0157-A2-CC | Covered Conductor | 157 | 157-81R | 0.0023888 | 2023-04-17 | 2023-07-15 | 0.39
0212-N-CC | Covered Conductor | 212 | 212-1177R | 0.00035267 | 2022-11-08 | 2023-04-28 | 4.47
442I CC | Covered Conductor | 442 | 442-728R | 7.4688e-05 | 2023-04-05 | 2023-05-16 | 0.38
0176-K-CC | Covered Conductor | 176 | 176-1834R, 176-194R | 0.0001175 | 2023-01-24 | 2023-04-23 | 2.7767
0445-I-CC | Covered Conductor | 445 | 445-1325F | 0.00068627 | 2022-12-16 | 2023-04-18 | 1.48
0445-A-CC | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-07-24 | 2023-10-21 | 1.69
0445-B-CC-ESH | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-08-15 | 2023-11-12 | 1.69
0445-C-CC | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-09-22 | 2023-12-20 | 0.39
0445-D-CC | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-07-31 | 2023-10-28 | 0.95
0445-E-CC | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-08-25 | 2023-11-22 | 0.45
0445-F-CC | Covered Conductor | 445 | 445-19R | 0.00031924 | 2023-09-22 | 2023-12-20 | 0.78
0445-L3-CC | Covered Conductor | 445 | 445-39R | 0.00032057 | 2023-07-03 | 2023-09-30 | 0.21
0445-G-CC | Covered Conductor | 445 | 445-39R, 445-894R | 0.000320573042022656,0.000293596746833 | 2023-09-29 | 2023-12-27 | 1.0251
0445-H-CC-ESH | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-10-02 | 2023-12-30 | 0.73
0445-J-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-08-26 | 2023-11-23 | 0.6
0445-K-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-09-15 | 2023-12-13 | 1.36
0445-L-CC-ESH | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-09-29 | 2023-12-27 | 2.35
0445-M-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-10-02 | 2023-12-30 | 0.82
0445-N-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-10-03 | 2023-12-31 | 1.33
0445-P-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-07-19 | 2023-10-16 | 2.35
0445-P-CC-FT-04 | Covered Conductor | 445 | 445-894R | 0.0002936 | 2021-12-21 | 2023-07-31 | 0.02
0445-I-CC-ESH | Covered Conductor | 445 | 445-1311R, 445-894R | 0.00150108329777934,0.000293596746833 | 2023-10-03 | 2023-12-31 | 1.5533
0448-D2-CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2023-07-13 | 2023-10-10 | 1.94
0448-E-CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2023-02-20 | 2023-05-20 | 2.89
0448-F-CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2023-05-18 | 2023-08-15 | 2.43
0448-F3-CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2023-04-17 | 2023-07-15 | 1.17
0448-D-CC | Covered Conductor | 448 | 448-11R, 448-9R | 0.00297805236951903,0.000853307565534908 | 2023-04-20 | 2023-07-18 | 2.1326
0448-G2-CC | Covered Conductor | 448 | 448-33R | 0.00027698 | 2022-12-20 | 2023-03-22 | 2.1
0448-H-CC | Covered Conductor | 448 | 448-33R | 0.00027698 | 2023-07-01 | 2023-09-28 | 1.48
0448-N2-CC | Covered Conductor | 448 | 448-47R | 0.0017472 | 2023-02-02 | 2023-05-02 | 2.24
0448-O-CC | Covered Conductor | 448 | 448-47R | 0.0017472 | 2023-03-27 | 2023-06-24 | 2.59
0448-O2-CC-2023 | Covered Conductor | 448 | 448-47R | 0.0017472 | 2022-09-10 | 2023-01-28 | 0.65
0448-P-CC | Covered Conductor | 448 | 448-47R | 0.0017472 | 2023-03-27 | 2023-06-24 | 2.85
0448-K-CC | Covered Conductor | 448 | 448-724R | 0.00014734 | 2023-09-07 | 2023-12-05 | 2.41
0448-K2-CC-2023 | Covered Conductor | 448 | 448-724R | 0.00014734 | 2022-09-14 | 2023-03-17 | 1.39
0448-A2-CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2023-03-27 | 2023-06-24 | 2.04
0448-A3-CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2023-04-24 | 2023-07-22 | 1.85
0448-B-CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2022-12-01 | 2023-03-29 | 2.38
0448-B2-CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2023-01-28 | 2023-04-28 | 1.91
0448-G-CC | Covered Conductor | 448 | 448-33R, 448-9R | 0.000276984102073685,0.000853307565534908 | 2023-03-22 | 2023-06-19 | 1.9813
0448-I-CC | Covered Conductor | 448 | 448-11R, 448-33R | 0.00297805236951903,0.000276984102073685 | 2022-10-08 | 2023-02-06 | 2.1782
0073-AA-CC | Covered Conductor | 73 | 73-23R | 0.00041443 | 2023-09-30 | 2023-12-28 | 1.08
0073-BB-CC | Covered Conductor | 73 | 73-23R | 0.00041443 | 2023-09-22 | 2023-12-20 | 0.22
0073-N-CC | Covered Conductor | 73 | 73-23R | 0.00041443 | 2023-10-02 | 2023-12-30 | 0.75
0073-O-CC | Covered Conductor | 73 | 73-23R | 0.00041443 | 2023-10-02 | 2023-12-30 | 1.45
0073-P-CC | Covered Conductor | 73 | 73-23R | 0.00041443 | 2023-10-02 | 2023-12-30 | 1.53
0079-Q-CC | Covered Conductor | 79 | 79-785 | 0.00052918 | 2023-07-12 | 2023-10-09 | 2.66
0972-P-CC | Covered Conductor | 972 | 972-1582R | 9.6996e-05 | 2023-09-22 | 2023-12-20 | 1.11
0972-Q-CC | Covered Conductor | 972 | 972-1582R | 9.6996e-05 | 2023-08-18 | 2023-11-15 | 1.93
0972-R-CC | Covered Conductor | 972 | 972-1582R | 9.6996e-05 | 2023-07-25 | 2023-10-22 | 0.86

## Response 5
Provide your workplan that describes where and when you will perform system hardening on distribution circuits in 2024. For projects that you expect to partially complete in 2024 (i.e., projects that are expected to start before 2024 and are expected to continue in 2024, or projects that are expected to be completed after 2024), please include the project and report the work that you forecast will actually be performed in calendar year 2024.
a) Order number | b) Program | c) Circuit ID number | d) Circuit-segment name or ID number (if the project affects more than one circuit-segment, please identify each one) | e) Relevant wildfire risk score(s) from the wildfire risk model that you are using to estimate distribution risk in your 2023-2025 WMP filing | f) The expected or actual start date of the project (construction start) | g) The expected completion date of the project. | h) Length (in circuit miles) of covered conductor to be installed in 2024 | i) Length (in circuit miles) of underground conductor to be installed in 2024 | j) Length (in circuit miles) of overhead conductor to be permanently removed in 2024 and replaced by underground conductor (note that this may differ slightly from the previous item due to differing overhead and underground routes) | k) Length (in circuit miles) of overhead conductor to be permanently removed in 2024 and not replaced with covered conductor or undergrounded) | l) Length (in circuit miles) of any bare-wire overhead system hardening project to be installed in 2024 (if this is greater than zero, please describe the type of system hardening project) | m) Length (in circuit miles) of any other type of system hardening project to be installed in 2024 (if this is greater than zero, please describe the type of system hardening project).
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 230 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 0.04 | N/A
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 231 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 0.3 | N/A
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 232 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 0.26 | N/A
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 234 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 2.11 | N/A
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 522 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 1.12 | N/A
2014-00009-ZZ | Transmission Hardening - Distribution Underbuild | 1235 |  | Bare OH hardening not currently modeled in WiNGS. | 2023-07-11 | 2024-04-18 | N/A | N/A | N/A | N/A | 0.04 | N/A
2019-0268 | Transmission Hardening - Distribution Underbuild | 1162 |  | Bare OH hardening not currently modeled in WiNGS. | 2024-05-10 | 2024-08-05 | N/A | N/A | N/A | N/A | 0.94 | N/A
2022-3032 | Transmission Hardening - Distribution Underbuild | 307 |  | Bare OH hardening not currently modeled in WiNGS. | 2024-05-30 | 2024-06-26 | N/A | N/A | N/A | N/A | 0.42 | N/A
ESH C0073 C SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2023-12-15 | 2024-01-17 |  | 1.98
ESH C0073 D SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2024-03-05 | 2024-03-29 |  | 1.79
ESH C0073 E SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2024-03-26 | 2024-04-24 |  | 1.92
ESH C0078 A SUG | Strategic Underground | 78 | 78-26R | 0.0002547 | 2024-08-09 | 2024-08-15 |  | 0.5
ESH C0078 B SUG | Strategic Underground | 78 | 78-26R | 0.0002547 | 2024-08-09 | 2024-08-15 |  | 0.4
ESH C0078 C SUG | Strategic Underground | 78 | 78-35R, 78-782R | 0.000193038228260689,8.51300626664095E-05 | 2024-08-09 | 2024-08-15 |  | 0.4
ESH C0210 B SUG | Strategic Underground | 210 | 210-172R | 0.00027354 | 2024-07-24 | 2024-08-16 |  | 1.6
ESH C0210 C SUG | Strategic Underground | 210 | 210-172R | 0.00027354 | 2024-06-19 | 2024-06-26 |  | 0.5
ESH C0210 E SUG | Strategic Underground | 210 | 210-9R | 6.2466e-05 | 2024-06-25 | 2024-07-17 |  | 3.2
ESH C0210 G SUG | Strategic Underground | 210 | 210-9R | 6.2466e-05 | 2024-08-20 | 2024-10-02 |  | 2.7
ESH C0211 B SUG | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-10-15 | 2024-12-18 |  | 4.4
ESH C0211 D SUG | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-10-01 | 2024-12-04 |  | 4.4
ESH C0211 G SUG | Strategic Underground | 211 | 211-279R | 0.0006846 | 2024-07-30 | 2024-09-04 |  | 2.1
ESH C0211 H SUG | Strategic Underground | 211 | 211-279R | 0.0006846 | 2024-07-17 | 2024-08-12 |  | 1.7
ESH C0211 I SUG | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-08-19 | 2024-09-30 |  | 2.8
ESH C0211 J SUG | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-08-05 | 2024-08-30 |  | 2.1
ESH C0212 A SUG | Strategic Underground | 212 | 212-638R | 3.3846e-05 | 2024-09-17 | 2024-09-23 |  | 0.27
ESH C0212 D SUG | Strategic Underground | 212 | 212-739R | 0.00029896 | 2024-09-24 | 2024-09-30 |  | 1.75
ESH C0212 F SUG | Strategic Underground | 212 | 212-739R | 0.00029896 | 2024-10-01 | 2024-10-07 |  | 0.4
ESH C0217 A SUG | Strategic Underground | 217 | 217-983R | 0.0028311 | 2024-09-13 | 2024-10-29 |  | 3.33
ESH C0217 B SUG | Strategic Underground | 217 | 217-983R | 0.0028311 | 2024-10-22 | 2024-12-24 |  | 3.7
ESH C0220 A SUG | Strategic Underground | 220 | 220-288R | 0.00013018 | 2024-04-08 | 2024-06-17 |  | 2.61
ESH C0220 D SUG | Strategic Underground | 220 | 220-288R, 220-294R | 0.000130176258989742,0.000543919859362151 | 2024-08-12 | 2024-09-30 |  | 3.38
ESH C0220 F SUG | Strategic Underground | 220 | 220-294R | 0.00054392 | 2024-09-18 | 2024-11-01 |  | 3.38
ESH C0220 G SUG | Strategic Underground | 220 | 220-294R | 0.00054392 | 2024-09-18 | 2024-11-01 |  | 3.38
ESH C0220 J SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-03-14 | 2024-04-03 |  | 2.92
ESH C0220 K SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-08-09 | 2024-08-22 |  | 0.87
ESH C0220 L SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-01-15 | 2024-02-07 |  | 1.6
ESH C0220 M SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-03-14 | 2024-04-10 |  | 2.16
ESH C0220 N SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-04-01 | 2024-05-10 |  | 2.65
ESH C0220 P SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-09-25 | 2024-10-16 |  | 1.33
ESH C0220 Q SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-04-29 | 2024-05-16 |  | 1.16
ESH C0220 S SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-06-24 | 2024-08-28 |  | 4.2
ESH C0220 T SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-10-03 | 2024-11-01 |  | 1.97
ESH C0220 U SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-04-25 | 2024-06-11 |  | 3.02
ESH C0220 V SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-09-26 | 2024-10-17 |  | 1.54
ESH C0222 AA SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-08-08 | 2024-09-23 |  | 3.35
ESH C0222 B SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-02-02 | 2024-03-21 |  | 3.43
ESH C0222 CC SUG | Strategic Underground | 222 | 222-1441R | 0.0011512 | 2024-02-05 | 2024-02-26 |  | 1.26
ESH C0222 D SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-06-10 | 2024-07-29 |  | 3.23
ESH C0222 F SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-07-05 | 2024-08-01 |  | 2.59
ESH C0222 G SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2024-03-29 | 2024-05-16 |  | 3.65
ESH C0222 GG SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-06-13 | 2024-06-27 |  | 0.02
ESH C0222 H SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2023-12-22 | 2024-01-29 |  | 2.49
ESH C0222 K SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2024-07-17 | 2024-08-13 |  | 2.94
ESH C0222 O SUG | Strategic Underground | 222 | 222-1433R | 0.0010778 | 2024-06-20 | 2024-07-25 |  | 2.03
ESH C0222 P SUG | Strategic Underground | 222 | 222-1433R | 0.0010778 | 2024-10-16 | 2024-11-14 |  | 1.61
ESH C0222 Q SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-09-05 | 2024-10-02 |  | 1.68
ESH C0222 R SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-01-12 | 2024-02-06 |  | 1.65
ESH C0222 S SUG | Strategic Underground | 222 | 222-1370R, 222-1401R | 0.00270885873660388,0.00647837280886684 | 2024-10-15 | 2024-11-13 |  | 2.25
ESH C0222 T SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-08-20 | 2024-09-13 |  | 1.73
ESH C0222 U SUG | Strategic Underground | 222 | 222-1401R, 222-1441R | 0.00647837280886684,0.00115120229483919 | 2024-04-01 | 2024-04-19 |  | 3.32
ESH C0222 V SUG | Strategic Underground | 222 | 222-1441R | 0.0011512 | 2024-01-02 | 2024-01-18 |  | 0.89
ESH C0222 W SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-01-25 | 2024-03-01 |  | 2.67
ESH C0222 Y SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-02-09 | 2024-03-11 |  | 3.45
ESH C0222 Z SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-02-07 | 2024-04-08 |  | 3.76
ESH C0358 A SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-10-01 | 2024-10-07 |  | 0.5
ESH C0358 B SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-10-15 | 2024-10-28 |  | 1
ESH C0358 C SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-11-05 | 2024-11-25 |  | 1.6
ESH C0358 D SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-11-12 | 2024-12-04 |  | 1.2
ESH C0441 B SUG | Strategic Underground | 441 | 441-30R | 0.00084586 | 2024-10-22 | 2024-10-28 |  | 0.5
ESH C0441 E SUG | Strategic Underground | 441 | 441-30R | 0.00084586 | 2024-11-12 | 2024-11-25 |  | 0.8
ESH C0445 A SUG | Strategic Underground | 445 | 445-19R, 445-39R | 0.000319236243341737,0.000320573042022656 | 2023-12-05 | 2024-01-08 |  | 1.35
ESH C0445 D SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2024-03-04 | 2024-05-09 |  | 4.33
ESH C0445 G SUG | Strategic Underground | 445 | 445-1311R | 0.0015011 | 2024-06-03 | 2024-08-02 |  | 4.33
ESH C0445 J SUG | Strategic Underground | 445 | 445-24R | 0.0011954 | 2024-11-20 | 2024-12-20 |  | 1.82
ESH C0445 N SUG | Strategic Underground | 445 | 445-24R | 0.0011954 | 2024-06-13 | 2024-07-03 |  | 1.26
ESH C0445 O SUG | Strategic Underground | 445 | 445-24R, 445-39R, 445-897R | 0.00119535926658874,0.000320573042022656,0.00011623549872629 | 2023-12-22 | 2024-01-11 |  | 1.09
ESH C0445 P SUG | Strategic Underground | 445 | 445-1311R | 0.0015011 | 2024-09-25 | 2024-10-16 |  | 1.48
ESH C075 A SUG | Strategic Underground | 75 | 75-996R | 3.7604e-05 | 2024-10-28 | 2024-11-08 |  | 0.2
ESH C0909 A SUG | Strategic Underground | 909 | 909-17R, 909-805R | 0.000102983773334738,0.00671426647920183 | 2024-05-07 | 2024-06-11 |  | 2.53
ESH C0909 B SUG | Strategic Underground | 909 | 909-805R | 0.0067143 | 2024-10-09 | 2024-10-29 |  | 0.55
ESH C1030 1B SUG | Strategic Underground | 1030 | 1030-18R | 0.00028884 | 2024-01-25 | 2024-03-18 |  | 3.47
ESH C1215 C SUG | Strategic Underground | 1215 | 1215-12R | 0.00085741 | 2024-05-22 | 2024-06-06 |  | 0.5
ESH C1215 D SUG | Strategic Underground | 1215 | 1215-12R | 0.00085741 | 2024-05-22 | 2024-06-06 |  | 1.4
ESH CSL1 C SUG | Strategic Underground | SL1 | CB SL1 | 0.00010054 | 2023-10-10 | 2024-01-05 |  | 5.74
ESH C0211 D SUG RFS | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-12-19 | 2025-01-17 |  |  | 3.074
ESH C0222 O SUG | Strategic Underground | 222 | 222-1433R | 0.0010778 | 2024-08-08 | 2024-09-06 |  |  | 2.0022
ESH C0358 A SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-10-22 | 2024-11-18 |  |  | 0.19335
ESH C0210 C SUG RFS | Strategic Underground | 210 | 210-172R | 0.00027354 | 2024-07-12 | 2024-08-08 |  |  | 0.29382
ESH C0445 N SUG | Strategic Underground | 445 | 445-24R | 0.0011954 | 2024-07-18 | 2024-08-15 |  |  | 1.3924
ESH C0445 F SUG | Strategic Underground | 445 | 445-39R | 0.00032057 | 2024-01-05 | 2024-02-01 |  |  | 0.33103
ESH C0909 B SUG | Strategic Underground | 909 | 909-805R | 0.0067143 | 2024-11-12 | 2024-12-12 |  |  | 1.6758
ESH C0909 A SUG | Strategic Underground | 909 | 909-805R | 0.0067143 | 2024-06-26 | 2024-07-24 |  |  | 0.23806
ESH C0222 AA SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-10-08 | 2024-11-04 |  |  | 2.9994
ESH C0220 M SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-04-25 | 2024-05-22 |  |  | 2.0891
ESH C0222 T SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-09-27 | 2024-10-25 |  |  | 0.13606
ESH C0211 G SUG RFS | Strategic Underground | 211 | 211-279R | 0.0006846 | 2024-09-18 | 2024-10-16 |  |  | 3.0433
ESH C0222 R SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-02-20 | 2024-03-19 |  |  | 1.0578
ESH C0222 U SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-05-06 | 2024-06-03 |  |  | 0.39558
ESH C0222 S SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-12-02 | 2024-12-30 |  |  | 1.4695
ESH C0222 BB SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-01-05 | 2024-02-02 |  |  | 0.46184
ESH C0212 A SUG | Strategic Underground | 212 | 212-638R | 3.3846e-05 | 2024-10-08 | 2024-11-04 |  |  | 0.22251
ESH C0445 A SUG | Strategic Underground | 445 | 445-39R | 0.00032057 | 2024-01-22 | 2024-02-19 |  |  | 0.42062
ESH C0222 I SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2024-01-10 | 2024-02-06 |  |  | 0.079181
ESH C0078 B SUG | Strategic Underground | 78 | 78-26R | 0.0002547 | 2024-08-30 | 2024-09-27 |  |  | 0.41731
ESH C1215 C SUG RFS | Strategic Underground | 1215 | 1215-12R | 0.00085741 | 2024-06-21 | 2024-07-19 |  |  | 0.88376
ESH C0358 D SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-12-19 | 2025-01-17 |  |  | 0.93115
ESH C0222 W SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-03-18 | 2024-04-12 |  |  | 2.5714
ESH C0078 C SUG | Strategic Underground | 78 | 78-782R | 8.513e-05 | 2024-08-30 | 2024-09-27 |  |  | 0.41875
ESH C0222 K SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2024-08-14 | 2024-09-11 |  |  | 1.8686
ESH C0222 G SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2024-06-03 | 2024-06-28 |  |  | 3.4033
ESH C0210 E SUG | Strategic Underground | 210 | 210-9R | 6.2466e-05 | 2024-07-31 | 2024-08-28 |  |  | 3.2461
ESH C0078 A SUG | Strategic Underground | 78 | 78-26R | 0.0002547 | 2024-08-30 | 2024-09-27 |  |  | 0.46417
ESH C0222 S SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-12-02 | 2024-12-30 |  |  | 0.76082
ESH C0222 Y SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-03-26 | 2024-04-22 |  |  | 3.0546
ESH C0222 T SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-09-27 | 2024-10-25 |  |  | 1.5941
ESH C0222 B SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-04-05 | 2024-05-02 |  |  | 2.9626
ESH C0073 E SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2024-05-08 | 2024-06-06 |  |  | 1.561
ESH C0211 J SUG RFS | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-09-17 | 2024-10-14 |  |  | 1.519
ESH C0909 A SUG | Strategic Underground | 909 | 909-17R | 0.00010298 | 2024-06-26 | 2024-07-24 |  |  | 0.024723
ESH C1215 D SUG RFS | Strategic Underground | 1215 | 1215-12R | 0.00085741 | 2024-06-21 | 2024-07-19 |  |  | 1.1172
ESH C0220 L SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-02-21 | 2024-03-20 |  |  | 0.22056
ESH C0445 A SUG | Strategic Underground | 445 | 445-19R | 0.00031924 | 2024-01-22 | 2024-02-19 |  |  | 0.52658
ESH C0222 J SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2024-01-12 | 2024-02-08 |  |  | 1.3127
ESH C0222 Q SUG | Strategic Underground | 222 | 222-1370R | 0.0027089 | 2024-10-16 | 2024-11-13 |  |  | 1.6617
ESH C0220 P SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-10-30 | 2024-11-27 |  |  | 1.5572
ESH C0445 O SUG | Strategic Underground | 445 | 445-897R | 0.00011624 | 2024-01-25 | 2024-02-22 |  |  | 0.47869
ESH C0222 D SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-08-13 | 2024-09-10 |  |  | 3.0365
ESH C0909 A SUG | Strategic Underground | 909 | 909-17R | 0.00010298 | 2024-06-26 | 2024-07-24 |  |  | 1.7605
ESH C0222 CC SUG | Strategic Underground | 222 | 222-1441R | 0.0011512 | 2024-03-11 | 2024-04-08 |  |  | 1.0827
ESH C0220 T SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-11-15 | 2024-12-17 |  |  | 1.7067
ESH C0210 G SUG RFS | Strategic Underground | 210 | 210-9R | 6.2466e-05 | 2024-10-16 | 2024-11-13 |  |  | 1.002
ESH C0445 O SUG | Strategic Underground | 445 | 445-24R | 0.0011954 | 2024-01-25 | 2024-02-22 |  |  | 0.20454
ESH C0220 L SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-02-21 | 2024-03-20 |  |  | 1.5467
ESH C0441 B SUG | Strategic Underground | 441 | 441-23R | 0.00070662 | 2024-11-12 | 2024-12-11 |  |  | 0.51478
ESH C0358 C SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-12-12 | 2025-01-10 |  |  | 1.4039
ESH C0222 Z SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-04-23 | 2024-05-20 |  |  | 3.6155
ESH C0222 F SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-08-16 | 2024-09-13 |  |  | 0.033886
ESH C0445 G SUG | Strategic Underground | 445 | 445-1311R | 0.0015011 | 2024-08-19 | 2024-09-16 |  |  | 3.1642
ESH C0212 D SUG | Strategic Underground | 212 | 212-739R | 0.00029896 | 2024-10-15 | 2024-11-11 |  |  | 0.7812
ESH C0222 U SUG | Strategic Underground | 222 | 222-1441R | 0.0011512 | 2024-05-06 | 2024-06-03 |  |  | 2.041
ESH C0445 P SUG | Strategic Underground | 445 | 445-1311R | 0.0015011 | 2024-10-30 | 2024-11-27 |  |  | 0.90898
ESH C0073 C SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2024-02-01 | 2024-02-28 |  |  | 2.012
ESH C0909 A SUG | Strategic Underground | 909 | 909-805R | 0.0067143 | 2024-06-26 | 2024-07-24 |  |  | 0.31738
ESH C0220 S SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-09-12 | 2024-10-10 |  |  | 3.7051
ESH C0220 J SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-04-18 | 2024-05-15 |  |  | 0.098506
ESH C0222 I SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2024-01-10 | 2024-02-06 |  |  | 1.27
ESH C0441 E SUG | Strategic Underground | 441 | 441-30R | 0.00084586 | 2024-12-12 | 2025-01-10 |  |  | 0.64958
ESH C0211 I SUG RFS | Strategic Underground | 211 | 211-280R | 0.00051805 | 2024-10-15 | 2024-11-11 |  |  | 2.3605
ESH C0445 F SUG | Strategic Underground | 445 | 445-39R | 0.00032057 | 2024-01-05 | 2024-02-01 |  |  | 3.5781
ESH C0222 C SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2023-12-19 | 2024-01-17 |  |  | 2.04
ESH C0211 J SUG RFS | Strategic Underground | 211 | 211-279R | 0.0006846 | 2024-09-17 | 2024-10-14 |  |  | 0.47903
ESH C0220 V SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-10-31 | 2024-12-02 |  |  | 1.4737
ESH C0211 H SUG RFS | Strategic Underground | 211 | 211-279R | 0.0006846 | 2024-08-26 | 2024-09-24 |  |  | 1.753
ESH C0212 F SUG | Strategic Underground | 212 | 212-739R | 0.00029896 | 2024-10-22 | 2024-11-18 |  |  | 0.30202
ESH C0222 F SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2024-08-16 | 2024-09-13 |  |  | 1.8204
ESH C0220 Q SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-05-31 | 2024-06-28 |  |  | 1.1393
ESH C0445 O SUG | Strategic Underground | 445 | 445-1311R | 0.0015011 | 2024-01-25 | 2024-02-22 |  |  | 0.14974
ESH C0210 B SUG RFS | Strategic Underground | 210 | 210-172R | 0.00027354 | 2024-08-30 | 2024-09-30 |  |  | 1.282
ESH C0222 U SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-05-06 | 2024-06-03 |  |  | 0.21378
ESH C1215 C SUG RFS | Strategic Underground | 1215 | 1215-28R | 0.00026664 | 2024-06-21 | 2024-07-19 |  |  | 0.035014
ESH C0220 N SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-05-24 | 2024-06-24 |  |  | 2.4901
ESH C0220 U SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-06-26 | 2024-07-24 |  |  | 3.1176
ESH C0909 B SUG | Strategic Underground | 909 | 909-805R | 0.0067143 | 2024-11-12 | 2024-12-12 |  |  | 0.34943
ESH C0220 K SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-09-09 | 2024-10-04 |  |  | 0.88963
ESH C0222 H SUG | Strategic Underground | 222 | 222-1523R | 0.0012893 | 2024-02-13 | 2024-03-11 |  |  | 2.44
ESH C0222 L SUG | Strategic Underground | 222 | 222-1503 | 6.1485e-05 | 2024-01-11 | 2024-02-07 |  |  | 1.3277
ESH C0217 A SUG RFS | Strategic Underground | 217 | 217-983R | 0.0028311 | 2024-11-13 | 2024-12-12 |  |  | 3.1645
ESH C0358 B SUG | Strategic Underground | 358 | 358-682F | 0.0026261 | 2024-11-12 | 2024-12-11 |  |  | 0.84173
ESH C0073 D SUG | Strategic Underground | 73 | 73-643R | 0.0021262 | 2024-04-12 | 2024-05-10 |  |  | 1.9257
ESH C0222 E SUG | Strategic Underground | 222 | 222-1364R | 0.0044181 | 2023-12-12 | 2024-01-10 |  |  | 2.1937
ESH C0445 D SUG | Strategic Underground | 445 | 445-17R | 0.00013592 | 2024-05-24 | 2024-06-21 |  |  | 3.5472
ESH C0222 V SUG | Strategic Underground | 222 | 222-1441R | 0.0011512 | 2024-02-02 | 2024-02-29 |  |  | 0.84963
ESH C0445 O SUG | Strategic Underground | 445 | 445-39R | 0.00032057 | 2024-01-25 | 2024-02-22 |  |  | 0.28454
ESH C0220 S SUG | Strategic Underground | 220 | 220-298R | 0.0018519 | 2024-09-12 | 2024-10-10 |  |  | 0.49854
ESH C0222 BB SUG | Strategic Underground | 222 | 222-1401R | 0.0064784 | 2024-01-05 | 2024-02-02 |  |  | 0.097455
0157-D-PH-02-CC | Covered Conductor | 157 | 157-204R | 0.00055395 | 2024-01-10 | 2024-04-08 | 1.13
0157-E-CC | Covered Conductor | 157 | 157-204R | 0.00055395 | 2024-01-10 | 2024-04-08 | 2.4
0157-F-CC | Covered Conductor | 157 | 157-204R | 0.00055395 | 2024-01-10 | 2024-04-08 | 2.15
0157-Y-CC | Covered Conductor | 157 | 157-204R | 0.00055395 | 2024-01-10 | 2024-04-08 | 1.72
0073-Q-CC | Covered Conductor | 73 | 73-1130, 73-23R | 0.000564608890536472,0.000414434157285546 | 2023-10-28 | 2024-01-25 | 0.39539
0445-T-CC | Covered Conductor | 445 | 445-1311R | 0.0015011 | 2024-01-10 | 2024-04-08 | 1.88
0445-I2-CC | Covered Conductor | 445 | 445-1325F | 0.00068627 | 2023-11-01 | 2024-01-29 | 2.12
0445-S-CC | Covered Conductor | 445 | 445-24R | 0.0011954 | 2024-01-10 | 2024-04-08 | 1.83
0445-O-CC | Covered Conductor | 445 | 445-894R | 0.0002936 | 2023-10-26 | 2024-01-23 | 1.13
448O CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2024-01-10 | 2024-03-10 | 0.74
448P CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2024-01-10 | 2024-03-09 | 0.81
448Q CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2024-01-10 | 2024-03-10 | 0.72
448TTT CC | Covered Conductor | 448 | 448-11R | 0.0029781 | 2024-01-10 | 2024-03-10 | 0.62
448M CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2024-01-10 | 2024-03-09 | 0.69
448N CC | Covered Conductor | 448 | 448-9R | 0.00085331 | 2024-01-10 | 2024-03-09 | 0.42
0073-R-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-11-03 | 2024-01-31 | 1.75
0073-S-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-11-18 | 2024-02-15 | 1.87
0073-T-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-20 | 2024-03-18 | 0.89
0073-U-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-11-10 | 2024-02-07 | 1.09
0073-V-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-05 | 2024-03-03 | 0.73
0073-W-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-09 | 2024-03-07 | 0.41
0073-X-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-15 | 2024-03-13 | 1.43
0073-Y-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-21 | 2024-03-19 | 0.82
0073-Z-CC | Covered Conductor | 73 | 73-1130 | 0.00056461 | 2023-12-28 | 2024-03-26 | 0.65
0972-S-CC | Covered Conductor | 972 | 972-1582R | 9.6996e-05 | 2023-11-06 | 2024-02-03 | 0.73
0075-A-CC | Covered Conductor | 75 | CB 91 | 4.8408e-06 | 2024-03-27 | 2024-06-24 | 0.32

## Response 7
Please provide a spreadsheet listing (as rows) each undergrounding project completed during the period of January 1, 2022, through December 31, 2022. For each project, please provide the following information (as columns):
a) Project ID number or other identifier | b) Circuit ID | c) ID of each circuit segment that was entirely undergrounded in the project | d) ID of each circuit segment that was partially undergrounded in the project | e) County or counties where undergrounding took place | f) Project start date | g) Project completion date | h) Total circuit-miles undergrounded | i) Total miles of trenching required | j) Total life-cycle electric costs5 of the project (i.e., costs attributed to your electric facilities), including costs for planning, design, permitting, and construction | k) Total life-cycle costs of the project, including costs attributed to non-electric utilities, including costs for planning, design, permitting, and construction | l) Whether this was a Rule 20 project (yes/no) | m) Whether this was a WMP project (yes/no) | n) Whether this was a post-wildfire rebuild project (yes/no) | o) Whether you shared trenches for this project with any telecommunications utilities (yes/no) | p) Whether you shared trenches for this project with gas facilities (yes/no).
Ph.1A Delridge | C1030 | NA | 1030-18R | San Diego | 2021-03-17 | 2022-03-21 | 4.2 | 2.911 | 4967160 | 4967160 | no | Yes | no | No | No
Ph.3A Santee Ln. | C1030 | NA | 1030-18R | San Diego | 2021-06-01 | 2022-08-15 | 5.22 | 3.69 | 7240469 | 7240469 | no | Yes | no | No | No
Ph.4 South Kiavo | C1030 | NA | 1030-18R | San Diego | 2021-06-01 | 2022-12-30 | 8.42 | 1.21 | 8755720 | 8755720 | no | Yes | no | No | No
Quick Win PH.1A W. Victoria Rd | C1458 | NA | 1458-454 | San Diego | 2020-04-01 | 2022-04-12 | 3.55 | 1.49 | 5253005 | 5253005 | no | Yes | no | No | No
Quick Win PH.2 AL Elem School | C1458 | NA | 1458-462 | San Diego | 2020-04-01 | 2022-12-16 | 2.44 | 1.27 | 4257940 | 4257940 | no | Yes | no | No | No
DUG PH.1 to Rincon's Harrah's Casino | C216 | NA | 216-220R | San Diego | 2020-01-02 | 2022-12-02 | 3.4 | 2.93 | 9403445 | 9403445 | no | Yes | no | No | No
DUG PH.2 Rincon Government Building | C216 | NA | 216-1893 | San Diego | 2020-01-02 | 2022-08-20 | 1.9 | 1.94 | 4411539 | 4411539 | no | Yes | no | No | No
DUG PH.1 (Dwntn Julian Connection) | C221 | NA | 221-38AE | San Diego | 2020-03-09 | 2022-09-20 | 1.85 | 1.1 | 5297326 | 5297326 | no | Yes | no | No | No
DUG PH.4 (Spencer Sch to Hwy 79) | C221 | NA | 221-1230F | San Diego | 2020-03-25 | 2022-09-27 | 2.89 | 2.27 | 11388360 | 11388360 | no | Yes | no | No | No
ESH Ph.A SUG - Menzanita Dr | C221 | NA | 221-824 | San Diego | 2021-10-21 | 2023-01-27 | 1.62 | 1.59 | 3347871 | 3347871 | no | Yes | no | No | No
DUG Ph.4 (Combined with C221 DUG) | C222 | NA | 222-1364R | San Diego | 2020-03-25 | 2022-12-16 | 2.14 | 0 | included in C221 DUG Ph.4 | included in C221 DUG Ph.4 | no | Yes | no | No | No
Quick Win Job#3-- E. Victoria Rd (FIRM) | C357 | NA | 347-45R | San Diego | 2020-04-20 | 2022-07-11 | 0.17 | 0.1 | do not have right now | do not have right now | no | Yes | no | Yes | No
DUG Ph.1 Alpine Blvd | C358 | NA | 358-576 | San Diego | 2020-03-11 | 2022-12-11 | 3.1 | 1.94 | 6520552 | 6520552 | no | Yes | no | Yes | No
DUG (Old Hwy 80) | C445 | NA | 445-1316F | San Diego | 2020-04-27 | 2022-03-20 | 3.47 | 2.35 | 7813083 | 7813083 | no | Yes | no | No | No
DUG Ph. 2 - Lyons Valley Rd | C75 | NA | CB75 | San Diego | 2021-06-01 | 2022-12-30 | 5.72 | 4.3 | 12106586 | 12106586 | no | Yes | no | No | No
DUG- Cole Grade Rd | C908 | NA | 908-2058 | San Diego | 2020-04-13 | 2022-07-20 | 3.19 | 1.97 | 7345135 | 7345135 | no | Yes | no | No | No
DUG PH.A - Ashley Rd | C972 | NA | 972-26R | San Diego | 2021-06-01 | 2022-11-30 | 6.59 | 5.5 | 14000938 | 14000938 | no | Yes | no | No | No
PH.B - Steffy Rd | C972 | NA | 972-26R | San Diego | 2021-06-01 | 2022-12-30 | 3.66 | 2.74 | 6729415 | 6729415 | no | Yes | no | No | No
ESH Ph.A SUG - Oak Height | SL1 | NA | NA | San Diego | 2021-10-21 | 2022-12-30 | 1.58 | 1.65 | 3536000 | 3536000 | no | Yes | no | No | No
Note: | J) Cost is total construction (civil, electrical and material) cost by end of Feb/2023, and estimated average engineering and design, other support (contractor and internal labor). See tab Q(J) for details.
d) Original OH segment ID is provided. Newly installed UG line may have a different segment ID, which are not provided here.

## Risk Scores (hidden)
upstreamardfacilityid | base_wf_risk
1001-1130R | 0
1001-1140R | 0
1001-1231 | 1.2852e-09
1001-1814AE | 6.2888e-07
1001-1820F | 3.8813e-05
1006-829F | 1.0634e-06
1021-1748F | 0.00040463
1021-1760R | 6.7803e-05
1021-25R | 0.00015879
1021-855 | 6.689e-05
1021-883R | 1.6304e-05
1021-92 | 6.7744e-06
1022-17F | 0.00010673
1022-26R | 5.0969e-06
1022-322R | 0.00011022
1023-200R | 1.2e-05
1023-46AE | 0.00012067
1023-48 | 9.8379e-05
1023-89 | 2.0236e-05
1030-1728R | 4.8667e-05
1030-1767 | 2.2651e-08
1030-1823F | 1.1821e-05
1030-18R | 0.00028884
1030-20R | 0.00087064
1030-23R | 0.0011028
1030-42R | 0.00097562
1030-989R | 0.0023536
1039-13 | 0.00017263
1073-872F | 6.2616e-07
1073-874F | 6.9114e-09
1073-886F | 6.7506e-09
1073-887F | 6.7941e-08
1079-9 | 2.3014e-08
1090-1734 | 1.1376e-05
1090-636R | 1.4632e-05
1090-639R | 0.00014527
1090-70F | 6.9543e-07
1090-73F | 6.7661e-05
1090-74F | 4.5916e-05
1094-35F | 1.2855e-05
1094-7 | 1.3118e-06
1100-1172R | 2.9875e-05
1105-1479 | 6.8455e-05
1105-1483 | 9.4308e-06
1118-1718 | 2.1982e-06
1138-6R | 0.00014205
1162-324R | 6.2691e-06
1166-15R | 0.00027671
1166-18R | 0.00013671
1166-342R | 0.0003111
1201-282F | 5.9999e-06
1215-10R | 3.9828e-05
1215-12R | 0.00085741
1215-28R | 0.00026664
1215-32R | 0.0019248
1233-252R | 0.00093653
1233-259R | 0.00011081
1242-127AE | 9.7214e-06
1243-319R | 0.00023956
1243-38R | 1.9448e-06
1243-45R | 0.00022098
1250-27R | 5.3839e-05
1250-671R | 6.3786e-05
1250-677R | 0.00031299
1250-8R | 0.00016038
1458-1056 | 3.4238e-09
1458-1058F | 4.716e-05
1458-1061 | 8.5504e-05
1458-1075F | 3.0163e-07
1458-1131R | 0.00015751
1458-454F | 2.1265e-06
1458-455F | 0 | 0.000319236243341737,0.000320573042022656
1458-519 | 0.00065957
1458-565R | 0.0001106
157-189R | 0.0012013
157-204R | 0.00055395
157-207R | 5.8329e-05
157-232R | 0.0016719
157-257R | 0.00058436
157-273R | 0.00054913
157-81R | 0.0023888
175-2024R | 3.461e-05
175-24R | 1.4163e-05
175-64R | 7.3576e-05
175-90R | 5.9633e-05
175-94R | 8.992e-06
176-161R | 6.0481e-05
176-164R | 1.1675e-05
176-1834R | 0.0001175
176-1836R | 5.2338e-07
176-197F | 0.00013576
176-200F | 2.1258e-06
176-41R | 3.5136e-05
177-955 | 5.6335e-07
178-968AE | 3.8239e-07
178-982 | 3.0768e-08
182-2240F | 6.8321e-05
182-2252R | 2.2102e-05
182-2254R | 3.0008e-06
183-439 | 1.77e-06
183-440 | 3.1225e-06
185-40AE | 0
185-51F | 2.9973e-05
185-52F | 0
197-1150F | 2.8521e-06
197-1155F | 1.4803e-07
198-37R | 1.1255e-05
200-613AE | 8.2491e-06
204-32R | 2.8582e-05
205-1550 | 1.8684e-08
206-1105 | 1.3836e-06
206-1817 | 1.0848e-05
209-1769F | 7.5743e-05
210-172R | 0.00027354
210-392 | 0.00024816
210-394 | 8.213e-05
210-9R | 6.2466e-05
211-279R | 0.0006846
211-280R | 0.00051805
211-312R | 0.00020715
212-1177R | 0.00035267
212-638R | 3.3846e-05
212-734R | 0.0003141
212-739R | 0.00029896
212-743R | 7.359e-05
212-773R | 0.00033091
212-799R | 5.5865e-05
212-880R | 1.0915e-05
212-886R | 0.00028178
212-888R | 8.5587e-05
214-1122R | 0.0020259
214-1135R | 0.00062023
214-17AE | 5.2309e-05
214-4R | 2.9564e-05
214-536R | 2.7404e-05
214-583R | 9.2706e-05
214-613R | 3.3217e-05
214-647R | 0.00024546
215-1531R | 0.00021593
215-1534R | 0.00076516
215-1544R | 2.9749e-05
215-38R | 0.00087331
216-1857 | 0.0013377
216-220R | 1.0911e-05
217-41AE | 9.0424e-05
217-48AE | 0.00011883
217-835R | 0.0013445
217-837R | 0.0016979
217-972R | 9.6462e-05
217-983R | 0.0028311
220-288R | 0.00013018
220-294R | 0.00054392
220-298R | 0.0018519
221-1230F | 0.00011519
221-23R | 5.3954e-05
221-344R | 0.0002124
221-35 | 1.497e-05
221-37AE | 0.00025484
221-38AE | 2.0519e-06
221-675R | 0.00015935
221-6R | 0.00015637
221-782R | 0.000105
221-788 | 9.3073e-05
221-824 | 9.8415e-05
222-1364R | 0.0044181
222-1370R | 0.0027089
222-1401R | 0.0064784
222-1433R | 0.0010778
222-1441R | 0.0011512
222-1503 | 6.1485e-05
222-1523R | 0.0012893
222-2013R | 0.0014386
222-2063 | 0.00053914
230-1008R | 5.9993e-06
230-127AE | 0.00027138
230-133AE | 0.00034788
230-1586R | 0.00020677
230-1606R | 3.756e-05
230-181 | 1.1414e-05
230-371AE | 6.5443e-06
231-1635R | 0.00053861
231-42 | 0.00029051
232-40AE | 2.6631e-08
233-123R | 6.8456e-05
233-41R | 3.7501e-05
233-81F | 1.6446e-05
233-86F | 0.00010751
234-48R | 4.1976e-05
235-897R | 6.9663e-05
235-899R | 0.001479
236-1535 | 0.0004796
236-1561R | 8.3285e-05
236-1567R | 6.8935e-05
236-1573R | 9.1977e-05
237-1761R | 0.00056856
237-1765R | 0.002068
237-17R | 0.0018176
237-2R | 0.00025068
237-30R | 0.0067252
239-15R | 0.00091593
239-2144R | 7.7843e-05
239-89R | 0.00013564
240-1028R | 1.1531e-05
240-1044 | 1.4501e-05
240-1148 | 7.404e-06
240-2004R | 4.7153e-05
240-2006R | 2.958e-05
240-2032R | 0.0001126
242-773F | 6.386e-06
243-14R | 4.5516e-09
246-34R | 3.0598e-05
247-46 | 9.4244e-06
247-48 | 1.5008e-09
249-24R | 0.00010991
252-129AE | 7.5014e-06
260-358R | 0.000295
281-28R | 1.4765e-05
283-55R | 0.00027897
283-71F | 5.8905e-05
283-80F | 2.7557e-10
288-2375 | 5.9357e-09
288-2380F | 2.0266e-07
296-68F | 4.3899e-07
305-32R | 0
305-35R | 0
307-1492R | 0
307-1538F | 4.7294e-06
307-234R | 8.7168e-05
308-485AE | 3.0114e-08
308-563AE | 3.0457e-06
311-1163F | 4.0455e-06
311-43 | 2.4739e-06
312-28R | 3.1579e-07
315-1151 | 8.2836e-07
315-485AE | 8.0442e-06
350-2182R | 4.5764e-06
350-2188R | 0.0001328
350-2192R | 0.00022972
350-2196R | 0.00014389
350-2201R | 0.00030022
350-41R | 0.00035865
351-819R | 0.00023797
351-871R | 0.00010098
352-27R | 0.00032338
353-593F | 3.4215e-05
353-594F | 1.3175e-05
353-900F | 1.8606e-05
353-901F | 4.1251e-05
353-902F | 2.4124e-07
353-904R | 0.00018191
353-914R | 0.0001125
354-24AE | 5.1059e-05
354-38R | 0.00011518
355-41R | 0.00014006
355-65R | 0
355-6R | 3.0694e-05
356-16R | 0.00016121
356-19R | 0.00039528
356-30AE | 0.00019482
357-1147R | 1.346e-06
357-1299R | 0.00056079
357-2047F | 7.302e-08
357-2049F | 0.00042612
357-45R | 0.0011847
357-50R | 0.00031878
357-750R | 0.00024858
358-33 | 3.5136e-05
358-585R | 0.00064786
358-682F | 0.0026261
387-15 | 2.3689e-05
393-14R | 9.8279e-06
396-699R | 0.00011121
411-1873R | 4.6676e-05
411-30R | 0.00017772
411-47R | 1.1958e-05
441-23R | 0.00070662
441-279R | 0.00010211
441-27R | 0.0010831
441-30R | 0.00084586
442-16R | 0.00069241
442-28R | 2.9258e-05
442-29R | 6.9572e-06
442-46R | 1.1416e-06
442-509R | 1.0395e-05
442-525 | 7.4659e-06
442-728R | 7.4688e-05
444-15R | 2.8164e-05
444-43R | 0.00053793
444-9R | 4.4322e-05
445-1311R | 0.0015011
445-1315F | 1.4979e-06
445-1323 | 3.1682e-06
445-1325F | 0.00068627
445-17R | 0.00013592
445-19R | 0.00031924
445-24R | 0.0011954 |  | 0.00119535926658874, 0.000320573042022656, 0.00011623549872629
445-39R | 0.00032057
445-894R | 0.0002936
445-897R | 0.00011624
448-1196F | 8.1741e-07
448-11R | 0.0029781
448-23R | 7.2342e-05
448-33R | 0.00027698
448-47R | 0.0017472
448-724R | 0.00014734
448-9R | 0.00085331
449-13R | 0.0010019
449-16R | 0.00010573
449-19R | 8.6546e-05
449-683R | 0.00025225
449-6R | 0.00063288
450-18 | 0.00044043
450-50R | 3.2041e-06
450-88R | 0
452-38AE | 1.389e-05
454-1814 | 2.0085e-06
454-47R | 0
454-48F | 8.2968e-05
463-1136F | 6.6026e-06
470-40AE | 4.8933e-05
470-47R | 0.00020429
471-36F | 3.4567e-05
476-885R | 0
486-61R | 0
500-1531 | 1.9877e-06
501-786 | 1.8792e-06
504-36R | 4.4554e-06
520-1045R | 9.3078e-05
520-10R | 6.0255e-05
520-1489R | 6.2217e-05
520-1509R | 6.1406e-05
520-1525R | 2.7865e-05
520-1527R | 0.00018601
520-1902R | 7.0157e-05
520-1904 | 0.00012758
520-22R | 2.8723e-05
520-35R | 0.00021352
520-45 | 8.3868e-05
521-14R | 0.0014179
521-1819R | 6.2793e-05
521-18R | 0.00032869
521-27R | 0.00026498
521-32R | 0.00010454
521-700R | 0.00044675
522-34 | 5.3039e-06
522-36 | 2.6992e-06
522-38R | 8.1183e-05
523-31AE | 1.3654e-05
524-1782 | 5.0715e-05
524-27R | 0.00017064
524-46R | 0.00020716
524-50R | 0.00015147
524-69R | 0.0051395
536-150R | 2.7935e-05
540-241 | 3.6358e-05
591-1594R | 1.4242e-06
594-1379F | 2.5174e-06
597-595 | 0.00031692
599-19R | 0.00013381
66-1213R | 0
67-24R | 0.00016901
67-34R | 0.00029927
67-37R | 8.5043e-05
67-45R | 0.00036741
73-1130 | 0.00056461
73-23R | 0.00041443
73-643R | 0.0021262
73-678R | 0.00084942
73-683R | 0.00056173
75-32R | 6.3227e-05
75-41 | 1.416e-05
75-996R | 3.7604e-05
770-259R | 1.6844e-06
78-26R | 0.0002547
78-35R | 0.00019304
78-782R | 8.513e-05
788-34R | 5.7993e-05
79-1215F | 7.291e-06
791-419F | 1.7436e-05
79-658R | 0.00021504
79-660R | 0.00048589
79-668R | 0.00015117
79-676R | 0.00014573
79-679R | 0.001147
79-685R | 0.00037177
79-714R | 8.1949e-05
79-785 | 0.00052918
79-799R | 0.00032255
79-808R | 0.0021449
799-504R | 1.3963e-06
835-10F | 8.065e-09
835-11F | 1.9417e-06
835-35F | 6.2376e-08
840-308F | 1.8196e-05
855-46AE | 6.5587e-07
859-42R | 2.4719e-05
907-1562AE | 0.0002654
907-1602 | 7.6991e-07
907-1604 | 6.6662e-09
907-1702R | 0.00040337
907-1716R | 0.0001102
907-2820R | 1.2488e-05
908-1172R | 0.00028635
908-1236R | 0.00045394
908-1368R | 0.00010264
908-1370R | 6.3947e-05
908-1372R | 0.00013931
908-2038R | 0.0013093
908-2040 | 8.4034e-05
908-2055F | 0.0001215
908-2062F | 9.1186e-08
908-30 | 9.6226e-06
909-17R | 0.00010298
909-805R | 0.0067143
91-7F | 1.6011e-05
920-1342R | 0.00010653
920-735AE | 2.1768e-05
921-800F | 7.8097e-06
928-19 | 1.6362e-05
968-476F | 1.6918e-06
970-1341R | 0.0013525
971-1973R | 0.00017719
971-29R | 0.00038394
971-371R | 0.00013176
971-381R | 5.0681e-06
971-383R | 0.00083674
971-388R | 0.00026188
972-1582R | 9.6996e-05
972-26R | 0.00030961
972-32R | 0.00040696
972-8 | 0.00039365
972-942R | 8.4866e-05
973-1226R | 0.00051814
973-530AE | 5.5391e-07
973-626R | 0.0004883
973-630R | 0.00033241
974-23R | 0.00016538
974-35R | 0.0001802
975-22R | 0.00012495
991-1 | 4.7719e-06
991-1206R | 0.00012688
CB 1023 | 1.1145e-05
CB 1090 | 2.3715e-05
CB 1101 | 5.897e-05
CB 1106 | 3.1374e-05
CB 1138 | 4.0935e-06
CB 1160 | 1.1038e-08
CB 1161 | 5.6667e-07
CB 1162 | 8.8697e-06
CB 1166 | 2.4212e-06
CB 1215 | 3.5057e-07
CB 1233 | 1.1983e-08
CB 1234 | 0.00044367
CB 1235 | 0.00019208
CB 1243 | 1.998e-05
CB 1245 | 2.4025e-06
CB 1250 | 8.4397e-05
CB 1299 | 2.6011e-06
CB 1458 | 0
CB 157 | 0
CB 185 | 3.3406e-08
CB 196 | 2.0464e-08
CB 197 | 0
CB 200 | 1.6484e-05
CB 202 | 2.2385e-05
CB 203 | 6.284e-06
CB 204 | 5.3034e-05
CB 210 | 1.3778e-06
CB 211 | 1.7644e-07
CB 212 | 2.9598e-06
CB 214 | 2.5472e-07
CB 215 | 4.6168e-06
CB 217 | 8.4974e-07
CB 220 | 4.942e-08
CB 222 | 1.2759e-05
CB 230 | 2.9155e-06
CB 231 | 0.00018585
CB 232 | 2.68e-05
CB 233 | 0.0001161
CB 234 | 0.00012914
CB 235 | 2.1084e-05
CB 236 | 0.00080694
CB 237 | 8.1819e-05
CB 239 | 2.6939e-08
CB 240 | 1.2512e-05
CB 242 | 4.2422e-06
CB 244 | 3.8278e-06
CB 246 | 5.4877e-05
CB 247 | 4.9179e-06
CB 248 | 7.3142e-06
CB 249 | 2.1382e-05
CB 260 | 1.2152e-05
CB 280 | 3.0863e-05
CB 283 | 1.9714e-07
CB 292 | 6.0125e-06
CB 300 | 0.00016555
CB 315 | 4.3437e-08
CB 327 | 4.7552e-06
CB 329 | 7.1107e-06
CB 330 | 8.0131e-06
CB 331 | 9.5447e-06
CB 350 | 5.786e-07
CB 351 | 0.00015924
CB 352 | 4.035e-07
CB 353 | 3.349e-07
CB 354 | 2.9248e-07
CB 355 | 0.00027953
CB 356 | 3.8274e-07
CB 357 | 0.00043541
CB 358 | 6.4574e-06
CB 396 | 5.9432e-08
CB 440 | 1.4855e-05
CB 441 | 0.00035581
CB 442 | 0.00011825
CB 443 | 1.6833e-06
CB 444 | 1.0934e-05
CB 449 | 2.1844e-06
CB 461 | 6.4378e-06
CB 470 | 1.3881e-05
CB 499 | 1.2737e-06
CB 520 | 3.3065e-08
CB 521 | 9.5365e-07
CB 522 | 7.768e-05
CB 523 | 1.9846e-05
CB 524 | 4.1874e-06
CB 533 | 5.2723e-09
CB 534 | 5.2972e-07
CB 535 | 8.0359e-07
CB 536 | 3.2663e-06
CB 540 | 8.3622e-06
CB 542 | 3.1183e-05
CB 568 | 1.8074e-07
CB 569 | 1.1994e-08
CB 576 | 1.4351e-05
CB 599 | 3.6134e-05
CB 67 | 1.0204e-06
CB 73 | 4.1907e-06
CB 776 | 4.3106e-06
CB 78 | 3.244e-06
CB 788 | 9.039e-06
CB 835 | 1.5209e-06
CB 907 | 8.7302e-05
CB 909 | 6.5227e-08
CB 91 | 4.8408e-06
CB 928 | 3.5045e-05
CB 970 | 3.9815e-05
CB 971 | 0.00057045
CB 972 | 4.3566e-05
CB 973 | 8.1222e-07
CB 974 | 7.3655e-07
CB 975 | 3.9348e-05
CB 980 | 4.051e-06
CB 981 | 1.8914e-06
CB CTL1 | 5.8569e-08
CB DV1 | 0
CB FB1 | 2.722e-05
CB FB2 | 1.4024e-05
CB JU1 | 5.1268e-05
CB MOR1 | 4.8495e-05
CB NVS1 | 1.923e-07
CB OK1 | 0.00023691
CB PE1 | 0.00036721
CB RA1 | 0.00015434
CB RA2 | 2.3406e-05
CB RA3 | 2.356e-06
CB RB1 | 1.1866e-08
CB RC1 | 3.1206e-05
CB SL1 | 0.00010054
CB SSC1 | 5.1252e-07
CTL1-3R | 3.7077e-05
DV1-3R | 0.00013434
RA1-402R | 0.00025001
RB1-427R | 0.00031945
RB1-433R | 0.00019434
TM1-10R | 0.00014234