## SDGE - Table 12_v2
| Utility | SDGE | Notes:
| Table No. | 12 | Risk-Spend-Efficiency (RSE) is defined as "An estimate of the cost-effectiveness of initiative, calculated by dividing the mitigation risk reduction benefit by the mitigation cost estimate based on the full set of risk reduction benefits estimated from the incurred costs."
| Date Modified | 2021-02-23 | CAPEX = Capital expenditure; OPEX = Operating expenditure. In future submissions update planned spend, line miles treated, RSE, etc. with updated projections and actuals. Additional instructions can be found in QR information.
[20 empty] | Planned - (Projected spend for 2020 cycle as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Planned - (Projected spend for 2021 as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Planned - (Projected spend for 2022 as reported in 2020 but using 2021 reporting method, which includes HFTD and non-HFTD spend) | [7 empty] | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected
[20 empty] | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total | HFTD | HFTD | Total | Total | HFTD | Total | HFTD | Total
| Table 12: Mitigation initiative financials | [18 empty] | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used) | CAPEX ($ thousands) | OPEX ($ thousands) | CAPEX ($ thousands) | OPEX ($ thousands) | Line miles to be treated | Line miles to be treated | Alternative units (if used) | Alternative units (if used)
| Metric type | WMP Table # / Category | 2021 WMP Initiative # | Initative activity | 2020 WMP Initiative # | Primary driver targeted | Secondary driver targeted | Year initiated | Estimated RSE in non-HFTD region | Estimated RSE in HFTD Zone 1 | Estimated RSE in HFTD Tier 2 | Estimated RSE in HFTD Tier 3 | If existing: most recent proceeding that has reviewed program | If new: memorandum account | Current compiance status - In / exceeding compliance with regulations | Associated rule(s) - if multiple, separate by semi-colon - ";" | If spend not disaggregated by category, note spend category or mark general operations | Alternative units in which initiative is reported (if not line miles); still required to report line miles | Comments | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2020 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2021 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2022 (as reported in 2020 using 2021 accounting) | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | Notes
| Other | Risk Assessment & Mapping | 7.3.1.1 | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] | 5.3.1.1. |  |  | 2012 | NA | NA | NA | NA | 2019 GRC | NA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 1190.5993 | 0 |  | NA |  | NA |  |  | 1539.3401 | 0 |  | NA |  | NA |  |  | 1881.4155 | 0 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Risk Assessment & Mapping | 7.3.1.2 | Climate-driven risk map and modelling based on various relevant weather scenarios | 5.3.1.2. |  |  | 2012 | [8 empty] | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Risk Assessment & Mapping | 7.3.1.3 | Ignition probability mapping | 5.3.1.3. |  |  | 2012 | [8 empty] | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Risk Assessment & Mapping | 7.3.1.4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | 5.3.1.4. |  |  | 2012 | [8 empty] | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Risk Assessment & Mapping | 7.3.1.5 | Match drop simulations | 5.3.1.5. |  |  | 2012 | [8 empty] | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Risk Assessment & Mapping | 7.3.1.6 | Weather driven risk map and modelling | 5.3.1.6. |  |  | 2012 | [8 empty] | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment [WRRM-Ops] |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Situational Awareness & Forecasting | 7.3.2.1 | Advanced weather monitoring and weather stations [Advanced weather station integration] | 5.3.2.1. |  |  | 2010 | NA | NA | NA | NA | 2019 GRC | NA | Exceeds | P.U. Code § 451 |  | Weather Stations |  | 775 |  | 775 |  | NA | NA | 20 | 20 | 775 |  | 775 |  | NA | NA | 20 | 20 | 775 |  | 775 |  | NA | NA | 20 | 20 | 1083 |  | 1083.4641 | 0 | NA | NA | 30 | 30 | 483 |  | 482.944 | 0 | NA | NA | 20 | 20 | 558 |  | 558.3647 | 0 | NA | NA | 20 | 20
| Other | Situational Awareness & Forecasting | 7.3.2.2 | Continuous monitoring sensors | 5.3.2.2. |  |  | NA | [10 empty] | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Situational Awareness & Forecasting | 7.3.2.3 | Fault indicators for detecting faults on electric lines and equipment [Wireless fault indicators] | 5.3.2.3. | PSPS - for sectionalization, etc. |  | 2011 | 131.86 | NA | 122.84 |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  | Fault Indicators |  | 630 |  | 630 |  | NA | NA | 500 | 500 | 630 |  | 630 |  | NA | NA | 500 | 500 | 0 |  | 0 |  | NA | NA | 0 | 0 | 835 |  | 835.298 | 0 | NA | NA | 502 | 502 | 656 |  | 655.9956 | 0 | NA | NA | 500 | 500 | 656 |  | 655.9956 | 0 | NA | NA | 500 | 500
| Other | Situational Awareness & Forecasting | 7.3.2.4.1 | Fire science and climate adaptation department | 5.3.2.4.1. |  |  | 2009 |  |  |  |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 608.2368 | 3363.3311 |  | NA |  | NA |  |  | 3485.6374 | 3288.9925 |  | NA |  | NA |  |  | 302.5709 | 3617.8918 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Situational Awareness & Forecasting | 7.3.2.4.2 | Fire potential index | 5.3.2.4.2. |  |  | 2012 | [8 empty] | Fire science and climate adaptation department |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Situational Awareness & Forecasting | 7.3.2.4.3 | Santa Ana wildfire threat index | 5.3.2.4.3. |  |  | 2014 | [8 empty] | Fire science and climate adaptation department |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Situational Awareness & Forecasting | 7.3.2.4.4 | High-performance computing infrastructure | 5.3.1.7. |  |  | 2012 |  |  |  |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 7310 | 0 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Situational Awareness & Forecasting | 7.3.2.5. | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions [Observers] | 5.3.2.5. | Equipment failure | Other contact with object | 2008 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Situational Awareness & Forecasting | 7.3.2.5. | Weather forecasting and estimating impacts on electric lines and equipment | 5.3.2.6. |  |  | 2009 | [8 empty] | Fire science and climate adaptation department |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.1 | Capacitor maintenance and replacement program [SCADA capacitors] | 5.3.3.1. | Equipment failure |  | 2016 |  |  | 408.85 | 932.76 | 2019 GRC |  | Exceeds | G.O. 95 |  | Capacitors |  | 1575 |  | 1575 |  | NA | NA | 30 | 30 | 1575 |  | 1575 |  | NA | NA | 30 | 30 | 1995 |  | 1995 |  | NA | NA | 36 | 36 | 992 |  | 992.1823 | 0 | NA | NA | 30 | 30 | 1587 |  | 1586.511 | 0 | NA | NA | 32 | 32 | 1791 |  | 1791.233 | 0 | NA | NA | 40 | 40
| Grid hardening | Grid Design & System Hardening | 7.3.3.2 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  |  |  | 1997 | [8 empty] | Substation inspections |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.3 | Covered conductor installation | 5.3.3.4. | Other contact with object | Equipment failure | 2020 |  |  | 42.77 | 76.73 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  |  |  | 1071 |  | 1071 |  | 1 | 1 | NA | NA | 10800 |  | 10800 |  | 10 | 10 | NA | NA | 10800 |  | 10800 |  | 10 | 10 | NA | NA | 1798 |  | 1797.6911 | 0 | 1.9 | 1.9 | NA | NA | 55000 | 1500 | 55000 | 1500 | 20 | 20 | NA | NA | 96000 | 2500 | 96000 | 2500 | 60 | 60 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.4 | Covered conductor maintenance |  |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.5 | Crossarm maintenance, repair, and replacement | 5.3.3.5. |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | [7 empty] | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.6 | Distribution pole replacement and reinforcement, including with composite poles (Pole replacement and reinforcement) | 5.3.3.6. |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [48 empty] | Grouped with RSE calculations for the various inspection programs. Pole replacement and reinforcment activities can be identified as a part of any of the inspection programs in section 7.3.6. We replace poles based on the inspection results.
| Grid hardening | Grid Design & System Hardening | 7.3.3.7 | Expulsion fuse replacement | 5.3.3.7. | Equipment failure |  | 2019 |  |  | 274.83 | 1417.2 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  | Fuses |  | 3737 |  | 3737 |  | NA | NA | 3000 | 3000 | 4983 |  | 4983 |  | NA | NA | 4000 | 4000 | 1903 |  | 1903 |  | NA | NA | 1535 | 1535 | 6521 |  | 6520.6375 | 0 | NA | NA | 3179 | 3179 | 10178 |  | 10177.77 | 0 | NA | NA | 3970 | 3970 | 3079 |  | 3078.9372 | 0 | NA | NA | 906 | 906
| Grid hardening | Grid Design & System Hardening | 7.3.3.8.1 | PSPS sectionalizing enhancements | 5.3.3.8.1. | PSPS - for sectionalization, etc. |  | 2019 | 610.11 |  | 473.43 | 1159.86 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  | Sectionalizing Devices |  | 413 |  | 550 |  | NA | NA | 7 | 10 | 413 |  | 550 |  | NA | NA | 7 | 10 | 413 |  | 550 |  | NA | NA | 7 | 10 | 3833 |  | 5111.3503 | 0 | NA | NA | 19 | 23 | 1704 |  | 2271.6558 | 0 | NA | NA | 6 | 10 | 1157 |  | 1541.66 | 0 | NA | NA | 9 | 10 | 75% of the customers benefitting from the PSPS sectionalizing installations are located in the HFTD. This 75% HFTD 25% non-HFTD split was used to split the costs. Units are split by actual location of the sectionalizing device installation.
| Grid hardening | Grid Design & System Hardening | 7.3.3.8.2 | Microgrids | 5.3.3.8.2. | PSPS - for sectionalization, etc. |  | 2019 |  |  | 30.78 |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Micro Grids |  | 10433 | 907 | 10433 | 907 | NA | NA | 3 | 3 | 7728 | 672 | 7728 | 672 | NA | NA | 3 | 3 | 7728 | 672 | 7728 | 672 | NA | NA | 1 | 1 | 3542 | 371 | 3542.0419 | 370.5416 | NA | NA | 2 | 4 | 18943 | 1427 | 18942.637 | 1426.8761 | NA | NA | 2 | 2 | 12912 | 1427 | 12912.4862 | 1426.8761 | NA | NA | 1 | 1 | Although two of our installed Microgrid sites are not in the HFTD, they serve customers that are located in the HFTD and have been impacted by PSPS events.
| Grid hardening | Grid Design & System Hardening | 7.3.3.9 | Installation of system automation equipment (Advanced Protection) | 5.3.3.2. | PSPS - for sectionalization, etc. |  | 2011 |  |  |  | 281.09 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Circuits |  | 5300 |  | 5300 |  | NA | NA | 8 | 8 | 9100 |  | 9100 |  | NA | NA | 9 | 9 | 9100 |  | 9100 |  | NA | NA | 15 | 15 | 9119 |  | 9119.2681 | 0 | NA | NA | 6 | 6 | 11092 |  | 11092.422 | 0 | NA | NA | 8 | 8 | 10953 |  | 10953.282 | 0 | NA | NA | 8 | 8
| Grid hardening | Grid Design & System Hardening | 7.3.3.10 | Maintenance, repair, and replacement of connectors, including hotline clamps | 5.3.3.10. | Equipment failure |  | 2019 | NA | NA | 43.25 | 108.44 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  | Hot Line Clamps |  |  | 3000 |  | 3000 | NA | NA | 1650 | 1650 |  | 3000 |  | 3000 | NA | NA | 1650 | 1650 |  | 3000 |  | 3000 | NA | NA | 1650 | 1650 |  | 3299 | 0 | 3298.581 | NA | NA | 2061 | 2061 |  | 5343 | 0 | 5342.9578 | NA | NA | 2250 | 2250 |  | 4321 | 0 | 4320.7694 | NA | NA | 1650 | 1650
| Grid hardening | Grid Design & System Hardening | 7.3.3.11.1 | Resiliency Grant Programs | 5.3.3.11.1. | PSPS - for sectionalization, etc. |  | 2020 | 36.55 |  | 36.55 | 73.11 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Generators |  |  | 4950 |  | 5210 | NA | NA | 1188 | 1250 |  | 5972 |  | 5972 | NA | NA | 1500 | 1500 |  | 8130 |  | 8130 | NA | NA | 1880 | 1880 |  | 4822 | 0 | 5075.892 | NA | NA | 1149 | 1420 |  | 7900 | 0 | 7900 | NA | NA | 2000 | 2000 |  | 7900 | 0 | 7900 | NA | NA | 2000 | 2000
| Grid hardening | Grid Design & System Hardening | 7.3.3.11.2 | Standby Power Programs | 5.3.3.11.3. | PSPS - for sectionalization, etc. |  | 2020 |  |  |  | 89.61 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Generators |  |  | 3000 |  | 3000 | NA | NA | 300 | 300 |  | 3000 |  | 3000 | NA | NA | 300 | 300 |  | 3000 |  | 3000 | NA | NA | 300 | 300 |  | 1754 | 0 | 1753.6305 | NA | NA | 75 | 75 |  | 10350 | 0 | 10350 | NA | NA | 413 | 413 |  | 10350 | 0 | 10350 | NA | NA | 412 | 412
| Grid hardening | Grid Design & System Hardening | 7.3.3.11.3 | Resiliency Assistance Programs | 5.3.3.11.2. | PSPS - for sectionalization, etc. |  | 2020 |  |  | 219.27 | 438.54 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Generators |  |  | 250 |  | 250 | NA | NA | 130 | 130 |  | 250 |  | 250 | NA | NA | 130 | 130 |  | 250 |  | 250 | NA | NA | 130 | 130 |  | 761 | 0 | 760.5866 | NA | NA | 1274 | 1274 |  | 1828 | 0 | 1828 | NA | NA | 1250 | 1250 |  | 1828 | 0 | 1828 | NA | NA | 1250 | 1250
| Grid hardening | Grid Design & System Hardening | 7.3.3.12 | Other corrective action | 5.3.3.12. |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.13 | Pole loading infrastructure hardening and replacement program | 5.3.3.13. |  |  | 2011 | [8 empty] | Distribution overhead system hardening (Bare Conductor Hardening) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.14 | Transformers maintenance and replacement | 5.3.3.14. |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.15 | Transmission tower maintenance and replacement | 5.3.3.15. |  |  | 1997 | [8 empty] | Detailed inspections of transmission electric lines and equipment (Transmission ground inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Grid hardening | Grid Design & System Hardening | 7.3.3.16 | Undergrounding of electric lines and/or equipment (Strategic undergrounding) | 5.3.3.16. | Other contact with object | Equipment failure | 2019 |  |  | 63.23 | 55.57 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  |  |  | 31000 |  | 31000 |  | 10 | 10 | NA | NA | 153075 | 3925 | 153075 | 3925 | 50 | 50 | NA | NA | 183300 | 4700 | 183300 | 4700 | 60 | 60 | NA | NA | 38850 |  | 38849.7358 | 0 | 15.58 | 15.58 | NA | NA | 120256 | 3127 | 120255.95 | 3126.655 | 25 | 25 | NA | NA | 197199 | 5127 | 197199.2 | 5127.179 | 80 | 80 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.1 | Distribution overhead system hardening (Bare Conductor Hardening) | 5.3.3.3. | Equipment failure | Other contact with object | 2011 | 1.05 |  | 32.63 | 58.1 | 2019 GRC |  | Exceeds | G.O. 95 |  |  |  | 81516 | 2004 | 84912 | 2088 | 97.92 | 102 | NA | NA | 11278 | 242 | 11748 | 252 | 13.44 | 14 | NA | NA | 7020 | 180 | 7020 | 180 | 8.4 | 8.4 | NA | NA | 132843 | 3308 | 138377.9791 | 3446.1072 | 95.5 | 99.5 | NA | NA | 88320 | 1920 | 92000 | 2000 | 96 | 100 | NA | NA | 5000 | 130 | 5000 | 130 | 5 | 5 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Overhead transmission fire hardening (Transmission) | 5.3.3.17.1. | Equipment failure | Other contact with object | 2009 |  |  |  |  | FERC |  | Exceeds | G.O. 95 | [7 empty] | 19.3 | 19.3 | NA | NA |  |  |  |  | 24.4 | 24.4 | NA | NA |  |  |  |  | 18.5 | 18.5 | NA | NA |  |  |  | 0 | 21.6 | 21.6 | NA | NA |  |  |  | 0 | 6.7 | 6.7 | NA | NA |  |  |  | 0 | 38.6 | 38.6 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Underground transmission fire hardening (Transmission) | 5.3.3.17.1. | Other contact with object | Equipment failure | 2009 |  |  |  |  | FERC |  | Exceeds | G.O. 95 | [7 empty] | 0 | 0 | NA | NA |  |  |  |  | 6 | 6 | NA | NA |  |  |  |  | 0 | 0 | NA | NA |  |  |  |  | 0 | 0 | NA | NA |  |  |  |  | 0 | 0 | NA | NA |  |  |  |  | 5.5 | 5.5 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.2 | Overhead transmission fire hardening (Distribution Underbuilt) | 5.3.3.17.1. | Equipment failure | Other contact with object | 2009 |  |  |  |  | 2019 GRC |  | Exceeds | G.O. 95 |  |  |  | 5871 |  | 5871 |  | 12.3 | 12.3 | NA | NA | 13765 |  | 13765 |  | 21.8 | 21.8 | NA | NA | 6070 |  | 6070 |  | 7.9 | 7.9 | NA | NA | 5030 |  | 5030.3896 | 0 | 9.4 | 9.4 | NA | NA | 5914 |  | 5914.4395 | 0 | 2.7 | 2.7 | NA | NA | 24015 |  | 24015 | 0 | 27 | 27 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Cleveland National Forest fire hardening - Transmission OH | 5.3.3.17.2. | Equipment failure | Other contact with object | 2009 |  |  |  |  | FERC |  | Exceeds | G.O. 95 | [7 empty] | 29 | 29 | NA | NA |  |  |  |  | 0 | 0 | NA | NA |  |  |  |  | 0 | 0 | NA | NA |  |  |  | 0 | 29.07 | 29.07 | NA | NA |  |  |  | 0 | 0 | 0 | NA | NA |  |  | 0 | 0 | 0 | 0 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Cleveland National Forest fire hardening - Distribution OH | 5.3.3.17.2. | Equipment failure | Other contact with object | 2009 |  |  |  | 52.44 | 2019 GRC |  | Exceeds | G.O. 95 |  |  |  | 35000 |  | 35000 |  | 50 | 50 | NA | NA | 9570 |  | 9570 |  | 1 | 1 | NA | NA | 0 |  | 0 |  | 0 | 0 | NA | NA | 46271 |  | 46270.9186 | 0 | 46.75 | 46.75 | NA | NA | 6965 |  | 6965.2302 | 0 | 6.8 | 6.8 | NA | NA |  |  | 0 | 0 |  | 0 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.17.3 | Cleveland National Forest fire hardening - Distribution UG | 5.3.3.17.2. | Other contact with object | Equipment failure | 2009 |  |  |  | 38.2 | 2019 GRC |  | Exceeds | G.O. 95 |  |  |  | 30000 |  | 30000 |  | 14 | 14 | NA | NA | 930 |  | 930 |  | 0.5 | 0.5 | NA | NA | 0 |  | 0 |  | 0 | 0 | NA | NA | 37973 |  | 37972.7471 | 0 | 14.37 | 14.37 | NA | NA | 6051 |  | 6051.2786 | 0 | 0 | 0 | NA | NA |  |  | 0 | 0 | 0 | 0 | NA | NA
| Grid hardening | Grid Design & System Hardening | 7.3.3.18.1 | Distribution communications reliability improvements | 5.3.3.18.1. |  |  | 2010 |  |  |  |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  | Base Stations | N/A | [26 empty] | 35472.7368 | 0 |  | NA |  | 15 |  |  | 50328.3202 | 0 |  | NA |  | 10 |  |  | 70945.6969 | 0 |  | NA |  | 25 | Upon further consideration of this initiative, it is now deemed a foundational initiative that is important for supporting various wildfire mitigation initiatives. Enhanced communication systems support the implementation of Advanced Protection as well as other systems such as weather monitoring.
| Grid hardening | Grid Design & System Hardening | 7.3.3.18.2 | Lightning arrestor removal and replacement | 5.3.3.18.2. | Equipment failure |  | 2020 | NA | NA | NA | 41.89 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  | Lighting Arrestors |  | 0 |  | 0 |  |  |  | 0 | 0 | 1050 |  | 1050 |  | NA | NA | 924 | 924 | 2100 |  | 2100 |  | NA | NA | 1848 | 1848 | 19 |  | 19.2033 | 0 | NA | NA | 0 | 0 | 1297 |  | 1296.9049 | 0 | NA | NA | 924 | 924 | 2611 |  | 2611.3668 | 0 | NA | NA | 1848 | 1848
| Asset inspection | Asset Management & Inspections | 7.3.4.1 | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) | 5.3.4.1. | Equipment failure |  | 1997 |  |  | 45.24 | 63.8 | 2019 GRC |  | Meets | G.O. 95 |  | Inspections |  |  | 1552 |  | 1552 | NA | NA | 17500 | 17500 |  | 1252 |  | 1252 | NA | NA | 22500 | 22500 |  | 632 |  | 632 | NA | NA | 18500 | 18500 | 8320 | 179 | 8320.2463 | 178.8139 | NA | NA | 17977 | 17977 | 7484 | 2852 | 7484.3549 | 2851.8139 | NA | NA | 22269 | 22269 | 7629 | 2190 | 7628.87 | 2189.8139 | NA | NA | 18055 | 18055 | As noted in the Comments section in Table 24 of the 2020 WMP, "SDG&E's corrective maintenance program inspection costs were not broken out in the previous WMP. SDG&E plans to track inspection costs within the HFTD going forward."
| Asset inspection | Asset Management & Inspections | 7.3.4.2 | Detailed inspections of transmission electric lines and equipment (Transmission ground inspections) | 5.3.4.2. | Equipment failure |  | 1997 |  |  |  |  | FERC |  | Meets | G.O. 95 |  | Inspections | [5 empty] | NA | NA | 41 | 41 |  |  |  |  | NA | NA | 36 | 36 |  |  |  |  | NA | NA | 36 | 36 | 838 |  | 838.1161 | 0 | NA | NA | 2679 | 2679 | 787 |  | 787.2 | 0 | NA | NA | 2715 | 2715 | 725 |  | 724.868 | 0 | NA | NA | 2715 | 2715 | The 2020 WMP captured Transmission System Inspections Targets by Transmission Lines. 2021 captures these targets by structures.
| Asset inspection | Asset Management & Inspections | 7.3.4.3 | Improvement of inspections | 5.3.4.3. |  |  | 2019 | [8 empty] | Drone assessments of distribution infrastructure |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | [7 empty] | 0 | 0
| Asset inspection | Asset Management & Inspections | 7.3.4.4 | Infrared inspections of distribution electric lines and equipment | 5.3.4.4. | Equipment failure |  | 2020 |  |  | 331.53 | 433.6 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Inspections |  |  | 245 |  | 245 | NA | NA | 8500 | 8500 |  | 245 |  | 245 | NA | NA | 8500 | 8500 |  | 245 |  | 245 | NA | NA | 8500 | 8500 |  | 175 | 0 | 174.5743 | NA | NA | 13077 | 13077 |  | 175 | 0 | 174.5743 | NA | NA | 18000 | 18000 |  | 175 | 0 | 174.5743 | NA | NA | 18000 | 18000
| Asset inspection | Asset Management & Inspections | 7.3.4.5 | Infrared inspections of transmission electric lines and equipment | 5.3.4.5. | Equipment failure |  | 2010 |  |  |  |  | FERC |  | Meets | P.U. Code § 451 |  | Inspections | [5 empty] | NA | NA | 113 | 113 |  |  |  |  | NA | NA | 113 | 113 |  |  |  |  | NA | NA | 113 | 113 |  |  | 0 | 0 | NA | NA | 6481 | 6481 |  |  | 0 | 0 | NA | NA | 6565 | 6565 |  |  | 0 | 0 | NA | NA | 6565 | 6565
| Asset inspection | Asset Management & Inspections | 7.3.4.6 | Intrusive pole inspections | 5.3.4.6. | Equipment failure |  | 1997 |  |  | 26.4 | 106.67 | 2019 GRC |  | Meets | G.O. 95 |  | Inspections | [5 empty] | NA | NA | 18000 | 18000 |  |  |  |  | NA | NA | 8000 | 8000 |  |  |  |  | NA | NA | 400 | 400 | 567 | 884 | 566.8189 | 883.6179 | NA | NA | 14450 | 14450 | 1521 | 633 | 1520.8088 | 633.266 | NA | NA | 9796 | 9796 | 1550 | 2190 | 1550.074 | 837.4191 | NA | NA | 380 | 380 | Intrusive pole inspection costs were not broken out in the 2020 WMP. As noted in the Comments section in Table 24 of the 2020 WMP, "SDG&E's corrective maintenance program inspection costs were not broken out in the previous WMP. SDG&E plans to track inspection costs within the HFTD going forward."
| Asset inspection | Asset Management & Inspections | 7.3.4.7 | LiDAR inspections of distribution electric lines and equipment | 5.3.4.7. |  |  | 2011 |  |  |  |  | 2019 GRC |  | Exceeds | G.O. 95 | [29 empty] | 0 | 0 | NA | NA | NA | NA |  | 1800 | 0 | 1799.865 | NA | NA | NA | NA |  | 1548 | 0 | 1548.36 | NA | NA | NA | NA | LiDAR inspections were not included in the 2020 WMP. LiDAR inspections on distribution and transmission lines are primarily used for grid hardening design efforts rather than for identifying issues like the other inspection programs.
| Asset inspection | Asset Management & Inspections | 7.3.4.8 | LiDAR inspections of transmission electric lines and equipment | 5.3.4.8. |  |  | 2009 |  |  |  |  | FERC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA
| Asset inspection | Asset Management & Inspections | 7.3.4.9.1 | HFTD Tier 3 Inspections | 5.3.4.9.1. | Equipment failure |  | 2009 |  |  | 17.18 | 106.81 | 2019 GRC |  | Exceeds | G.O. 95 |  | Inspections |  |  | 368 |  | 368 | NA | NA | 11500 | 11500 |  | 368 |  | 368 | NA | NA | 11500 | 11500 |  | 368 |  | 368 | NA | NA | 12500 | 12500 | 1248 | 400 | 1248.382 | 400.1001 | NA | NA | 11864 | 11864 | 2459 | 381 | 2459.3216 | 381.1001 | NA | NA | 10815 | 10815 | 2507 | 384 | 2506.8864 | 384.1001 | NA | NA | 12380 | 12380
| Asset inspection | Asset Management & Inspections | 7.3.4.9.2 | Drone assessments of distribution infrastructure | 5.3.4.9.2. | Equipment failure |  | 2019 |  |  | 9.39 | 16.35 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  | Inspections |  | 3600 | 50500 | 3600 | 50500 | NA | NA | 33000 | 33000 | 2430 | 45100 | 2430 | 45100 | NA | NA | 19750 | 19750 | 2430 | 34925 | 2430 | 34925 | NA | NA | 16500 | 16500 | 15901 | 51953 | 15901.2796 | 51953.4138 | NA | NA | 37310 | 37310 | 13595 | 35358 | 13595.0588 | 35357.792 | NA | NA | 22000 | 22000 | 11205 | 28664 | 11205.1503 | 28664.121 | NA | NA | 22000 | 22000
| Asset inspection | Asset Management & Inspections | 7.3.4.9.3 | Circuit ownership | 5.3.4.9.3. | Equipment failure |  | 2019 |  |  | 6.61 | 13.24 | 2020 WMP | WMPMA | Exceeds | G.O. 95 |  |  | N/A | [26 empty] | 41.2877 | 0 |  | NA |  | NA |  |  | 0 | 125 |  | NA |  | NA |  |  | 0 | 125 |  | NA |  | NA
| Asset inspection | Asset Management & Inspections | 7.3.4.10.1 | (Drone assessment of transmission) | 5.3.4.10. | Equipment failure |  | 2020 |  |  |  |  | FERC |  | Exceeds | G.O. 95 |  | Inspections | [27 empty] | 0 | 0 | NA | NA | 2679 | 2679 |  |  | 0 | 0 | NA | NA | 2715 | 2715 |  |  | 0 | 0 | NA | NA | 2715 | 2715 | Drone Assessments of Transmission were not included in the 2020 WMP.
| Asset inspection | Asset Management & Inspections | 7.3.4.10.2 | Additional Transmission Aerial 69kV Tier 3 Visual Inspection |  | Equipment failure |  | 2010 |  |  |  |  | FERC |  | Exceeds | G.O. 95 |  | Inspections | [5 empty] | NA | NA | 27 | 27 |  |  |  |  | NA | NA | 27 | 27 |  |  |  |  | NA | NA | 27 | 27 |  |  | 0 | 0 | NA | NA | 1957 | 1957 |  |  | 0 | 0 | NA | NA | 1792 | 1792 |  |  | 0 | 0 | NA | NA | 1792 | 1792 | The 2020 WMP captured Transmission System Inspections Targets by Transmission Lines. 2021 captures these targets by structures.
| Asset inspection | Asset Management & Inspections | 7.3.4.11 | Patrol inspections of distribution electric lines and equipment - CMP | 5.3.4.11. | Equipment failure |  | 1997 |  |  | 285.9 | 440.92 | 2019 GRC |  | Meets | G.O. 95 |  | Inspections | [5 empty] | NA | NA | 86000 | 86000 |  |  |  |  | NA | NA | 86000 | 86000 |  |  |  |  | NA | NA | 86000 | 86000 | 789 | 295 | 789.4054 | 294.7671 | NA | NA | 86075 | 86075 | 910 | 277 | 910.0155 | 276.7671 | NA | NA | 86000 | 86000 | 927 | 279 | 927.3866 | 278.7671 | NA | NA | 86000 | 86000 | Patrol Inspection costs were not broken out in the 2020 WMP. As noted in the Comments section in Table 24 of the 2020 WMP, "SDG&E's corrective maintenance program inspection costs were not broken out in the previous WMP. SDG&E plans to track inspection costs within the HFTD going forward."
| Asset inspection | Asset Management & Inspections | 7.3.4.12 | Patrol inspections of transmission electric lines and equipment | 5.3.4.12. | Equipment failure |  | 1997 |  |  |  |  | FERC |  | Meets | G.O. 95 |  | Inspections | [5 empty] | NA | NA | 117 | 117 |  |  |  |  | NA | NA | 117 | 117 |  |  |  |  | NA | NA | 117 | 117 |  |  | 0 | 0 | NA | NA | 6940 | 6940 |  |  | 0 | 0 | NA | NA | 7024 | 7024 |  |  | 0 | 0 | NA | NA | 7024 | 7024 | The 2020 WMP captured Transmission System Inspections Targets by Transmission Lines. 2021 captures these targets by structures.
| Asset inspection | Asset Management & Inspections | 7.3.4.13 | Pole loading assessment program to determine safety factor | 5.3.4.13. |  |  | 2011 | [8 empty] | Distribution overhead system hardening (Bare Conductor Hardening) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Asset inspection | Asset Management & Inspections | 7.3.4.14 | Quality assurance / quality control of inspections (Monitoring and auditing of inspections) | 5.3.4.14. |  |  | 1997 | [8 empty] | Detailed inspections of distribution electric lines and equipment (5-year detailed inspections) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Asset inspection | Asset Management & Inspections | 7.3.4.15 | Substation inspections | 5.3.4.15. |  |  | 1997 |  |  | 0 | 0 |  |  |  | G.O. 174 | [7 empty] | NA | NA | 330 | 330 |  |  |  |  | NA | NA | 330 | 330 |  |  |  |  | NA | NA | 330 | 330 |  |  | 0 | 0 | NA | NA | 405 | 405 |  |  | 0 | 0 | NA | NA | 330 | 330 |  |  | 0 | 0 | NA | NA | 330 | 330 | The way SDG&E designs and constructs its substations, with the steel structures and gravel and concrete base makes it difficult for a fire to spread outside the substation. With very little ignition history, SDG&E performs substation inspection and maintenance more for the importance of substation reliability.
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.1 | Additional efforts to manage community and environmental impacts | 5.3.5.1. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.2 | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) | 5.3.5.2. | Contact with vegetation |  | 1998 | 3.04 |  | 128.44 | 230.3 | 2019 GRC |  | Meets | P.U. Code § 451 |  | Inspections |  |  | 27775 |  | 27775 | NA | NA | 238329 | 455000 |  | 27775 |  | 27775 | NA | NA | 238329 | 455000 |  | 27775 |  | 27775 | NA | NA | 238329 | 455000 |  | 57791 | 0 | 57790.5637 | NA | NA | 236354 | 451207 |  | 49765 | 0 | 49765 | NA | NA | 238159 | 455000 |  | 49765 | 0 | 49765 | NA | NA | 238159 | 455000
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.3 | Detailed inspections of vegetation around transmission electric lines and equipment | 5.3.5.3. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.4 | Emergency response vegetation management due to red flag warning or other urgent conditions | 5.3.5.4. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.5 | Fuel management and reduction of “slash” from vegetation management activities | 5.3.5.5. | Contact with vegetation |  | 2019 |  |  |  | 28.58 | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  | Sturctures Cleared |  |  | 5000 |  | 5000 | NA | NA | 500 | 500 |  | 5000 |  | 5000 | NA | NA | 500 | 500 |  | 5000 |  | 5000 | NA | NA | 500 | 500 |  | 5805 | 0 | 5805.0607 | NA | NA | 324 | 324 |  | 6206 | 0 | 6206.2369 | NA | NA | 500 | 500 |  | 6206 | 0 | 6206.2369 | NA | NA | 500 | 500
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.6 | Improvement of inspections | 5.3.5.6. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.7 | LiDAR inspections of vegetation around distribution electric lines and equipment (vegetation management technology) | 5.3.5.7. |  |  | 2019 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.8 | LiDAR inspections for vegetation around transmission electric lines and equipment | 5.3.5.8. |  |  | 2019 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.9 | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations (Enhanced inspections, patrols, and trims) | 5.3.5.9. | Contact with vegetation |  | 2019 |  |  | 66.93 | 119.84 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  | Trees Trimmed to enahced levels |  |  | 23603 |  | 23603 | NA | NA | 17000 | 17000 |  | 23603 |  | 23603 | NA | NA | 17000 | 17000 |  | 23603 |  | 23603 | NA | NA | 17000 | 17000 |  | 10235 | 0 | 10235 | NA | NA | 17095 | 17095 |  | 10235 | 0 | 10235 | NA | NA | 17000 | 17000 |  | 10235 |  | 10235 | NA | NA | 17000 | 17000
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.10 | Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations | 5.3.5.10. |  |  | 2019 | [8 empty] | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations (Enhanced inspections, patrols, and trims) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.11 | Patrol inspections of vegetation around distribution electric lines and equipment | 5.3.5.11. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.12 | Patrol inspections of vegetation around transmission electric lines and equipment | 5.3.5.12. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.13 | Quality assurance / quality control of vegetation inspections | 5.3.5.13. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.14 | Recruiting and training of vegetation management personnel | 5.3.5.14. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.15 | Remediation of at-risk species | 5.3.5.15. |  |  | 2019 | [8 empty] | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations (Enhanced inspections, patrols, and trims) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.16 | Removal and remediation of trees with strike potential to electric lines and equipment (Hazard tree removal and Right Tree-Right Place) | 5.3.5.16. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation inspection | Vegetation Management & Inspections | 7.3.5.17 | Substation inspections | 5.3.5.17. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.18 | Substation vegetation management | 5.3.5.18. |  |  | 1998 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.19 | Vegetation inventory system (Tree database) | 5.3.5.19. |  |  | 2002 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Vegetation management project | Vegetation Management & Inspections | 7.3.5.20 | Vegetation management to achieve clearances around electric lines and equipment (Pole brushing) | 5.3.5.20. | Contact with vegetation |  | 1998 |  |  | 162.48 | 272.48 | 2019 GRC |  | Meets | P.U. Code § 451 |  | Poles Brushed |  |  | 5943 |  | 5943 | NA | NA | 35500 | 35500 |  | 5943 |  | 5943 | NA | NA | 35500 | 35500 |  | 5943 |  | 5943 | NA | NA | 35500 | 35500 |  | 5433 | 0 | 5433.4403 | NA | NA | 36563 | 36563 |  | 5433 | 0 | 5433 | NA | NA | 35500 | 35500 |  | 5433 | 0 | 5433.4403 | NA | NA | 35500 | 35500
| Other | Grid Operations & Operating Protocols | 7.3.6.1.1 | Recloser protocols | 5.3.6.1. | Other contact with object | Equipment failure | 2008 | NA | NA | 372838.28 | 532348.21 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA
| Other | Grid Operations & Operating Protocols | 7.3.6.1.2 | Sensitive/Fast Protection settings |  | Other contact with object | Equipment failure | 2015 |  |  | 47363.6 | 106433.39 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA
| Other | Grid Operations & Operating Protocols | 7.3.6.2 | Crew accompanying ignition prevention and suppression resources and services (Wildfire infrastructure protection teams – Contract fire resources) | 5.3.6.2. | Equipment failure | Other contact with object | 2009 |  |  | 68.58 | 69.69 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 2587.6835 |  | NA |  | NA |  |  | 0 | 2936 |  | NA |  | NA |  |  | 0 | 2936 |  | NA |  | NA | Contract fire resources are used to accompany field crews based on weather conditions and the FPI. For this reason SDG&E is unable to split the contract fire resources by HFTD or non-HFTD.
| Other | Grid Operations & Operating Protocols | 7.3.6.3 | Personnel work procedures and training in conditions of elevated fire risk (Other special work procedures) | 5.3.6.3. | Equipment failure | Other contact with object | 2008 |  |  | 61.9 | 84.57 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA
| Other | Grid Operations & Operating Protocols | 7.3.6.4 | Protocols for PSPS re-energization | 5.3.6.4. | Other contact with object | Equipment failure | 2013 |  |  |  |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 663.1793 | 0 | NA | NA | NA | NA |  |  | 0 | 0 |  | NA |  | NA |  |  | 0 | 0 |  | NA |  | NA | This is an activity that is foundational to supporting wildfire mitigation efforts and is part of core PSPS operations. Costs for protocols cannot be separated out and evluating benefits for having protocols cannot be meaningfully measured.
| Other | Grid Operations & Operating Protocols | 7.3.6.5 | PSPS events and mitigation of PSPS impacts | 5.3.6.5. | Other contact with object | Equipment failure | 2013 |  |  | 92.98 | 93.89 |  |  |  |  | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Grid Operations & Operating Protocols | 7.3.6.6.1 | Aviation firefighting program | 5.3.6.6.1. | Equipment failure | Other contact with object | 2008 | 1.1 |  | 15.72 | 26.07 | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 7092.4023 | 6766.2945 |  | NA |  | NA |  |  | 10184.752 | 7609.9686 |  | NA |  | NA |  |  | 2462.871 | 10320.0687 |  | NA |  | NA
| Other | Data Governance | 7.3.7.1 | Centralized repository for data | 5.3.7.1. |  |  | 2019 |  |  |  |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 5272.0007 | 0 |  | NA |  | NA |  |  | 19003.9973 | 0 |  | NA |  | NA |  |  | 12890.1801 | 0 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Data Governance | 7.3.7.2 | Collaborative research on utility ignition and/or wildfire (Innovation lab and other collaboration) | 5.3.7.2. |  |  | 2012 | [8 empty] | Fire science and climate adaptation department |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Data Governance | 7.3.7.3 | Documentation and disclosure of wildfire-related data and algorithms | 5.3.7.3. |  |  | 2020 |  |  |  |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 2208.0274 | 0 |  | NA |  | NA |  |  | 3689.0099 | 0 |  | NA |  | NA |  |  | 3689.0099 | 0 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Data Governance | 7.3.7.4.1 | Ignition management program | 5.3.7.4.1. |  |  | 2019 | [8 empty] | Fire science and climate adaptation department |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Data Governance | 7.3.7.4.2 | Reliability database | 5.3.7.4.2. |  |  | 2000 | [8 empty] | Centralized repository for data |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Resource Allocation Methodology | 7.3.8.1 | Allocation methodology development and application (Asset management) | 5.3.8.1. |  |  | 2019 |  |  |  |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 1623.2195 | 329.3843 |  | NA |  | NA |  |  | 2844.9162 | 387.3481 |  | NA |  | NA |  |  | 0 | 387.3481 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Resource Allocation Methodology | 7.3.8.2 | Risk reduction scenario development and analysis | 5.3.8.2. |  |  | 2019 | [8 empty] | Allocation methodology development and application (Asset management) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Resource Allocation Methodology | 7.3.8.3 | Risk spend efficiency analysis - not to include PSPS | 5.3.8.3. |  |  | 2019 | [8 empty] | Allocation methodology development and application (Asset management) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Resource Allocation Methodology | 7.3.8.4.1 | Wildfire mitigation personnel | 5.3.8.4.1. |  |  | 2019 |  |  |  |  | 2020 WMP |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 3389.3683 |  | NA |  | NA |  |  | 0 | 4154.9904 |  | NA |  | NA |  |  | 0 | 5229.9904 |  | NA |  | NA | This initiative is foundational to supporting wildfire mitigation efforts. Quantifying an RSE for such a mitigation would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring the effectiveness of that reduction. It supports various initiatives by providing better information to make risk-informed mitigation decisions.
| Other | Resource Allocation Methodology | 7.3.8.4.2 | PSPS mitigation engineering team | 5.3.8.4.2. |  |  | 2020 | [8 empty] | Wildfire mitigation personnel |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.1 | Adequate and trained workforce for service restoration | 5.3.9.4.1 |  |  | 2013 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.2 | Community outreach, public awareness, and communications efforts | 5.3.9.4.2 |  |  | 2013 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.3 | Customer support in emergencies | 5.3.9.4.3 |  |  | 2013 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.4 | Disaster and emergency preparedness plan (CERP) | 5.3.9.4.4 |  |  | 2013 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.5 | Preparedness and planning for service restoration (Mutual assistance and contractors) | 5.3.9.4.5 |  |  | 2013 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.6 | Protocols in place to learn from wildfire events (After action reports) | 5.3.9.4.6 |  |  | 2017 | [8 empty] | Other - Emergency management Operations |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Emergency Planning & Preparedness | 7.3.9.7 | Other - Emergency management Operations | 5.3.9.4.7 |  |  | 2013 |  |  |  |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 2139.689 | 12213.5006 |  | NA |  | NA |  |  | 5472.7429 | 12153.3722 |  | NA |  | NA |  |  | 3077.9117 | 12153.3722 |  | NA |  | NA
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1 | Community engagement | 5.3.10.1. |  |  | 2013 |  |  |  |  | 2020 WMP | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 447.6256 |  | NA |  | NA |  |  | 0 | 447.6256 |  | NA |  | NA |  |  | 0 | 447.6256 |  | NA |  | NA | This initiative is primarily around educating the community about wildfire safety, resiliency and emergency preparedness. Quantifying an RSE for it would be difficult and not beneficial because it cannot be directly tied to reducing a risk driver and measuring effectiveness of that reduction.
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.1.1 | PSPS communication practices | 5.3.6.5.3. |  |  | 2013 |  |  |  |  | 2019 GRC |  | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 4473.8742 | 8227.1676 |  | NA |  | NA |  |  | 3302.1294 | 9386.4925 |  | NA |  | NA |  |  | 2656.4703 | 9188.9101 |  | NA |  | NA
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.2 | Cooperation and best practice sharing with agencies outside California | 5.3.10.2. |  |  | 2013 | [8 empty] | PSPS communication practices |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.3 | Cooperation with suppression agencies | 5.3.10.3. |  |  | 2013 | [8 empty] | PSPS communication practices |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.4 | Forest service and fuel reduction cooperation and joint roadmap | 5.3.10.4. |  |  | 2019 | [8 empty] | Detailed inspections of vegetation around distribution electric lines and equipment (tree trimming) |  | N/A | [26 empty] | 0 | 0 | [6 empty] | 0 | 0 | [6 empty] | 0 | 0
| Other | Stakeholder Cooperation & Community Engagement | 7.3.10.5 | Mylar Balloon Alternative |  |  |  | 2012 |  |  |  |  | 2021 WMP Update | WMPMA | Exceeds | P.U. Code § 451 |  |  | N/A | [26 empty] | 0 | 85.765 |  | NA |  | NA |  |  | 0 | 85.765 |  | NA |  | NA |  |  | 0 | 85.765 |  | NA |  | NA | The current scope of this initiative is focused on outreach efforts to drive adoption of the alternative technology for Mylar balloons. No current deployment of this technology is in place to allow for a calculation of RSEs based on measureable indicators of effectiveness.
x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Notes:
1) Amounts shown above are CPUC-jurisdiction direct costs
2) Only CPUC-related costs are recorded in the Wildfire Mitigation Plan Memorandum Account for recovery.