## TAT WrkSht
[23 empty] | 3 | [5 empty] | 1 | [15 empty] | 4 |  |  |  | 5 |  |  |  | 6 | [8 empty] | 6a |  | 6/6a |  | 9a |  |  |  |  | 7 |  | 9 |  |  |  |  | 7a |  |  | 9b | [5 empty] | 9/9a/9b |  | 7/7a |  |  |  |  | 11 | [5 empty] | 8 | [9 empty] | 10 | [8 empty] | 12 | [5 empty] | Project Completed |  | Project Completed
ID | Site Name | Site Address | Site City | Site Zip | County | Project Status | District | Region | Design Hub | Substation | Circuit | SR# | TD# | Related TD | Customer Want Date | Number of Ports | Rule 29 Project? | Project Level | Engineering Required? | Engineering Feasibility Request | Engineering Complete | Eng | Engineering TAT | Project Received | Site Visit Requested | PA | Pre-Assessment TAT | SI | Site Inquiry TAT | Site Visit Scheduled | Site Visit Complete | FVR Received | SV | Site Visit TAT | FVR | FVR TAT | Submittal Complete | S | Submittal TAT | Sent to Design Hub | Confirmed | Preliminary Planned Received | Preliminary Design Received | P | Prelim TAT | Preliminary Design to Customer | Preliminary Design Approved | PA | Prelim Appr TAT | Final Received Planned | Final Design Received | F | Final TAT | Final Design to Customer | FC | Final to Cust TAT | Invoice Sent | Payment Received | Contract Sent | Contract Received | C | Contract TAT | F-C | Fin-Contr to Cust | SC | Signed Contract TAT | Easement Requested | Easement Sent to Property Owner | Easement Executed | ES | Easement sent TAT | ES2 | Easement Sig TAT | E | Easement TAT | Permit Requested | PR | Permit Request TAT | Permit Received | P | Permit TAT | CR | CR1 | CR2 | CR3 | CR4 | Const Req TAT | E-P | Ease-Perm Req | PWRD Submitted to Civil | Civil Started | Civil Complete | CC | Civil Const TAT | Precon Requested | Trench Requested | Mandrel Requested | Precon Completed ? | PC | Precon TAT | Trench Inspection Complete | Tr | Trench TAT | Mandrel Inspection Complete | Mn | Mandrel TAT | Final Inspection Requested | Final Inspection Complete | CC | Customer Const TAT | FI | Final Insp TAT | Submitted to Regional Scheduling | Electrical Started | ReS | Reg Sched TAT | Electrical Completed | ReC | Region Const TAT | Project Completed | Commissioning Letter | CL | Commision Letter TAT | PR | Project Received | SC | Submittal Complete | YEAR CMPL
1 | Chino Hills | 280 Peyton Dr. | Chino Hills | 91709 | San Bernardino County | 9. Complete | 22 - Montebello | Metro East | Alhambra | [9 empty] | NO |  |  |  |  | 2016-01-14 | 2016-01-19 |  |  | 4 | 4 | 2016-01-19 | 2016-01-21 | 2016-01-26 | 3 | 3 | 4 | 4 | 2016-02-26 | 32 | 32 | 2016-03-02 |  | 2016-09-06 | [14 empty] | 2018-08-13 |  | 2018-08-13 | [7 empty] | 2018-07-30 | 2018-08-27 | 2018-09-11 |  |  | 12 | 12 | 32 | 32 | [6 empty] | 2018-08-13 | [13 empty] | 2020-04-27
2 | Lake Elsinore | 17600 Collier | Lake Elsinore | 92530 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2079620 | 1067675 |  |  | 2 |  |  | NO |  |  |  |  | 2015-12-11 | 2015-12-16 |  |  | 4 | 4 | 2015-12-16 | 2015-12-22 | 2015-12-27 | 5 | 5 | 4 | 4 | 2016-01-27 | 34 | 34 | 2016-01-30 | 2016-01-30 |  | 2016-03-02 | 26 | 26 | 2016-03-04 | 2016-03-11 | 6 | 6 | 2016-04-05 | 2016-04-05 | 18 | 18 | 2016-04-06 | 2 | 2 | 2016-04-06 | 2016-05-06 | 2016-04-06 | 2016-05-06 | 2 | 2 | 41 | 41 | 23 | 23 | 2016-02-29 | 2016-03-29 | 2016-06-09 | -27 |  | 53 | 53 | 74 | 74 | [6 empty] | 2016-03-29 |  | 2016-06-09 | [5 empty] | 2016-06-20 | 2016-07-04 | 2016-07-04 | 11 | 11 | 2016-02-26 | 2016-03-09 | 2016-06-22 | 2016-02-26 | 1 | 1 | 2016-03-09 | 9 | 9 | 2016-06-22 | 1 | 1 | 2016-06-29 | 2016-06-29 | 89 | 89 | 1 | 1 | 2016-07-20 |  |  |  | 2016-08-03 | 11 | 11 | 2016-08-03 |  |  |  | 169 | 169 | 136 | 136 | 2016
3 | San Dimas | 973 1/2 W. Arrow Hwy | San Dimas | 91773 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Alhambra |  |  | 1805300 | 1150864 |  |  | 2 |  |  | NO |  |  |  |  | 2016-02-01 | 2016-02-03 |  |  | 3 | 3 | 2016-02-03 | 2016-02-09 | 2016-02-15 | 5 | 5 | 5 | 5 | 2016-06-02 | 89 | 89 | 2016-06-02 | 2016-06-02 | 2016-07-01 | 2016-07-06 | 25 | 25 | 2016-07-06 | 2016-07-07 | 2 | 2 | 2016-07-27 | 2016-08-12 | 27 | 27 | 2016-08-12 | 1 | 1 | 2016-08-17 | 2016-09-16 | 2016-08-17 | 2016-09-16 | 4 | 4 | 52 | 52 | 23 | 23 | [23 empty] | 2016-08-17 | 2016-09-02 | 2016-09-02 | 13 | 13 | 2016-07-06 | 2016-08-12 | 2016-08-19 | 2016-07-08 | 3 | 3 | 2016-08-12 | 26 | 26 | 2016-08-19 | 1 | 1 | 2016-08-19 | 2016-08-19 | 33 | 33 | 1 | 1 | 2017-02-15 | [6 empty] | 2017-03-23 |  |  |  | 299 | 299 | 211 | 211 | 2017
4 | Rolling Hills | 550 Deep Valley Dr. EV | Rolling Hills Estates | 90274 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2141520 | 1153679 |  |  | 2 |  |  | NO |  |  |  |  | 2016-02-03 | 2016-02-03 |  |  | 1 | 1 | 2016-02-03 | 2016-02-10 | 2016-02-15 | 6 | 6 | 4 | 4 | 2016-03-15 | 30 | 30 | 2016-06-01 | 2016-06-01 | 2016-07-08 | 2016-07-14 | 88 | 88 | 2016-07-14 | 2016-07-14 | 1 | 1 | 2016-07-27 | 2016-09-08 | 41 | 41 | 2016-09-09 | 2 | 2 | 2016-09-07 | 2016-10-07 | 2016-09-07 | 2016-10-07 | -2 |  | 62 | 62 | 23 | 23 | [23 empty] | 2016-09-19 | 2016-10-03 | 2016-10-03 | 11 | 11 | 2016-07-14 | 2016-08-18 | 2016-09-23 | 2016-07-15 | 2 | 2 | 2016-08-18 | 25 | 25 | 2016-09-23 | 1 | 1 | 2016-09-23 | 2016-09-23 | 52 | 52 | 1 | 1 | 2016-11-10 |  |  |  | 2016-12-02 | 17 | 17 | 2016-12-09 |  |  |  | 223 | 223 | 194 | 194 | 2016
5 | Winco Moreno Valley | 12880 Day St | Moreno Valley | 92553 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar |  |  | 2138350 | 1159215 |  |  | 2 |  |  | NO |  |  |  |  | 2016-02-26 | 2016-03-02 |  |  | 4 | 4 | 2016-03-02 | 2016-03-09 | 2016-03-11 | 6 | 6 | 3 | 3 | 2016-05-19 | 60 | 60 | 2016-05-19 | 2016-05-19 | 2016-07-22 | 2016-07-14 | 41 | 41 | 2016-07-14 | 2016-07-14 | 1 | 1 | 2016-08-05 | 2016-08-11 | 21 | 21 | 2016-08-12 | 2 | 2 | 2016-08-17 | 2016-08-25 | 2016-08-17 | 2016-08-25 | 5 | 5 | 31 | 31 | 7 | 7 | [28 empty] | 2016-08-03 | 2017-01-18 | 2017-02-03 | 2016-08-03 | 1 | 1 | 2017-01-18 | 121 | 121 | 2017-02-03 | 1 | 1 | [10 empty] | 2017-05-22 |  |  | 2017-05-22 |  |  |  | 322 | 322 | 263 | 263 | 2017
6 | Bridgeport/Santa Clarita | 23811 Newhall Ranch Rd. | Santa Clarita | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2143030 | 1150821 |  |  | 2 |  |  | NO |  |  |  |  | 2016-03-08 | 2016-03-10 |  |  | 3 | 3 | 2016-03-10 | 2016-03-29 | 2016-04-01 | 14 | 14 | 4 | 4 | 2016-05-02 | 40 | 40 | 2016-05-31 | 2016-05-31 | 2016-07-01 | 2016-06-27 | 41 | 41 | 2016-06-27 | 2016-06-27 | 1 | 1 | 2016-07-22 | 2016-08-08 | 31 | 31 | 2016-08-09 | 2 | 2 | 2016-08-08 | 2016-09-08 | 2016-08-08 | 2016-09-08 | 1 | 1 | 54 | 54 | 24 | 24 | [23 empty] | 2016-08-26 | 2016-09-05 | 2016-09-05 | 7 | 7 | 2016-07-11 | 2016-07-22 | 2016-08-30 | 2016-07-29 | 15 | 15 | 2016-07-22 | -6 |  | 2016-08-30 | 1 | 1 | 2016-09-29 | 2016-09-29 | 59 | 59 | 1 | 1 | 2016-10-19 | 2016-11-09 | 16 | 16 | 2016-11-10 | 17 | 17 | 2016-11-15 |  |  |  | 181 | 181 | 142 | 142 | 2016
7 | Menifee Town Center | 30340 Haun Rd. | Menifee | 92584 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 2150040 |  |  |  | 4 |  |  | NO |  |  |  |  | 2016-03-24 | 2016-07-25 |  |  | 88 | 88 | 2016-04-06 | 2016-04-06 | 2016-04-11 | -79 |  | 4 | 4 | 2016-05-11 | 35 | 35 | 2016-07-11 | 2016-07-11 | 2016-08-11 | 2016-08-12 | 68 | 68 | 2016-08-12 | 2016-08-15 | 2 | 2 |  | 2016-08-15 | 1 | 1 | 2016-08-16 | 2 | 2 | 2016-08-16 | 2016-09-14 | 2016-08-16 | 2016-09-14 | 2 | 2 | 23 | 23 | 22 | 22 | [50 empty] | 2016-08-04 |  |  | 2016-08-05 |  |  |  | 97 | 97 | 63 | 63 | 2016
8 | Walmart/Murietta | 41200 Murrietta Hot Springs Rd. | Murietta | 92562 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2151900 |  |  |  |  | NO |  | NO |  |  |  |  | 2016-03-28 | 2016-03-31 |  |  | 4 | 4 | 2016-03-31 | 2016-04-13 |  | 10 | 10
9 | Walmart/Simi Valley | 2801 Cochran St. | Simi Valley | 93065 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2151900 | 1165085 |  |  | 2 |  |  | NO |  |  |  |  | 2016-03-28 | 2016-03-31 |  |  | 4 | 4 | 2016-03-31 | 2016-04-12 | 2016-04-15 | 9 | 9 | 4 | 4 | 2016-05-16 | 36 | 36 | 2016-06-27 | 2016-06-27 | 2016-07-27 | 2016-07-25 | 51 | 51 | 2016-07-25 | 2016-07-26 | 2 | 2 | 2016-08-16 | 2016-08-18 | 18 | 18 | 2016-08-18 | 1 | 1 | 2016-08-18 | 2016-09-16 | 2016-08-18 | 2016-09-16 | 1 | 1 | 39 | 39 | 22 | 22 | [23 empty] | 2016-10-28 | 2016-11-11 | 2016-11-11 | 11 | 11 | 2016-07-26 | 2016-10-03 | 2016-11-01 | 2016-07-29 | 4 | 4 | 2016-10-03 | 47 | 47 | 2016-11-01 | 1 | 1 | 2016-11-01 | 2016-11-01 | 71 | 71 | 1 | 1 | 2016-11-07 |  |  |  | 2016-11-30 | 18 | 18 | 2016-12-09 |  |  |  | 185 | 185 | 150 | 150 | 2016
10 | Walmart/Redlands | 2050 W. Redlands Blvd., Unit EV | Redlands | 92373 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2151910 | 1148415 |  |  | 3 |  |  | NO |  |  |  |  | 2016-03-29 | 2016-03-31 |  |  | 3 | 3 | 2016-03-31 | 2016-04-13 | 2016-04-18 | 10 | 10 | 4 | 4 | 2016-05-18 | 37 | 37 | 2016-05-24 | 2016-05-24 | 2016-06-24 | 2016-06-14 | 20 | 20 | 2016-06-15 | 2016-08-15 | 44 | 44 | 2016-07-07 | 2016-07-05 | -30 |  | 2016-07-06 | 2 | 2 | 2016-07-18 | 2016-08-18 | 2016-07-18 | 2016-08-18 | 10 | 10 | 4 | 4 | 24 | 24 | 2016-06-24 |  | 2016-08-31 | -8 |  |  |  | 49 | 49 | [8 empty] | 2016-08-31 | [5 empty] | 2016-11-01 | 2016-11-10 | 2016-11-10 | 8 | 8 | 2016-07-15 | 2016-09-29 | 2016-10-28 | 2016-07-27 | 9 | 9 | 2016-09-29 | 47 | 47 | 2016-10-28 | 1 | 1 | 2016-11-04 | 2016-11-04 | 81 | 81 | 1 | 1 | 2016-11-16 |  |  |  | 2017-01-03 | 35 | 35 | 2017-01-10 |  |  |  | 206 | 206 | 170 | 170 | 2017
11 | Walmart/Highland | 4220 E. Highland Ave. | Highland | 92346 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2151910 | 1145135 |  |  | 3 |  |  | NO |  |  |  |  | 2016-03-29 | 2016-03-31 |  |  | 3 | 3 | 2016-03-31 | 2016-04-13 | 2016-04-18 | 10 | 10 | 4 | 4 | 2016-05-18 | 37 | 37 | 2016-05-24 | 2016-05-24 | 2016-06-22 | 2016-06-06 | 14 | 14 | 2016-06-10 | 2016-06-15 | 4 | 4 | 2016-07-01 | 2016-06-23 | 7 | 7 | 2016-06-24 | 2 | 2 | 2016-08-04 | 2016-09-05 | 2016-08-04 | 2016-09-05 | 31 | 31 | 59 | 59 | 23 | 23 | 2016-06-15 |  | 2016-07-05 | -7 |  |  |  | 15 | 15 | [8 empty] | 2016-09-05 | [5 empty] | 2016-08-26 | 2016-09-12 | 2016-09-12 | 12 | 12 | 2016-07-18 | 2016-08-12 | 2016-08-30 | 2016-07-27 | 8 | 8 | 2016-08-12 | 13 | 13 | 2016-08-30 | 1 | 1 | 2016-10-21 | 2016-10-21 | 70 | 70 | 1 | 1 | 2016-11-04 |  |  |  | 2016-12-02 | 21 | 21 | 2016-12-09 |  |  |  | 184 | 184 | 148 | 148 | 2016
12 | Walmart/Rancho Cucamonga | 12521 Foothill Blvd. | Rancho Cucamonga | 91739 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2151910 | 1148039 | [5 empty] | NO |  |  |  |  | 2016-03-29 | 2016-03-31 |  |  | 3 | 3 | 2016-03-31 | 2016-04-13 | 2016-04-15 | 10 | 10 | 3 | 3 | 2016-05-16 | 35 | 35 | 2016-05-24 | 2016-05-24 | 2016-06-24 | 2016-06-10 | 20 | 20 | 2016-06-15 |  |  |  | 2016-07-07 | 2016-06-24 |  |  | 2016-06-27 | 2 | 2 | 2016-07-19 |  | 2016-07-19 |  | 18 | 18 |  |  |  |  | 2016-06-27 |  |  | 2 | 2
13 | Rancho Mirage | 42370 1/2 Bob Hope Dr. | Rancho Mirage | 92770 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2088670 | 1076525 |  |  | 2 |  |  | NO |  |  |  |  | 2015-11-05 | 2015-11-05 |  |  | 1 | 1 | 2015-11-05 | 2015-11-19 | 2015-11-23 | 11 | 11 | 3 | 3 | 2016-01-29 | 62 | 62 | 2016-02-02 | 2016-02-02 |  | 2016-02-26 | 21 | 21 | 2016-02-26 | 2016-02-29 | 2 | 2 |  | 2016-03-28 | 21 | 21 | 2016-03-30 | 3 | 3 | 2016-03-30 | 2016-04-28 | 2016-03-30 | 2016-04-28 | 3 | 3 | 44 | 44 | 22 | 22 | [28 empty] | 2016-03-21 | 2016-04-04 | [7 empty] | 2016-05-25 |  |  |  | 2016-05-25 | 48 | 48 |  |  | 2016-07-05 |  |  |  | 2016-07-25 | 15 | 15 | 2016-07-25 |  |  |  | 188 | 188 | 127 | 127 | 2016
14 | Los Altos Market Place | 2080 N Bellflower Blvd | Long Beach | 90815 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2016-05-24 | 2016-05-25 |  |  | 2 | 2 | 2016-05-25 | 2016-06-01 | 2016-06-03 | 6 | 6 | 3 | 3
15 | Vail Ranch/Temecula | 31727 Temecula Pkwy. | Temecula | 92592 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2187290 | 1169408 |  |  | 2 |  |  | NO |  |  |  |  | 2016-06-10 | 2016-06-13 |  |  | 2 | 2 | 2016-06-13 | 2016-06-16 | 2016-06-20 | 4 | 4 | 3 | 3 | 2016-07-19 | 28 | 28 | 2016-07-12 | 2016-07-12 | 2016-08-09 | 2016-08-02 | 11 | 11 | 2016-08-02 | 2016-08-05 | 4 | 4 | 2016-08-25 | 2016-08-09 | 3 | 3 | 2016-09-09 | 24 | 24 | 2016-08-16 | 2016-09-16 | 2016-08-12 | 2016-09-12 | 4 | 4 | 27 | 27 | 22 | 22 | [23 empty] | 2016-10-14 | 2016-10-28 | 2016-10-28 | 11 | 11 | 2016-08-17 | 2016-10-04 | 2016-10-17 | 2016-08-25 | 7 | 7 | 2016-10-04 | 29 | 29 | 2016-10-17 | 1 | 1 | 2016-10-31 | 2016-10-31 | 54 | 54 | 1 | 1 | 2016-11-03 |  |  |  | 2016-12-02 | 22 | 22 | 2016-12-09 |  |  |  | 131 | 131 | 104 | 104 | 2016
16 | West Hollywood Bristol Farms | 9039 Beverly Dr. | West Hollywood | 90048 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2332660 | 1268773 |  |  | 2 |  |  | NO |  |  |  |  | 2016-06-15 | 2016-06-16 |  |  | 2 | 2 | 2016-06-16 | 2016-06-20 | 2017-04-13 | 3 | 3 | 214 | 214 | 2017-04-20 | 222 | 222 | 2017-04-25 |  | 2017-05-23 | 2017-05-22 | 23 | 23 | 2017-05-22 | 2017-05-30 | 7 | 7 |  | 2017-06-29 | 23 | 23 | 2017-06-29 | 1 | 1 | 2017-06-29 | 2017-07-19 | 2017-06-29 | 2017-08-16 | 1 | 1 | 57 | 57 | 35 | 35 | [23 empty] | 2017-11-17 | 2017-12-04 | 2017-12-04 | 12 | 12 | 2017-10-04 | 2017-11-13 | 2017-12-12 | 2017-10-10 | 5 | 5 | 2017-11-15 | 27 | 27 | 2017-12-12 | 1 | 1 | 2018-01-02 | 2018-01-10 | 71 | 71 | 7 | 7 | 2018-01-29 | 2018-03-13 | 32 | 32 | 2018-03-13 | 32 | 32 | 2018-03-13 |  |  |  | 455 | 455 | 234 | 234 | 2018
17 | adenaadena | 606 Fair Oaks Dr. | South Pasadena | 91030 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Alhambra |  |  | 2188400 | [6 empty] | NO |  |  |  |  | 2016-06-15 | 2016-06-16 |  |  | 2 | 2 | 2016-06-16 | 2016-06-20 | 2016-06-22 | 3 | 3 | 3 | 3
18 | Alton Parkway - Irvine #1 | 15231 Alton Parkway | Irvine | 92618 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2210480 | 1201609 |  |  | 2 |  |  | NO |  |  |  |  | 2016-07-28 | 2016-08-05 |  |  | 7 | 7 | 2016-08-05 | 2016-08-12 | 2017-02-27 | 6 | 6 | 142 | 142 | 2017-03-27 | 173 | 173 | 2016-08-17 | 2016-08-17 | 2016-09-16 | 2016-08-25 | -153 |  | 2016-08-26 | 2016-10-20 | 40 | 40 | 2016-11-10 | 2016-10-20 | 1 | 1 | 2016-10-20 | 1 | 1 | 2018-06-04 | 2018-07-09 | 2018-06-04 | 2018-08-01 | 423 | 423 | 465 | 465 | 43 | 43 | [23 empty] | 2017-01-11 | 2017-02-09 | 2017-02-10 | 23 | 23 | 2016-09-29 | 2016-12-28 |  | 2016-09-30 | 2 | 2 | 2017-01-11 | 74 | 74 | 2017-01-11 |  |  | 2018-08-30 | [5 empty] | 2018-12-31 | [6 empty] | 2019-02-15 |  |  |  | 667 | 667 | 495 | 495 | 2019
19 | Alton Parkway | 15251 Alton Parkway | Irvine | 92618 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2217740 | 1180608 |  |  | 2 |  |  | NO |  |  |  |  | 2016-07-28 | 2016-08-16 |  |  | 14 | 14 | 2016-08-16 | 2016-09-26 | 2016-09-29 | 30 | 30 | 4 | 4 | 2016-10-28 | 67 | 67 | 2016-08-18 | 2016-08-18 | 2016-09-16 | 2016-09-14 | -33 |  | 2016-09-14 | 2016-10-20 | 27 | 27 | 2016-11-10 | 2016-11-15 | 19 | 19 | 2016-11-22 | 6 | 6 | 2018-06-26 | 2018-08-14 | 2018-06-26 | 2018-08-01 | 421 | 421 | 465 | 465 | 27 | 27 | [23 empty] | 2017-01-14 | 2017-02-09 | 2017-02-10 | 20 | 20 | 2016-09-29 | 2017-01-11 | 2017-01-11 | 2016-09-30 | 2 | 2 | 2017-01-13 | 76 | 76 | 2017-01-13 | 3 | 3 | 2018-08-30 | [5 empty] | 2018-12-31 | [6 empty] | 2019-02-15 |  |  |  | 667 | 667 | 601 | 601 | 2019
20 | Alton Parkway - Irvine #2 | 15285 Alton Parkway | Irvine | 92618 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2217750 | 1179805 |  |  | 2 |  |  | NO |  |  |  |  | 2016-07-28 | 2016-08-05 |  |  | 7 | 7 | 2016-08-05 | 2016-08-12 | 2016-08-17 | 6 | 6 | 4 | 4 |  |  |  | 2016-08-17 | 2016-08-17 | 2016-09-16 | 2016-09-09 |  |  | 2016-09-12 | 2016-10-20 | 29 | 29 | 2016-11-10 | 2016-11-15 | 19 | 19 | 2016-11-22 | 6 | 6 | 2018-06-26 | 2018-08-19 | 2018-06-26 | 2018-08-01 | 421 | 421 | 465 | 465 | 27 | 27 | [23 empty] | 2017-01-24 | 2017-02-10 | 2017-02-15 | 17 | 17 | 2016-12-29 | 2017-01-11 | 2017-01-16 | 2016-12-30 | 2 | 2 | 2017-01-13 | 11 | 11 | 2017-01-18 | 3 | 3 | 2018-04-12 | 2018-04-21 | 342 | 342 | 7 | 7 | 2018-12-31 | [6 empty] | 2019-02-15 |  |  |  | 667 | 667 |  |  | 2019
21 | Baker | 72157 Baker Boulevard | Baker | 92309 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2214810 | 1230996 |  |  | 6 |  |  | NO |  |  |  |  | 2016-08-10 | 2016-08-10 |  |  | 1 | 1 | 2016-08-10 | 2016-08-15 | 2016-08-18 | 4 | 4 | 4 | 4 |  |  |  | 2016-12-19 |  | 2017-01-17 | 2017-03-01 |  |  | 2017-03-01 | 2017-03-30 | 22 | 22 |  | 2017-05-23 | 39 | 39 | 2017-05-23 | 1 | 1 | 2017-05-23 | 2017-05-23 | 2018-02-14 | 2018-02-15 | 192 | 192 | 231 | 231 | 2 | 2 | 2017-05-02 | 2017-05-16 | 2017-07-25 | -16 |  | 51 | 51 | 61 | 61 | 2018-02-14 | 192 | 192 |  |  |  | 2017-05-16 | 2017-05-16 | 2018-02-15 |  |  |  | 192 | 192 | 2018-04-24 |  |  |  |  | 2017-09-12 | 2018-02-15 | 2018-02-15 | 2017-10-18 | 27 | 27 | 2018-02-22 | 92 | 92 | 2018-02-22 | 6 | 6 | [6 empty] | 2018-03-28 | 2018-05-07 | 29 | 29 |  |  |  | 2018-06-18 |  |  |  | 484 | 484 |  |  | 2018
22 | One Enterprise | One Enterprise Way | Aliso Viejo | 92656 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2217760 | 1199990 | [5 empty] | NO |  |  |  |  | 2016-08-12 | 2016-08-31 |  |  | 14 | 14 | 2016-08-31 | 2016-09-08 | 2016-09-13 | 7 | 7 | 4 | 4 | 2016-09-13 | 23 | 23 | 2016-09-14 | 2016-09-14 | 2016-11-07 | 2016-10-27 | 33 | 33 | 2016-10-27 | 2017-10-27 | 262 | 262 |  | 2017-10-27 | 1 | 1 | 2017-10-27 | 1 | 1 | 2017-07-10 | 2017-09-25 | 2017-07-10 | 2017-09-13 | -80 |  | -33 |  | 48 | 48 | 2016-10-28 | 2016-11-14 | 2017-09-15 | -261 |  | 220 | 220 | 231 | 231 | [6 empty] | 2016-11-14 |  | 2017-09-15 | [5 empty] | 2017-10-02 | 2017-10-12 | 2017-10-12 | 9 | 9 | 2017-05-05 | 2017-09-21 | 2017-10-02 | 2017-05-11 | 5 | 5 | 2017-09-25 | 98 | 98 | 2017-10-02 | 1 | 1 | 2018-02-06 | 2018-02-15 | 205 | 205 | 8 | 8
23 | BNSF Hostler San Bernardino | 1535 W. 4th St. | San Bernardino | 92411 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2213900 | 1264003 | 1268299 |  | 4 |  |  | NO |  |  |  |  | 2016-08-08 | 2016-08-09 |  |  | 2 | 2 | 2016-08-09 | 2016-08-26 | 2016-08-29 | 14 | 14 | 2 | 2 | 2016-10-05 | 43 | 43 | 2016-10-05 |  | 2016-11-07 | 2017-03-15 | 116 | 116 | 2017-03-15 | 2017-05-16 | 45 | 45 |  | 2017-05-19 | 4 | 4 | 2017-05-19 | 1 | 1 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-10-03 | 1 | 1 | 101 | 101 | 98 | 98 | 2017-05-15 | 2017-06-22 | 2017-08-16 | -5 |  | 40 | 40 | 68 | 68 | 2017-08-23 | 69 | 69 | 2017-09-20 | 21 | 21 | 2017-05-19 | 2017-05-19 | 2017-10-03 | 2017-10-03 | 98 | 98 | 69 | 69 | 2017-10-06 |  |  |  |  | 2017-07-06 | 2017-08-23 |  | 2017-07-13 | 6 | 6 | 2017-09-01 | 37 | 37 |  |  |  | 2017-09-19 | 2017-10-03 | 64 | 64 | 11 | 11 | 2017-10-06 | 2018-01-08 | 67 | 67 | 2018-01-08 | 67 | 67 | 2018-01-09 |  |  |  | 372 | 372 | 330 | 330 | 2018
24 | BNSF Railway/Commerce | 2818 Eastern Ave. | Commerce | 90040 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Alhambra |  |  | 2213910 | [6 empty] | true |  |  |  |  | 2016-08-08 | 2016-08-24 |  |  | 13 | 13 | 2016-08-24 | 2016-09-01 | 2016-09-05 | 7 | 7 | 3 | 3
25 | Buena Park | 6692 Auto Center Dr. | Buena Park | 90621 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 1968900 | 1093074 |  |  | 8 |  |  | NO | 2018-04-20 | 2018-07-11 | 59 | 59 | 2015-03-20 | 2018-04-20 | 59 | 59 | 806 | 806 |  | 2018-05-05 | 2018-05-05 | 11 | 11 | 0 | [7 empty] | 2016-01-06 | [7 empty] | 2016-03-11 | [15 empty] | 2016-03-15 |  | 2016-04-28 | 3 | 3 |  |  | 33 | 33 | [19 empty] | 2016-04-14 |  | 2016-08-26 | 2016-04-28 | 11 | 11 |  |  |  | 2016-08-26 | 1 | 1 | 2016-08-30 | 2016-08-30 | 99 | 99 | 1 | 1 | 2016-09-13 |  |  |  | 2016-10-16 | 24 | 24 | 2016-10-17 |  |  |  | 412 | 412 |  |  | 2016
26 | Main Place Mall/Santa Ana | 2800 3/4 Main St. | Santa Ana | 92705 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2052040 | 1097289 |  |  | 12 |  |  | NO |  |  |  |  | 2015-08-26 | [7 empty] | 2016-10-11 | [10 empty] | 2016-01-21 |  |  | 2016-01-21 | 2016-01-25 | 3 | 3 | 2016-02-18 | 2016-02-18 | 19 | 19 |  |  |  | 2016-03-17 | 2016-03-23 | 2016-03-17 | 2016-03-22 | 21 | 21 | 42 | 42 | 4 | 4 | 2016-03-09 |  | 2016-05-17 | 15 | 15 |  |  | 50 | 50 | [8 empty] | 2016-05-17 | [10 empty] | 2016-07-15 | 2016-08-16 |  | 2016-08-03 | 14 | 14 |  |  |  | 2016-09-21 |  |  |  | 2016-10-11 | 63 | 63 |  |  | 2016-10-28 |  |  |  | 2016-11-28 | 22 | 22 | 2016-12-02 |  |  |  | 333 | 333 |  |  | 2016
27 | Desert Tortoise Casino | 73829 Baseline Rd | Twenty-Nine Palms | 92277 | San Bernardino County | 9. Complete | 84 - 29 Palms | Rurals | SBRO |  |  | 2106460 | 1120008 |  |  | 8 |  |  | true |  |  |  |  | 2015-12-16 | 2016-01-11 |  |  | 19 | 19 | 2016-01-11 | 2016-01-15 | 2016-09-23 | 5 | 5 | 181 | 181 | 2016-10-21 | 223 | 223 | 2016-03-02 | 2017-03-02 | 2016-03-30 | 2016-03-29 | -149 |  | 2016-03-31 | 2016-04-05 | 4 | 4 | 2016-04-26 | 2016-05-04 | 22 | 22 | 2016-05-05 | 2 | 2 | 2016-05-31 | 2016-06-14 | 2016-05-31 | 2016-06-14 | 20 | 20 | 51 | 51 | 11 | 11 | 2016-04-27 |  | 2016-10-03 | -6 |  |  |  | 114 | 114 | [8 empty] | 2016-10-03 | [5 empty] | 2016-08-31 | 2016-09-16 | 2016-09-16 | 13 | 13 | 2016-08-12 | 2016-08-26 | 2016-09-02 | 2016-08-19 | 6 | 6 | 2016-08-26 | 6 | 6 | 2016-09-02 | 1 | 1 | 2016-09-19 | 2016-09-19 | 27 | 27 | 1 | 1 | 2016-11-01 |  |  |  | 2016-11-23 | 17 | 17 | 2016-12-02 |  |  |  | 253 | 253 | 31 | 31 | 2016
28 | San Bernardino Inland Center | 500 Inland Center Drive | San Bernardino | 92408 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2394060 | 1335398 |  |  | 14 |  |  | NO | 2017-08-15 | 2017-10-04 | 37 | 37 | 2016-06-22 | 2017-08-31 | 25 | 25 | 312 | 312 | 2017-08-31 | 2017-09-11 | 2017-09-11 | 8 | 8 | 1 | 1 |  |  |  | 2017-10-06 | 2017-10-06 | 2017-11-03 | 2017-11-15 |  |  | 2017-11-15 | 2017-11-20 | 4 | 4 |  | 2017-12-08 | 15 | 15 | 2018-01-11 | 25 | 25 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-03-10 | 32 | 32 | 80 | 80 | 35 | 35 | 2017-12-13 | 2018-01-10 | 2018-02-21 | 4 | 4 | 31 | 31 | 51 | 51 | [6 empty] | 2018-01-10 |  | 2018-03-10 | [5 empty] | 2018-03-23 |  |  |  |  | 2018-01-03 | 2018-03-12 | 2018-04-04 | 2018-01-08 | 4 | 4 | 2018-03-15 | 49 | 49 | 2018-04-06 | 3 | 3 | 2018-04-23 | 2018-04-27 | 83 | 83 | 5 | 5 | 2018-05-02 | [6 empty] | 2018-06-19 |  |  |  | 520 | 520 |  |  | 2018
29 | Visalia, CA- 207 E Oak Ave | 207 E. Oak Ave. | Visalia | 93291 | Tulare County | 9. Complete | 51 - Tulare | San Joaquin | Ventura |  |  | 2226890 | 1226301 | [5 empty] | NO |  |  |  |  | 2016-08-31 | 2016-09-02 |  |  | 3 | 3 | 2016-09-02 | 2016-09-13 | 2016-09-16 | 8 | 8 | 4 | 4 |  |  |  | 2017-01-12
30 | Corona City Hall | 386 S. Vicentia Ave | Corona | 92882 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Alhambra |  |  | 2235390 | 1217436 |  |  | 2 |  |  | NO |  |  |  |  | 2016-09-21 | 2016-09-21 |  |  | 1 | 1 | 2016-09-21 | 2016-09-26 | 2016-09-28 | 4 | 4 | 3 | 3 | 2016-10-25 | 25 | 25 | 2016-10-20 |  | 2016-11-17 | 2016-12-14 | 37 | 37 | 2016-12-14 | 2016-12-16 | 3 | 3 | 2017-01-11 | 2017-01-11 | 19 | 19 | 2017-01-11 | 1 | 1 | 2017-01-26 | 2017-02-10 | 2017-01-26 |  | 12 | 12 |  |  |  |  | 2017-01-27 |  | 2017-05-11 | 13 | 13 |  |  | 75 | 75 | [14 empty] | 2017-08-04 |  |  |  |  | 2017-07-10 | 2017-07-10 |  | 2017-07-12 | 3 | 3 | 2017-07-12 | 1 | 1 |  |  |  | 2017-08-31 | 2017-09-09 | 45 | 45 | 7 | 7 | 2017-12-13 | 2017-12-21 | 7 | 7 | 2017-12-21 | 7 | 7 | 2017-12-21 |  |  |  | 327 | 327 | 303 | 303 | 2017
31 | Corona Corporate Yard Corona Corporate Yard | 735 Public Safety Way | Corona | 92880 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Alhambra |  |  | 2235390 | 1217503 |  |  | 2 |  |  | YES |  |  |  |  | 2016-09-21 | 2016-09-23 |  |  | 3 | 3 | 2016-09-23 | 2016-09-28 | 2016-10-03 | 4 | 4 | 4 | 4 | 2016-12-14 | 61 | 61 | 2016-10-20 |  | 2016-11-17 | 2016-12-14 | 1 | 1 | 2016-12-15 | 2016-12-15 | 1 | 1 | 2017-01-11 | 2017-01-11 | 20 | 20 | 2017-01-26 | 12 | 12 | 2017-01-26 | 2017-02-10 | 2017-01-26 | 2017-02-10 | 12 | 12 | 42 | 42 | 12 | 12 | 2017-01-06 |  | 2017-05-19 | -4 |  |  |  | 96 | 96 | [8 empty] | 2017-05-19 | [5 empty] | 2017-08-04 |  |  |  |  | 2017-07-14 | 2017-07-16 |  | 2017-07-20 | 5 | 5 | 2017-07-20 | 1 | 1 |  |  |  | 2017-08-31 | 2017-09-04 | 37 | 37 | 3 | 3 | 2017-11-16 | 2017-12-21 | 26 | 26 | 2017-12-21 | 26 | 26 | 2017-12-21 |  |  |  | 327 | 327 | 267 | 267 | 2017
32 | KP Coral Tree | 1210 E. 223rd St., HM | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 2236110 | 1234282 | [5 empty] | true |  |  |  |  | 2016-09-21 | 2016-09-22 |  |  | 2 | 2 | 2016-09-22 | 2016-10-11 | 2016-10-14 | 14 | 14 | 4 | 4 | 2017-02-06 | 99 | 99 | 2017-02-06 |  | 2017-03-07 | 2017-03-15 | 28 | 28 | 2017-03-15 | 2017-03-16 | 2 | 2 |  | 2017-03-31 | 12 | 12 | 2017-03-31 | 1 | 1 | 2017-03-31 |  | 2017-03-17 | 2020-03-17 | -11 |  | 781 | 781 | 780 | 780 | [23 empty] | 2018-04-25 |  |  |  |  | 2018-04-19 | [11 empty] | 2018-04-12 | 2019-01-28 | 203 | 203 | 208 | 208
33 | Santa Monica | 350 Broadway | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2245970 | [6 empty] | true |  |  |  |  | 2016-10-11
34 | TESLA/Redlands | 27651 San Bernardino Ave. | Redlands | 92374 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 2245970 | [6 empty] | NO |  |  |  |  | 2016-10-10 | 2016-10-21 |  |  | 10 | 10 | 2016-10-21 | 2016-11-03 | 2016-11-12 | 10 | 10 | 7 | 7
35 | Redlands, CA- 27320 W. Lugonia Ave. (Target) | 27320 W. Lugonia Ave. | Redlands | 92374 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | true | 2018-12-12 | 2019-02-06 | 41 | 41 | 2018-12-28 | 2019-02-15 | -8 |  | 36 | 36 | 2019-02-15 |  | 2019-02-28
36 | Calabasas, CA - 4799 Commons Way | 4799 Commons Way EVCS1 | Calabasas | 91302 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2246014 | 1892523 |  |  | 20 |  |  | NO | 2017-03-27 | 2017-04-13 | 14 | 14 | 2016-10-10 | 2016-10-21 | 125 | 125 | 10 | 10 | 2016-10-21 | 2016-11-04 | 2016-11-12 | 11 | 11 | 6 | 6 |  |  |  | 2017-06-20 |  | 2017-07-19 | 2017-07-06 |  |  | 2017-07-14 | 2021-04-05 | 959 | 959 | 2021-04-26 | [6 empty] | 2022-03-21 | 2022-03-21 | 2022-03-21 | [8 empty] | 2021-09-07 | 2021-11-15 |  |  | 49 | 49 |  |  | 2022-02-09 |  |  | 2022-02-23 | 10 | 10 | 2021-09-07 | 2021-09-07 | [6 empty] | 2022-01-20 |  |  |  |  | 2021-12-27 | 2022-01-05 | 2022-01-12 | 2018-02-07 | -994 | [7 empty] | 2022-03-25 | 2022-04-05 | 70 | 70 | 8 | 8 | 2022-04-06 |  |  |  | 2022-05-10 | 25 | 25 | 2022-05-10 |  |  |  | 1435 | 1435 |  |  | 2022
37 | TESLA/Commerce Site | 67330 Telegraph Rd. | Commerce | 90040 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Alhambra |  |  | 2246020 | [6 empty] | true |  |  |  |  | 2016-10-10 | 2016-10-21 |  |  | 10 | 10
38 | Corona Hills Plaza | 350 N. McKinley St. | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Alhambra |  |  | 2246020 | [6 empty] | NO |  |  |  |  | 2016-10-10 | 2016-10-21 |  |  | 10 | 10 | 2016-10-21 | 2016-11-02 | 2016-11-06 | 9 | 9 | 3 | 3
39 | TESLA/Thousand Oaks | 100 Promenade Wy. | Thousand Oaks | 9368 | Ventura County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2246030 | [6 empty] | true |  |  |  |  | 2016-10-10 | 2016-10-21 |  |  | 10 | 10 | 2016-10-21 | 2016-11-01 | 2016-11-12 | 8 | 8 | 9 | 9
40 | Commerce, CA - 100 Citaldel Dr | 100 Citadel Dr. | Commerce | 90040 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2780183 | 1629748 |  |  | 20 |  |  | NO | 2019-04-12 | 2019-04-15 | 2 | 2 | 2016-10-10 | 2016-10-21 | 647 | 647 | 10 | 10 | 2016-10-21 | 2016-11-07 | 2016-12-03 | 12 | 12 | 20 | 20 | 2019-11-13 | 808 | 808 |  |  | 2019-12-18 | 2019-12-17 | 25 | 25 | 2019-12-23 |  |  |  |  | 2020-03-20 |  |  | 2020-03-20 | 1 | 1 | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-04-18 | 1 | 1 |  |  | 21 | 21 |  | 2020-05-14 | 2021-03-30 |  |  | 219 | 219 | [8 empty] | 2020-03-20 |  | 2021-03-30 | [5 empty] | 2021-04-21 | 2021-05-04 |  |  |  | 2021-03-30 | [11 empty] | 2021-04-27 | 2021-05-27 | 43 | 43 | 23 | 23 | 2021-05-11 |  |  |  | 2021-07-09 | 42 | 42 | 2021-07-09 |  |  |  | 1225 | 1225 | 418 | 418 | 2021
41 | BNSF - Hobart Yard | 4940 Sheila St. | Commerce | 90040 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2260250 | 1222205 |  |  | 2 |  |  | NO |  |  |  |  | 2016-11-11 | 2016-11-11 |  |  | 1 | 1 | 2016-11-11 | 2016-11-17 | 2016-11-19 | 5 | 5 | 2 | 2 | 2016-11-30 | 14 | 14 | 2016-11-30 |  | 2016-12-29 | 2017-01-03 | 25 | 25 | 2017-03-13 | 2017-02-06 | -26 |  | 2017-03-02 | 2017-03-13 | 26 | 26 | 2017-06-07 | 63 | 63 | 2017-06-07 | 2017-06-08 | 2017-06-07 | 2017-06-08 | 63 | 63 | 89 | 89 | 2 | 2 | 2017-05-12 | 2017-05-31 | 2017-07-10 | 45 | 45 | 29 | 29 | 42 | 42 | [6 empty] | 2017-05-31 |  | 2017-07-10 | [6 empty] | 2017-09-01 | 2017-09-06 |  |  | 2017-06-01 | 2017-07-24 |  | 2017-06-07 | 5 | 5 | 2017-07-31 | 39 | 39 | 2017-09-09 |  |  |  | 2017-09-09 | 72 | 72 |  |  | 2017-09-11 | 2017-10-19 | 29 | 29 | 2017-10-20 | 30 | 30 | 2017-10-20 |  |  |  | 246 | 246 | 233 | 233 | 2017
42 | 1 Polaris Way | 1 Polaris Way | Aliso Viejo | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2258440 | 1215082 |  |  | 4 |  |  | NO |  |  |  |  | 2016-11-02 | 2016-11-07 |  |  | 4 | 4 | 2016-11-07 | 2016-11-10 | 2016-11-14 | 4 | 4 | 3 | 3 | 2016-12-02 | 23 | 23 | 2016-12-03 |  | 2017-01-03 | 2017-01-05 | 25 | 25 | 2017-01-10 | 2017-01-16 | 5 | 5 | 2017-02-06 | 2017-06-27 | 117 | 117 | 2017-06-27 | 1 | 1 | 2018-03-09 | 2018-04-04 | 2018-03-09 |  | 184 | 184 | [27 empty] | 2017-07-17 | 2017-08-11 | 2017-08-14 | 21 | 21 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 1 | 1 | 2017-07-14 | 4 | 4 | 2017-07-11 | 1 | 1 | 2018-02-26 | 2018-03-03 | 169 | 169 | 5 | 5 | 2018-04-05 | [6 empty] | 2018-04-27 |  |  |  | 388 | 388 | 366 | 366 | 2018
43 | 2 Polaris Way | 2 Polaris Wy. | Aliso Viejo | 92677 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2258440 |  |  |  | 4 |  |  | NO |  |  |  |  | 2016-11-02 | 2016-11-07 |  |  | 4 | 4 | 2016-11-10 | 2016-11-10 | 2016-11-15 | 4 | 4 | 4 | 4
44 | 3 Polaris Way | 3 Polaris Way | Aliso Viejo | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2259700 | 1221526 |  |  | 4 |  |  | NO |  |  |  |  | 2016-11-02 | 2016-11-02 |  |  | 1 | 1 | 2016-11-02 | 2016-11-10 | 2016-11-15 | 7 | 7 | 4 | 4 | 2016-12-03 | 23 | 23 | 2016-12-03 |  | 2017-01-03 | 2017-01-31 | 42 | 42 | 2017-01-31 | 2017-08-08 | 136 | 136 |  | 2017-08-08 | 1 | 1 | 2017-08-08 | 1 | 1 | 2018-03-29 | 2018-04-04 | 2018-03-29 |  | 168 | 168 | [27 empty] | 2017-10-26 | 2017-10-30 | 2017-11-17 | 17 | 17 | 2017-07-11 | 2017-10-10 |  | 2017-08-15 | 26 | 26 | 2017-10-13 | 44 | 44 |  |  |  | 2018-03-02 | 2018-03-06 | 171 | 171 | 3 | 3 | 2018-04-05 | 2018-04-17 | 9 | 9 | 2018-04-17 | 9 | 9 | 2018-05-10 |  |  |  | 397 | 397 | 374 | 374 | 2018
45 | 4 Polaris Way | 4 Polaris Way | Aliso Viejo | 92677 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2259710 | [6 empty] | NO |  |  |  |  | 2016-11-02 | 2016-11-02 |  |  | 1 | 1 | 2016-11-02 | 2016-11-10 | 2016-11-15 | 7 | 7 | 4 | 4 | 2017-07-25 | 190 | 190 | 2017-07-25
46 | 5 Polaris Way | 5 Polaris Way | Aliso Viejo | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2259710 | 1223433 |  |  | 4 |  |  | NO |  |  |  |  | 2016-11-02 | 2016-11-02 |  |  | 1 | 1 | 2016-11-02 | 2016-11-10 | 2016-11-15 | 7 | 7 | 4 | 4 | 2016-12-04 | 23 | 23 | 2016-12-03 |  | 2017-01-03 | 2017-01-09 | 26 | 26 | 2017-01-11 | 2017-10-05 | 192 | 192 |  | 2017-10-05 | 1 | 1 | 2017-10-06 | 2 | 2 | 2018-03-29 | 2018-04-04 | 2018-03-29 |  | 126 | 126 | [27 empty] | 2017-10-26 | 2017-10-30 | 2017-11-01 | 5 | 5 | 2017-10-10 | 2017-10-10 |  | 2017-10-12 | 3 | 3 | 2017-10-12 | 1 | 1 |  |  |  | 2018-02-26 | 2018-03-05 | 105 | 105 | 6 | 6 | 2018-04-05 | [6 empty] | 2018-05-03 |  |  |  | 392 | 392 | 369 | 369 | 2018
47 | HASBC/Virginia Way #3 - Barstow | 501 E. Virginia Way | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2269060 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2017-07-05 |  |  | 157 | 157 | 2017-07-05 | 2017-07-12 | 2016-12-21 | 6 | 6 | -146 |  |  |  |  | 2017-02-07 |  | 2017-02-08
48 | HASBC/Virgina Way #2 - Barstow | 760 E. Virginia Way P5193941 | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2269060 | 1319510 | [5 empty] | NO |  |  |  |  | 2017-09-22 | 2016-12-08 |  |  | -207 |  | 2016-12-08 | 2016-12-16 | 2016-12-18 | 7 | 7 | 1 | 1 | 2017-09-22 | 1 | 1 | 2017-09-27 | 2017-09-28 | 2017-10-25 | 2017-10-06 | 11 | 11 | 2017-10-09 | 2017-10-11 | 3 | 3 | 2017-11-01 | 2017-10-31 | 15 | 15 | 2017-10-31 | 1 | 1 | 2017-10-31 |  | 2017-10-31 |  | 1 | 1 |  |  |  |  | 2017-10-12 | 2017-10-31 | 2018-04-12 | -14 |  | 118 | 118 | 131 | 131 | [6 empty] | 2017-10-31 | [7 empty] | 2018-07-10 |  |  |  |  | 2017-12-06 |  |  | 2017-12-06 | 1 | 1 | [7 empty] | 2018-10-02 | 215 | 215
49 | HASBC/Virginia Way-Barstow | 764 E. Virgina Wy. | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2276560 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-18 | 7 | 7 | 1 | 1
50 | HASBC - Hesperia #1 | 17426 Sequoia Ave. | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2277380 | 1257005 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-27 | 7 | 7 | 8 | 8 |  |  |  | 2017-02-13 |  |  | 2017-03-15 |  |  | 2017-03-15 | 2017-03-15 | 1 | 1 |  | 2017-05-01 | 34 | 34 | 2017-05-03 | 3 | 3 | 2018-08-03 |  | 2018-08-03 |  | 330 | 330 |  |  |  |  | 2018-02-15 | 2018-02-22 | 2018-04-12 | 209 | 209 | 36 | 36 | 41 | 41 | [6 empty] | 2018-02-22 | [7 empty] | 2018-02-02 | 2018-02-13 | 2018-02-13 | 8 | 8 | 2017-12-26 | 2018-01-18 |  | 2018-01-03 | 7 | 7 | 2018-01-31 | 21 | 21 |  |  |  | 2018-07-17 | 2018-07-19 | 148 | 148 | 3 | 3
51 | HASBC - Hesperia 2 | 15188 Sequoia St. | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2277410 | 1289678 | 1311793 |  |  |  |  | NO |  |  |  |  | 2016-11-29 | 2017-06-20 |  |  | 146 | 146 | 2017-06-20 | 2017-06-21 | 2016-12-29 | 2 | 2 | -125 |  |  |  |  | 2017-04-25 |  | 2017-05-24 | 2017-06-05 |  |  | 2017-06-05 | 2017-07-20 | 34 | 34 | 2017-08-15 | 2017-09-27 | 50 | 50 | 2017-09-27 | 1 | 1 | 2017-09-27 |  | 2017-09-27 |  | 1 | 1 |  |  |  |  | 2017-08-08 | 2018-02-22 |  | -37 | [11 empty] | 2017-09-27 | [7 empty] | 2018-08-03 |  | 2018-09-19 | 34 | 34 | 2018-02-26 |  |  | 2018-02-28 | 3 | 3 | [7 empty] | 2018-10-11 | 164 | 164
52 | HASBC - Victorville #1 | 14469 Rodeo Dr. | Victorville | 92395 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2277390 | 1253180 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-20 | 7 | 7 | 3 | 3 |  |  |  | 2017-02-08 | [49 empty] | 2018-09-21
53 | HASBC - County Office | 715 E. Brier Dr. | San Bernardino | 92411 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2277400 | 1240801 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-27 | 7 | 7 | 8 | 8 |  |  |  | 2017-02-08 |  | 2017-03-10 | 2017-03-10 |  |  | 2017-03-13 | 2017-04-12 | 23 | 23 |  | 2018-03-27 | 250 | 250 | 2018-03-29 | 3 | 3 | 2018-04-02 |  | 2018-04-02 |  | 5 | 5 | [27 empty] | 2018-01-18 | 2018-02-01 | 2018-02-09 | 17 | 17 | 2017-09-27 | 2017-11-27 | 2018-01-08 | 2017-11-22 | 41 | 41 | 2017-11-29 | 6 | 6 | 2018-01-10 | 3 | 3
54 | HASBC - Fontana | 8181 Redwood Ave. | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 2277350 | 1265037 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-12 |  |  | 10 | 10 | 2016-12-12 | 2016-12-22 | 2016-12-27 | 9 | 9 | 4 | 4 |  |  |  | 2017-04-25 |  | 2017-05-24 | 2017-05-18 |  |  | 2017-05-18
55 | HASBC - San Bernardino Arrowhead Woods | 1650 W. 16th St. | San Bernardino | 92411 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2277360 | 1362168 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2017-06-20 |  |  | 146 | 146 | 2017-06-20 | 2017-06-30 | 2017-08-25 | 9 | 9 | 41 | 41 |  |  |  | 2017-04-25 |  | 2018-02-14 | 2018-03-05 |  |  | 2018-03-05 | 2018-03-06 | 2 | 2 | 2018-03-27 | 2018-03-19 | 10 | 10 | 2018-03-19 | 1 | 1 | 2018-03-19 |  | 2018-03-19 |  | 1 | 1 |  |  |  |  | 2018-03-27 | 2018-03-29 | 2018-12-06 | 7 | 7 | 181 | 181 | 183 | 183 | [6 empty] | 2018-03-19 | [24 empty] | 2018-10-30
56 | HASBC - Twin Peaks | 707 Grandview Rd. | Twin Peaks | 92391 | San Bernardino County | 9. Complete | 40 - Arrowhead | Rurals | SBRO |  |  | 2277370 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-21 |  |  | 17 | 17 | 2016-12-21 | 2016-12-22 | 2017-01-03 | 2 | 2 | 9 | 9
57 | Community Hospital of San Bernardino | 1805 Medical Center Dr. | San Bernardino | 92411 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2279050 | 1333837 |  |  | 3 |  |  | NO |  |  |  |  | 2016-12-22 | 2016-12-27 |  |  | 4 | 4 | 2016-12-27 | 2017-01-04 | 2017-01-08 | 7 | 7 | 3 | 3 | 2017-02-02 | 31 | 31 | 2017-02-07 |  | 2017-11-27 | 2017-11-20 | 208 | 208 | 2017-11-20 | 2017-11-21 | 2 | 2 | 2017-12-14 | 2017-12-01 | 9 | 9 | 2017-12-01 | 1 | 1 |  | 2018-03-26 | 2018-01-24 | 2018-04-30 | 39 | 39 | 115 | 115 | 69 | 69 | 2017-12-01 | 2018-01-08 | 2018-04-06 | 1 | 1 | 65 | 65 | 91 | 91 | [6 empty] | 2018-01-08 |  | 2018-04-30 | [6 empty] | 2018-05-04 | 2018-05-07 |  |  | 2018-01-05 |  |  | 2018-01-07 | 1 | 1 | 2017-12-15 | -16 |  | 2017-12-15 |  |  | 2018-01-10 | 2018-02-05 | 22 | 22 | 19 | 19 | 2018-05-07 | [6 empty] | 2018-06-05 |  |  |  | 379 | 379 | 349 | 349 | 2018
58 | HASBC/Yucaipa | 13629 3rd St. | Yucaipa | 92399 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2279670 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-23 |  |  | 19 | 19 | 2016-12-23 | 2016-12-23 | 2017-01-09 | 1 | 1 | 12 | 12 |  |  |  | 2017-02-07 |  | 2017-02-09 |  |  |  | 2017-01-11
59 | HASBC/Virginia Way-Barstow | 762 E. Virginia Wy. | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2279780 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-27 | 7 | 7 | 8 | 8
60 | HASBC/Virginia Way - Barstow | 763 E. Virginia Wy. | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2279820 | [6 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-27 | 7 | 7 | 8 | 8
61 | HASBC/Virginia Way - Barstow #1 | 755 E. Virginia Way P5193935 | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2280070 | 1257062 | [5 empty] | NO |  |  |  |  | 2016-11-29 | 2016-12-08 |  |  | 8 | 8 | 2016-12-08 | 2016-12-16 | 2016-12-27 | 7 | 7 | 8 | 8 | 2017-02-07 | 51 | 51 | 2017-02-07 |  |  | 2017-05-17 | 72 | 72 | 2017-05-17 | 2017-05-17 | 1 | 1 |  | 2017-11-14 | 130 | 130 | 2017-11-15 | 2 | 2 | 2018-07-23 |  | 2018-07-23 |  | 180 | 180 | [27 empty] | 2018-07-10 |  |  |  |  | 2017-12-01 | 2018-03-05 |  | 2017-12-06 | 4 | 4 | 2018-03-07 | 66 | 66 |  |  |  |  | 2018-10-02 | 218 | 218
62 | West Hollywood | 838 N. Doheny Dr. | West Hollywood | 90069 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2283770 | [6 empty] | true |  |  |  |  | 2017-01-10 | 2017-01-11 |  |  | 2 | 2 | 2017-01-11 | 2017-01-19 | 2017-01-23 | 7 | 7 | 3 | 3
63 | Bridgeport Market Place Santa Clarita | 24001 Newhall Ranch Rd. | Santa Clarita | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2284900 | 1274657 |  |  | 24 |  |  | true | 2017-03-27 | 2017-04-12 | 13 | 13 | 2017-01-12 | 2017-01-13 | 64 | 64 | 2 | 2 | 2017-01-13 | 2017-01-19 | 2017-01-23 | 5 | 5 | 3 | 3 |  |  |  | 2017-05-25 |  | 2017-06-22 | 2017-06-09 |  |  | 2017-06-09 | 2017-06-21 | 9 | 9 | 2017-07-13 | 2017-07-17 | 19 | 19 | 2017-07-17 | 1 | 1 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-24 | 2 | 2 | 24 | 24 | 5 | 5 | 2017-06-27 | 2017-11-17 | 2017-12-14 | -15 |  | 20 | 20 | 123 | 123 | 2018-02-14 | 153 | 153 | 2018-02-23 | 8 | 8 | 2017-07-18 | 2017-07-18 | 2017-12-14 | 2018-02-23 | 159 | 159 | 153 | 153 | 2018-02-08 |  | 2018-02-23 | 12 | 12 | 2017-12-29 | 2018-01-29 |  | 2018-01-04 | 5 | 5 | 2018-02-07 | 25 | 25 |  |  |  | 2018-02-09 | 2018-02-24 | 41 | 41 | 11 | 11 | 2018-03-05 | 2018-03-14 | 8 | 8 | 2018-03-30 | 20 | 20 | 2018-03-30 |  |  |  | 317 | 317 |  |  | 2018
64 | Fountain Valley Expansion | 17940 Newhope St. | Fountain Valley | 92708 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2288490 | 1272623 |  |  | 16 |  |  | true | 2017-05-12 | 2017-05-15 | 2 | 2 | 2017-01-18 | 2017-01-24 | 80 | 80 | 5 | 5 | 2017-01-24 | 2017-02-08 | 2017-02-12 | 12 | 12 | 3 | 3 |  |  |  | 2017-04-17 |  | 2017-05-15 | 2017-05-26 |  |  | 2017-05-26 | 2017-05-28 | 1 | 1 | 2017-06-19 | 2017-06-29 | 24 | 24 | 2017-07-25 | 19 | 19 | 2017-07-25 | 2017-08-24 | 2017-07-25 | 2017-08-15 | 19 | 19 | 57 | 57 | 16 | 16 | [12 empty] | 2017-09-08 | [10 empty] | 2017-08-30 | [16 empty] | 2017-08-30 | 2017-09-05 |  |  | 5 | 5 | 2017-09-21 | [6 empty] | 2017-10-22 |  |  |  | 198 | 198 |  |  | 2017
65 | Barstow Site Expansion | 2812 Lenwood Rd. | Barstow | 92311 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2288490 | 1259796 |  |  | 16 |  |  | true | 2020-10-19 |  |  |  | 2017-01-20 | 2017-01-24 |  |  | 3 | 3 | 2017-01-24 | 2017-02-01 | 2017-02-06 | 7 | 7 | 4 | 4 | 2017-04-17 | 62 | 62 | 2017-04-17 | 2017-04-17 | 2017-05-15 | 2017-04-24 | 6 | 6 | 2017-04-24 | 2017-04-26 | 3 | 3 | 2017-05-15 | 2017-05-01 | 4 | 4 | 2017-05-01 | 1 | 1 | 2017-05-01 | 2017-05-11 | 2017-05-01 | 2017-05-07 | 1 | 1 | 8 | 8 | 5 | 5 | 2017-05-01 | 2017-05-03 | 2017-05-10 | 1 | 1 | 6 | 6 | 8 | 8 | [6 empty] | 2017-05-01 |  | 2017-05-10 | [5 empty] | 2017-05-04 | 2017-05-05 | 2017-05-05 | 2 | 2 |  |  |  | 2017-05-15 |  |  | 2017-05-15 | 1 | 1 | 2017-05-15 |  |  |  | 2017-05-15 |  |  |  |  | 2017-05-16 | 2017-05-18 | 3 | 3 | 2017-05-18 | 3 | 3 | 2017-05-18 |  |  |  | 85 | 85 | 24 | 24 | 2017
66 | Commons at Gallatin Way - CA086 Downey | 9588 Lakewood Blvd. | Downey | 90240 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2289070 | 1313899 |  |  | 12 |  |  | true | 2017-03-27 | 2017-04-13 | 14 | 14 | 2017-01-20 | 2017-07-06 | -61 |  | 120 | 120 | 2017-07-07 | 2017-07-14 | 2017-07-19 | 7 | 7 | 4 | 4 |  |  |  | 2017-12-15 |  | 2017-08-30 | 2017-09-16 |  |  | 2017-09-16 | 2017-09-19 | 2 | 2 | 2017-10-10 | 2017-10-19 | 23 | 23 | 2017-10-25 | 5 | 5 | 2017-10-25 | 2017-11-14 | 2017-10-25 | 2017-11-10 | 5 | 5 | 39 | 39 | 13 | 13 | [9 empty] | 2018-02-07 | 76 | 76 | 2018-02-15 | 7 | 7 | [6 empty] | 80 | 80 | 2018-02-15 |  |  |  |  | 2017-12-15 | 2018-02-23 | 2018-03-09 | 2017-12-18 | 2 | 2 | 2018-02-21 | 48 | 48 |  |  |  | 2018-03-23 | 2018-03-28 | 74 | 74 | 4 | 4 | 2018-04-05 | [6 empty] | 2018-05-18 |  |  |  | 346 | 346 |  |  | 2018
67 | Marina Pacifica/Long Beach | 6272 E. Pacific Coast Highway | Long Beach | 90803 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 2288930 | 1328407 | [5 empty] | NO | 2017-03-27 | 2017-04-13 | 14 | 14 | 2017-01-20 | 2017-03-14 | 23 | 23 | 38 | 38 | 2017-03-14 | 2017-03-23 | 2017-03-26 | 8 | 8 | 2 | 2 | 2017-06-28 | 114 | 114 | 2017-06-29 | 2017-06-30 | 2017-09-22 | 2017-09-22 | 63 | 63 | 2017-09-22 | 2017-10-13 | 16 | 16 | 2017-10-24 | 2017-11-29 | 34 | 34 | 2017-11-29 | 1 | 1 | 2017-11-30 |  | 2017-11-30 |  | 2 | 2
68 | Westlake Village CBRE - Westlake Village 1 | 3011 Townsgate | Westlake Village | 91361 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2288600 | 1295256 |  |  | 2 |  |  | true |  |  |  |  | 2017-01-23 | 2017-01-24 |  |  | 2 | 2 | 2017-01-24 | 2017-01-26 | 2017-01-30 | 3 | 3 | 3 | 3 | 2017-06-12 | 101 | 101 | 2017-06-13 |  |  | 2018-05-10 | 239 | 239 | 2018-05-10 | 2018-05-14 | 3 | 3 |  | 2018-05-14 | 1 | 1 | 2018-05-14 | 1 | 1 | 2017-08-09 | 2017-08-21 | 2017-08-09 |  | -199 | [28 empty] | 2019-05-29 |  | 2019-06-24 | 19 | 19 | 2017-12-11 | 2018-08-27 |  | 2017-12-13 | 3 | 3 | [6 empty] | 2018-04-12 | 2019-07-29 | 426 | 426 | 338 | 338 | 2019-08-02 | [6 empty] | 2019-09-03 |  |  |  | 682 | 682 | 582 | 582 | 2019
69 | Hesperia Target | 12795 Main St. | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2294589 | 1550961 |  |  | 16 |  |  | true | 2017-03-27 | 2019-01-17 | 474 | 474 | 2017-02-03 | 2018-12-13 | 26 | 26 | 485 | 485 |  |  | 2019-01-16 | [7 empty] | 2019-05-15 | 2019-05-20 | 2019-06-18 | 2019-06-18 |  |  | 2019-06-19 | 2019-06-28 | 8 | 8 | 2019-07-22 | 2019-07-18 | 15 | 15 | 2019-07-18 | 1 | 1 | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-06-22 | 236 | 236 | 253 | 253 | 4 | 4 | 2019-07-23 | 2020-07-06 | 2020-09-30 | 4 | 4 | 62 | 62 | 306 | 306 |  |  |  | 2019-07-29 |  |  | 2020-06-17 |  | 2020-09-30 | 2020-09-30 |  |  |  |  | 2020-09-30 |  | 2020-10-14 | 11 | 11 | [13 empty] | 2020-11-16 |  |  |  |  | 2020-10-13 |  |  |  | 2020-11-12 | 22 | 22 | 2020-11-12 |  |  |  | 978 | 978 |  |  | 2020
70 | Palm Desert, CA- 34380/34500 Monterey Ave. | 34380/34500 Monterey Ave. | Palm Desert | 92211 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2294620 | 1301351 | [5 empty] | true | 2017-03-27 | 2017-05-02 | 27 | 27 | 2017-02-03 | 2017-06-26 | -40 |  | 102 | 102 | 2017-06-26 | 2017-06-30 |  | 5 | 5 |  |  | 2017-07-19 | 119 | 119 | 2017-07-21 | 2017-07-27 | 2017-08-18 | 2017-08-23 | 26 | 26 | 2017-08-23
71 | Tustin - The District | 2437 Park Ave. | Tustin | 92782 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-02-03 | 2017-02-06 |  |  | 2 | 2 | 2017-02-06 | 2017-02-10 | 2017-02-12 | 5 | 5 | 1 | 1
72 | Castaic Old Road | 31785 The Old Rd. | Castaic | 91384 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2294480 | [6 empty] | NO |  |  |  |  | 2017-02-02 | 2017-02-06 |  |  | 3 | 3 | 2017-02-06 | 2017-02-17 | 2017-03-12 | 10 | 10 | 16 | 16
73 | Rialto Marketplace | 1310 S Riverside Ave. | Rialto | 92376 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2301340 | 1276520 |  |  | 2 |  |  | true |  |  |  |  | 2017-02-21 | 2017-02-21 |  |  | 1 | 1 | 2017-02-21 | 2017-03-02 | 2017-03-02 | 8 | 8 | 1 | 1 | 2017-05-08 | 55 | 55 | 2017-05-10 | 2017-05-16 | 2017-06-14 | 2017-06-20 | 32 | 32 | 2017-06-20 | 2017-07-13 | 18 | 18 | 2017-08-07 | 2017-08-11 | 22 | 22 | 2017-08-11 | 1 | 1 | 2017-08-15 | 2017-09-01 | 2017-08-15 | 2017-08-16 | 3 | 3 | 25 | 25 | 2 | 2 | 2017-08-11 |  | 2017-11-20 | 1 | 1 |  |  | 72 | 72 | 2017-09-25 | 32 | 32 | 2017-11-30 | 49 | 49 |  |  | 2017-11-20 | 2017-11-30 |  |  | 32 | 32 | 2017-09-25 | 2017-10-10 | 2017-10-10 | 12 | 12 | 2017-08-18 | 2017-09-20 | 2017-09-20 | 2017-08-24 | 5 | 5 | 2017-09-21 | 21 | 21 | 2017-09-21 | 2 | 2 | 2017-11-13 | 2017-11-15 | 64 | 64 | 3 | 3 | 2017-11-17 | 2017-12-21 | 25 | 25 | 2017-12-22 | 26 | 26 | 2017-12-22 |  |  |  | 219 | 219 | 165 | 165 | 2017
74 | Culver City Expansion | 6000 Sepulveda Blvd | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2308600 |  |  |  | 16 |  |  | NO |  | 2021-04-26 |  |  | 2017-03-08 | 2017-03-08 | 1066 | 1066 | 1 | 1 | 2017-03-08 | 2017-03-15 | 2017-03-18 | 6 | 6 | 3 | 3 | 2017-04-17 | 29 | 29 | 2017-04-17 | 2017-04-17 | 2017-05-10 | 2017-04-19 | 3 | 3 | 2017-04-19 | 2017-04-19 | 1 | 1 | 2017-05-15 | 2017-04-19 | 1 | 1 | 2017-04-19 | 1 | 1 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 1 | 1 | 1 | 1 | 1 | 1 | [28 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 1 | 1 | 2017-04-19 | 1 | 1 | 2017-04-19 | 1 | 1 | 2017-04-19 | 2017-04-19 | 1 | 1 | 1 | 1 | 2017-04-19 | 2017-04-19 | 1 | 1 | 2017-04-19 | 1 | 1 | 2017-04-19 |  |  |  | 31 | 31 | 3 | 3 | 2017
75 | Yermo I | 35858 Ghost Town Rd | Yermo | 92398 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2307680 | [6 empty] | true |  |  |  |  | 2017-03-07 | 2017-03-07 |  |  | 1 | 1 | 2017-03-07 | 2017-03-08 | 2017-03-12 | 2 | 2 | 3 | 3
76 | Victor Valley Mall | 14400 Bear Valley Rd #735 | Victorville | 92392 | San Bernardino County | 9. Complete | 73 - Victorville | Rurals | SBRO |  |  | 2305980 | [6 empty] | true |  |  |  |  | 2017-03-02 | 2017-03-02 |  |  | 1 | 1 | 2017-03-02 | 2017-03-08 | 2017-03-12 | 5 | 5 | 3 | 3
77 | The Commons at Ultra Gas & Mart | 71808 1/4 Baker Blvd | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2305970 | 1281347 |  |  | 40 |  |  | NO | 2017-03-27 | 2017-04-12 | 13 | 13 | 2017-03-02 | 2017-03-02 | 30 | 30 | 1 | 1 | 2017-03-02 | 2017-03-08 | 2017-03-19 | 5 | 5 | 8 | 8 |  |  |  | 2017-05-31 |  | 2017-06-28 | 2017-06-28 |  |  | 2017-06-29 | 2017-07-06 | 6 | 6 | 2017-07-31 | 2017-07-31 | 18 | 18 | 2017-07-31 | 1 | 1 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-10-24 | 22 | 22 | 79 | 79 | 41 | 41 | 2017-07-17 | 2017-08-10 | 2017-09-01 | -11 |  | 17 | 17 | 35 | 35 | [6 empty] | 2017-08-10 |  | 2017-10-24 | [5 empty] | 2017-10-02 | 2017-10-11 | 2017-10-11 | 8 | 8 | 2017-08-13 | 2017-09-26 |  | 2017-08-16 | 3 | 3 | 2017-10-11 | 41 | 41 |  |  |  | 2017-10-12 | 2017-10-26 | 54 | 54 | 11 | 11 | 2017-10-27 | [6 empty] | 2017-11-14 |  |  |  | 184 | 184 |  |  | 2017
78 | Country Hills Shopping Center Torrance | 2905 Rolling Hills Rd | Torrance | 90505 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2305430 | [6 empty] | NO |  |  |  |  | 2017-03-01 | 2017-03-01 |  |  | 1 | 1 | 2017-03-01 | 2017-03-10 |  | 8 | 8 | [5 empty] | 2018-01-31 |  | 2018-02-26 | 2018-02-23 |  |  | 2018-02-23 | 2018-05-09 | 54 | 54 |  | 2018-06-01 | 18 | 18 | 2018-06-01 | 1 | 1 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-13 | 1 | 1 | 26 | 26 | 9 | 9 | 2018-05-16 | 2018-08-27 | 2018-09-26 | -13 |  | 23 | 23 | 96 | 96 | [6 empty] | 2018-06-01 |  | 2018-09-26 | [5 empty] | 2018-08-22 |  | 2018-09-25 | 25 | 25 | 2018-07-09 | [11 empty] | 2018-09-24 | 2018-09-26 | 58 | 58 | 3 | 3
79 | Montebello Plaza 1 | 2500 W. Via Campo | Montebello | 90640 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Alhambra |  |  | 2305400 | [6 empty] | NO |  |  |  |  | 2017-03-01 | 2017-03-01 |  |  | 1 | 1 | 2017-03-01 | 2017-03-10 | 2017-03-14 | 8 | 8 | 3 | 3
80 | Cudahy Plaza | 7907 S Atlantic Ave | Cudahy | 90201 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2305350 | [6 empty] | true |  |  |  |  | 2017-03-01 | 2017-03-01 |  |  | 1 | 1 | 2017-03-01 | 2017-03-10 | 2017-03-14 | 8 | 8 | 3 | 3
81 | Oxnard Expansion | 2751 Park View Ct #261 | Oxnard | 93036 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 2310960 | 1258431 |  |  | 18 |  |  | true |  |  |  |  | 2017-03-13 | 2017-03-13 |  |  | 1 | 1 | 2017-03-14 | 2017-03-21 | 2017-03-26 | 7 | 7 | 4 | 4 | 2017-04-17 | 26 | 26 | 2017-04-17 | 2017-04-17 | 2017-05-15 | 2017-04-25 | 7 | 7 | 2017-03-14 | 2017-04-25 | 31 | 31 | 2017-05-16 | 2017-04-25 | 1 | 1 | 2017-05-03 | 7 | 7 | 2017-05-11 | 2017-05-25 | 2017-05-11 | 2017-05-15 | 13 | 13 | 15 | 15 | 3 | 3 | [31 empty] | 2017-05-11 |  |  | 2017-05-11 | 1 | 1 | 2017-05-11 |  |  |  | 2017-05-11 |  |  |  |  | 2017-05-16 | 2017-06-06 | 16 | 16 | 2017-06-06 | 16 | 16 | 2017-06-06 |  |  |  | 62 | 62 | 37 | 37 | 2017
82 | Falcon Ridge Town Center | 15258 Summit Ave, #100 | Fontana | 92336 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 2312380 | 1302709 |  |  | 24 |  |  | true | 2017-03-27 | 2017-04-13 | 14 | 14 | 2017-03-16 | 2017-03-31 | 10 | 10 | 12 | 12 | 2017-04-04 | 2017-04-06 | 2017-04-09 | 5 | 5 | 2 | 2 | 2017-07-31 | 98 | 98 | 2017-08-01 |  | 2017-08-31 | 2017-09-01 | 25 | 25 | 2017-09-01 | 2018-05-09 | 179 | 179 | 2018-05-23 | 2018-05-24 | 12 | 12 | 2018-05-24 | 1 | 1 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-11 | 33 | 33 | 46 | 46 | 3 | 3 | 2018-05-09 |  | 2018-10-22 | -12 |  |  |  | 119 | 119 | [8 empty] | 2018-10-22 | [10 empty] | 2018-03-12 | 2018-05-03 | 2018-06-14 | 2018-03-14 | 3 | 3 | [6 empty] | 2019-02-28 | [5 empty] | 2019-03-01 |  |  |  | 2019-03-29 | 21 | 21 | 2019-03-29 |  |  |  | 532 | 532 | 435 | 435 | 2019
83 | Whittier Whittwood Town Center | 15466 Whittier Blvd | Whittier | 90603 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2312440 | [6 empty] | true |  |  |  |  | 2017-03-16 | 2017-03-16 |  |  | 1 | 1 | 2017-03-16 | 2017-03-28 | 2017-04-01 | 9 | 9 | 4 | 4
84 | West Covina Eastland Center (old request) | 2753 E Eastland Center Dr. | West Covina | 91791 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Alhambra |  |  | 2312470 | 1318973 | [5 empty] | true | 2017-03-27 | 2017-04-14 | 15 | 15 | 2017-03-16 | 2017-08-17 | -90 |  | 111 | 111 | 2017-08-17 | 2017-08-22 | 2017-08-23 | 4 | 4 | 2 | 2 |  |  |  | 2017-08-31 |  | 2017-09-28 | 2017-09-28 |  |  | 2017-09-28 | 2017-11-13 | 33 | 33 | 2017-12-06 | 2017-11-28 | 12 | 12 | 2017-11-28 | 1 | 1 | 2018-01-30 |  | 2018-01-30 |  | 46 | 46 |  |  |  |  | 2018-01-09 | 2018-01-18 |  | 31 | 31 | [10 empty] | 2018-01-18
85 | Mojave, CA- 16936 CA-14 (Expansion) | 16936 CA-14 | Mojave | 93501 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 3122416 | 1879850 |  |  | 6 |  |  | true | 2021-06-22 | 2021-07-21 | 21 | 21 | 2017-03-23 | 2017-03-23 | 1115 | 1115 | 1 | 1 | 2017-03-23 | 2017-03-30 | 2021-06-28 | 6 | 6 | 1094 | 1094 |  |  |  | 2017-05-02 | 2021-07-06 | 2017-05-31 | 2017-05-09 |  |  | 2017-05-09 | 2021-08-18 | 1102 | 1102 | 2021-08-18 | 2021-08-18 | 1 | 1 | 2021-08-18 | 1 | 1 | 2021-09-09 | 2021-09-24 | 2021-09-09 |  | 16 | 16 | [27 empty] | 2021-09-29 |  | 2021-11-30 | 42 | 42 | [13 empty] | 2021-12-02 |  |  |  |  | 2021-12-02 |  |  |  | 2021-12-18 | 12 | 12 | 2021-12-18 |  |  |  | 1218 | 1218 |  |  | 2021
86 | Yermo II CA096 Eddie's World | 36017 1/2 Calico Rd | Yermo | 92398 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2315760 | 1285658 |  |  | 18 |  |  | NO | 2017-03-31 | 2017-04-13 | 10 | 10 | 2017-03-22 | 2017-03-23 | 16 | 16 | 2 | 2 | 2017-03-23 | 2017-03-31 | 2017-04-03 | 7 | 7 | 2 | 2 |  |  |  | 2017-06-02 |  | 2017-06-30 | 2017-07-07 |  |  | 2017-07-07 | 2017-07-07 | 1 | 1 | 2017-07-28 | 2017-07-27 | 15 | 15 | 2017-07-27 | 1 | 1 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 14 | 14 | 28 | 28 | 1 | 1 | 2017-07-28 | 2017-07-28 | 2017-08-21 | 2 | 2 | 17 | 17 | 17 | 17 | 2019-02-08 | 402 | 402 |  |  |  | 2017-07-28 | 2017-07-28 | 2017-08-21 |  |  |  | 402 | 402 | 2017-08-25 | 2017-09-01 | 2017-09-01 | 6 | 6 | 2017-07-18 | 2017-08-07 | 2017-08-28 | 2017-07-27 | 8 | 8 | 2017-08-17 | 16 | 16 | 2017-09-01 | 5 | 5 | 2017-09-06 | 2017-09-12 | 41 | 41 | 5 | 5 | 2017-09-19 | [6 empty] | 2017-10-13 |  |  |  | 148 | 148 |  |  | 2017
87 | Evgo Whittwood Town Center | 15526 Whittier Blvd | Whittier | 90603 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2317890 | [6 empty] | true |  |  |  |  | 2017-03-28 | 2017-03-28 |  |  | 1 | 1 | 2017-03-28 |  | 2017-04-04
88 | Lake Elsinore Outlets | 17600 Collier Avenue | Lake Elsinore | 92530 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2319970 | 1280430 |  |  | 21 |  |  | true | 2017-08-09 | 2017-08-14 | 4 | 4 | 2017-03-30 | 2017-03-31 | 97 | 97 | 2 | 2 | 2017-04-03 | 2017-04-06 | 2017-04-23 | 5 | 5 | 12 | 12 | 2017-05-31 | 45 | 45 | 2017-05-31 | 2017-06-14 |  | 2017-09-01 | 68 | 68 | 2017-09-01 | 2017-09-07 | 5 | 5 | 2017-09-27 | 2017-09-07 | 1 | 1 | 2017-09-07 | 1 | 1 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-09 | 22 | 22 | 23 | 23 | 2 | 2 | 2017-09-08 | 2017-10-13 | 2017-11-27 | 2 | 2 | 32 | 32 | 57 | 57 | 2017-09-20 | 10 | 10 | 2017-09-28 | 7 | 7 | 2017-10-06 | 2017-09-20 | 2017-11-27 | 2017-11-27 | 49 | 49 | 10 | 10 | 2017-12-06 | 2017-12-18 | 2017-12-18 | 9 | 9 | 2017-10-12 | 2017-10-24 |  | 2017-10-16 | 3 | 3 | [6 empty] | 2018-01-08 | 2018-01-11 | 66 | 66 | 4 | 4 | 2018-01-24 | [6 empty] | 2018-02-27 |  |  |  | 239 | 239 | 195 | 195 | 2018
89 | Calabasas, CA- 4799 Commons Way | 4799 Commons Way | Calabasas | 91302 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2320070 | 1286494 | [5 empty] | NO | 2021-02-01 | 2021-02-09 | 7 | 7 | 2017-03-30 | 2017-03-31 | 996 | 996 | 2 | 2 | 2017-04-03 | 2017-04-13 |  | 10 | 10 | [5 empty] | 2017-05-31 |  | 2017-06-28 | [8 empty] | 2021-07-09 |  |  | 2021-07-09 | 1 | 1 | [33 empty] | 2022-01-20 |  | 2022-01-27 | 6 | 6 |  |  | 2022-01-13 | [9 empty] | 2022-02-24
90 | Valencia Hilton | 27710 The Old Road | Valencia | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 2321010 | 1354258 |  |  | 3 |  |  | NO |  |  |  |  | 2017-04-04 | 2017-11-09 |  |  | 158 | 158 | 2017-11-13 | 2017-11-16 | 2017-11-16 | 6 | 6 | 1 | 1 | 2017-11-30 | 173 | 173 | 2017-11-30 |  | 2018-03-23 | 2018-03-01 | 66 | 66 | 2018-03-01 | 2018-03-12 | 8 | 8 |  | 2018-03-13 | 2 | 2 | 2018-03-13 | 1 | 1 | 2018-04-03 | 2018-04-23 | 2018-04-03 | 2018-04-06 | 16 | 16 | 20 | 20 | 4 | 4 | [23 empty] | 2019-01-07 |  |  |  |  | 2018-07-13 | [5 empty] | 2018-12-18 | [5 empty] | 2019-03-07 | 2019-03-14 | 175 | 175 | 6 | 6 | 2019-03-19 | [6 empty] | 2019-10-09 |  |  |  | 657 | 657 | 485 | 485 | 2019
91 | Lebec | 5521 Dennis McCarthy Dr. | Lebec | 93243 | Kern County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2320950 | [6 empty] | true |  |  |  |  | 2017-04-04 | 2017-04-04 |  |  | 1 | 1 | 2017-04-04 | 2017-04-27 | 2017-04-30 | 18 | 18 | 2 | 2
92 | The Promenade at Westlake Village | 100 Promenade Way | Thousand Oaks | 91362 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2322330 | 1288098 |  |  | 24 |  |  | true | 2017-03-31 | 2017-04-13 | 10 | 10 | 2017-04-05 | 2017-04-06 | 6 | 6 | 2 | 2 | 2017-04-06 | 2017-04-13 | 2017-04-23 | 6 | 6 | 7 | 7 | 2017-06-15 | 52 | 52 | 2017-06-20 |  | 2017-07-17 | 2017-07-13 | 21 | 21 | 2017-07-13 | 2017-10-12 | 66 | 66 | 2017-11-02 | 2017-11-09 | 21 | 21 | 2017-11-09 | 1 | 1 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-19 | 6 | 6 | 27 | 27 | 2 | 2 | 2017-10-10 | 2017-11-08 | 2017-11-28 | -23 |  | 15 | 15 | 36 | 36 | 2018-02-14 | 70 | 70 |  |  |  | 2017-11-08 | 2017-11-08 | 2017-11-28 |  |  |  | 70 | 70 | 2018-02-01 | 2018-01-10 | 2018-01-11 | -16 |  | 2017-11-13 | 2017-12-12 | 2017-12-29 | 2017-11-16 | 4 | 4 | 2017-12-15 | 22 | 22 | 2018-01-05 | 6 | 6 | 2018-02-15 | 2018-02-21 | 73 | 73 | 5 | 5 | 2018-02-22 | 2018-03-01 | 6 | 6 | 2018-03-05 | 8 | 8 | 2018-03-05 |  |  |  | 239 | 239 | 188 | 188 | 2018
93 | South Bay Pavilion | 20700 S Avalon Blvd | Carson | 90746 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2322340 | [6 empty] | NO | 2021-05-25 | 2021-06-09 | 11 | 11 | 2017-04-05 | 2017-04-06 | 1076 | 1076 | 2 | 2 | 2017-04-06 | 2017-04-13 | 2017-04-22 | 6 | 6 | 7 | 7 | [5 empty] | 2021-11-15
94 | Cabazon Expansion | 48400 Seminole Drive | Cabazon | 92230 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO |  |  | 2326480 | 1271490 |  |  | 4 |  |  | NO |  |  |  |  | 2017-04-14 | 2017-04-14 |  |  | 1 | 1 | 2017-04-14 | 2022-09-15 | 2022-09-15 | 1390 | 1390 | 1 | 1 |  |  |  | 2017-05-02 |  | 2017-05-31 | 2017-05-03 |  |  | 2017-05-31 | 2017-05-31 | 1 | 1 | 2017-06-01 | 2017-06-02 | 3 | 3 | 2017-06-02 | 1 | 1 | 2017-06-02 | 2017-06-06 | 2017-06-02 | 2017-06-06 | 1 | 1 | 5 | 5 | 3 | 3 | [9 empty] | 2017-06-01 | -2 |  | 2017-07-17 | 33 | 33 | [6 empty] | -2 | [8 empty] | 2017-06-20 | [6 empty] | 2017-07-12 | 17 | 17 |  | 2017-07-11 |  |  |  |  | 2017-07-20 | 2017-08-20 | 22 | 22 | 2017-08-21 | 23 | 23 | 2017-08-21 |  |  |  | 92 | 92 |  |  | 2017
95 | Cypress | 6261 Katella Ave. | Cypress | 90630 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2331650 | 1289168 |  |  | 4 |  |  | NO |  |  |  |  | 2017-04-25 | 2017-04-25 |  |  | 1 | 1 | 2017-04-25 | 2017-05-02 | 2017-05-02 | 6 | 6 | 1 | 1 |  |  |  | 2017-05-23 |  | 2017-06-21 | 2017-07-12 |  |  | 2017-07-13 | 2017-02-06 | -114 |  | 2018-02-27 | 2018-03-08 | 284 | 284 | 2018-03-21 | 10 | 10 | 2018-05-10 | 2018-08-22 | 2018-08-15 | 2018-08-22 | 115 | 115 | 403 | 403 | 6 | 6 | 2018-08-24 | 2018-09-18 | 2019-03-05 | 122 | 122 | 121 | 121 | 138 | 138 | [6 empty] | 2018-08-15 |  | 2019-03-05 | [7 empty] | 2018-11-25 |  |  | 2018-05-18 | 2018-06-12 | 2018-08-29 | 2018-05-23 | 4 | 4 | [7 empty] | 2019-01-21 | 177 | 177 |  |  | 2019-03-13 |  |  |  | 2019-04-22 | 29 | 29 | 2019-04-22 |  |  |  | 520 | 520 |  |  | 2019
96 | 57-Warland | 5770 Warland Drive | Cypress | 90630 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2331670 | 1288627 |  |  | 2 |  |  | NO |  |  |  |  | 2017-04-25 | 2017-04-25 |  |  | 1 | 1 | 2017-04-25 | 2017-05-02 | 2017-05-07 | 6 | 6 | 4 | 4 |  |  |  | 2017-05-23 |  | 2017-06-21 | 2017-07-12 |  |  | 2017-07-13 | 2018-02-06 | 149 | 149 | 2018-02-27 | 2018-03-22 | 33 | 33 | 2018-03-22 | 1 | 1 | 2018-05-10 | 2019-03-14 | 2018-05-10 | 2019-03-11 | 36 | 36 | 285 | 285 | 218 | 218 | [25 empty] | 2018-11-14 |  |  | 2018-05-18 | 2018-06-22 | 2018-08-29 | [10 empty] | 2019-01-21 | 177 | 177 |  |  | 2019-03-14 |  |  |  | 2019-04-16 | 24 | 24 | 2019-04-16 |  |  |  | 516 | 516 |  |  | 2019
97 | 111-Knott | 11155 Knott Ave. | Cypress | 90630 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2331670 | [6 empty] | NO |  |  |  |  | 2017-04-25 | 2017-04-25 |  |  | 1 | 1 | 2017-04-25 | 2017-05-02 | 2017-05-07 | 6 | 6 | 4 | 4 |  |  |  | 2017-05-23 |  | 2017-06-21
98 | 110-Knott | 11075 Knott Ave. | Cypress | 90630 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2331680 | [6 empty] | NO |  |  |  |  | 2017-04-25 | 2017-04-25 |  |  | 1 | 1 | 2017-04-25 | 2017-05-02 | 2017-05-14 | 6 | 6 | 9 | 9 |  |  |  | 2017-05-23 |  | 2017-06-21
99 | Newport Coast Community | 6401 San Joaquin Hills Rd. | Newport Beach | 92657 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2332130 | 1315155 |  |  | 2 |  |  | NO |  |  |  |  | 2017-04-26 | 2017-04-26 |  |  | 1 | 1 | 2017-04-26 | 2017-05-04 | 2017-05-14 | 7 | 7 | 7 | 7 |  |  |  | 2017-08-16 |  | 2017-09-29 | 2017-10-02 |  |  | 2017-10-02 | 2017-10-04 | 3 | 3 | 2017-10-18 | 2017-10-18 | 11 | 11 | 2017-10-18 | 1 | 1 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 23 | 23 | 33 | 33 | 1 | 1 | [23 empty] | 2017-11-30 | 2017-12-07 | 2017-12-08 | 7 | 7 | 2017-10-25 | 2017-11-28 | 2017-12-13 | 2017-10-26 | 2 | 2 | 2017-11-30 | 26 | 26 |  |  |  | 2017-12-13 | 2017-12-22 | 43 | 43 | 8 | 8 | 2018-01-02 | 2018-01-08 | 5 | 5 | 2018-01-08 | 5 | 5 | 2018-01-08 |  |  |  | 184 | 184 |  |  | 2018
100 | Gardena Transit | 13999 S. Western Ave. | Gardena | 90249 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 2338920 | 1274074 | [5 empty] | NO |  |  |  |  | 2017-05-09 | 2017-05-11 |  |  | 3 | 3 | 2017-05-11 | 2017-05-16 | 2017-05-18 | 4 | 4 | 3 | 3 |  |  |  | 2017-05-11 |  | 2017-06-09 | 2017-06-13 |  |  | 2017-06-13 | 2017-07-26 | 32 | 32 |  | 2018-04-19 | 192 | 192 | 2018-04-19 | 1 | 1 | 2018-04-20 |  | 2018-04-20 |  | 2 | 2 | [6 empty] | 2018-03-28
101 | Commons at Aliso Viejo | 26501 Aliso Viejo Rd. | Aliso Viejo | 92656 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2342670 | [6 empty] | NO |  |  |  |  | 2017-05-16 | 2017-05-16 |  |  | 1 | 1 | 2017-05-16 | 2017-05-24 | 2017-06-03 | 7 | 7 | 8 | 8
102 | Santa Monica Shell Station | 1866 Lincoln Blvd. | Santa Monica | 90404 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra |  |  | 2345580 | [6 empty] | NO |  |  |  |  | 2017-05-22 | 2017-05-23 |  |  | 2 | 2 | 2017-05-23 | 2017-06-02 | 2017-06-03 | 9 | 9 | 1 | 1
103 | Huntington Beach Mobil Station | 16001 Beach Blvd. | Huntington Beach | 92647 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 2345610 |  |  |  | 0 | NO |  | NO |  |  |  |  | 2017-05-22 | 2017-05-23 |  |  | 2 | 2 | 2017-05-23 | 2017-06-06 | 2017-06-10 | 11 | 11 | 4 | 4 |  |  |  | 2018-05-29 |  | 2018-06-27
104 | Irvine Mobile Station | 5333 University Ave. | Irvine | 92612 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [7 empty] | NO | Level 3 | true |  |  |  |  | 2017-05-22 | 2017-06-12 |  |  | 16 | 16 | 2017-06-12
105 | Westminster Mall | 1025 Westminster Mall | Westminster | 92683 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 2349970 | 1311722 |  |  | 24 |  |  | NO | 2017-05-12 | 2017-05-19 | 6 | 6 | 2017-05-31 | 2017-06-01 | -10 |  | 2 | 2 | 2017-06-01 | 2017-06-08 | 2017-06-11 | 6 | 6 | 2 | 2 |  |  |  | 2017-08-02 |  | 2018-06-14 | 2018-06-18 |  |  | 2018-06-18 | [10 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-07-23 |  |  |  |  | 19 | 19 | 2018-06-25 | 2018-06-27 | 2018-07-17 |  |  | 15 | 15 | 17 | 17 | [6 empty] | 2018-06-27 |  | 2018-07-23 | [7 empty] | 2018-11-28 |  |  |  | 2018-10-11 | 2018-10-17 | [9 empty] | 2018-11-29 | [12 empty] | 2018-12-17 |  |  |  | 404 | 404 |  |  | 2018
106 | Newhall-Santa Clarita 76 Station | 24551 Lyons Ave. | Newhall | 91321 | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura |  |  | 2352870 | [6 empty] | NO |  |  |  |  | 2017-06-06 | 2017-06-06 |  |  | 1 | 1 | 2017-06-07 | 2017-06-14 | 2017-07-03 | 7 | 7 | 14 | 14
107 | Rancho Palos Verdes Shell Station | 28103 Hawthorne Blvd. | Rancho Palos Verdes | 90275 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2352840 | 1261155 | [5 empty] | NO |  |  |  |  | 2017-06-06 | 2017-06-06 |  |  | 1 | 1 | 2017-06-07 | 2017-06-16 |  | 9 | 9
108 | Redwood Fontana B | 8181B Redwood Ave. | Fontana | 92335 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2356200 | 1302473 | [5 empty] | true |  |  |  |  | 2017-06-13 | 2017-05-30 |  |  | -11 |  | 2017-05-30 | 2017-06-06 | 2017-06-14 | 6 | 6 | 7 | 7 | 2017-06-14 | 2 | 2 | 2017-06-14 |  | 2017-07-13 | 2017-07-26 | 31 | 31 | 2017-07-26 | 2017-07-26 | 1 | 1 | 2017-08-16 | 2017-08-30 | 26 | 26 | 2017-08-30 | 1 | 1 | 2017-08-30 |  | 2017-08-30 |  | 1 | 1 |  |  |  |  | 2017-08-14 | 2018-01-30 | 2018-04-12 | -13 |  | 53 | 53 | 174 | 174 | [6 empty] | 2017-08-30 | [7 empty] | 2018-06-27 |  |  |  |  | 2018-05-04 | [12 empty] | 2018-10-02 | 108 | 108
109 | Irvine Park Place | 3023.25 Michelson Dr. | Irvine | 92612 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2360940 | 1317330 |  |  | 11 |  |  | NO | 2017-08-10 | 2017-08-17 | 6 | 6 | 2017-06-22 | 2017-06-23 | 40 | 40 | 2 | 2 | 2017-06-23 | 2017-07-03 | 2017-07-03 | 7 | 7 | 1 | 1 | 2017-09-08 | 57 | 57 | 2017-09-10 |  | 2018-02-05 | 2018-02-09 | 111 | 111 | 2018-02-09 | 2019-02-13 | 264 | 264 | 2019-03-06 | 2019-03-18 | 24 | 24 | 2019-03-18 | 1 | 1 | 2019-05-20 | 2019-07-03 | 2019-05-20 | 2019-05-20 | 46 | 46 | 69 | 69 | 1 | 1 | 2019-03-29 | 2019-04-22 | 2019-07-18 | 10 | 10 | 64 | 64 | 80 | 80 | [6 empty] | 2019-04-22 |  | 2019-07-18 | [5 empty] | 2019-07-03 |  | 2019-07-25 | 17 | 17 | [12 empty] | 2019-08-16 | 2019-08-21 |  |  | 4 | 4 | 2019-07-15 |  |  |  | 2019-09-15 | 45 | 45 | 2019-09-15 |  |  |  | 582 | 582 | 526 | 526 | 2019
110 | Valencia Circle Drive | 26735 Circle Drive | Valencia | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2361280 | [6 empty] | true |  |  |  |  | 2017-06-23 | 2017-07-14 |  |  | 16 | 16 | 2017-07-14 | 2017-07-19 | 2017-07-29 | 4 | 4 | 8 | 8
111 | Cerritos Los Cerritos Center | 239 Los Cerritos Center | Cerritos | 90703 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra |  |  | 2363890 | 1321321 |  |  | 12 |  |  | NO | 2017-06-13 | 2017-06-28 | 12 | 12 | 2017-06-28 | 2017-06-29 | -2 |  | 2 | 2 | 2017-06-29 | 2017-07-05 | 2017-07-10 | 5 | 5 | 4 | 4 |  |  |  | 2017-08-03 |  | 2018-06-06 | 2018-06-18 |  |  | 2018-06-18 | 2018-06-18 | 1 | 1 |  | 2019-10-04 | 340 | 340 | 2019-10-04 | 1 | 1 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2020-04-06 | -482 |  | 468 | 468 | 610 | 610 | 2017-11-21 | 2017-11-29 | 2019-05-24 | -489 |  | 388 | 388 | 394 | 394 | 2020-06-03 | 170 | 170 | 2020-06-25 | 17 | 17 | 2017-11-29 | 2017-11-29 | 2020-04-06 | 2020-06-25 | 668 | 668 | 170 | 170 | 2020-03-18 |  | 2020-04-17 | 23 | 23 | [13 empty] | 2020-06-24 |  |  |  |  | 2020-07-13 |  |  |  | 2020-08-31 | 36 | 36 | 2020-08-31 |  |  |  | 824 | 824 |  |  | 2020
112 | Corona Del Mar-Newport Beach | 2201 East Coast Highway | Corona Del Mar | 92625 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2364160 |  |  |  | 0 |  |  | true |  |  |  |  | 2017-06-29 | 2017-06-29 |  |  | 1 | 1 | 2017-06-29 | 2017-07-06 | 2017-07-24 | 6 | 6 | 13 | 13 | 2017-07-22 | 17 | 17
113 | Santa Barbara, CA- 633 1/2 East Cabrillo Boulevard (#2 - Fess Parker) | 633 1/2 East Cabrillo Boulevard | Santa Barbara | 93103 | Santa Barbara County | 6. Requirements (permit, easment, etc.) | 49 - Santa Barbara | North Coast | Ventura |  |  | 2369560 | [6 empty] | YES | 2017-06-23 | 2017-06-28 | 4 | 4 | 2017-07-10 | 2017-07-12 | -11 |  | 3 | 3 | 2017-07-13 | 2017-07-18 | 2017-07-31 | 5 | 5 | 10 | 10
114 | Santa Barbara, CA - 121 South Hope Avenue | 110 South Hope Avenue EV1 | Santa Barbara | 93105 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 2368227 | 1438190 |  | 2024-09-20 |  | NO |  | YES | 2017-06-23 | 2017-06-28 | 4 | 4 | 2017-07-10 | 2017-07-10 | -9 |  | 1 | 1 | 2017-07-10 | 2017-07-18 | 2017-07-31 | 7 | 7 | 10 | 10 |  |  |  | 2018-08-16 | 2018-08-17 | 2018-08-31 | 2018-09-05 |  |  | 2018-09-05 | 2022-05-03 | 933 | 933 | 2022-05-24 | 2022-05-27 | 19 | 19 | 2022-05-31 | 2 | 2 | 2022-06-13 | 2022-08-19 | 2022-06-13 | 2022-09-15 | 11 | 11 | 95 | 95 | 67 | 67 | 2023-05-18 | 2023-08-01 |  | 247 | 247 | [10 empty] | 2022-06-13
115 | Huntington Beach, CA- 7777 Edinger Avenue | 7777 Edinger Avenue | Huntington Beach | 92647 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2393300 | 1336188 |  |  | 4 | NO |  | NO | 2017-07-10 | 2017-07-17 | 6 | 6 | 2017-08-29 | 2017-09-20 | -48 |  | 17 | 17 | 2017-09-21 | 2017-09-29 | 2017-10-03 | 8 | 8 | 3 | 3 |  |  |  | 2017-10-13 |  |  | 2017-12-19 |  |  | 2017-12-19 | 2018-01-02 | 11 | 11 | 2018-02-05 | 2018-03-06 | 46 | 46 | 2018-03-06 | 1 | 1 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 402 | 402 | 447 | 447 | 1 | 1 | 2021-03-04 |  |  | 770 | 770
116 | Redwood Fontana A | 8181A Redwood Avenue | Fontana | 92336 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2370020 | 1298547 | [5 empty] | true |  |  |  |  | 2017-07-13 | 2017-07-14 |  |  | 2 | 2 | 2017-07-14 | 2017-07-17 | 2017-07-19 | 2 | 2 | 3 | 3 | 2017-07-19 | 5 | 5 | 2017-07-20 |  | 2017-08-17 | 2017-08-16 | 21 | 21 | 2017-08-17 | 2017-09-11 | 18 | 18 | 2017-10-02 | 2017-10-04 | 18 | 18 | 2017-10-04 | 1 | 1 | 2017-10-04 |  | 2017-10-04 |  | 1 | 1 |  |  |  |  | 2017-08-14 | 2018-01-30 | 2018-04-12 | -38 |  | 53 | 53 | 174 | 174 | [6 empty] | 2017-10-04 | [7 empty] | 2018-06-27 | 2018-07-25 | 2018-07-26 | 22 | 22 | [13 empty] | 2018-10-02
117 | Downey Stonewood Center CA113 | 251 Stonewood Street | Downey | 90241 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2380370 | 1297693 |  |  | 12 |  |  | true | 2017-07-08 | 2017-09-27 | 58 | 58 | 2017-08-03 | 2017-08-04 | 39 | 39 | 2 | 2 | 2017-08-04 | 2017-08-07 | 2017-08-10 | 2 | 2 | 4 | 4 |  |  |  | 2018-03-15 |  | 2018-01-26 | 2018-01-31 |  |  | 2018-01-31 | 2018-02-07 | 6 | 6 | 2018-02-28 | 2018-03-01 | 17 | 17 | 2018-03-01 | 1 | 1 | 2018-03-09 |  | 2018-03-09 | 2018-03-20 | 7 | 7 | 30 | 30 | 8 | 8 | [9 empty] | 2018-05-10 | 51 | 51 | 2018-05-30 | 15 | 15 | [6 empty] | 51 | 51 | 2018-04-24 | 2018-05-12 | 2018-05-13 | 14 | 14 | 2018-03-20 | 2018-04-30 | 2018-05-07 | 2018-03-21 | 2 | 2 |  |  |  | 2018-05-14 | 6 | 6 | 2018-05-07 | 2018-05-16 | 42 | 42 | 8 | 8 | 2018-05-23 | [6 empty] | 2018-06-22 |  |  |  | 232 | 232 |  |  | 2018
118 | The Oaks Mall - Thousand Oaks | 350 Hillcrest Drive | Thousand Oaks | 91360 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2404560 | 1374500 |  |  | 20 |  |  | NO | 2017-07-26 | 2017-08-07 | 9 | 9 | 2017-09-20 | 2017-09-12 | -27 |  | -7 |  | 2017-09-12 | 2017-09-14 | 2017-09-17 | 3 | 3 | 2 | 2 |  |  |  | 2017-09-21 |  | 2018-03-12 | 2018-03-08 |  |  | 2018-03-08 | 2018-03-19 | 8 | 8 | 2018-04-09 | 2018-04-23 | 26 | 26 | 2018-04-23 | 1 | 1 | 2018-04-23 | 2018-04-26 | 2018-04-23 | 2018-04-26 | 1 | 1 | 29 | 29 | 4 | 4 | 2018-04-02 | 2018-04-23 | 2018-06-13 | -16 |  | 38 | 38 | 53 | 53 | 2018-05-01 | 7 | 7 | 2018-05-22 | 16 | 16 | 2018-04-23 | 2018-04-23 | 2018-06-13 | 2018-06-13 | 38 | 38 | 7 | 7 | 2018-04-26 | 2018-05-07 | 2018-05-08 | 9 | 9 | 2018-01-31 | 2018-04-09 |  | 2018-01-31 | 1 | 1 | 2018-04-09 | 49 | 49 |  |  |  | 2018-06-01 | 2018-06-05 | 90 | 90 | 3 | 3 | 2018-06-14 |  |  |  | 2018-07-27 | 32 | 32 | 2018-07-27 |  |  |  | 223 | 223 |  |  | 2018
119 | HASBC - Victorville #2 | 14469 Rodeo Road | Victorville | 92395 | San Bernardino County | 9. Complete | 73 - Victorville | Rurals | SBRO |  |  | 2277390 | 1242144 | [5 empty] | NO |  |  |  |  | 2017-07-24 | 2016-12-08 |  |  | -163 |  | 2016-12-08 | 2016-12-16 | 2016-12-20 | 7 | 7 | 3 | 3 | 2016-12-20 | -155 |  | 2017-07-26 | 2017-07-27 | 2017-08-23 | [8 empty] | 2018-03-15 |  |  | 2018-03-13 | -3 |  | 2018-03-13 |  | 2018-03-13 |  | -3 | [33 empty] | 2018-06-12 | [12 empty] | 2018-10-17 | 92 | 92
120 | Irvine Site #1 - Airport Professional Center | 17838 1/4 Fitch Avenue | Irvine | 92614 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2378190 | 1300418 |  |  | 3 |  |  | true |  |  |  |  | 2017-07-31 | 2017-06-19 |  |  | -31 |  | 2017-06-22 | [9 empty] | 2017-08-11 | [38 empty] | 2017-09-14 | [27 empty] | 2017-09-21 | 2017-09-25 |  |  | 3 | 3 | 2017-10-16 | 2017-10-18 | 3 | 3 | 2017-10-18 | 3 | 3 | 2017-10-18 |  |  |  | 58 | 58 |  |  | 2017
121 | Santa Monica Place | 395 Santa Monica Place | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2394020 | 1308095 |  |  | 10 |  |  | NO | 2017-08-14 | 2017-09-06 | 18 | 18 | 2017-07-31 | 2017-09-07 | -2 |  | 29 | 29 | 2017-09-07 | 2017-09-13 | 2017-10-15 | 5 | 5 | 23 | 23 | 2017-10-15 | 55 | 55 | 2017-10-16 |  | 2018-05-04 | 2018-05-04 | 145 | 145 | 2018-05-04 | 2018-05-07 | 2 | 2 | 2018-05-21 | 2018-06-01 | 20 | 20 | 2018-06-01 | 1 | 1 | 2018-06-01 | 2018-06-19 | 2018-06-01 | 2018-06-08 | 1 | 1 | 25 | 25 | 6 | 6 | 2018-06-08 | 2018-06-26 | 2018-07-03 | 6 | 6 | 6 | 6 | 18 | 18 | 2018-09-07 | 71 | 71 |  |  |  | 2018-06-01 | 2018-06-01 | 2018-07-03 |  |  |  | 71 | 71 | 2018-11-08 |  | 2018-12-10 | 23 | 23 | 2018-09-06 | 2018-09-24 | 2019-01-24 | 2018-09-12 | 5 | 5 | [7 empty] | 2018-12-11 | 69 | 69 |  |  | 2018-12-11 | [6 empty] | 2019-02-18 |  |  |  | 406 | 406 | 351 | 351 | 2019
122 | Newport Coast Community Center #1 | 6401 San Joaquin Hills | Newport Beach | 92657 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2386400 | [6 empty] | NO |  |  |  |  | 2017-08-14 | 2017-04-24 |  |  | -81 |  | 2017-04-26 | 2017-05-14 | 2017-05-14 | 15 | 15 | 0 |  |  |  |  | 2017-08-16 |  | 2017-10-04
123 | Newport Coast Community Center #2 | 6401 1/4 San Joaquin Hills Road | Newport Beach | 92657 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2386430 | [6 empty] | true |  |  |  |  | 2017-08-14 | 2017-04-24 |  |  | -81 |  | 2017-04-26 | 2017-05-14 | 2017-05-14 | 15 | 15 | 0 |  |  |  |  | 2017-08-16 |  | 2017-10-04
124 | Lancaster Green Commuter | 43063 10th Street West | Lancaster | 93534 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2401415 | 1313890 |  |  | 2 |  |  | NO |  |  |  |  | 2017-09-12 | 2017-11-20 |  |  | 50 | 50 | 2017-11-27 | 2017-11-28 | 2017-12-03 | 7 | 7 | 4 | 4 | 2018-07-13 | 219 | 219 | 2018-07-17 | 2018-07-20 | 2018-08-03 | 2018-08-15 | 24 | 24 | 2018-08-15 | 2018-08-15 | 1 | 1 |  | 2018-08-27 | 9 | 9 | 2018-08-27 | 1 | 1 | 2018-09-24 | 2018-08-27 | 2020-07-28 | 2020-07-28 | 497 | 497 | 505 | 505 | 1 | 1 | [23 empty] | 2019-06-10 |  | 2019-07-12 | 25 | 25 | [13 empty] | 2020-07-23 |  |  |  |  | 2020-07-31 | [6 empty] | 2020-10-08 |  |  |  | 797 | 797 | 579 | 579 | 2020
125 | CalTrans Phillip Raine Rest Area #1 (LOC6) | Southbound Route 99 | Tulare | 93274 | Tulare County | 9. Complete | 51 - Tulare | San Joaquin | Ventura |  |  | 2409960 | 1320813 |  |  | 4 |  |  | NO |  |  |  |  | 2017-09-29 | 2017-10-03 |  |  | 3 | 3 | 2017-10-04 | 2017-10-06 | 2017-10-16 | 4 | 4 | 7 | 7 | 2017-10-16 | 12 | 12 | 2017-10-17 |  | 2017-11-13 | 2017-10-27 | 10 | 10 | 2017-10-27 | 2017-12-28 | 45 | 45 | 2018-01-12 | 2018-01-02 | 4 | 4 | 2018-01-03 | 2 | 2 | 2019-08-09 | 2019-12-10 | 2019-08-09 |  | 419 | 419 | [13 empty] | 2020-04-01 | 583 | 583 | 2020-05-01 | 23 | 23 | [6 empty] | 584 | 584 | [7 empty] | 2020-04-09 | [10 empty] | 2020-09-11 |  |  |  |  | 2020-10-30 |  |  |  | 2020-12-22 | 35 | 35 | 2020-12-22 |  |  |  | 834 | 834 | 823 | 823 | 2020
126 | CalTrans Tulare 2 | Phillip Raine Rest Area - Northbound Route 99 | Tulare | 93274 | Tulare County | 9. Complete | 51 - Tulare | San Joaquin | Ventura |  |  | 2409981 | 1320834 |  |  | 4 |  |  | NO |  |  |  |  | 2017-09-29 | 2017-10-03 |  |  | 3 | 3 | 2017-10-04 | 2017-10-06 | 2017-10-16 | 4 | 4 | 7 | 7 | 2017-10-16 | 12 | 12 | 2017-10-17 |  | 2017-11-13 | 2017-10-27 | 10 | 10 | 2017-10-27 | 2017-12-28 | 45 | 45 | 2018-01-12 | 2018-01-02 | 4 | 4 | 2018-01-03 | 2 | 2 | 2018-02-05 | 2019-12-10 | 2018-02-05 |  | 25 | 25 | [13 empty] | 2020-04-01 | 583 | 583 | 2020-05-01 | 23 | 23 | [6 empty] | 584 | 584 | [7 empty] | 2020-04-09 | [10 empty] | 2020-09-12 |  |  |  |  | 2020-10-30 |  |  |  | 2020-12-22 | 35 | 35 | 2021-01-22 |  |  |  | 854 | 854 | 843 | 843 | 2021
127 | CalTrans Delano #1 (LOC8) | 805 S Lexington | Delano | 93215 | Kern County | 9. Complete | 51 - Tulare | San Joaquin | Ventura |  |  | 2409988 | 1578783 |  |  | 4 |  |  | NO |  |  |  |  | 2017-09-29 | 2017-10-03 |  |  | 3 | 3 | 2017-10-04 | 2017-10-06 | 2017-10-16 | 4 | 4 | 7 | 7 | 2017-10-16 | 12 | 12 | 2017-10-17 |  | 2018-06-13 | [14 empty] | 2019-08-20 | 2019-12-10 | 2019-08-20 | 2020-04-01 |  |  |  |  | 159 | 159 | [9 empty] | 2020-04-01 |  |  | 2020-06-09 | 49 | 49 | [13 empty] | 2020-03-24 |  | 2020-04-09 | [10 empty] | 2020-09-11 | 121 | 121 |  |  | 2020-11-18 |  |  |  | 2021-01-05 | 31 | 31 | 2021-01-05 |  |  |  | 842 | 842 | 831 | 831 | 2021
128 | Inglewood #1 La Brea Avenue | 113 South La Brea Avenue | Inglewood | 90301 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2430140 | 1470323 |  |  | 4 |  |  | true |  |  |  |  | 2016-11-15 | 2017-11-16 |  |  | 263 | 263 | 2017-11-16 | 2017-11-21 | 2018-02-01 | 4 | 4 | 53 | 53 |  |  |  | 2018-10-19 |  | 2018-11-21 | 2018-11-20 |  |  | 2018-11-20 | 2018-11-29 | 8 | 8 | 2018-12-21 | 2018-12-05 | 5 | 5 | 2018-12-05 | 1 | 1 | 2018-12-27 | 2019-04-11 | 2018-12-27 | 2019-04-24 | 17 | 17 | 105 | 105 | 85 | 85 | 2018-12-07 | 2019-01-02 | 2019-05-17 | 3 | 3 | 98 | 98 | 116 | 116 | 2019-03-07 | 67 | 67 | 2019-03-14 | 6 | 6 | 2018-12-27 | 2018-12-27 | 2019-05-17 | 2019-05-17 | 102 | 102 | 67 | 67 | 2019-03-01 |  |  |  |  | 2019-01-31 | [11 empty] | 2019-03-18 | 2019-03-20 | 35 | 35 | 3 | 3 | 2019-05-20 |  |  |  | 2019-07-03 | 33 | 33 | 2019-07-03 |  |  |  | 687 | 687 |  |  | 2019
129 | Barstow WalMart 100049-0524 | 301 Montara Road | Barstow | 92311 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2433354 | 1484738 |  |  | 8 |  |  | NO | 2018-01-19 | 2019-01-15 | 258 | 258 | 2017-11-27 | 2017-11-28 | 296 | 296 | 2 | 2 | 2017-11-28 | 2017-12-06 | 2017-12-11 | 7 | 7 | 4 | 4 | 2018-12-03 | 266 | 266 | 2018-12-05 | 2018-12-06 | 2019-01-03 | 2019-01-11 | 30 | 30 | 2019-01-11 | 2019-04-02 | 58 | 58 | 2019-04-23 | 2019-04-15 | 10 | 10 | 2019-04-15 | 1 | 1 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-02 | 13 | 13 | 23 | 23 | 2 | 2 | 2019-04-15 | 2019-05-06 | 2019-08-30 | 1 | 1 | 85 | 85 | 100 | 100 | [6 empty] | 2019-05-01 |  | 2019-08-30 | [5 empty] | 2019-08-20 |  | 2019-10-04 | 34 | 34 | [13 empty] | 2019-11-20 |  |  |  |  | 2019-12-05 |  |  |  | 2020-03-12 | 68 | 68 | 2020-03-12 |  |  |  | 596 | 596 | 331 | 331 | 2020
130 | Montebello Plaza 200072-0282 | 2401-2629 W. Via Campo | Montebello | 90640 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2433430 | 1396840 |  |  | 3 |  |  | NO |  |  |  |  | 2017-11-27 | 2017-11-28 |  |  | 2 | 2 | 2017-11-28 | 2017-12-07 | 2017-12-11 | 8 | 8 | 3 | 3 |  |  |  | 2018-01-30 | 2018-02-15 | 2018-02-28 | 2018-03-01 |  |  | 2018-03-01 | 2018-04-25 | 40 | 40 | 2018-05-16 | 2018-05-10 | 12 | 12 | 2018-05-18 | 7 | 7 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-06-06 | 12 | 12 | 31 | 31 | 9 | 9 | 2018-07-12 |  | 2018-10-16 | 46 | 46 |  |  | 69 | 69 | [8 empty] | 2018-10-16 | [5 empty] | 2018-09-03 |  |  |  |  | 2018-08-09 | 2018-08-17 | 2018-11-06 | [9 empty] | 2018-12-07 | 2018-12-07 | 87 | 87 | 1 | 1 | 2018-12-12 |  |  |  | 2019-01-23 | 31 | 31 | 2019-01-23 |  |  |  | 303 | 303 |  |  | 2019
131 | Buena Park Place | 8191-8371 La Palma Avenue | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2433450 | [6 empty] | YES |  |  |  |  | 2017-11-27 | 2017-11-28 |  |  | 2 | 2 | 2017-11-28 | 2017-12-07 | 2017-12-11 | 8 | 8 | 3 | 3
132 | Lakewood, CA - 500 Lakewood Center Mall | 500 Lakewood Center Mall | Lakewood | 90712 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 2442190 | 1488758 | [5 empty] | true | 2021-10-22 |  |  |  | 2017-12-18 | 2017-12-18 |  |  | 1 | 1 | 2017-12-19 | 2018-01-23 | 2018-01-30 | 27 | 27 | 6 | 6 |  |  |  | 2018-03-01 | 2018-03-06 | 2018-08-13 | 2018-08-13 |  |  | 2018-08-13 | 2018-11-26 | 76 | 76 | 2018-12-17 | 2018-12-20 | 19 | 19 | 2018-12-20 | 1 | 1 | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-02-13 | 20 | 20 | 58 | 58 | 21 | 21 | [41 empty] | 2019-10-11
133 | Boku International - Ojai | 987 West Ojai Avenue | Ojai | 93023 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 2502880 | 1400751 |  |  | 12 |  |  | NO | 2017-11-28 | 2017-12-26 | 21 | 21 | 2017-11-28 | 2017-12-18 | 7 | 7 | 15 | 15 | 2017-12-19 | 2018-01-02 | 2018-01-22 | 12 | 12 | 15 | 15 | 2018-05-08 | 116 | 116 | 2018-05-09 |  |  | 2018-06-05 | 21 | 21 | 2018-06-05 | 2018-06-12 | 6 | 6 | 2018-06-26 | 2018-06-18 | 5 | 5 | 2018-06-18 | 1 | 1 | 2018-08-21 | 2018-08-21 | 2018-08-21 | 2018-09-09 | 47 | 47 | 64 | 64 | 14 | 14 | 2018-08-01 | 2018-11-09 | 2019-06-05 | 33 | 33 | 149 | 149 | 221 | 221 | [6 empty] | 2018-08-21 |  | 2019-06-05 | [10 empty] | 2019-04-23 | [12 empty] | 2019-06-05 | 32 | 32 |  |  | 2019-06-06 |  |  |  | 2019-07-16 | 29 | 29 | 2019-07-16 |  |  |  | 426 | 426 | 311 | 311 | 2019
134 | Redlands Target | 27320 West Lugonia Avenue | Redlands | 92373 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | NO | 2018-12-12 |  |  |  | 2017-11-30 | 2017-11-30 |  |  | 1 | 1 | 2017-11-30 | 2017-12-01 | 2017-12-01 | 2 | 2 | 1 | 1
135 | Redlands WalMart 100043-1250 | 2050 West Redlands Boulevard | Redlands | 92373 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-30 | 2018-02-13 | 8 | 8 | 11 | 11
136 | Victorville WalMart 100042-1248 | 11896 Amargosa Road | Victorville | 92392 | San Bernardino County | 9. Complete | 73 - Victorville | Rurals | SBRO | [9 empty] | true |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-25 | 2018-02-16 | 5 | 5 | 17 | 17
137 | Hesperia WalMart 100042-0986 | 13401 Main Street | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2533960 | 1431270 |  |  | 10 |  |  | true | 2018-02-22 | 2018-03-21 | 20 | 20 | 2017-11-30 | 2018-01-19 | 44 | 44 | 37 | 37 | 2018-01-19 | 2018-01-25 | 2018-02-08 | 5 | 5 | 11 | 11 | 2018-07-17 | 164 | 164 | 2018-07-18 | 2018-07-23 | 2018-08-15 | 2018-08-28 | 31 | 31 | 2018-08-28 | 2018-11-07 | 52 | 52 | 2018-11-29 | 2019-01-24 | 57 | 57 | 2019-01-24 | 1 | 1 |  | 2019-03-06 | 2019-03-06 | 2019-03-18 | 30 | 30 | 94 | 94 | 9 | 9 | 2019-02-01 | 2019-02-21 | 2019-05-06 | 7 | 7 | 53 | 53 | 67 | 67 | 2019-07-15 | 123 | 123 | 2019-07-19 | 5 | 5 | 2019-02-21 | 2019-02-21 | 2019-05-06 | 2019-07-19 | 107 | 107 | 123 | 123 | 2019-08-05 |  | 2019-09-06 | 25 | 25 | 2019-03-29 | 2019-06-03 | [10 empty] | 2019-10-11 | 2019-10-17 | 145 | 145 | 5 | 5 | 2019-10-21 |  |  |  | 2019-12-12 | 39 | 39 | 2019-12-12 |  |  |  | 531 | 531 | 368 | 368 | 2019
138 | Thousand Oaks WalMart 100040-0972 | 512 Ventu Park Road | Thousand Oaks | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2018-01-19 | 2018-02-25 | 26 | 26 | 2017-11-30 | 2017-12-01 | 61 | 61 | 2 | 2 | 2017-12-01 | 2017-12-06 | 2017-12-13 | 4 | 4 | 6 | 6
139 | Newbury Park Target | 2705 Teller Road | Newbury Park | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-06 | 2017-12-13 | 4 | 4 | 6 | 6
140 | Westlake Village Target | 30740 Russell Ranch Road | Westlake Village | 91362 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-06 | 2017-12-13 | 4 | 4 | 6 | 6
141 | Diamond Bar Target 200052-1522 | 747 Grand Avenue | Diamond Bar | 91765 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 2878073 | 1414317 |  |  | 3 |  |  | YES |  |  |  |  | 2017-11-30 | 2018-07-26 |  |  | 171 | 171 | 2018-07-30 | 2018-08-01 | 2018-03-01 | 5 | 5 | -110 |  |  |  |  | 2018-06-05 | 2018-06-05 | 2018-07-03 | 2018-07-03 |  |  | 2018-07-03 |  |  |  |  | 2018-10-12 |  |  | 2018-10-12 | 1 | 1 | 2018-10-12 | 2018-10-31 | 2018-10-12 | 2018-10-19 | 1 | 1 |  |  | 6 | 6 | 2018-11-05 | 2018-11-20 | 2019-04-18 | 17 | 17 | 108 | 108 | 119 | 119 | 2019-10-01 | 253 | 253 | 2019-11-14 | 33 | 33 | 2018-10-12 | 2018-10-12 | 2019-04-18 | 2019-11-14 | 285 | 285 | 253 | 253 | 2019-08-14 |  | 2019-09-05 | 17 | 17 | [13 empty] | 2019-09-25 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-14 | 33 | 33 | 2019-11-14 |  |  |  | 511 | 511 |  |  | 2019
142 | Fullerton Target 200053-1524 | 2920 Yorba Linda Boulevard | Fullerton | 92831 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-15 | 2017-12-28 | 11 | 11 | 10 | 10
143 | Orange Target 200054-1490 | 2191 North Tustin Street | Orange | 92865 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2018-02-09 |  |  | 52 | 52 | 2018-02-12 | 2018-02-20 | 2018-03-07 | 8 | 8 | 12 | 12
144 | Brea WalMart 200060-1235 | 2595 East Imperial Highway | Brea | 92821 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-29 | 2018-02-15 | 7 | 7 | 14 | 14
145 | Buena Park Target 200075-1521 | 7530 Orangethorpe Avenue | Buena Park | 90621 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2605540 | 1493312 |  |  | 6 |  |  | true | 2018-12-27 | 2018-12-28 | 2 | 2 | 2017-11-30 | 2017-12-01 | 281 | 281 | 2 | 2 | 2017-12-01 | 2017-12-07 | 2017-12-11 | 5 | 5 | 3 | 3 |  |  |  | 2018-12-27 |  | 2019-01-28 | 2019-01-30 |  |  | 2019-01-31 | 2019-02-06 | 5 | 5 | 2019-02-28 | 2019-02-19 | 10 | 10 | 2019-02-25 | 5 | 5 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-10-24 | 37 | 37 | 187 | 187 | 142 | 142 | 2019-03-29 | 2019-04-22 | 2019-07-11 | 29 | 29 | 59 | 59 | 75 | 75 | 2019-08-30 | 135 | 135 | 2019-10-02 | 24 | 24 | 2019-04-10 | 2019-04-10 | 2019-10-24 | 2019-10-24 | 142 | 142 | 139 | 139 | [6 empty] | 2019-10-11 | [10 empty] | 2019-10-28 | 2019-11-14 |  |  | 14 | 14 | 2019-11-19 |  |  |  | 2019-12-17 | 21 | 21 | 2019-12-20 |  |  |  | 537 | 537 |  |  | 2019
146 | Fullerton Target (Malvern) 200075-1520 | 1893- A W Malvern Avenue | Fullerton | 92835 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3023194 | 1819207 |  |  | 4 |  |  | NO | 2020-04-20 | 2020-05-04 | 11 | 11 | 2017-11-30 | 2020-04-07 | 20 | 20 | 611 | 611 | 2021-06-30 |  | 2020-04-19 |  |  |  |  | 2021-01-22 | 810 | 810 | 2021-01-25 | 2021-01-25 | 2021-02-26 | 2021-02-26 | 25 | 25 | 2021-03-02 | 2021-03-03 | 2 | 2 | 2021-03-31 | 2021-04-13 | 30 | 30 | 2021-04-29 | 13 | 13 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-29 | 52 | 52 | 84 | 84 | 4 | 4 |  | 2021-06-10 | 2021-07-12 |  |  | 22 | 22 | [8 empty] | 2021-06-10 |  | 2021-07-12 | [5 empty] | 2021-08-30 |  | 2021-09-16 | 13 | 13 | [12 empty] | 2021-08-23 | 2021-10-08 |  |  | 34 | 34 | 2021-10-12 |  |  |  | 2021-11-19 | 28 | 28 | 2021-11-19 |  |  |  | 1020 | 1020 | 211 | 211 | 2021
147 | Garden Grove Target | 12100 Harbor Boulevard | Garden Grove | 92840 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 |  | 2017-12-18
148 | Anaheim WalMart #1 | 1120 South Anaheim Boulevard | Anaheim | 92805 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01
149 | Anaheim WalMart #2 | 440 North Euclid Avenue | Anaheim | 92801 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01
150 | Lakewood WalMart 200041-1239 | 2770 East Carson Street | Lakewood | 90712 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-29 | 2018-02-02 | 7 | 7 | 5 | 5
151 | Seal Beach Target | 12300 Seal Beach Boulevard | Seal Beach | 90740 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01
152 | Cypress Target 200061 | 6835 Katella Avenue | Cypress | 90630 | Orange County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2548538 | 1464326 |  |  | 5 |  |  | NO | 2020-11-24 |  |  |  | 2017-11-30 | 2018-02-09 |  |  | 52 | 52 | 2018-02-12 | 2018-03-20 | 2018-03-20 | 28 | 28 | 1 | 1 | 2018-08-20 | 188 | 188 | 2018-08-20 | 2018-08-21 | 2018-09-19 | 2018-11-07 | 58 | 58 | 2018-11-08 | 2019-06-27 | 166 | 166 | 2019-07-19 | 2019-07-25 | 21 | 21 | 2019-07-25 | 1 | 1 | 2020-01-03 | 2019-09-03 | 2020-01-03 |  | 116 | 116 |  |  |  |  | 2019-12-19 | 2020-01-03 | 2021-01-11 | 106 | 106 | 257 | 257 | 267 | 267 | [6 empty] | 2020-01-03 | [7 empty] | 2019-10-01 |  | 2019-10-14 | 10 | 10 |  |  | 2019-10-23 | [10 empty] | 2021-01-29 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-11 | 28 | 28 | 2021-03-11 |  |  |  | 843 | 843 | 656 | 656 | 2021
153 | Costa Mesa Target 200056-1489 | 3030 Harbor Boulevard | Costa Mesa | 92626 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2018-02-09 |  |  | 52 | 52 | 2018-02-12 | 2018-02-21 | 2018-02-23 | 9 | 9 | 3 | 3
154 | Huntington Beach Target | 9882 Adams Avenue | Huntington Beach | 92646 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2584400 | 1475787 |  |  | 4 |  |  | true |  |  |  |  | 2017-11-30 | 2018-07-26 |  |  | 171 | 171 | 2018-07-26 | 2018-07-27 | 2018-07-27 | 2 | 2 | 1 | 1 | 2018-11-02 | 242 | 242 | 2018-11-05 |  | 2018-12-06 | 2018-12-13 | 30 | 30 | 2018-12-13 |  |  |  |  | 2019-04-22 |  |  | 2019-04-22 | 1 | 1 | 2019-05-03 | 2019-05-30 | 2019-05-03 | 2019-05-14 | 10 | 10 |  |  | 8 | 8 | 2019-02-04 | 2019-04-29 | 2019-08-29 | -56 |  | 89 | 89 | 149 | 149 | [6 empty] | 2019-04-29 |  | 2019-08-29 | [5 empty] | 2019-08-26 |  | 2019-09-11 | 13 | 13 | 2022-04-07 | [12 empty] | 2019-09-30 | -637 |  |  |  | 2019-10-09 |  |  |  | 2019-11-04 | 19 | 19 | 2019-11-04 |  |  |  | 503 | 503 | 262 | 262 | 2019
155 | Santa Ana Target | 3300 South Bristol Street | Santa Ana | 92704 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2599300 | 1487399 |  |  | 5 |  |  | NO | 2018-12-11 | 2019-01-02 | 17 | 17 | 2017-11-30 | 2018-02-09 | 234 | 234 | 52 | 52 | 2018-02-12 | 2018-02-15 | 2018-02-19 | 5 | 5 | 3 | 3 | 2018-12-11 | 269 | 269 | 2018-12-11 |  | 2019-01-11 | 2019-01-11 | 24 | 24 | 2019-01-11 |  |  |  |  | 2019-10-03 |  |  | 2019-10-03 | 1 | 1 | 2020-07-27 | 2020-08-14 | 2020-07-27 | 2020-07-28 | 208 | 208 |  |  | 2 | 2 | 2019-05-22 | 2020-06-17 | 2020-09-09 | -97 |  | 59 | 59 | 335 | 335 | 2020-07-15 | 200 | 200 | 2020-07-17 | 3 | 3 | 2020-06-17 | 2020-06-17 | 2020-09-09 | 2020-09-09 | 59 | 59 | 200 | 200 | [6 empty] | 2019-10-24 | [11 empty] | 2020-07-19 |  |  |  |  | 2020-07-20 |  |  |  | 2020-11-10 | 81 | 81 | 2020-11-10 |  |  |  | 763 | 763 | 495 | 495 | 2020
156 | Santa Ana WalMart 200056-1410 | 3600 West McFadden Avenue | Santa Ana | 92704 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2533860 | 1431398 |  |  | 3 |  |  | NO |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-29 | 2018-01-29 | 7 | 7 | 1 | 1 | 2018-07-16 | 163 | 163 | 2018-07-24 |  | 2018-08-15 | 2018-09-04 | 37 | 37 |  | 2018-11-08 |  |  | 2018-11-29 | 2018-12-31 | 38 | 38 | 2019-01-02 | 3 | 3 | 2019-01-09 | 2019-01-22 | 2019-01-09 | 2019-01-11 | 8 | 8 | 47 | 47 | 3 | 3 | 2018-12-31 | 2019-02-19 | 2019-05-31 | 1 | 1 | 74 | 74 | 110 | 110 | [6 empty] | 2019-01-09 |  | 2019-05-31 | [10 empty] | 2019-01-17 | [12 empty] | 2019-07-12 | 127 | 127 |  |  | 2019-08-29 |  |  |  | 2019-10-04 | 27 | 27 | 2019-10-04 |  |  |  | 482 | 482 | 320 | 320 | 2019
157 | Aliso Viejo Target | 26932 La Paz Road | Aliso Viejo | 92656 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-08 |  | 6 | 6
158 | Laguna Niguel WalMart 200039-1231 | 27470 Alicia Parkway | Laguna Niguel | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2538840 | 1442377 | [5 empty] | true |  |  |  |  | 2017-11-30 | 2018-01-19 |  |  | 37 | 37 | 2018-01-19 | 2018-01-29 | 2018-02-14 | 7 | 7 | 13 | 13 | 2018-07-27 | 172 | 172 | 2018-07-31 |  | 2018-08-28 | 2018-09-04 | 28 | 28 | 2018-09-04 |  |  |  |  | 2019-08-13 |  |  | 2019-08-13 | 1 | 1 | 2019-07-18 | 2019-07-30 | 2019-07-18 | 2019-09-16 | -19 |  |  |  | 43 | 43 | 2019-07-09 | 2019-08-20 | 2019-09-27 | -26 |  | 29 | 29 | 59 | 59 | [6 empty] | 2019-07-18 |  | 2019-09-27
159 | Palm Desert WalMart 100051-1406 | 34220 Monterey Avenue | Palm Desert | 92211 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO | 2018-01-19 |  |  |  | 2017-11-30 | 2017-12-07 |  |  | 6 | 6 | 2017-12-18 | 2017-12-20 | 2018-02-13 | 10 | 10 | 40 | 40
160 | Colton WalMart | 1120 South Mount Vernon Avenue | Colton | 92324 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-08 |  | 6 | 6
161 | Duarte WalMart 200050-1506 | 1600 Mountain Avenue | Duarte | 91010 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-13 | 2018-01-02 | 8 | 8 | 15 | 15
162 | Upland WalMart 100040-1503 | 1540 West Foothill Boulevard | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO | 2018-01-19 | 2018-03-07 | 34 | 34 | 2017-12-04 | 2017-12-04 | 68 | 68 | 1 | 1 | 2017-12-06 | 2017-12-12 | 2018-01-02 | 7 | 7 | 16 | 16
163 | Ontario Target 100040-03 | 4200 East 4th Street | Ontario | 91764 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-14 | 2018-01-02 | 9 | 9 | 14 | 14
164 | San Dimas Target | 888 West Arrow Highway | San Dimas | 91773 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 2543059 | 1448027 |  |  | 4 |  |  | NO |  |  |  |  | 2017-12-04 | 2018-05-07 |  |  | 111 | 111 | 2018-05-10 | 2018-05-17 | 2019-07-08 | 9 | 9 | 298 | 298 |  |  |  | 2018-08-09 | 2018-08-09 | 2018-09-07 | 2018-09-20 |  |  | 2018-09-21 | 2020-06-04 | 441 | 441 |  | 2020-06-19 | 12 | 12 | 2020-06-19 | 1 | 1 | 2020-07-14 | 2019-09-26 | 2020-07-14 | 2020-07-20 | 17 | 17 | 32 | 32 | 5 | 5 | 2019-11-01 | 2019-12-03 | 2020-09-09 | -162 |  | 196 | 196 | 218 | 218 | 2020-09-17 | 63 | 63 | 2020-10-20 | 24 | 24 | 2019-12-03 | 2019-12-03 | 2020-09-09 | 2020-10-20 | 225 | 225 | 63 | 63 | [5 empty] | 2020-07-17 | [12 empty] | 2020-11-10 | 82 | 82 |  |  | 2020-11-10 |  |  |  | 2021-01-07 | 38 | 38 | 2021-01-07 |  |  |  | 798 | 798 |  |  | 2021
165 | Torrance Target 200064-01 | 3433 Sepulveda Boulevard | Torrance | 90505 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2017-12-06 |  |  | 3 | 3 | 2017-12-06 | 2017-12-18 | 2018-01-02 | 9 | 9 | 12 | 12
166 | West Covina Eastland Center | 2753 E Eastland Center Drive | West Covina | 91791 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO | 2018-12-27 | 2019-01-10 | 11 | 11 | 2017-12-04 | 2017-12-04 | 289 | 289 | 1 | 1 | 2017-12-06 | 2017-12-19 | 2018-02-23 | 12 | 12 | 49 | 49
167 | San Dimas Brixmor | 853-1073 West Arrow Highway | San Dimas | 91773 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-11 | 2017-12-24 | 6 | 6 | 10 | 10
168 | Torrance Country Hills Shopping Center 200064-0162 | 2965 Rolling Hills Road | Torrance | 90505 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2459880 | 1383258 |  |  | 3 |  |  | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-11 | 2017-12-24 | 6 | 6 | 10 | 10 | 2018-01-30 | 42 | 42 | 2018-01-31 | 2018-02-05 | 2018-05-11 | 2018-05-02 | 67 | 67 | 2018-05-02 | 2018-05-09 | 6 | 6 |  | 2018-06-01 | 18 | 18 | 2018-06-01 | 1 | 1 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-13 | 1 | 1 | 26 | 26 | 9 | 9 | 2018-05-16 | 2018-06-01 | 2018-09-26 | -13 |  | 84 | 84 | 96 | 96 | [6 empty] | 2018-06-01 |  | 2018-09-26 | [5 empty] | 2018-08-16 |  |  |  |  | 2018-07-04 | 2018-08-08 | 2018-08-14 | [9 empty] | 2018-09-26 | 2019-08-16 | 293 | 293 | 233 | 233 | [7 empty] | 2018-11-06 |  |  |  | 242 | 242 | 201 | 201 | 2018
169 | Torrance Del Amo Center 200056-0176 | 21436 Del Amo Circle North | Torrance | 90503 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2490800 | 1418156 |  |  | 6 |  |  | YES | 2018-01-19 | 2018-02-13 | 18 | 18 | 2017-12-04 | 2017-12-04 | 52 | 52 | 1 | 1 | 2017-12-06 | 2017-12-11 | 2018-01-02 | 6 | 6 | 17 | 17 | 2018-04-04 | 88 | 88 | 2018-04-11 | 2018-04-13 | 2018-05-10 | 2018-05-22 | 35 | 35 | 2018-05-22 | 2018-05-24 | 3 | 3 |  | 2018-07-02 | 28 | 28 | 2018-07-02 | 1 | 1 | 2018-07-02 | 2019-05-30 | 2018-07-02 | 2018-07-26 | 1 | 1 | 46 | 46 | 19 | 19 | 2018-05-30 | 2018-07-02 | 2018-08-17 | -24 |  | 35 | 35 | 58 | 58 | 2019-03-07 | 179 | 179 |  |  |  | 2018-07-02 | 2018-07-02 | 2018-08-17 |  |  |  | 179 | 179 | 2019-03-05 |  |  |  |  | 2019-01-03 | [12 empty] | 2019-04-23 | 79 | 79 |  |  | 2019-05-30 |  |  |  | 2019-06-28 | 22 | 22 | 2019-06-28 |  |  |  | 410 | 410 | 323 | 323 | 2019
170 | West Covina Eastland Center Walmart | 2753 E. Eastland Center | West Covina | 91791 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona | [9 empty] | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-14 | 2018-01-02 | 9 | 9 | 14 | 14
171 | Ontario Mills 100040-0296 | 1 Mills Circle | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2522490 | 1425907 |  |  | 8 |  |  | true | 2018-01-19 | 2018-03-07 | 34 | 34 | 2017-12-04 | 2018-05-10 | -47 |  | 114 | 114 | 2018-05-10 | 2018-05-10 | 2018-05-13 | 1 | 1 | 2 | 2 | 2018-06-21 | 144 | 144 | 2018-06-25 | 2018-06-25 | 2018-07-23 | 2018-08-10 | 37 | 37 | 2018-08-13 | 2018-08-14 | 2 | 2 | 2018-09-10 | 2018-09-14 | 24 | 24 | 2018-09-18 | 3 | 3 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-29 | 30 | 30 | 55 | 55 | 3 | 3 | 2018-10-23 | 2018-11-08 | 2018-12-10 | 28 | 28 | 23 | 23 | 35 | 35 | [6 empty] | 2018-10-25 |  | 2018-12-10 | [5 empty] | 2019-03-27 |  |  |  |  | 2018-12-24 | 2019-03-05 | [11 empty] | 2019-05-07 | 97 | 97 |  |  | 2019-06-14 |  |  |  | 2019-08-22 | 50 | 50 | 2019-08-22 |  |  |  | 449 | 449 | 306 | 306 | 2019
172 | Upland Mountain Square 100040-1347 | 250 South Mountain Avenue | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-12 | 2018-01-02 | 7 | 7 | 16 | 16
173 | Tustin Larwin Square 100038-1641 | 13421 Newport Avenue | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2018-02-13 |  |  | 52 | 52 | 2018-02-15 | 2018-02-20 | 2018-03-21 | 6 | 6 | 22 | 22
174 | Tustin Heights Kimco | 1138 Irvine Boulevard | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2018-03-22 |  |  | 79 | 79 | 2018-03-27 | 2018-04-08 | 2018-04-08 | 12 | 12 | 0
175 | Santa Ana Home Depot Plaza (Kimco) | 3500 West Macarther Boulevard | Santa Ana | 92704 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06
176 | La Mirada Theater Center (Kimco) 200075-1408 | 15210 Rosecrans Boulevard | La Mirada | 90638 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2471990 | 1392801 |  |  | 3 |  |  | NO |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-20 | 2017-12-23 | 13 | 13 | 3 | 3 | 2018-03-26 | 81 | 81 | 2018-03-28 | 2018-03-28 | 2018-07-11 | 2018-07-11 | 78 | 78 | 2018-07-11 | 2018-07-12 | 2 | 2 | 2018-08-17 | 2018-08-20 | 28 | 28 | 2018-08-21 | 2 | 2 | 2018-08-21 | 2018-09-11 | 2018-08-21 | 2018-08-30 | 2 | 2 | 36 | 36 | 8 | 8 |  |  | 2019-01-24 | [14 empty] | 2019-01-24 | [10 empty] | 2018-10-10 |  |  | 2018-10-15 | 4 | 4 | [6 empty] | 2019-02-18 | 2019-02-18 | 94 | 94 | 1 | 1 | 2019-03-29 |  |  |  | 2019-04-23 | 18 | 18 | 2019-04-23 |  |  |  | 362 | 362 | 282 | 282 | 2019
177 | Westminster Kimco Pavilions Place 200076-1403 | 16450 Beach Boulevard | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-20 | 2017-12-23 | 13 | 13 | 3 | 3
178 | Lakewood Plaza (Bellflower) Kimco | 17220 Lakewood Boulevard | Bellflower | 90706 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2017-12-04 | 2017-12-04 |  |  | 1 | 1 | 2017-12-06 | 2017-12-20 | 2017-12-23 | 13 | 13 | 3 | 3
179 | Orange Outlets 200054 | 20 City Boulevard West | Orange | 92868 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2555210 | 1448145 |  |  | 4 |  |  | NO | 2018-01-19 | 2018-02-26 | 27 | 27 | 2017-12-07 | 2018-05-22 | -62 |  | 119 | 119 |  |  | 2018-11-29 | [7 empty] | 2018-09-04 |  | 2018-10-02 |  |  |  |  | 2018-11-09 |  |  |  | 2019-01-10 | 45 | 45 | 2019-01-10 | 1 | 1 | 2019-06-20 | 2019-07-26 | 2019-06-20 | 2019-06-27 | 116 | 116 | 165 | 165 | 6 | 6 | 2019-01-10 | 2019-02-19 | 2019-03-04 | 1 | 1 | 10 | 10 | 38 | 38 | [6 empty] | 2019-02-19 |  | 2019-06-27 | [5 empty] | 2019-07-08 | 2019-08-07 | 2019-08-07 | 23 | 23 |  |  | 2019-06-04 | [9 empty] | 2019-08-19 | 2019-09-05 |  |  | 14 | 14 | 2019-09-10 |  |  |  | 2019-10-16 | 27 | 27 | 2019-10-16 |  |  |  | 485 | 485 |  |  | 2019
180 | Brea Mall 200060-0108 | 1065 Brea Mall | Brea | 92821 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2497561 | 1431429 |  |  | 4 |  |  | true | 2018-03-20 | 2018-06-18 | 65 | 65 | 2017-12-07 | 2018-01-19 | 107 | 107 | 32 | 32 | 2018-01-19 | 2017-12-20 | 2017-12-20 | -23 |  | 1 | 1 |  |  |  | 2018-04-27 | 2018-04-27 | 2018-08-08 | 2018-09-17 |  |  | 2018-09-17 | 2019-10-15 | 282 | 282 | 2019-11-07 | 2019-11-07 | 18 | 18 | 2019-11-07 | 1 | 1 | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-11 | -218 |  | -198 |  | 4 | 4 | 2018-05-24 | 2019-02-07 | 2020-04-23 | -381 |  | 313 | 313 | 498 | 498 | [6 empty] | 2019-01-08 |  | 2020-04-23 | [5 empty] | 2020-06-10 |  | 2020-07-06 | 18 | 18 | 2020-05-07 | [12 empty] | 2020-07-28 | 57 | 57 |  |  | 2020-07-30 |  |  |  | 2020-08-25 | 19 | 19 | 2020-08-25 |  |  |  | 704 | 704 |  |  | 2020
181 | Santa Monica, CA - 1421 Santa Monica Blvd | 1421 Santa Monica Blvd | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2442205 | 1361685 |  |  | 26 |  |  | true | 2020-01-31 | 2020-02-13 | 10 | 10 | 2017-12-18 | 2018-01-17 | 540 | 540 | 23 | 23 | 2018-01-18 | 2018-01-22 | 2020-02-12 | 4 | 4 | 536 | 536 |  |  |  | 2018-01-30 |  | 2020-03-30 | 2020-03-30 |  |  | 2020-03-31 | 2021-04-29 | 273 | 273 |  | 2021-05-19 | 15 | 15 | 2021-05-19 | 1 | 1 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-24 | 14 | 14 | 40 | 40 | 13 | 13 | 2020-05-29 | 2020-07-15 | 2021-09-27 | -245 |  | 303 | 303 | 335 | 335 | 2021-12-02 | 136 | 136 |  |  |  | 2020-07-15 | 2020-07-15 | 2021-09-27 |  |  |  | 136 | 136 | [18 empty] | 2022-01-08 |  |  |  |  | 2022-01-05 |  |  |  | 2022-02-01 | 19 | 19 | 2022-02-01 |  |  |  | 1056 | 1056 |  |  | 2022
182 | Costa Mesa, CA- 3333 Bristol St (South Coast Plaza) | 3333 Bristol Street | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2442200 | [6 empty] | NO | 2019-10-18 |  |  |  | 2017-12-18 | 2017-12-18 |  |  | 1 | 1 | 2017-12-19 | 2018-01-18 | 2018-02-02 | 24 | 24 | 12 | 12
183 | Hesperia Target | 12795 Main Street | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [9 empty] | YES |  |  |  |  | 2017-11-30 | 2017-12-01 |  |  | 2 | 2 | 2017-12-01 | 2017-12-10 | 2017-12-11 | 6 | 6 | 1 | 1
184 | Rolling Hills, CA - 550 Deep Valley Drive (Phase 1) | 550 Deep Valley Dr | Rolling Hills Estates | 90274 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Ventura |  |  | 2490790 | 1395056 |  |  |  | NO |  | true | 2023-08-17 | 2023-09-27 | 29 | 29 | 2023-07-07 | 2023-08-15 | 31 | 31 | 28 | 28 | 2023-08-16 | 2023-08-21 | 2023-09-05 | 5 | 5 | 11 | 11
185 | Malibu Cross Creek Road | 3822 Cross Creek Rd EV1 | Malibu | 90265 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2571130 | 1457253 |  |  | 8 |  |  | NO | 2018-01-02 | 2018-01-10 | 7 | 7 | 2017-12-28 | 2018-01-16 | -5 |  | 14 | 14 | 2018-01-16 | 2018-02-12 | 2018-02-20 | 20 | 20 | 7 | 7 |  |  |  | 2018-10-09 |  | 2018-11-07 | 2018-11-07 |  |  | 2018-11-08 | 2019-09-25 | 230 | 230 | 2019-10-16 | 2019-10-17 | 17 | 17 | 2019-10-17 | 1 | 1 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2020-02-17 | 35 | 35 | 101 | 101 | 51 | 51 | 2018-12-21 | 2019-01-16 | 2020-03-18 | -215 |  | 303 | 303 | 321 | 321 | [6 empty] | 2019-01-16 |  | 2020-03-18 | [5 empty] | 2020-08-23 |  | 2020-09-02 | 8 | 8 | 2020-06-04 | [12 empty] | 2020-10-13 | 92 | 92 |  |  | 2020-11-04 |  |  |  | 2020-12-15 | 27 | 27 | 2020-12-15 |  |  |  | 765 | 765 |  |  | 2020
186 | Inyokern Airport | 1669 Airport Road | Inyokern | 93527 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 2816858 | 1662016 |  |  | 2 |  |  | NO |  |  |  |  | 2017-12-26 | 2017-12-26 |  |  | 1 | 1 | 2018-01-03 | 2018-01-11 | 2018-01-12 | 13 | 13 | 2 | 2 |  |  |  | 2020-02-06 |  |  | 2020-02-28 |  |  | 2020-02-28 | 2020-02-28 | 1 | 1 | 2020-03-20 | 2020-02-28 | 1 | 1 | 2020-02-28 | 1 | 1 | 2020-03-17 | 2020-06-18 | 2020-03-17 | 2020-07-31 | 13 | 13 | 109 | 109 | 97 | 97 |  | 2020-06-01 | 2020-07-16 |  |  | 33 | 33 | [8 empty] | 2020-03-17 |  | 2020-07-31 | [5 empty] | 2020-03-17 |  | 2020-03-27 | 9 | 9 | 2020-02-28 | 2020-03-06 |  | 2020-03-03 | 3 | 3 | 2020-03-16 | 10 | 10 |  |  |  | 2020-04-22 | 2020-05-17 | 56 | 56 | 18 | 18 | 2020-08-25 | [6 empty] | 2020-09-28 |  |  |  | 714 | 714 |  |  | 2020
187 | Lancaster Park and Ride | 1601 West Avenue K | Lancaster | 93534 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2448730 | 1441031 |  |  |  | NO |  | true |  |  |  |  | 2018-01-04 | 2018-03-02 |  |  | 42 | 42 | 2018-03-02 | 2018-03-12 | 2018-03-14 | 7 | 7 | 3 | 3 |  |  |  | 2018-08-09 |  |  | 2018-08-30 |  |  | 2018-08-30 | 2018-09-05 | 5 | 5 | 2018-09-26 | [6 empty] | 2018-11-02 | 2019-04-18 | 2018-11-02 | 2019-04-17 |  |  | 161 | 161 | 119 | 119 | [9 empty] | 2019-04-03 | [18 empty] | 2018-12-19 | 2019-02-27 | 2019-06-07 | [9 empty] | 2019-04-15 | 2019-06-24 | 134 | 134 | 51 | 51
188 | Mirage River Mall | 71800 Highway 111 | Rancho Mirage | 92270 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2485660 | 1392626 |  |  | 24 |  |  | NO | 2018-01-09 | 2018-01-12 | 4 | 4 | 2018-01-09 | 2018-01-09 | 4 | 4 | 1 | 1 | 2018-01-11 | 2018-01-18 | 2018-01-22 | 8 | 8 | 3 | 3 | 2018-03-28 | 57 | 57 | 2018-03-29 |  | 2018-04-30 | 2018-05-09 | 31 | 31 | 2018-05-09 | 2018-05-22 | 10 | 10 |  | 2019-07-11 | 298 | 298 | 2019-07-11 | 1 | 1 | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-07-24 | 9 | 9 | 307 | 307 | 2 | 2 | 2018-06-19 | 2019-01-29 | 2019-07-24 | -278 |  | 127 | 127 | 287 | 287 | [6 empty] | 2019-01-29 |  | 2019-07-24 | [5 empty] | 2019-07-03 |  | 2019-07-29 | 19 | 19 | 2019-05-17 |  | 2019-06-26 | [9 empty] | 2019-07-25 | 2019-08-08 | 60 | 60 | 11 | 11 | 2019-08-08 |  |  |  | 2019-09-11 | 25 | 25 | 2019-09-11 |  |  |  | 437 | 437 | 381 | 381 | 2019
189 | Palmdale West Avenue S | 434 West Avenue S | Palmdale | 93550 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2018-01-09 | 2018-01-12 |  |  | 4 | 4 | 2018-01-12 | 2018-01-23 | 2018-02-14 | 8 | 8 | 17 | 17
190 | Palmdale East Avenue S | 210 East Avenue S | Palmdale | 93550 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2018-01-08 | 2018-01-12 |  |  | 5 | 5 | 2018-01-12 | 2018-01-23 | 2018-02-14 | 8 | 8 | 17 | 17
191 | Seal Beach Target 200061-1488 | 12300 Seal Beach Boulevard | Seal Beach | 90740 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2018-01-29
192 | Malibu Whole Foods Civic Center | 23475 Civic Center Way | Malibu | 90265 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2523690 | 1418468 |  |  | 5 |  |  | NO | 2018-02-07 | 2018-02-25 | 13 | 13 | 2018-02-08 | 2018-02-08 | 12 | 12 | 1 | 1 | 2018-02-08 | 2018-02-12 | 2018-03-01 | 3 | 3 | 14 | 14 |  |  |  | 2018-06-27 |  | 2018-07-26 | 2018-07-03 |  |  | 2018-07-03 | 2018-07-18 | 12 | 12 | 2018-08-17 | 2018-08-17 | 23 | 23 | 2018-08-17 | 1 | 1 | 2018-08-24 |  | 2018-08-24 | 2018-08-30 | 6 | 6 | 32 | 32 | 5 | 5 | [28 empty] | 2018-12-03 |  | 2019-01-31 | [9 empty] | 2019-01-24 | 2019-04-24 | 103 | 103 | 65 | 65 | 2019-04-26 |  |  |  | 2019-05-08 | 9 | 9 | 2019-05-08 |  |  |  | 325 | 325 |  |  | 2019
193 | Palmdale Target | 39440 10th Street West | Palmdale | 93551 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura |  |  | 2551041 | 1441520 |  |  | 4 |  |  | NO |  |  |  |  | 2018-03-08 | 2018-03-12 |  |  | 3 | 3 | 2018-03-12 | 2018-03-15 | 2018-03-18 | 4 | 4 | 2 | 2 |  |  |  | 2018-08-24 |  | 2018-09-11 | 2018-08-31 |  |  | 2018-09-04 | 2018-09-04 | 1 | 1 | 2018-09-25 | 2018-09-06 | 3 | 3 |  |  |  | 2018-10-04 | 2018-10-16 | 2018-10-04 | 2019-02-06 | 21 | 21 | 112 | 112 | 90 | 90 | 2018-09-12 | 2018-10-05 | 2018-11-19 | 5 | 5 | 32 | 32 | 49 | 49 | 2019-10-18 |  |  | 2020-02-21 | 88 | 88 | 2018-10-04 | 2018-10-04 | 2019-02-06 | 2020-02-21 | 359 | 359 | 292 | 292 | [5 empty] | 2018-09-12 | 2018-10-24 |  | 2018-09-12 | 1 | 1 | [7 empty] | 2019-10-30 | 296 | 296 |  |  | 2020-03-16 | 2020-04-16 | 24 | 24 |  |  |  | 2020-04-20 |  |  |  | 550 | 550 |  |  | 2020
194 | Blythe Red Roof Inn | 850 West Hobson Way | Blythe | 92225 | Riverside County | 9. Complete | 87 - Blythe | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2018-03-29 | 2018-03-29 |  |  | 1 | 1 | 2018-04-06 | 2018-04-09 | 2018-04-16 | 8 | 8 | 6 | 6
195 | Baker Grewal Travel Center | 72922 Baker Boulevard | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2583310 | 1470600 |  |  | 5 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-09 | 2018-03-21 | 12 | 12 | 9 | 9 | 2018-11-02 | 184 | 184 | 2018-11-02 |  | 2018-12-05 | 2018-12-05 | 24 | 24 | 2018-12-06 | 2018-12-11 | 4 | 4 | 2019-01-02 | 2018-12-14 | 4 | 4 | 2018-12-26 | 9 | 9 | 2019-01-08 | 2019-06-13 | 2019-01-08 | 2019-04-15 | 18 | 18 | 90 | 90 | 70 | 70 | 2018-12-17 | 2018-12-26 | 2019-02-01 | 2 | 2 | 28 | 28 | 35 | 35 | [6 empty] | 2018-12-26 |  | 2019-04-15 | [7 empty] | 2019-03-18 |  |  |  | 2019-02-11 | 2019-02-20 | [9 empty] | 2019-09-09 | 2019-10-03 |  |  | 19 | 19 | 2019-10-07 |  |  |  | 2019-11-21 | 34 | 34 | 2019-12-05 |  |  |  | 468 | 468 | 285 | 285 | 2019
196 | Baker Shell Rasor Road | 66150 Rasor Road | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-12 | 11 | 11 | 3 | 3
197 | Inyokern Robbers Roost Mini Mart | 49901 Highway 14 | Inyokern | 93527 | Kern County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura | [9 empty] | NO |  |  |  |  | 2018-07-02 | 2018-07-02 |  |  | 1 | 1 | 2018-07-05
198 | Mojave Dennys | 16262 Sierra Highway | Mojave | 93501 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 2570288 | 1461615 |  |  | 3 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-13 | 11 | 11 | 4 | 4 |  |  |  | 2018-10-08 |  | 2018-11-05 | 2018-10-24 |  |  | 2018-10-24 | 2019-07-18 | 192 | 192 | 2019-08-08 | 2019-07-30 | 9 | 9 | 2019-07-30 | 1 | 1 | 2019-07-30 | 2020-05-12 | 2019-11-21 | 2020-03-02 | 83 | 83 | 160 | 160 | 70 | 70 | 2018-10-30 | 2018-11-27 | 2020-10-09 | -196 |  | 483 | 483 | 503 | 503 | 2020-09-25 | 298 | 298 | 2020-10-13 | 13 | 13 | 2018-11-27 | 2018-11-27 | 2020-10-09 | 2020-10-13 | 485 | 485 | 298 | 298 | [18 empty] | 2021-01-22 |  |  |  |  | 2021-01-26 | [6 empty] | 2021-02-23 |  |  |  | 773 | 773 |  |  | 2021
199 | Barstow Love's | 2978 Lenwood Road | Barstow | 92311 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2554057 | 1466751 |  |  | 4 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-12 | 11 | 11 | 3 | 3 | 2018-08-29 | 137 | 137 | 2018-08-29 |  | 2018-09-27 | 2018-09-24 | 19 | 19 | 2018-09-24 | 2018-09-24 | 1 | 1 |  | 2018-10-16 | 17 | 17 | 2018-10-16 | 1 | 1 | 2019-11-21 | 2020-04-22 | 2019-11-21 | 2020-03-02 | 288 | 288 | 373 | 373 | 70 | 70 |  | 2018-12-18 | 2019-10-15 |  |  | 216 | 216 | [8 empty] | 2018-12-18 |  | 2020-03-02 | [5 empty] | 2020-03-02 | 2020-03-17 | 2020-03-17 | 12 | 12 | 2020-01-24 |  | 2020-02-11 | 2020-01-29 | 4 | 4 |  |  |  | 2020-02-14 | 4 | 4 | 2020-04-07 | 2020-04-08 | 53 | 53 | 2 | 2 | 2020-04-23 | 2020-05-27 | 24 | 24 | 2020-05-28 | 25 | 25 | 2020-05-28 |  |  |  | 589 | 589 | 453 | 453 | 2020
200 | Yermo Eddie's World 3 | 35999 Calico Boulevard | Yermo | 92398 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2559790 | 1450211 |  |  | 4 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-12 | 11 | 11 | 3 | 3 | 2018-09-12 | 147 | 147 | 2018-09-13 |  | 2018-10-11 | 2018-10-10 | 21 | 21 | 2018-10-10 | 2018-10-25 | 12 | 12 | 2018-11-15 | 2018-11-30 | 27 | 27 | 2018-12-04 | 3 | 3 | 2018-12-04 | 2019-01-30 | 2018-12-04 | 2019-02-06 | 3 | 3 | 75 | 75 | 47 | 47 | 2018-11-08 | 2018-12-03 | 2019-02-01 | -17 |  | 45 | 45 | 62 | 62 | 2019-02-08 | 49 | 49 | 2019-02-11 | 2 | 2 | 2018-12-03 | 2018-12-03 | 2019-02-06 | 2019-02-11 | 51 | 51 | 51 | 51 | [6 empty] | 2019-01-28 | 2020-02-10 | [6 empty] | 2020-02-14 | 5 | 5 | 2020-02-28 | 2020-03-10 |  |  | 8 | 8 | 2020-03-27 | 2020-04-23 | 20 | 20 | 2020-04-23 | 20 | 20 | 2020-04-23 |  |  |  | 565 | 565 | 419 | 419 | 2020
201 | Tehachapi Dennys | 847 #A Magellan Drive | Tehachapi | 93561 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 2570369 | 1459354 |  |  | 3 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-12 | 11 | 11 | 3 | 3 |  |  |  | 2018-10-08 |  | 2018-11-05 | 2018-10-19 |  |  | 2018-10-19 | 2018-11-16 | 21 | 21 | 2018-12-10 | 2018-11-18 | 1 | 1 | 2018-11-19 | 1 | 1 | 2018-12-05 | 2019-01-29 | 2018-12-05 | 2019-02-06 | 13 | 13 | 59 | 59 | 46 | 46 | 2018-11-28 | 2018-12-17 | 2019-04-08 | 8 | 8 | 81 | 81 | 94 | 94 | 2020-03-04 | 335 | 335 | 2020-03-27 | 18 | 18 | 2018-12-05 | 2018-12-05 | 2019-04-08 | 2020-03-27 | 340 | 340 | 335 | 335 | 2020-06-02 | 2020-06-23 | 2020-06-23 | 16 | 16 | 2020-03-02 |  | 2020-04-09 | [6 empty] | 2020-04-16 | 6 | 6 |  | 2020-05-11 | 51 | 51 |  |  | 2020-05-18 | 2020-06-19 | 24 | 24 | 2020-06-23 | 26 | 26 | 2020-06-23 |  |  |  | 607 | 607 |  |  | 2020
202 | Victorville Motel 6 | 16868 Stoddard Wells Road | Victorville | 92394 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 2559793 | 1452698 |  |  | 4 |  |  | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-12 | 11 | 11 | 3 | 3 | 2018-09-12 | 147 | 147 | 2018-09-13 |  | 2018-10-11 | 2018-10-10 | 21 | 21 | 2018-10-10 | 2018-10-25 | 12 | 12 |  | 2018-12-03 | 28 | 28 | 2018-12-04 | 2 | 2 | 2018-12-04 | 2019-01-29 | 2018-12-04 | 2019-02-06 | 2 | 2 | 75 | 75 | 47 | 47 | 2018-11-07 |  | 2019-05-14 | -19 |  |  |  | 135 | 135 | [8 empty] | 2019-05-14 | [11 empty] | 2019-11-20 | 2020-01-13 | [9 empty] | 2020-02-11 | 2020-02-26 |  |  | 11 | 11 | 2020-02-27 | 2020-02-26 | -2 |  | 2020-02-27 | 1 | 1 | 2020-02-27 |  |  |  | 525 | 525 | 379 | 379 | 2020
203 | Boron Chevron | 5852 CA-58 | Boron | 93516 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 2597160 | [6 empty] | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-08 | 2018-03-13 | 11 | 11 | 4 | 4 | 2018-12-04 | 206 | 206 | 2018-12-05 |  | 2019-01-03
204 | Yorba Linda Town Center #1 | 4902 Main Street | Yorba Linda | 92886 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2018-02-16 | 2018-03-20 |  |  | 23 | 23 | 2018-03-21 | 2018-03-27 |  | 6 | 6
205 | Alhambra Place | 100 East Main Street | Alhambra | 91801 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-03-21 | 2018-03-23 | 2018-04-04 | 26 | 26 | 9 | 9
206 | Pacoima BRX | 9635 Laurel Canyon Boulevard | Pacoima | 91331 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 |  | 8 | 8
207 | Paramount City Hall | 16400 Colorado Avenue | Paramount | 90723 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 | 2018-03-01 | 8 | 8 | 3 | 3
208 | Paramount Sheriff Station | 15001 Paramount Boulevard | Paramount | 90723 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 | 2018-03-01 | 8 | 8 | 3 | 3
209 | Cathedral City Brixmor Plaza Rio Vista | 67800 Vista Chino | Cathedral City | 92234 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-26 | 2018-02-28 | 7 | 7 | 3 | 3
210 | Valley Wells Southbound Rest Area | 88610 I-15 Freeway | Nipton | 92364 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2483442 | 1390892 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 | 2018-03-03 | 8 | 8 | 4 | 4 | 2018-03-23 | 26 | 26 | 2018-03-26 | 2018-03-27 | 2018-04-30 | 2018-04-30 | 27 | 27 | 2018-04-30 | 2018-08-03 | 70 | 70 |  | 2018-09-28 | 41 | 41 | 2018-09-28 | 1 | 1 | 2018-09-28 | 2019-12-24 | [49 empty] | 2020-08-31 |  |  |  |  | 2020-09-30 |  |  |  | 2020-11-20 | 37 | 37 | 2020-11-20 |  |  |  | 714 | 714 | 689 | 689 | 2020
211 | Valley Wells Northbound Rest Area | 88611 I-15 Freeway | Nipton | 92364 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2483424 | 1386205 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 | 2018-03-03 | 8 | 8 | 4 | 4 | 2018-03-26 | 27 | 27 | 2018-03-26 |  |  | 2018-04-23 | 21 | 21 | 2018-04-23 | 2018-08-03 | 75 | 75 |  | 2018-10-01 | 42 | 42 | 2018-10-02 | 2 | 2 | 2018-10-02 | 2019-12-24 | [49 empty] | 2020-08-31 |  |  |  |  | 2020-09-30 |  |  |  | 2021-01-21 | 76 | 76 | 2021-01-21 |  |  |  | 753 | 753 | 727 | 727 | 2021
212 | Kane NB I-15 Rest Area | 54171 I-15 Freeway | Baker | 92364 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 2505487 | 1408010 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-16 | 2018-02-16 |  |  | 1 | 1 | 2018-02-19 | 2018-02-27 | 2018-03-03 | 8 | 8 | 4 | 4 | 2018-05-02 | 54 | 54 | 2018-05-16 | 2018-05-17 |  | 2018-06-25 | 39 | 39 | 2018-06-25 |  |  |  |  | 2018-09-04 |  |  | 2018-09-04 | 1 | 1 | 2018-08-03 | 2019-12-24 | 2018-08-03 | 2020-09-18 | -23 |  |  |  | 550 | 550 | [9 empty] | 2020-07-30 | 493 | 493 | 2020-09-21 | 37 | 37 | [6 empty] | 493 | 493 | [18 empty] | 2020-09-09 |  |  |  |  | 2020-10-06 |  |  |  | 2020-11-20 | 33 | 33 | 2020-11-20 |  |  |  | 714 | 714 | 661 | 661 | 2020
213 | Huntington Beach Marina Village | 5922 Edinger Avenue | Huntington Beach | 92649 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2510920 | 1411540 |  |  | 3 |  |  | NO |  |  |  |  | 2018-02-16 | 2018-02-19 |  |  | 2 | 2 | 2018-02-23 |  | 2018-03-06 | [7 empty] | 2018-05-29 | 2018-05-30 |  | 2018-08-06 |  |  | 2018-08-06 | 2018-08-07 | 2 | 2 | 2019-02-20 | 2019-04-22 | 185 | 185 | 2019-04-22 | 1 | 1 | 2019-05-06 | 2019-06-24 | 2019-05-06 | 2019-06-19 | 11 | 11 | 227 | 227 | 33 | 33 | 2019-02-27 | 2019-04-29 | 2019-10-10 | -39 |  | 119 | 119 | 162 | 162 | 2019-06-13 | 39 | 39 | 2019-06-17 | 3 | 3 | 2019-04-29 | 2019-04-29 | 2019-10-10 | 2019-10-10 | 119 | 119 | 39 | 39 | 2019-07-11 |  | 2019-07-24 | 10 | 10 | 2019-02-15 | [12 empty] | 2019-07-11 | 105 | 105 |  |  | 2019-10-11 |  |  |  | 2019-11-23 | 31 | 31 | 2019-11-23 |  |  |  | 461 | 461 |  |  | 2019
214 | Westminster Mall 2 200077 | 1025 Westminster Mall | Westminster | 92683 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2562370 | 1460654 |  |  | 4 |  |  | NO |  |  |  |  | 2018-02-16 | 2018-05-14 |  |  | 62 | 62 | 2018-05-18 | 2018-05-21 | 2018-05-24 | 6 | 6 | 4 | 4 | 2018-09-18 | 153 | 153 | 2018-09-19 |  | 2018-10-17 | 2018-10-23 | 26 | 26 | 2018-10-25 | 2018-10-29 | 3 | 3 | 2018-11-21 | 2019-01-10 | 54 | 54 | 2019-01-10 | 1 | 1 | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-02-15 | 21 | 21 | 80 | 80 | 7 | 7 | 2019-01-10 | 2019-02-08 | 2019-03-14 | 1 | 1 | 25 | 25 | 46 | 46 | [6 empty] | 2019-02-07 |  | 2019-03-14 | [5 empty] | 2019-06-29 |  | 2019-07-24 | 18 | 18 | [13 empty] | 2019-09-04 |  |  |  |  | 2019-09-05 |  |  |  | 2019-10-12 | 27 | 27 | 2019-10-12 |  |  |  | 431 | 431 | 279 | 279 | 2019
215 | Kane SB I-15 Rest Area | 54170 I-15 Freeway | Baker | 92364 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2505481 | 1408246 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-21 | 2018-02-21 |  |  | 1 | 1 | 2018-02-21 | 2018-02-27 | 2018-03-03 | 5 | 5 | 4 | 4 | 2018-05-02 | 51 | 51 | 2018-05-16 | 2018-05-17 |  | 2018-06-25 | 39 | 39 | 2018-06-25 | 2018-07-11 | 13 | 13 | 2018-07-25 | 2018-08-03 | 18 | 18 | 2018-08-03 | 1 | 1 | 2018-08-03 | 2019-12-24 | 2018-08-03 | 2020-09-18 | 1 | 1 | 567 | 567 | 550 | 550 | [29 empty] | 2020-01-07 | [11 empty] | 2020-09-10 |  |  |  |  | 2020-10-06 |  |  |  | 2020-11-20 | 33 | 33 | 2020-11-20 |  |  |  | 711 | 711 | 661 | 661 | 2020
216 | Foothill Transit | 5460 Peck Road | Arcadia | 91007 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2018-02-20 | 2018-02-22 |  |  | 3 | 3 | 2018-02-22 | 2018-03-02 | 2018-03-08 | 7 | 7 | 5 | 5 | 2018-03-08 | 13 | 13 | 2018-03-13 |  | 2018-04-10 | 2018-06-08 | 67 | 67
217 | Santa Monica Chevron | 1819 Cloverfield Boulevard | Santa Monica | 90404 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-07-28 |  |  |  | 2018-02-22 | 2018-02-22 |  |  | 1 | 1 | 2018-02-22 | 2018-03-02 | 2018-04-04 | 7 | 7 | 24 | 24
218 | Rancho Santa Margarita Target | 30602 Santa Margarita Parkway | Rancho Santa Margarita | 92688 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2527320 | 1432819 |  |  | 3 |  |  | true |  |  |  |  | 2018-02-22 | 2018-02-22 |  |  | 1 | 1 | 2018-02-22 | 2018-02-28 | 2018-03-02 | 5 | 5 | 3 | 3 | 2018-07-02 | 93 | 93 | 2018-07-05 | 2018-07-05 | 2018-08-02 | 2018-08-14 | 32 | 32 | 2018-08-14 | 2018-08-17 | 4 | 4 |  | 2018-09-14 | 21 | 21 | 2018-09-18 | 3 | 3 | 2018-09-18 | 2018-11-08 | 2018-09-18 | 2018-10-01 | 3 | 3 | 32 | 32 | 10 | 10 | 2018-11-19 | 2019-01-10 | 2019-08-19 | 47 | 47 | 158 | 158 | 196 | 196 | 2019-10-03 | 273 | 273 | 2019-10-04 | 2 | 2 | 2018-09-18 | 2018-09-18 | 2019-08-19 | 2019-10-04 | 274 | 274 | 275 | 275 | 2019-10-02 |  | 2019-10-22 | 15 | 15 |  | 2019-08-06 | 2019-10-22 | [10 empty] | 2019-11-14 |  |  |  |  | 2019-11-15 |  |  |  | 2019-12-21 | 26 | 26 | 2019-12-21 |  |  |  | 477 | 477 | 385 | 385 | 2019
219 | Palm Springs City Parking Garage | 101 North Museum Drive | Palm Springs | 92262 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2508810 | 1468922 |  |  | 11 |  |  | NO | 2018-02-22 | 2018-03-26 | 23 | 23 | 2018-02-22 | 2018-02-26 | 21 | 21 | 3 | 3 | 2018-03-01 | 2018-03-07 | 2018-03-08 | 8 | 8 | 2 | 2 |  |  |  | 2018-05-24 |  | 2018-06-21 | 2018-10-12 |  |  | 2018-10-12 |  |  |  |  | 2019-01-09 |  |  | 2019-01-09 | 1 | 1 | 2019-02-28 | 2019-04-24 | 2019-02-28 | 2019-03-01 | 37 | 37 |  |  | 2 | 2 | [9 empty] | 2019-04-16 | 70 | 70 | 2019-05-28 | 31 | 31 | [6 empty] | 70 | 70 | 2019-04-16 |  |  |  |  | 2019-03-27 | 2019-04-16 | 2019-04-05 | 2019-04-01 | 4 | 4 | [6 empty] | 2019-05-08 | 2019-05-08 | 31 | 31 | 1 | 1 | 2019-05-09 |  |  |  | 2019-06-14 | 27 | 27 | 2019-06-14 |  |  |  | 342 | 342 |  |  | 2019
220 | Culver City AAA | 4512 Sepulveda Boulevard | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-21 | 2017-06-04 |  |  | -188 |  | 2018-06-06 | 2018-06-08 | 2018-05-23 | 265 | 265 | -13
221 | Artesia AAA | 18642 South Gridley Road | Artesia | 90701 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-21 | 2018-06-04 |  |  | 74 | 74 | 2018-06-06 | 2018-06-08 | 2018-06-11 | 5 | 5 | 2 | 2
222 | Santa Monica AAA | 2730 Santa Monica Boulevard | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-21 | 2018-02-23 |  |  | 3 | 3 | 2018-02-23 | 2018-03-02 | 2018-03-15 | 6 | 6 | 10 | 10
223 | Long Beach AAA | 4800 Airport Plaza Drive | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-22 | 2018-02-23 |  |  | 2 | 2 | 2018-02-23 | 2018-03-01 | 2018-03-13 | 5 | 5 | 9 | 9
224 | Torrance AAA | 23001 Hawthorne Boulevard | Torrance | 90505 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-02-22 | 2018-06-04 |  |  | 73 | 73 | 2018-06-07 | 2018-06-08 | 2018-03-13 | 5 | 5 | -64 |  | 2018-06-08 | 77 | 77
225 | Manhattan Beach AAA | 700 South Aviation Boulevard | Manhattan Beach | 90266 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2018-02-22 | 2018-06-04 |  |  | 73 | 73 | 2018-06-07 | 2018-06-11 | 2018-03-15 | 6 | 6 | -63
226 | Menifee Target | 30340 Haun Road | Menifee | 92584 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar |  |  | 2537870 | 1428439 |  |  | 13 |  |  | NO | 2019-03-25 | 2019-04-01 | 6 | 6 | 2018-02-28 | 2018-03-01 | 283 | 283 | 2 | 2 | 2018-03-01 | 2018-03-12 | 2018-06-01 | 8 | 8 | 60 | 60 | 2018-07-26 | 107 | 107 | 2018-07-27 | 2018-07-31 | 2018-09-06 | 2018-08-31 | 27 | 27 | 2018-09-04 | 2018-09-07 | 4 | 4 |  | 2018-09-10 | 2 | 2 | 2018-09-10 | 1 | 1 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-11-01 | 34 | 34 | 40 | 40 | 6 | 6 | 2018-09-27 | 2018-10-25 | 2019-02-26 | 14 | 14 | 89 | 89 | 109 | 109 | 2019-06-26 | 208 | 208 | 2019-07-08 | 9 | 9 | 2018-10-25 | 2018-10-25 | 2019-02-26 | 2019-07-08 | 183 | 183 | 208 | 208 | 2019-06-24 | 2019-07-05 | 2019-07-12 | 15 | 15 |  |  | 2019-06-21 | [10 empty] | 2019-07-19 |  |  |  |  | 2019-07-29 |  |  |  | 2019-09-27 | 45 | 45 | 2019-09-27 |  |  |  | 413 | 413 | 307 | 307 | 2019
227 | Coso Junction Safety Roadside Rest Area | 107 Plant F6-1 Coso | Little Lake | 93542 | Inyo County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura |  |  | 2550978 | 1439199 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-27 | 2018-03-01 |  |  | 3 | 3 | 2018-03-01 | 2018-03-13 | 2018-03-14 | 9 | 9 | 2 | 2 |  |  |  | 2018-08-24 |  | 2018-09-21 | 2018-08-27 |  |  | 2018-08-28 |  |  |  |  | 2019-10-07 |  |  | 2019-10-08 | 2 | 2 | 2019-10-30 | 2019-12-20 | 2019-10-30 | 2019-12-09 | 18 | 18 |  |  | 29 | 29 | [23 empty] | 2020-09-25 |  | 2020-10-09 | 11 | 11 | 2019-12-11 | [12 empty] | 2020-10-23 | 222 | 222 |  |  | 2020-10-28 |  |  |  | 2020-12-30 | 42 | 42 | 2020-12-30 |  |  |  | 732 | 732 |  |  | 2020
228 | Boron Westbound Rest Area | Boron Westbound Rest Area Hwy 58 | Boron | 93516 | Kern County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura |  |  | 2550988 | 1439638 |  |  | 2 |  |  | NO |  |  |  |  | 2018-02-27 | 2018-03-01 |  |  | 3 | 3 | 2018-03-01 | 2018-03-21 | 2018-03-26 | 15 | 15 | 4 | 4 |  |  |  | 2018-08-24 |  | 2018-09-12 | 2018-08-28 |  |  | 2018-08-28 |  |  |  |  | 2019-10-07 |  |  | 2019-10-08 | 2 | 2 | 2019-10-30 | 2019-12-20 | 2019-10-30 | 2019-12-09 | 18 | 18 |  |  | 29 | 29 | [9 empty] | 2020-01-23 | 76 | 76 | [9 empty] | 77 | 77 | [5 empty] | 2019-12-11 | [11 empty] | 2020-08-04 | 2020-09-04 | 188 | 188 | 24 | 24 | 2020-10-08 |  |  |  | 2020-10-21 | 10 | 10 | 2020-10-21 |  |  |  | 686 | 686 |  |  | 2020
229 | Boron Eastbound Rest Area | Boron Rest Area | Boron | 93516 | Kern County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura |  |  | 2550991 | 1441473 |  |  | 2 |  |  | YES |  |  |  |  | 2018-02-17 | 2018-03-01 |  |  | 9 | 9 | 2018-03-01 | 2018-03-21 | 2018-03-26 | 15 | 15 | 4 | 4 |  |  |  | 2018-08-24 |  | 2018-09-12 | 2018-09-10 |  |  | 2018-09-10 |  |  |  |  | 2019-11-08 |  |  | 2019-11-08 | 1 | 1 | 2019-11-14 | 2019-12-20 | 2019-11-14 | 2019-12-09 | 5 | 5 |  |  | 18 | 18 | [9 empty] | 2020-01-23 | 53 | 53 | [9 empty] | 53 | 53 | [18 empty] | 2020-09-21 |  |  |  |  | 2020-10-13 |  |  |  | 2021-01-15 | 64 | 64 | 2021-01-15 |  |  |  | 749 | 749 |  |  | 2021
230 | Marina Del Rey, CA - 13574U Bali Way | 13574U Bali Way | Marina Del Rey | 90292 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2505280 | 1411384 |  |  | 8 | NO |  | YES | 2018-03-01 | 2018-03-13 | 9 | 9 | 2018-02-28 | 2018-03-01 | 9 | 9 | 2 | 2 | 2022-01-19 | 2018-03-05 | 2018-03-05 | 3 | 3 | 1 | 1 | 2018-05-15 | 55 | 55 | 2018-05-16 | 2018-05-16 | 2018-06-15 | 2018-06-13 | 22 | 22 | 2018-06-13 | 2018-07-18 | 26 | 26 |  | 2018-07-18 | 1 | 1 | 2018-07-18 | 1 | 1 | 2019-05-23 | 2019-08-02 | 2019-05-23 | 2019-06-25 | 222 | 222 | 245 | 245 | 24 | 24 | [9 empty] | 2022-03-31 | 945 | 945 | [9 empty] | 945 | 945 | 2022-04-11 |  | 2022-04-25 | 11 | 11 | 2022-01-13 | 2022-02-17 | 2022-03-25 | [10 empty] | 2022-05-04 | 78 | 78 |  |  | 2022-05-10 |  |  |  | 2022-07-20 | 50 | 50 | 2022-07-20 |  |  |  | 1122 | 1122 | 1068 | 1068 | 2022
231 | Ontario Trucksite Activation | 4325 E. Guasti Road | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | true |  |  |  |  | 2018-02-28
232 | Target Simi Valley | 2907 Cochran Street | Simi Valley | 93065 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2503820 | 1406191 | [5 empty] | true | 2018-03-01 | 2018-05-11 | 52 | 52 | 2018-03-01 | 2018-03-05 | 50 | 50 | 3 | 3 | 2018-03-05 | 2018-03-12 | 2018-03-14 | 6 | 6 | 3 | 3 | 2018-05-10 | 51 | 51 | 2018-05-11 |  | 2018-05-29
233 | Palmdale Antelope Valley Mall | 1233 Rancho Vista Boulevard | Palmdale | 93551 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2522138 | 1421020 |  |  | 12 |  |  | true | 2018-03-05 | 2018-04-16 | 31 | 31 | 2018-03-02 | 2018-03-02 | 32 | 32 | 1 | 1 | 2018-03-05 | 2018-03-14 | 2018-03-19 | 9 | 9 | 4 | 4 |  |  |  | 2018-06-22 | 2018-06-22 |  | 2018-07-23 |  |  | 2018-07-24 | 2018-08-01 | 7 | 7 |  | 2018-08-02 | 2 | 2 | 2018-08-02 | 1 | 1 | 2019-05-31 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 217 | 217 | 224 | 224 | 7 | 7 | 2018-08-29 | 2018-11-09 | 2018-12-14 | 20 | 20 | 26 | 26 | 78 | 78 | [6 empty] | 2018-11-09 |  | 2019-06-10 | [5 empty] | 2020-07-13 |  |  |  |  | 2020-01-27 | 2020-07-16 | [11 empty] | 2020-08-10 | 138 | 138 |  |  | 2020-08-20 |  |  |  | 2020-10-14 | 39 | 39 | 2020-10-15 |  |  |  | 679 | 679 |  |  | 2020
234 | Montecito, CA- 1595 S Jameson Ln | 1555 Jameson Lane | Montecito | 93108 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura |  |  | 2608892 | 1493887 |  |  | 8 |  |  | true | 2018-03-05 | 2018-03-29 | 19 | 19 | 2018-03-04 | 2018-06-14 | -56 |  | 74 | 74 | 2018-06-18 | 2018-06-21 | 2018-06-27 | 6 | 6 | 5 | 5 |  |  |  | 2019-01-04 | 2019-01-04 |  | 2019-03-04 |  |  | 2019-03-05 | 2019-03-11 | 5 | 5 |  | 2019-04-26 | 35 | 35 | 2019-03-29 | -21 |  | 2019-04-29 | 2021-04-26 | 2019-04-29 | 2020-09-03 | 2 | 2 | 384 | 384 | 349 | 349 |  | 2019-12-05 | 2021-05-05 |  |  | 357 | 357 |  |  | 2021-07-06 | 578 | 578 | 2021-05-27 | -27 |  | 2019-04-29 | 2019-04-29 | 2021-05-05 | 2021-05-27 | 531 | 531 | 558 | 558 | [18 empty] | 2021-06-09 |  |  |  |  | 2021-06-14 |  |  |  | 2021-09-02 | 58 | 58 | 2021-09-02 |  |  |  | 899 | 899 |  |  | 2021
235 | Santa Barbara, CA- 3943 State Street (Five Points Shopping Center) | 3943 State Street | Santa Barbara | 93105 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura |  |  | 2492341 | 1390674 |  |  | 16 |  |  | true | 2018-03-06 | 2018-04-13 | 29 | 29 | 2018-03-06 | 2021-06-30 | -825 |  | 853 | 853 | 2018-03-07 | 2018-03-12 | 2018-03-13 | -849 |  | 2 | 2 | 2018-04-13 | 29 | 29 | 2018-04-16 |  | 2018-07-19 | 2018-07-24 | 73 | 73 | 2018-07-24 | 2018-10-19 | 64 | 64 | 2018-11-09 | 2019-08-28 | 224 | 224 | 2019-08-28 | 1 | 1 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 523 | 523 | 746 | 746 | 1 | 1 | 2018-10-24 | 2018-11-16 | 2021-04-21 | -221 |  | 621 | 621 | 638 | 638 | [6 empty] | 2018-11-16 |  | 2021-09-20 | [10 empty] | 2021-05-13 | 2021-05-26 | [10 empty] | 2021-08-04 | 2021-09-03 | 80 | 80 | 23 | 23 | 2021-09-07 |  |  |  | 2021-10-01 | 19 | 19 | 2021-10-01 |  |  |  | 918 | 918 | 890 | 890 | 2021
236 | Goleta Marketplace | 7035 Marketplace Drive | Goleta | 93117 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura |  |  | 2517993 | 1426269 |  |  | 12 |  |  | true | 2018-03-06 | 2018-04-16 | 30 | 30 | 2018-03-06 | 2018-03-06 | 30 | 30 | 1 | 1 | 2018-03-07 | 2018-03-12 | 2018-03-13 | 5 | 5 | 2 | 2 |  |  |  | 2018-06-14 |  |  | 2018-07-25 |  |  | 2018-07-25 | 2018-09-05 | 31 | 31 |  | 2019-09-07 | 263 | 263 | 2019-09-07 | 0 |  | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-09-25 | 5 | 5 | 276 | 276 | 9 | 9 | 2018-09-14 | 2018-10-17 | 2019-02-28 | -256 |  | 97 | 97 | 120 | 120 | 2020-02-06 | 107 | 107 | 2020-02-26 | 14 | 14 | 2018-10-17 | 2018-10-17 | 2019-09-25 | 2020-02-26 | 353 | 353 | 107 | 107 | 2020-02-07 |  | 2020-02-21 | 10 | 10 |  | 2020-01-10 | [11 empty] | 2020-02-28 |  |  |  |  | 2020-02-28 |  |  |  | 2020-03-31 | 23 | 23 | 2020-03-31 |  |  |  | 538 | 538 |  |  | 2020
237 | Hermosa Beach, CA - Ardmore Ave. | 710 16th Street | Hermosa Beach | 90254 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2503840 | 1412651 |  |  | 20 |  |  | true | 2018-03-21 | 2018-04-16 | 19 | 19 | 2018-03-07 | 2018-03-08 | 28 | 28 | 2 | 2 | 2018-03-08 | 2018-03-15 | 2018-03-18 | 6 | 6 | 2 | 2 | 2018-05-10 | 47 | 47 | 2018-05-11 |  | 2018-07-02 | 2018-06-28 | 36 | 36 | 2018-06-28 | 2018-10-11 | 76 | 76 | 2018-11-01 | 2018-08-27 | -34 |  | 2018-08-27 | 1 | 1 | 2019-06-20 | 2019-06-20 | 2019-06-20 | 2019-09-03 | 214 | 214 | 234 | 234 | 54 | 54 | 2018-09-14 | 2018-10-19 | 2019-09-19 | 15 | 15 | 240 | 240 | 265 | 265 | 2020-02-25 | 389 | 389 | 2020-04-01 | 27 | 27 | 2018-10-19 | 2018-10-19 | 2019-09-19 | 2020-04-01 | 376 | 376 | 389 | 389 | [18 empty] | 2020-04-15 |  |  |  |  | 2020-04-24 |  |  |  | 2020-05-21 | 20 | 20 | 2020-05-21 |  |  |  | 574 | 574 | 528 | 528 | 2020
238 | Manhattan Beach Manhattan Village | 1180 Rosecrans Avenue | Manhattan Beach | 90266 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2532590 | 1427751 |  |  | 12 |  |  | NO | 2018-03-09 | 2018-04-16 | 27 | 27 | 2018-03-09 | 2018-03-12 | 26 | 26 | 2 | 2 | 2018-03-12 |  | 2018-03-15 |  |  |  |  | 2018-07-16 | 92 | 92 | 2018-07-16 | 2018-07-17 | 2018-08-15 | 2018-08-16 | 24 | 24 | 2018-08-16 |  |  |  |  | 2018-09-07 |  |  | 2018-09-07 | 1 | 1 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 1 | 1 |  |  | 1 | 1 | 2018-09-06 | 2018-09-13 | 2018-11-20 | -2 |  | 49 | 49 | 54 | 54 | 2018-09-05 | -3 |  | 2018-09-27 | 17 | 17 | 2018-09-07 | 2018-09-05 | 2018-11-20 | 2018-11-20 | 55 | 55 | -3 |  | 2018-10-08 |  | 2018-11-16 | 30 | 30 | [12 empty] | 2018-11-19 | [5 empty] | 2018-09-28 | 2018-10-22 | 17 | 17 | 2018-10-22 | 17 | 17 | 2018-10-26 |  |  |  | 166 | 166 | 75 | 75 | 2018
239 | Lawndale Plaza | 15205 Hawthorne Boulevard | Lawndale | 90260 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-03-08 | 2018-03-21 |  |  | 10 | 10
240 | Gardena Plaza | 1420 West Redondo Beach Boulevard | Gardena | 90247 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2018-03-08 | 2018-03-21 |  |  | 10 | 10
241 | Tulare, CA - 2195 E Prosperity Ave | 2195 East Prosperity Avenue | Tulare | 93274 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura |  |  | 2538250 | 1436232 | [5 empty] | NO | 2018-03-13 | 2018-03-14 | 2 | 2 | 2018-03-12 | 2018-03-13 | 2 | 2 | 2 | 2 | 2018-03-13 | 2018-03-22 | 2018-03-26 | 8 | 8 | 3 | 3 |  |  |  | 2018-07-30 | 2018-08-01 | 2018-08-15 | 2018-08-20 |  |  | 2018-08-20
242 | Santa Monica Bristol Farms | 3105 Wilshire Boulevard | Santa Monica | 90064 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-03-13 | 2018-03-13 |  |  | 1 | 1 | 2018-03-13 | 2018-03-21 | 2018-04-05 | 7 | 7 | 12 | 12
243 | Buena Park McDonalds | 7050 Knott Avenue | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2018-03-13 | 2018-03-13 |  |  | 1 | 1 | 2018-03-13 | 2018-03-20 | 2018-04-05 | 6 | 6 | 13 | 13
244 | Corona Target | 2615 Tuscanny Street | Corona | 92881 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | true | 2018-03-16 |  |  |  | 2018-03-16 | 2018-03-16 |  |  | 1 | 1 | 2018-03-16
245 | Citadel Outlets | 100 Citadel Drive | Commerce | 90040 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2780180 | [6 empty] | YES | 2018-03-16 | 2018-04-02 | 12 | 12 | 2018-03-16 | 2018-03-16 | 12 | 12 | 1 | 1 | 2018-03-16 | 2018-03-23 | 2018-03-26 | 6 | 6 | 2 | 2 |  |  |  | 2019-11-14 |  |  | 2020-02-11 |  |  | 2020-02-11
246 | Barstow, CA- 2796 Tanger Way | 2796 Tanger Way EV1 | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 3066935 | 1844781 |  |  | 20 |  |  | NO | 2019-11-12 | 2019-11-19 | 6 | 6 | 2018-03-16 | 2018-03-16 | 438 | 438 | 1 | 1 | 2021-06-29 | 2018-03-22 | 2021-03-31 | 5 | 5 | 777 | 777 |  |  |  | 2021-04-02 |  | 2021-05-05 | 2021-05-05 |  |  | 2021-05-05 | 2021-05-17 | 9 | 9 | 2021-12-02 | 2021-11-04 | 121 | 121 | 2021-11-04 | 1 | 1 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-03 | 60 | 60 | 181 | 181 | 2 | 2 | 2021-11-04 | 2021-11-15 | 2021-12-23 | 1 | 1 | 27 | 27 | 33 | 33 | 2022-02-17 | 71 | 71 | 2022-03-17 | 20 | 20 | 2021-11-15 | 2021-11-15 | 2022-02-03 | 2022-03-17 | 84 | 84 | 71 | 71 | 2022-03-17 |  |  |  |  | 2022-01-27 | [12 empty] | 2023-02-28 | 275 | 275 | [6 empty] | 2022-05-20 |  |  | 2022-05-20 |  |  |  | 1069 | 1069 |  |  | 2022
247 | Whittier McDonalds | 5545 E. Whittier Boulevard | Los Angeles | 90022 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2018-03-16 | 2018-03-18 |  |  | 1 | 1 | 2018-03-22 | 2018-03-28 | 2018-04-06 | 8 | 8 | 8 | 8
248 | Lazy Acres Log Angeles | 986 Artesia Boulevard | Los Angeles | 90254 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2018-03-16 | 2018-03-16 |  |  | 1 | 1 | 2018-03-18
249 | Brea, CA- Brea Mall Dr | 242 Brea Mall Way | Brea | 92821 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2571098 | 1469623 |  |  | 20 |  |  | NO | 2018-03-19 | 2018-03-28 | 8 | 8 | 2018-03-19 | 2018-03-21 | 6 | 6 | 3 | 3 | 2018-03-21 | 2018-03-23 | 2018-03-26 | 3 | 3 | 2 | 2 |  |  |  | 2018-10-09 |  | 2018-11-07 | 2018-11-16 |  |  | 2018-11-16 | 2018-11-21 | 4 | 4 | 2018-12-17 | 2019-01-09 | 36 | 36 | 2019-01-09 | 1 | 1 | 2019-02-25 | 2021-03-19 | 2019-02-25 | 2020-07-24 | 34 | 34 | 433 | 433 | 365 | 365 | 2019-02-13 | 2021-03-02 | 2021-03-11 | 26 | 26 | 8 | 8 | 529 | 529 | [6 empty] | 2019-02-25 |  | 2021-03-11 | [23 empty] | 2021-05-17 |  |  |  |  | 2021-05-20 |  |  |  | 2021-06-24 | 25 | 25 | 2021-06-24 |  |  |  | 840 | 840 |  |  | 2021
250 | Montecito Vons 2101 100031 | 1040 Coast Village Road | Montecito | 93108 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | true |  |  |  |  | 2018-03-19 | 2018-05-18 |  |  | 45 | 45 | 2018-05-21
251 | Culver City Target | 10820 Jefferson Boulevard | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-04-17 |  |  |  | 2018-03-26 | 2018-03-28 |  |  | 3 | 3 | 2018-04-10 | 2018-04-11 | 2018-04-11 | 11 | 11 | 1 | 1 | 2020-04-17 | 537 | 537
252 | Gardena Target 200042 | 2169 West Redondo Beach | Gardena | 90247 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2529720 | 1432429 |  |  | 3 |  |  | NO |  |  |  |  | 2018-03-27 | 2018-05-17 |  |  | 38 | 38 | 2018-05-21 | 2018-05-24 | 2018-05-24 | 6 | 6 | 1 | 1 | 2018-07-10 | 76 | 76 | 2018-07-10 | 2018-07-12 | 2018-08-13 | 2018-08-13 | 25 | 25 | 2018-08-13 | 2018-09-20 | 29 | 29 | 2018-10-11 | 2018-09-28 | 7 | 7 | 2018-09-28 | 1 | 1 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-10-04 | 1 | 1 | 11 | 11 | 5 | 5 | 2018-08-31 | 2018-10-08 | 2018-11-02 | -21 |  | 20 | 20 | 46 | 46 | 2018-09-28 | 1 | 1 | 2018-10-09 | 8 | 8 | 2018-09-28 | 2018-09-28 | 2018-11-02 | 2018-11-02 | 26 | 26 | 1 | 1 | [17 empty] | 2019-02-18 | 2019-02-18 |  |  | 1 | 1 | 2019-03-06 |  |  |  | 2019-04-09 | 25 | 25 | 2019-04-09 |  |  |  | 271 | 271 | 196 | 196 | 2019
253 | Visalia Transit | 525 North Cain Street | Visalia | 93291 | Tulare County | 9. Complete | 51 - Tulare | San Joaquin | Ventura |  |  | 2492710 | 1397590 | [5 empty] | true |  |  |  |  | 2018-04-04 | 2018-04-05 |  |  | 2 | 2 | 2018-04-10 |  | 2018-04-14 |  |  |  |  | 2018-04-16 | 9 | 9 | 2018-04-16 | 2018-04-18 |  | 2018-05-10 | 19 | 19 | 2018-05-10 | 2018-05-14 | 3 | 3 |  | 2018-05-14 | 1 | 1 | 2018-05-14 | 1 | 1 | 2018-07-14 | 2018-08-07 | 2018-07-14 |  | 45 | 45 | [13 empty] | 2018-07-31 | 57 | 57 | 2018-08-16 | 13 | 13 | [6 empty] | 57 | 57 | [5 empty] | 2018-07-14 |  |  | 2018-07-19 | 4 | 4
254 | Hawthorne Courtyard Marriott | 4427 West El Segundo Boulevard | Hawthorne | 90250 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2534610 | 1435264 |  |  | 12 |  |  | YES | 2018-04-05 | 2018-04-24 | 14 | 14 | 2018-04-04 | 2018-04-05 | 14 | 14 | 2 | 2 | 2018-04-11 | 2018-04-13 | 2018-04-24 | 7 | 7 | 8 | 8 | 2018-07-18 | 76 | 76 | 2018-07-20 |  | 2018-08-21 | 2018-11-08 | 82 | 82 | 2018-11-08 | 2018-11-14 | 5 | 5 | 2018-12-05 | 2018-12-11 | 20 | 20 | 2018-12-12 | 2 | 2 | 2019-07-25 | 2019-07-25 | 2019-07-25 | 2019-08-21 | 163 | 163 | 201 | 201 | 20 | 20 | 2018-11-30 | 2019-08-29 | 2019-09-04 | -8 |  | 5 | 5 | 199 | 199 | 2019-08-06 | 170 | 170 | 2019-08-23 | 14 | 14 | 2019-07-25 | 2019-07-25 | 2019-09-04 | 2019-09-04 | 30 | 30 | 171 | 171 | [6 empty] | 2019-07-29 | 2019-08-21 | [9 empty] | 2019-08-26 | 2019-09-11 |  |  | 13 | 13 | 2019-09-13 |  |  |  | 2019-09-26 | 10 | 10 | 2019-10-02 |  |  |  | 391 | 391 | 316 | 316 | 2019
255 | Mojave, CA - 16246 Sierra Highway | 16246 Sierra Highway | Mojave | 93501 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 3173645 | 1912584 |  |  | 12 |  |  | NO | 2018-04-05 | 2021-04-23 | 784 | 784 | 2018-04-04 | 2018-04-05 | 784 | 784 | 2 | 2 | 2018-04-11 | 2018-04-25 | 2021-04-30 | 15 | 15 | 775 | 775 | 2021-09-15 | 885 | 885 | 2021-09-17 | 2021-09-21 | 2021-11-09 | 2021-11-08 | 39 | 39 | 2021-11-08 | 2022-01-27 | 54 | 54 |  | 2022-03-10 | 30 | 30 | 2022-03-10 | 1 | 1 | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-20 | 19 | 19 | 59 | 59 | 12 | 12 | 2022-03-29 | 2022-05-09 | 2022-05-18 | 14 | 14 | 8 | 8 | 37 | 37 | 2022-04-07 | 21 | 21 | 2022-05-20 | 32 | 32 | 2022-04-05 | 2022-04-05 | 2022-05-18 | 2022-05-20 | 34 | 34 | 21 | 21 | 2022-07-08 | [17 empty] | 2022-07-29 | [8 empty] | 2022-08-15 |  |  | 2022-08-15 |  |  |  | 1115 | 1115 | 231 | 231 | 2022
256 | Beaumont Kohl's | 1479 East 2nd Street | Beaumont | 92223 | Riverside County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2551238 | 1451126 |  |  | 4 |  |  | NO |  |  |  |  | 2018-03-29 | 2018-03-29 |  |  | 1 | 1 | 2018-04-06 | 2018-04-09 | 2018-04-16 | 8 | 8 | 6 | 6 | 2018-08-23 | 106 | 106 | 2018-08-24 |  | 2018-09-26 | 2018-10-01 | 28 | 28 | 2018-10-02 | 2018-10-03 | 2 | 2 |  | 2018-11-01 | 22 | 22 | 2018-11-01 | 1 | 1 | 2018-11-20 | 2018-12-19 | 2018-11-20 | 2020-01-10 | 14 | 14 | 332 | 332 | 298 | 298 | 2018-11-01 | 2018-11-05 | 2019-05-31 | 1 | 1 | 150 | 150 | 152 | 152 | 2020-01-07 | 308 | 308 |  |  |  | 2018-11-05 | 2018-11-05 | 2020-01-10 |  |  |  | 308 | 308 | 2019-12-05 |  |  |  |  | 2019-09-30 |  | 2019-11-13 | [10 empty] | 2019-12-03 | 47 | 47 |  |  | 2019-12-05 | 2020-03-03 | 61 | 61 | 2020-03-04 | 62 | 62 | 2020-03-04 |  |  |  | 502 | 502 | 397 | 397 | 2020
257 | Palm Desert Kohl's | 34940 Monterey Avenue | Palm Desert | 92211 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2551235 | 1446905 |  |  | 6 |  |  | NO |  |  |  |  | 2018-03-29 | 2018-03-29 |  |  | 1 | 1 | 2018-04-06 | 2018-04-09 | 2018-04-16 | 8 | 8 | 6 | 6 | 2018-08-23 | 106 | 106 | 2018-08-24 |  | 2018-09-26 | 2018-09-21 | 22 | 22 | 2018-09-24 | 2018-09-24 | 1 | 1 | 2018-10-16 | 2018-10-10 | 13 | 13 | 2018-10-10 | 1 | 1 | 2018-10-11 | 2018-11-02 | 2018-10-11 | 2018-10-11 | 2 | 2 | 14 | 14 | 1 | 1 | 2018-10-05 | 2018-11-17 | 2019-05-31 | -4 |  | 140 | 140 | 171 | 171 | [6 empty] | 2018-10-11 |  | 2019-05-31 | [5 empty] | 2019-11-05 | 2019-11-20 | 2019-11-21 | 13 | 13 | 2019-08-06 | 2019-10-08 | [10 empty] | 2019-12-05 | 2019-12-19 | 98 | 98 | 11 | 11 | 2019-12-19 | [6 empty] | 2020-02-21 |  |  |  | 494 | 494 | 389 | 389 | 2020
258 | Santa Ana Del Taco | 2900 South Main Street | Santa Ana | 92707 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2018-04-04 | 2018-04-05 |  |  | 2 | 2 | 2018-04-11 | 2018-04-12 | 2018-04-17 | 6 | 6 | 4 | 4
259 | Los Angeles Washington Place | 11281 West Washington Place | Los Angeles | 90064 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | true | 2018-05-15 | 2018-06-04 | 15 | 15 | 2018-04-05 | 2018-06-06 | -3 |  | 45 | 45 | 2018-06-11
260 | Murrieta Target | 27818 Clinton Keith Road | Murrieta | 92562 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | true | 2018-03-29 | 2018-04-09 | 8 | 8 | 2018-03-29 | 2018-03-29 | 8 | 8 | 1 | 1 | 2018-04-02 | 2018-04-05 |  | 6 | 6
261 | Chino Hills, CA- 13920 City Center Drive (Shoppes) | 3401 Grand Ave EV1 | Chino Hills | 91709 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2520314 | 1422354 |  |  | 16 |  |  | true | 2018-04-11 | 2018-04-23 | 9 | 9 | 2018-04-11 | 2018-04-11 | 9 | 9 | 1 | 1 | 2018-04-13 | 2018-04-17 | 2018-06-22 | 5 | 5 | 49 | 49 |  |  |  | 2018-06-22 | 2018-06-22 | 2018-07-20 | 2018-07-17 |  |  | 2018-07-17 | 2019-10-02 | 317 | 317 | 2019-10-23 | 2019-10-23 | 16 | 16 | 2019-10-23 | 1 | 1 | 2019-12-04 | 2019-03-21 | 2019-12-04 | 2020-09-02 | 31 | 31 | 236 | 236 | 191 | 191 | 2020-08-07 | 2020-08-10 | 2020-08-26 | 203 | 203 | 13 | 13 | 14 | 14 | 2021-03-25 | 359 | 359 | 2021-04-02 | 7 | 7 | 2019-12-04 | 2019-12-04 | 2020-09-02 | 2021-04-02 | 335 | 335 | 359 | 359 | 2021-04-29 | 2021-05-06 | 2021-05-06 | 6 | 6 |  | 2021-05-10 | 2021-05-17 | [9 empty] | 2021-05-28 | 2021-06-09 |  |  | 8 | 8 | 2021-06-10 |  |  |  | 2021-07-14 | 24 | 24 | 2021-07-14 |  |  |  | 836 | 836 |  |  | 2021
262 | Torrance, CA- 3490 Fashion Way (Del Amo Simon) | 3490 Fashion Way | Torrance | 90503 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2538877 | 1466630 |  |  | 20 |  |  | true | 2018-04-11 | 2018-05-01 | 15 | 15 | 2018-04-11 | 2018-04-11 | 15 | 15 | 1 | 1 | 2018-04-13 | 2018-04-18 | 2018-04-23 | 6 | 6 | 4 | 4 | 2018-07-30 | 79 | 79 | 2018-07-31 | 2018-07-31 |  | 2018-11-11 | 75 | 75 | 2018-11-11 | 2019-07-15 | 176 | 176 | 2019-08-05 | 2019-08-14 | 23 | 23 | 2019-08-14 | 1 | 1 | 2019-02-20 | 2019-02-08 | 2019-02-20 | 2019-08-30 | -126 |  | 35 | 35 | 138 | 138 | 2019-01-17 | 2019-02-06 | 2019-03-04 | -150 |  | 19 | 19 | 33 | 33 | 2020-09-24 | 286 | 286 | 2020-09-29 | 4 | 4 | 2019-02-06 | 2019-02-06 | 2019-08-30 | 2020-09-29 | 424 | 424 | 286 | 286 | 2020-09-22 |  | 2020-10-06 | 11 | 11 | [13 empty] | 2020-10-30 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-13 | 30 | 30 | 2021-01-13 |  |  |  | 710 | 710 | 632 | 632 | 2021
263 | Montebello, CA - 2134 Montebello Town Center Dr | 2134 Montebello Town Center Road | Montebello | 90640 | Los Angeles County | 10. Customer Hold | 22 - Montebello | Metro East | Pomona |  |  | 2592360 | 694861 | [5 empty] | YES | 2018-04-12 | 2018-04-25 | 10 | 10 | 2018-04-12 | 2018-04-12 | 10 | 10 | 1 | 1 | 2018-04-16 | 2018-04-19 | 2018-04-21 | 6 | 6 | 2 | 2 |  |  |  | 2018-11-26 |  | 2018-12-26 | 2018-12-28 |  |  | 2018-12-28
264 | West Hollywood, CA- 8560 W Sunset Blvd (Equinox) | 8560 West Sunset Boulevard | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2974100 | 1780736 | [5 empty] | true | 2018-04-17 | 2019-09-25 | 377 | 377 | 2018-04-17 | 2018-04-17 | 377 | 377 | 1 | 1 | 2018-04-18 | 2018-04-19 | 2018-04-28 | 3 | 3 | 7 | 7 | 2020-10-22 | 652 | 652 | 2020-10-22 | 2020-10-23 | 2020-11-25 | 2020-11-25 | 24 | 24 | 2020-11-25 | 2021-05-04 | 109 | 109 | 2021-06-16 | 2021-07-14 | 50 | 50 | 2021-07-14 | 1 | 1 | 2021-07-14 | 2021-07-14 | 2021-07-14 |  | 1 | 1 |  |  |  |  | 2021-08-03 | 2021-08-03 |  | 15 | 15 | [10 empty] | 2021-07-14
265 | One Culver - Washington Boulevard | 10000 Washington Boulevard | Culver City | 90232 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2018-04-17 | 2018-04-30 | 10 | 10 | 2018-04-17 | 2018-04-17 | 10 | 10 | 1 | 1 | 2018-04-18 | 2018-04-23 |  | 5 | 5
266 | Lebec Jack In The Box Frazier Park | 75 Frazier Mountain Park Road | Lebec | 93243 | Kern County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2540167 | 1437051 |  |  | 3 |  |  | NO |  |  |  |  | 2018-04-20 | 2018-05-03 |  |  | 10 | 10 | 2018-05-08 | 2018-05-11 | 2018-05-13 | 7 | 7 | 1 | 1 | 2018-08-02 | 75 | 75 | 2018-08-02 |  |  | 2018-08-22 | 15 | 15 | 2018-08-22 | 2018-08-22 | 1 | 1 |  | 2018-08-27 | 4 | 4 | 2018-08-27 | 1 | 1 | 2018-08-30 | 2018-09-13 | 2018-08-30 | 2019-04-08 | 4 | 4 | 164 | 164 | 158 | 158 | 2018-08-27 | 2018-10-03 | 2019-07-25 | 1 | 1 | 212 | 212 | 239 | 239 | [6 empty] | 2018-08-30 |  | 2019-07-25 | [5 empty] | 2019-10-25 |  | 2019-11-21 | 20 | 20 |  | 2019-10-18 |  |  |  |  | 2019-10-23 | [5 empty] | 2019-11-21 | 2019-12-02 |  |  | 8 | 8 | 2019-12-03 | 2020-01-13 | 29 | 29 | 2020-01-14 | 30 | 30 | 2020-01-14 |  |  |  | 452 | 452 | 378 | 378 | 2020
267 | Castaic Mobile - Sloan Canyon | 27983 Sloan Canyon Road | Castaic | 91384 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2529590 | 1422628 |  |  | 4 |  |  | true |  |  |  |  | 2018-04-20 | 2018-05-04 |  |  | 11 | 11 | 2018-05-07 | 2018-05-11 | 2018-05-13 | 6 | 6 | 1 | 1 | 2018-07-10 | 58 | 58 | 2018-07-10 | 2018-07-12 |  | 2018-07-24 | 11 | 11 | 2018-07-24 | 2018-07-24 | 1 | 1 |  | 2018-07-24 | 1 | 1 | 2018-07-24 | 1 | 1 | 2018-08-11 | 2018-08-30 | 2018-08-11 | 2018-09-24 | 14 | 14 | 45 | 45 | 31 | 31 | 2018-07-25 | 2018-08-27 | 2018-09-11 | 2 | 2 | 12 | 12 | 35 | 35 | [6 empty] | 2018-08-11 |  | 2018-09-24 | [5 empty] | 2019-01-04 |  | 2019-01-29 | 18 | 18 | 2018-10-09 | 2018-11-09 | [10 empty] | 2019-01-07 | 2019-02-21 | 98 | 98 | 34 | 34 | 2019-03-05 |  |  |  | 2019-04-08 | 25 | 25 | 2019-04-08 |  |  |  | 252 | 252 | 195 | 195 | 2019
268 | Buena Park The Source | 6928 Beach Boulevard | Buena Park | 90621 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2605490 | 1498288 |  |  | 24 |  |  | true | 2018-04-23 | 2018-07-10 | 57 | 57 | 2018-04-20 | 2018-04-23 | 57 | 57 | 2 | 2 | 2018-04-26 | 2018-04-26 | 2018-05-05 | 4 | 4 | 7 | 7 |  |  |  | 2018-12-27 |  | 2019-01-21 | 2019-04-19 |  |  | 2019-04-19 | 2019-05-11 | 16 | 16 | 2019-06-03 | 2019-05-28 | 12 | 12 | 2019-05-29 | 2 | 2 | 2019-07-09 | 2019-09-06 | 2019-07-09 | 2019-08-19 | 31 | 31 | 71 | 71 | 30 | 30 | 2019-06-24 | 2019-07-22 | 2019-10-24 | 20 | 20 | 69 | 69 | 89 | 89 | [6 empty] | 2019-07-09 |  | 2019-10-24 | [23 empty] | 2020-01-08 |  |  |  |  | 2019-11-19 |  |  |  | 2019-12-20 | 24 | 24 | 2019-12-20 |  |  |  | 436 | 436 |  |  | 2019
269 | EVgo LLC | 1217 Euclid Street | Santa Monica | 90404 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2018-05-09 | 2018-06-04 | 19 | 19 | 2018-04-07 | 2018-04-30 | 26 | 26 | 16 | 16 | 2018-05-02 |  | 2018-05-09
270 | Hawthorne Target | 2700 W 120th Street | Hawthorne | 90250 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2552753 | 1463444 |  |  | 12 |  |  | NO | 2018-04-27 | 2018-05-15 | 13 | 13 | 2018-04-27 | 2018-06-12 | -21 |  | 33 | 33 | 2018-06-14 | [9 empty] | 2018-08-28 |  | 2018-09-28 | 2018-10-31 |  |  | 2018-10-31 | 2018-11-28 | 21 | 21 | 2019-09-11 | 2019-09-11 | 206 | 206 | 2019-09-11 | 1 | 1 | 2019-09-11 | 2019-10-15 | 2019-09-11 | 2019-09-27 | 1 | 1 | 218 | 218 | 13 | 13 | 2019-09-11 |  | 2019-09-30 | 1 | 1 |  |  | 14 | 14 | 2020-07-24 | 223 | 223 | 2020-08-24 | 22 | 22 |  |  | 2019-09-30 | 2020-08-24 |  |  | 223 | 223 | 2020-06-03 | [5 empty] | 2020-04-23 | [11 empty] | 2020-07-23 |  |  |  |  | 2020-08-05 |  |  |  | 2020-09-28 | 38 | 38 | 2020-09-28 |  |  |  | 626 | 626 |  |  | 2020
271 | Blythe Chevron | 321 South Lovekin Boulevard | Blythe | 92225 | Riverside County | 11. Cancelled | 87 - Blythe | Rurals | SBRO | [9 empty] | true |  |  |  |  | 2018-04-27 | 2018-04-30 |  |  | 2 | 2 | 2018-05-01
272 | Temecula 2nd Street Parking Lot | 42484-42910 2nd Street | Temecula | 92590 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO | 2018-05-08 | 2018-06-20 | 32 | 32 | 2018-05-08 | 2018-05-08 | 32 | 32 | 1 | 1 | 2018-05-11 | 2018-05-16 | 2018-05-19 | 7 | 7 | 3 | 3
273 | Bellflower Unified School District | 15330 South Woodruff Avenue | Bellflower | 90706 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-05-10 | 2018-05-13 |  |  | 2 | 2 | 2018-05-15 | [9 empty] | 2018-05-23 | 2018-05-24 | 2018-08-07 | 2018-08-07 |  |  | 2018-08-07 | 2018-08-08 | 2 | 2
274 | South Pasadena Mound Ave | 820 Mound Avenue | South Pasadena | 91030 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  |  | 2560380 | 1456458 |  |  | 2 |  |  | true |  |  |  |  | 2018-05-10 | 2018-07-06 |  |  | 42 | 42 | 2018-07-10 | 2018-07-12 | 2018-07-12 | 5 | 5 | 1 | 1 |  |  |  | 2018-09-14 |  | 2018-10-12 | 2018-10-16 |  |  | 2018-10-16 | 2018-10-16 | 1 | 1 | 2018-11-07 | 2018-11-08 | 18 | 18 | 2018-11-08 | 1 | 1 | 2018-11-09 | 2018-11-20 | 2018-11-09 | 2019-05-13 | 2 | 2 | 150 | 150 | 132 | 132 | 2018-11-28 | 2018-12-12 | 2019-06-24 | 15 | 15 | 139 | 139 | 149 | 149 | 2018-12-07 | 22 | 22 | 2018-12-22 | 11 | 11 | 2018-11-09 | 2018-11-09 | 2019-06-24 | 2019-06-24 | 162 | 162 | 22 | 22 | 2018-12-12 |  | 2019-01-14 | 24 | 24 | 2018-11-07 | [11 empty] | 2019-01-29 | 2019-01-29 | 60 | 60 | 1 | 1 | 2019-06-26 |  |  |  | 2019-07-18 | 17 | 17 | 2019-07-19 |  |  |  | 312 | 312 |  |  | 2019
275 | Newport Beach Fashion Island | 799 Newport Center Dr, EV | Newport Beach | 92660 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2959868 | 1762827 |  |  | 8 |  |  | NO | 2020-09-15 |  |  |  | 2018-06-01 | 2018-06-01 |  |  | 1 | 1 | 2018-06-01 | 2018-06-01 | 2020-09-14 | 1 | 1 | 591 | 591 | 2020-09-15 | 592 | 592 | 2020-09-23 | 2020-09-24 | 2020-10-26 | 2021-01-04 | 75 | 75 | 2021-01-04 | 2021-01-14 | 9 | 9 | 2021-02-04 | 2021-02-08 | 17 | 17 | 2021-02-12 | 5 | 5 | 2021-02-10 | 2021-02-10 | 2021-02-18 | 2021-03-02 | 8 | 8 | 32 | 32 | 9 | 9 |  | 2021-03-03 | 2021-03-31 |  |  | 21 | 21 | [8 empty] | 2021-02-18 |  | 2021-03-31 | [5 empty] | 2021-10-27 |  |  |  |  | 2021-08-30 | 2021-10-19 | [10 empty] | 2021-11-24 | 2021-11-29 | 62 | 62 | 2 | 2 | 2022-01-21 |  |  |  | 2022-03-08 | 32 | 32 | 2022-03-08 |  |  |  | 961 | 961 | 370 | 370 | 2022
276 | Irvine Cypress Village | 14001 Jeffrey Road | Irvine | 92620 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2740866 | 1597973 |  |  | 4 |  |  | NO |  |  |  |  | 2018-06-04 | 2018-06-05 |  |  | 2 | 2 | 2018-06-07 | 2018-06-11 | 2018-06-13 | 5 | 5 | 3 | 3 |  |  |  | 2019-08-26 |  |  | 2019-09-27 |  |  | 2019-09-30 | 2019-11-05 | 27 | 27 | 2019-11-27 | 2020-02-21 | 76 | 76 | 2020-02-21 | 1 | 1 | 2020-03-20 | 2020-06-19 | 2020-03-20 | 2020-04-16 | 21 | 21 | 115 | 115 | 20 | 20 | 2020-03-13 | 2020-04-01 | 2020-06-05 | 16 | 16 | 47 | 47 | 60 | 60 | 2020-07-14 | 101 | 101 | 2020-07-27 | 10 | 10 | 2020-03-20 | 2020-03-20 | 2020-06-05 | 2020-07-27 | 90 | 90 | 101 | 101 | [18 empty] | 2020-09-25 |  |  |  |  | 2020-09-30 |  |  |  | 2021-01-25 | 78 | 78 | 2021-01-25 |  |  |  | 679 | 679 |  |  | 2021
277 | Manhattan Beach Chevron | 2301 North Aviation Boulevard | Manhattan Beach | 90266 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2573480 | 1489235 |  |  | 2 |  |  | NO |  |  |  |  | 2018-06-06 | 2018-07-06 |  |  | 23 | 23 | 2018-07-10 | [9 empty] | 2018-10-12 |  | 2018-11-09 | 2018-11-30 |  |  | 2018-12-04 | 2018-12-14 | 9 | 9 | 2019-01-21 | 2019-01-24 | 30 | 30 | 2019-01-24 | 1 | 1 | 2019-01-24 | 2019-02-14 | 2019-01-24 | 2019-05-10 | 1 | 1 | 106 | 106 | 77 | 77 | 2019-01-16 | 2019-02-25 | 2019-04-19 | -7 |  | 40 | 40 | 68 | 68 | 2019-05-21 | 84 | 84 |  |  |  | 2019-01-24 | 2019-01-24 | 2019-05-10 |  |  |  | 84 | 84 | [5 empty] | 2019-02-26 | [12 empty] | 2019-04-10 | 32 | 32 |  |  | 2019-05-17 | [6 empty] | 2019-07-21 |  |  |  | 293 | 293 |  |  | 2019
278 | Aliso Viejo Chevron | 23022 Aliso Creek Road | Aliso Viejo | 90656 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2573520 | 1476959 |  |  | 2 |  |  | YES |  |  |  |  | 2018-06-11 | 2018-06-14 |  |  | 4 | 4 | 2018-06-15 | 2018-06-18 | 2018-06-19 | 3 | 3 | 2 | 2 |  |  |  | 2018-10-18 |  | 2018-11-15 | 2018-12-14 |  |  | 2018-12-17 | 2019-01-25 | 30 | 30 | 2019-02-15 | 2019-03-08 | 31 | 31 | 2019-03-12 | 3 | 3 | 2019-04-22 | 2019-04-30 | 2019-04-22 | 2019-04-22 | 32 | 32 | 62 | 62 | 1 | 1 | [41 empty] | 2019-04-25 |  |  |  |  | 2019-04-30 |  |  |  | 2019-07-18 | 58 | 58 | 2019-07-18 |  |  |  | 289 | 289 |  |  | 2019
279 | Long Beach Albertsons (Vons) | 600 East Broadway | Long Beach | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2575560 | 1469500 | [5 empty] | NO | 2018-10-16 |  |  |  | 2018-06-14 | 2018-06-14 |  |  | 1 | 1 | 2018-06-15 | 2018-06-18 | 2018-06-28 | 3 | 3 | 9 | 9 | 2018-10-16 | 89 | 89 | 2018-10-16 |  | 2018-11-21 | 2018-11-20 | 26 | 26 | 2018-11-20 | 2018-11-27 | 6 | 6 | 2018-12-19 | 2018-12-27 | 23 | 23 | 2018-12-27 | 1 | 1 | 2018-12-27 |  | 2018-12-27 |  | 1 | 1 |  |  |  |  | 2018-12-03 | 2019-01-02 |  | -19 | [11 empty] | 2018-12-27
280 | Garden Grove WalMart | 11822 Gilbert Street | Garden Grove | 92841 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2018-06-18 | 2018-06-19 |  |  | 2 | 2 | 2018-06-20 | 2018-06-22 |  | 4 | 4
281 | Yorba Linda Town Center #2 | 18421 Yorba Linda Boulevard | Yorba Linda | 92886 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2527420 | 1432807 |  |  | 3 |  |  | NO |  |  |  |  | 2018-06-14 | 2018-06-14 |  |  | 1 | 1 | 2018-06-20 |  | 2018-07-06 | [7 empty] | 2018-07-08 |  |  | 2018-09-05 |  |  | 2018-09-05 | 2018-09-17 | 9 | 9 | 2018-10-08 | 2018-10-24 | 28 | 28 | 2018-10-24 | 1 | 1 | 2018-11-02 | 2019-06-04 | 2018-11-02 | 2018-11-02 | 8 | 8 | 35 | 35 | 1 | 1 | 2019-05-23 | 2019-05-31 | 2019-07-05 | 152 | 152 | 26 | 26 | 32 | 32 | [6 empty] | 2018-11-02 |  | 2019-07-05 | [5 empty] | 2019-05-23 |  |  |  |  | 2019-04-08 | [12 empty] | 2019-09-09 | 111 | 111 |  |  | 2019-10-11 |  |  |  | 2019-11-06 | 19 | 19 | 2019-11-06 |  |  |  | 365 | 365 |  |  | 2019
282 | Santa Monica WaiveCar | 2102 Pico Boulevard | Santa Monica | 90405 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2529610 | 1428829 | [5 empty] | NO |  |  |  |  | 2018-06-18 | 2018-06-19 |  |  | 2 | 2 | 2018-06-21 | 2018-06-28 | 2018-06-28 | 8 | 8 | 1 | 1 | 2018-07-10 | 17 | 17 | 2018-07-10 |  | 2018-08-07 | 2018-08-03 | 19 | 19 | 2018-08-03 |  |  |  |  | 2018-09-05 |  |  | 2018-09-05 | 1 | 1 | 2018-09-05 |  | 2018-09-05 |  | 1 | 1 |  |  |  |  | 2018-08-24 | 2018-10-08 |  | -9 | [11 empty] | 2018-09-05
283 | Santa Ana South Harbor | 3002 South Harbor Boulevard | Santa Ana | 92704 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2560340 | 1450920 |  |  | 2 |  |  | NO |  |  |  |  | 2018-07-06 | 2018-07-06 |  |  | 1 | 1 | 2018-07-09 |  | 2018-07-12 | [7 empty] | 2018-09-14 |  | 2018-10-12 | 2018-10-23 |  |  | 2018-10-23 | 2018-10-25 | 3 | 3 | 2018-11-15 | 2018-11-16 | 17 | 17 | 2018-11-16 | 1 | 1 | 2018-12-26 | 2019-02-15 | [8 empty] | 2019-01-08 | 2019-01-29 | 2019-02-06 | 38 | 38 | 7 | 7 | 22 | 22 | [14 empty] | 2019-01-02 | 2019-01-28 | 2019-01-28 | 19 | 19 | [13 empty] | 2019-02-08 |  |  |  |  | 2019-02-20 |  |  |  | 2019-04-12 | 38 | 38 | 2019-04-12 |  |  |  | 201 | 201 |  |  | 2019
284 | Santa Clarita WalMart SuperCenter 100035 | 27931 Kelly Johnson Parkway | Santa Clarita | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 2583696 | 1470286 |  |  | 8 |  |  | NO |  |  |  |  | 2018-07-01 | 2018-07-17 |  |  | 12 | 12 | 2018-07-20 | 2018-07-24 | 2018-07-24 | 6 | 6 | 1 | 1 | 2018-10-31 | 88 | 88 | 2018-11-02 |  | 2018-12-05 | 2018-11-28 | 21 | 21 | 2018-11-28 | 2018-12-06 | 7 | 7 | 2018-12-26 | 2018-12-07 | 2 | 2 | 2018-12-07 | 1 | 1 | 2019-01-03 | 2019-01-03 | 2019-01-03 | 2019-01-15 | 20 | 20 | 29 | 29 | 9 | 9 | 2018-12-21 | 2019-01-16 | 2019-02-27 | 11 | 11 | 31 | 31 | 49 | 49 | 2019-08-26 | 187 | 187 | 2019-09-03 | 7 | 7 | 2019-01-03 | 2019-01-03 | 2019-02-27 | 2019-09-03 | 174 | 174 | 187 | 187 | 2019-09-05 |  | 2019-10-01 | 19 | 19 | 2019-06-17 | 2019-08-19 | [10 empty] | 2019-10-10 | 2019-10-17 | 89 | 89 | 6 | 6 | 2019-10-24 |  |  |  | 2020-01-29 | 68 | 68 | 2020-01-29 |  |  |  | 411 | 411 | 324 | 324 | 2020
285 | Delano WalMart SuperCenter CA100299 | 530 Woollomes Avenue | Delano | 93215 | Kern County | 9. Complete | 51 - Tulare | San Joaquin | Ventura | [9 empty] | true |  |  |  |  | 2018-07-17 | 2018-07-17 |  |  | 1 | 1 | 2018-07-18
286 | Simi Valley Tierra Rejada | 51 Tierra Rejada Road | Simi Valley | 93065 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2573543 | 1458171 |  |  | 12 |  |  | NO | 2018-07-16 | 2018-07-24 | 7 | 7 | 2018-07-13 | 2018-07-16 | 7 | 7 | 2 | 2 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 4 | 4 | 2 | 2 | 2018-10-12 | 66 | 66 | 2018-10-12 |  | 2018-11-09 | 2018-10-24 | 9 | 9 | 2018-10-24 | 2018-10-25 | 2 | 2 | 2018-11-15 | 2018-12-18 | 39 | 39 | 2018-12-18 | 1 | 1 | 2019-01-09 | 2019-01-09 | 2019-01-09 | 2019-07-11 | 17 | 17 | 186 | 186 | 132 | 132 | 2018-10-25 | 2018-11-27 | 2020-02-19 | -39 |  | 319 | 319 | 342 | 342 | 2020-06-25 | 394 | 394 | 2020-07-07 | 8 | 8 | 2018-11-27 | 2018-11-27 | 2020-02-19 | 2020-07-07 | 416 | 416 | 394 | 394 | [6 empty] | 2020-06-17 | 2020-07-14 | [10 empty] | 2020-07-28 |  |  |  |  | 2020-08-06 |  |  |  | 2020-09-19 | 31 | 31 | 2020-09-19 |  |  |  | 565 | 565 | 500 | 500 | 2020
287 | South Gate Walmart 200073 | 4651 Firestone Boulevard | South Gate | 90280 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2663014 | 1544490 |  |  | 2 |  |  | NO |  |  |  |  | 2018-07-19 | 2018-07-20 |  |  | 2 | 2 | 2018-07-24 | 2018-07-26 | 2018-07-26 | 5 | 5 | 1 | 1 | 2019-04-04 | 186 | 186 | 2019-04-09 | 2019-04-11 | 2019-05-10 | 2019-05-14 | 29 | 29 | 2019-05-14 | 2019-05-31 | 14 | 14 |  | 2019-06-21 | 16 | 16 | 2019-06-21 | 1 | 1 | 2019-06-24 | 2019-07-01 | 2019-06-24 | 2019-06-27 | 2 | 2 | 20 | 20 | 4 | 4 | 2019-07-18 | 2019-07-22 | 2019-08-30 | 20 | 20 | 30 | 30 | 32 | 32 | [6 empty] | 2019-06-24 |  | 2019-08-30 | [5 empty] | 2019-10-17 |  | 2019-11-08 | 17 | 17 |  | 2019-10-10 | 2019-10-10 | [10 empty] | 2019-11-19 |  |  |  |  | 2019-11-20 | [6 empty] | 2020-01-07 |  |  |  | 383 | 383 | 198 | 198 | 2020
288 | Calabasas Park Sorrento | 23400 Park Sorrento | Calabasas | 91302 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2532747 | 1464009 |  |  | 2 |  |  | NO |  |  |  |  | 2018-07-05 | 2018-07-05 |  |  | 1 | 1 | 2018-07-09 | 2018-07-11 | 2018-07-15 | 5 | 5 | 3 | 3 |  |  |  | 2018-07-16 | 2018-07-17 | 2018-07-31 | 2018-08-17 |  |  | 2018-08-17 | 2019-06-20 | 220 | 220 | 2018-11-28 | 2018-11-08 | -161 |  | 2018-11-08 | 1 | 1 | 2019-10-07 | 2019-10-23 | 2019-10-07 | 2020-02-26 | 238 | 238 | 177 | 177 | 100 | 100 | 2018-11-20 |  | 2020-02-21 | 9 | 9 |  |  | 326 | 326 | 2020-01-07 | 303 | 303 | 2020-01-16 | 8 | 8 |  |  | 2020-02-26 | 2020-02-26 |  |  | 303 | 303 | 2020-01-16 |  | 2020-02-19 | 23 | 23 | 2019-09-24 |  | 2019-12-26 | [9 empty] | 2020-02-20 | 2020-02-27 | 110 | 110 | 6 | 6 | 2020-02-28 |  |  |  | 2020-03-29 | 21 | 21 | 2020-03-29 |  |  |  | 449 | 449 |  |  | 2020
289 | Calabasas Lost Hills D'Anza Park | 3605 Lost Hills Road | Calabasas | 91301 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 2532760 | 1431034 |  |  | 2 |  |  | NO |  |  |  |  | 2018-07-05 | 2018-07-05 |  |  | 1 | 1 | 2018-07-07 | 2018-07-11 | 2018-07-15 | 5 | 5 | 3 | 3 |  |  |  | 2018-07-16 | 2018-07-17 | 2018-07-31 | 2018-08-07 |  |  | 2018-08-08 | 2018-08-10 | 3 | 3 |  | 2018-10-15 | 47 | 47 | 2018-10-15 | 1 | 1 | 2019-04-15 | 2019-04-29 | [9 empty] | 2018-10-17 | 2018-12-03 |  |  | 34 | 34 | [16 empty] | 2019-09-16 |  |  |  |  | 2018-08-21 | [12 empty] | 2019-10-04 | 294 | 294 |  |  | 2019-10-09 |  |  |  | 2019-11-07 | 22 | 22 | 2019-11-07 |  |  |  | 351 | 351 |  |  | 2019
290 | Adelanto, CA - Cactus Rd | 12063 Cactus Road | Adelanto | 92301 | San Bernardino County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2018-07-11 | 2018-07-26 | 12 | 12 | 2018-07-11 | 2018-07-11 | 12 | 12 | 1 | 1 | 2018-07-23
291 | El Monte Mountain View School District | 11032 Fineview Street | El Monte | 91733 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona |  |  | 2532660 | 1434221 |  |  | 2 |  |  | true |  |  |  |  | 2018-07-06 | 2018-07-06 |  |  | 1 | 1 | 2018-07-10 | 2018-07-11 | 2018-07-13 | 4 | 4 | 3 | 3 |  |  |  | 2018-07-16 | 2018-07-17 | 2018-08-14 | 2018-08-15 |  |  | 2018-08-15 | [7 empty] | 2018-09-14 |  |  | 2018-09-14 | 2018-11-07 | 2018-09-14 | 2018-10-30 |  |  |  |  | 33 | 33 | [40 empty] | 2018-10-25 | 2018-10-25 |  |  | 1 | 1 | 2018-11-09 | [6 empty] | 2018-12-19 |  |  |  | 119 | 119 |  |  | 2018
292 | Arcadia Albertsons 200050 | 298 East Live Oak | Arcadia | 91006 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  |  | 2570250 | 1463403 |  |  | 3 |  |  | true | 2018-10-05 |  |  |  | 2018-07-16 | 2018-07-17 |  |  | 2 | 2 | 2018-07-20 | 2018-07-24 | 2018-07-25 | 6 | 6 | 2 | 2 |  |  |  | 2018-10-08 |  | 2018-11-20 | 2018-11-19 |  |  | 2018-11-20 | 2019-02-15 | 64 | 64 | 2019-03-12 | 2019-03-13 | 19 | 19 | 2019-03-15 | 3 | 3 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-19 | 3 | 3 | 23 | 23 | 3 | 3 | 2019-01-18 | 2019-02-14 | 2019-04-18 | -39 |  | 46 | 46 | 65 | 65 | 2019-07-29 | 97 | 97 | 2019-08-30 | 25 | 25 | 2019-02-14 | 2019-02-14 | 2019-04-18 | 2019-08-30 | 142 | 142 | 99 | 99 | [5 empty] | 2019-05-28 | [12 empty] | 2019-08-14 | 57 | 57 |  |  | 2019-08-30 |  |  |  | 2019-10-03 | 25 | 25 | 2019-10-03 |  |  |  | 319 | 319 |  |  | 2019
293 | Bishop Vons (Albertsons) 100003 | 1190E North Main Street | Bishop | 93514 | Inyo County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  | 2552360 | 1449080 |  |  | 4 |  |  | true | 2018-08-28 | 2018-09-19 | 17 | 17 | 2018-07-23 | 2018-07-23 | 43 | 43 | 1 | 1 | 2018-07-23 | 2018-07-30 | 2018-07-31 | 6 | 6 | 2 | 2 |  |  |  | 2018-08-28 |  | 2018-10-18 | 2018-09-28 |  |  | 2018-09-28 | 2018-10-18 | 15 | 15 | 2018-11-09 | 2018-10-22 | 3 | 3 |  |  |  | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-12-02 | 22 | 22 | 32 | 32 | 9 | 9 | 2018-10-25 | 2018-11-20 | 2019-04-29 | 4 | 4 | 115 | 115 | 133 | 133 | [6 empty] | 2018-11-20 |  | 2019-04-29 | [11 empty] | 2019-05-31 | 2019-07-29 | [9 empty] | 2019-09-09 | 2019-09-19 |  |  | 9 | 9 | 2019-09-23 |  |  |  | 2019-12-04 | 53 | 53 | 2019-12-04 |  |  |  | 358 | 358 |  |  | 2019
294 | Downey WalMart 200055 | 9001 Apollo Way | Downey | 90242 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2565840 | 1455410 |  |  | 3 |  |  | NO | 2018-09-26 |  |  |  | 2018-06-28 | 2018-06-28 |  |  | 1 | 1 | 2018-06-28 | 2018-06-29 | 2018-07-02 | 2 | 2 | 2 | 2 |  |  |  | 2018-09-26 |  | 2018-10-24 | 2018-10-29 |  |  | 2018-10-30 | 2018-11-28 | 22 | 22 | 2018-12-19 | 2018-12-12 | 11 | 11 | 2018-12-12 | 1 | 1 | 2018-12-12 | 2018-12-26 | 2018-12-12 | 2018-12-18 | 1 | 1 | 15 | 15 | 5 | 5 | 2018-11-17 | 2019-04-09 | 2019-06-24 | -18 |  | 55 | 55 | 156 | 156 | 2019-07-30 | 165 | 165 | 2019-08-06 | 6 | 6 | 2018-12-12 | 2018-12-12 | 2019-06-24 | 2019-08-06 | 170 | 170 | 165 | 165 | 2019-07-22 | 2019-08-19 | 2019-08-20 | 22 | 22 |  |  |  | 2019-03-14 | [8 empty] | 2019-08-22 | 2019-08-29 |  |  | 6 | 6 | 2019-08-29 |  |  |  | 2019-09-26 | 21 | 21 | 2019-09-26 |  |  |  | 326 | 326 |  |  | 2019
295 | Chatsworth Amazon | 9031 North Lurline Avenue | Chatsworth | 91311 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2018-07-31 | 2018-07-31 |  |  | 1 | 1 | 2018-08-03
296 | El Monte Amazon | 4187 Temple City Boulevard | El Monte | 91731 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2018-07-31 | 2018-07-31 |  |  | 1 | 1 | 2018-08-03
297 | Long Beach Target 200071 | 2270 North Bellflower Boulevard | Long Beach | 90875 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-07-30 | 2018-07-30 |  |  | 1 | 1 | 2018-08-02
298 | Culver City Washington Place | 11203 West Washington Place | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2615110 | [6 empty] | true |  |  |  |  | 2018-07-24 | 2018-07-26 |  |  | 3 | 3 | 2018-07-30 | 2018-08-02 | 2018-08-02 | 6 | 6 | 1 | 1 |  |  |  | 2019-01-15 | 2019-01-16 | 2019-02-13
299 | Bridgeport Shell 100550 | 453 Main Street | Bridgeport | 93517 | Mono County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  | 2562390 | 1449943 |  |  | 4 |  |  | NO | 2018-09-07 | 2018-09-26 | 14 | 14 | 2018-08-02 | 2018-08-03 | 39 | 39 | 2 | 2 | 2018-08-10 | 2018-08-15 | 2018-08-22 | 9 | 9 | 6 | 6 | 2018-09-17 | 33 | 33 | 2018-09-19 |  | 2018-10-17 | 2018-09-28 | 10 | 10 | 2018-09-28 | 2018-10-18 | 15 | 15 | 2018-11-09 | 2018-10-22 | 3 | 3 | 2018-11-20 | 22 | 22 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-12-27 | 22 | 22 | 51 | 51 | 28 | 28 | 2018-10-25 |  | 2018-11-27 | 4 | 4 |  |  | 24 | 24 | 2019-04-18 | 108 | 108 | 2019-08-12 | 83 | 83 |  |  | 2018-12-27 | 2019-08-12 |  |  | 129 | 129 | [5 empty] | 2019-05-13 |  | 2019-05-13 | [10 empty] | 2019-08-06 | 62 | 62 |  |  | 2019-08-12 |  |  |  | 2019-10-23 | 53 | 53 | 2019-10-23 |  |  |  | 320 | 320 | 288 | 288 | 2019
300 | Blythe Denny's | 876 W Donlon Street | Blythe | 92225 | Riverside County | 11. Cancelled | 87 - Blythe | Rurals | SBRO |  |  | 2583275 | 1470250 |  |  | 4 |  |  | NO |  |  |  |  | 2018-08-10 | 2018-08-10 |  |  | 1 | 1 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2 | 2 | 2 | 2 | 2018-11-02 | 61 | 61 | 2018-11-02 |  | 2018-12-05 | 2018-12-12 | 29 | 29 | 2018-12-12 | 2018-12-12 | 1 | 1 | 2019-01-04 | 2020-03-16 | 326 | 326 | 2020-03-16 | 1 | 1 | 2019-02-14 | 2019-08-12 | 2020-03-19 | 2020-03-23 | 4 | 4 | 331 | 331 | 3 | 3 | 2019-01-02 | 2019-01-07 | 2019-06-29 | -311 |  | 125 | 125 | 128 | 128 | 2020-05-13 | 43 | 43 | 2020-07-10 | 41 | 41 | 2019-01-07 | 2019-01-07 | 2020-03-23 | 2020-07-10 | 390 | 390 | 43 | 43 | [5 empty] | 2020-05-13 | 2020-05-27 | [10 empty] | 2020-06-03 | 2020-07-13 | 42 | 42 | 28 | 28 | 2020-07-14 | 2020-08-03 | 15 | 15 | 2020-08-03 | 15 | 15 | 2020-08-03 |  |  |  | 512 | 512 | 452 | 452 | 2020
301 | Monrovia Albertsons Pavillions 200046 | 130 West Foothill Boulevard | Monrovia | 91016 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2018-08-08 | 2018-08-09 |  |  | 2 | 2 | 2018-08-14 |  | 2018-08-16
302 | Culver City Sepulveda Boulevard | 3800 Sepulveda Boulevard | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-07-24 | 2018-07-26 |  |  | 3 | 3 | 2018-07-28 | 2018-08-01 | 2018-08-01 | 5 | 5 | 1 | 1
303 | Baker Alien Fresh Jerky 100048 | 72302 Baker Boulevard | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [9 empty] | true |  |  |  |  | 2018-08-09 | 2018-08-10 |  |  | 2 | 2 | 2018-08-14 | 2018-08-17 | 2018-08-20 | 6 | 6 | 2 | 2
304 | Rowland Heights, CA - 1600 S Azusa Ave (Puente Hills Mall) | 1600 South Azusa Avenue | Rowland Heights | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO | 2018-08-13 | 2021-05-07 | 702 | 702 | 2018-08-13 | 2018-08-13 | 702 | 702 | 1 | 1 | 2018-08-15 | 2018-08-16 | 2018-08-20 | 4 | 4 | 3 | 3
305 | Santa Monica Pier | 1540 Palisades Beach Road | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-08-10 | 2018-08-10 |  |  | 1 | 1 | 2018-08-14
306 | Tulare Target Phase 2 | 2195 E Prosperity Ave | Tulare | 93274 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura |  |  | 2538250 | 1436399 | [5 empty] | NO |  |  |  |  | 2018-03-09 | [18 empty] | 2018-08-20 |  |  | 2018-08-20
307 | Los Angeles Mega-Hub | Sawtelle Boulevard and Pico Boulevard | Los Angeles | 90064 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-08-22 | 2018-08-23 |  |  | 2 | 2 | 2018-08-30 | 2018-09-04 | 2018-09-04 | 9 | 9 | 1 | 1
308 | Rosemead, CA | 3600 Rosemead Blvd | Rosemead | 91770 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2607480 | 1496016 | [5 empty] | NO | 2018-09-05 | 2018-09-18 | 10 | 10 | 2018-09-04 | 2018-09-05 | 10 | 10 | 2 | 2 | 2018-09-27 |  | 2019-01-02 | [7 empty] | 2019-01-02 | 2019-01-02 | 2019-01-31 | 2019-02-05 |  |  | 2019-02-06 | 2019-05-29 | 81 | 81 | 2019-06-19 | 2019-07-09 | 30 | 30 | 2019-07-09 | 1 | 1 | 2019-07-16 | 2019-07-16 | 2019-07-16 |  | 6 | 6
309 | Santa Monica Watt Companies | 2716 Ocean Park Blvd | Santa Monica | 90405 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2018-09-05 | 2018-09-18 | 10 | 10 | 2018-09-04 | 2018-09-05 | 10 | 10 | 2 | 2 | 2018-09-12 |  | 2018-09-19
310 | Mojave Comfort Inn | 1385 CA-58 BUS | Mojave | 93501 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 2603718 | 1485444 |  |  | 4 |  |  | NO | 2018-09-18 | 2018-09-21 | 4 | 4 | 2018-09-03 | 2018-09-04 | 14 | 14 | 2 | 2 | 2018-09-10 |  | 2018-09-15 |  |  |  |  | 2018-09-15 | 10 | 10 | 2018-12-20 | 2018-12-21 | 2019-01-15 | 2019-01-09 | 83 | 83 | 2019-01-09 | 2019-03-26 | 55 | 55 | 2019-04-16 | 2019-04-04 | 8 | 8 | 2019-04-04 | 1 | 1 | 2019-05-15 | 2019-05-15 | 2019-05-15 | 2019-05-16 | 30 | 30 | 38 | 38 | 2 | 2 | 2019-04-17 | 2019-05-08 | 2019-06-12 | 10 | 10 | 26 | 26 | 41 | 41 | 2019-10-08 | 134 | 134 | 2019-10-28 | 15 | 15 | 2019-05-08 | 2019-05-08 | 2019-06-12 | 2019-10-28 | 124 | 124 | 134 | 134 | [7 empty] | 2019-07-29 | [9 empty] | 2019-10-28 | 2019-11-21 |  |  | 19 | 19 | 2019-11-22 |  |  |  | 2020-01-06 | 31 | 31 | 2020-01-06 |  |  |  | 350 | 350 | 340 | 340 | 2020
311 | San Bernardino 7-11 | 3993 N Sierra Way | San Bernardino | 92405 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2577020 | 1469886 |  |  | 2 |  |  | NO |  |  |  |  | 2018-09-06 | 2018-09-06 |  |  | 1 | 1 |  | 2018-09-20 | 2018-09-20 | 11 | 11 | 1 | 1 | 2018-10-17 | 30 | 30 | 2018-10-18 |  | 2018-11-16 | 2018-11-20 | 25 | 25 | 2018-11-20 | 2018-11-28 | 7 | 7 | 2018-12-20 | 2019-01-14 | 34 | 34 | 2019-01-24 | 9 | 9 | 2019-02-01 | 2019-02-14 | 2019-02-01 | 2019-05-08 | 15 | 15 | 116 | 116 | 69 | 69 | 2019-01-11 | 2019-02-04 | 2019-02-25 | -2 |  | 16 | 16 | 32 | 32 | 2019-03-28 | 46 | 46 | 2019-05-29 | 45 | 45 | 2019-02-01 | 2019-02-01 | 2019-05-08 | 2019-05-29 | 84 | 84 | 54 | 54 | 2019-03-28 | [16 empty] | 2019-05-14 | 2019-05-14 |  |  | 1 | 1 | 2019-05-30 | 2019-07-11 | 31 | 31 | 2019-07-12 | 32 | 32 | 2019-07-12 |  |  |  | 222 | 222 | 193 | 193 | 2019
312 | Corona Walmart Supercenter 100018 | 479 McKinley St. | Corona | 92879 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2580401 | 1473471 |  |  | 4 |  |  | true | 2018-10-25 |  |  |  | 2018-09-03 | 2018-09-04 |  |  | 2 | 2 |  | 2018-09-18 | 2018-09-28 | 11 | 11 | 9 | 9 | 2018-10-25 | 39 | 39 | 2018-10-26 | 2018-10-29 | 2018-11-29 | 2018-11-29 | 26 | 26 | 2018-11-29 | 2019-04-22 | 103 | 103 | 2019-05-13 | 2019-05-14 | 17 | 17 | 2019-05-14 | 1 | 1 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-03-25 | -45 |  | -21 |  | 9 | 9 | 2019-03-05 | 2019-04-05 | 2019-07-29 | -51 |  | 82 | 82 | 105 | 105 | 2019-09-30 | 100 | 100 | 2019-10-03 | 4 | 4 | 2019-03-13 | 2019-03-13 | 2019-07-29 | 2019-10-03 | 147 | 147 | 100 | 100 | 2019-12-19 |  | 2020-01-08 | 14 | 14 |  |  | 2019-09-26 | [9 empty] | 2020-01-06 | 2020-01-20 |  |  | 10 | 10 | 2020-01-21 |  |  |  | 2020-03-02 | 29 | 29 | 2020-03-02 |  |  |  | 388 | 388 | 350 | 350 | 2020
313 | Olancha Coso Jct Ranch Store | US-395 & Gill Station Coso Road | Olancha | 93549 | Inyo County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura |  |  | 2581965 | 1463902 |  |  | 4 |  |  | true | 2018-10-31 | 2018-11-09 | 8 | 8 | 2018-09-18 | 2018-08-24 | 56 | 56 | -18 |  | 2018-09-18 | 2018-10-02 | 2018-10-19 | 28 | 28 | 14 | 14 |  |  |  | 2018-11-20 |  | 2018-12-18 | 2019-01-25 |  |  | 2019-01-25 | 2019-02-04 | 7 | 7 | 2019-02-25 | 2019-02-11 | 6 | 6 | 2019-02-12 | 2 | 2 | 2019-05-13 | 2019-05-13 | 2019-05-13 | 2019-05-14 | 66 | 66 | 72 | 72 | 2 | 2 | 2019-03-29 | 2019-04-24 | 2019-09-09 | 35 | 35 | 99 | 99 | 117 | 117 | 2019-07-01 | 100 | 100 | 2019-11-18 | 101 | 101 | 2019-04-24 | 2019-04-24 | 2019-09-09 | 2019-11-18 | 149 | 149 | 101 | 101 | 2019-06-21 | [5 empty] | 2019-06-05 | 2019-06-02 | [10 empty] | 2020-03-13 |  |  |  |  | 2020-03-17 |  |  |  | 2020-07-02 | 77 | 77 | 2020-07-02 |  |  |  | 464 | 464 |  |  | 2020
314 | Murrieta Sam's Club | 40500 Murrieta Hot Sptings Rd | Murrieta | 92563 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2582890 | 1524088 |  |  | 4 |  |  | true | 2018-11-01 |  |  |  | 2018-09-24 | [15 empty] | 2018-11-01 |  | 2019-04-03 | 2019-04-05 |  |  | 2019-04-05 | 2019-04-18 | 10 | 10 |  | 2019-06-06 | 36 | 36 | 2019-06-06 | 1 | 1 | 2019-08-28 | 2019-09-26 | 2019-08-28 | 2019-09-05 | 60 | 60 | 101 | 101 | 7 | 7 | 2019-06-20 | 2019-06-28 | 2019-11-18 | 11 | 11 | 102 | 102 | 108 | 108 | [6 empty] | 2019-06-28 |  | 2019-11-18 | [5 empty] | 2019-08-26 | [17 empty] | 2019-10-18 |  |  |  |  | 2019-10-18 |  |  |  | 2019-11-04 | 12 | 12 | 2019-11-04 |  |  |  | 291 | 291 |  |  | 2019
315 | Tulare WalMart SuperCenter 5536 100299 | 1110 East Prosperity Avenue | Tulare | 93274 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura |  |  | 2601295 | 1483873 |  |  | 4 |  |  | NO | 2018-12-14 | 2018-12-18 | 3 | 3 | 2018-08-20 | 2018-08-20 | 87 | 87 | 1 | 1 | 2018-08-20 | 2018-08-28 | 2018-08-31 | 7 | 7 | 4 | 4 |  |  |  | 2018-12-14 | 2018-12-17 | 2019-01-07 | 2019-01-16 |  |  | 2019-01-16 | 2019-02-04 | 14 | 14 | 2019-02-25 | 2019-02-11 | 6 | 6 | 2019-02-12 | 2 | 2 | 2019-03-07 | 2019-03-25 | 2019-03-07 | 2019-03-19 | 19 | 19 | 32 | 32 | 9 | 9 | 2019-02-22 | 2019-03-13 | 2019-04-08 | 10 | 10 | 19 | 19 | 32 | 32 | 2019-07-30 | 121 | 121 | 2019-08-12 | 10 | 10 | 2019-03-07 | 2019-03-07 | 2019-04-08 | 2019-08-12 | 113 | 113 | 122 | 122 | 2019-11-01 | [17 empty] | 2019-09-27 |  |  |  |  | 2019-10-08 |  |  |  | 2020-01-20 | 73 | 73 | 2020-01-20 |  |  |  | 369 | 369 |  |  | 2020
316 | Orange, CA- City Blvd | 20 City Blvd W | Orange | 92868 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2019-03-25 | 2019-04-01 | 6 | 6 | 2018-10-24 | [7 empty] | 2018-11-29
317 | San Fernando, CA- 1012 Celis St | 1012 Celis St | San Fernando | 91340 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 2789313 | 1637750 |  |  | 12 |  |  | NO | 2018-10-08 | 2019-05-08 | 153 | 153 | 2018-10-05 | 2018-10-10 | 151 | 151 | 4 | 4 |  |  | 2018-11-29 |  |  |  |  | 2019-12-03 | 303 | 303 | 2019-12-05 | 2019-12-06 | 2020-01-09 | 2020-01-06 | 24 | 24 | 2020-01-06 | 2020-01-22 | 12 | 12 | 2020-02-12 | 2020-02-03 | 9 | 9 | 2020-02-04 | 2 | 2 | 2020-02-24 | 2020-10-26 | 2020-02-24 |  | 15 | 15 | [5 empty] | 2020-08-28 | 2020-09-17 |  |  | 14 | 14 |  |  | 2021-01-29 | 249 | 249 | 2021-02-12 | 11 | 11 | 2020-02-24 | 2020-02-24 |  |  |  |  | 250 | 250 | 2021-02-12 |  | 2021-03-09 | 17 | 17 | [13 empty] | 2021-03-10 |  |  |  |  | 2021-03-12 |  |  |  | 2021-04-27 | 33 | 33 | 2021-04-27 |  |  |  | 655 | 655 | 353 | 353 | 2021
318 | Monterey Park Atlantic Times Square | 500 N Atlantic Blvd | Monterey Park | 91754 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2023-06-16 | 2023-06-16 |  |  | 1 | 1 | 2023-06-20 | 2023-06-21 |  | 4 | 4
319 | Irvine Concourse | 1920 Main Street | Irvine | 92617 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2618721 | 1505350 |  |  | 24 |  |  | NO | 2018-09-24 | 2018-10-10 | 13 | 13 | 2018-09-23 | 2018-09-24 | 13 | 13 | 1 | 1 |  | 2018-10-08 | 2018-10-08 | 11 | 11 | 1 | 1 |  |  |  | 2019-01-22 | 2019-01-22 | 2019-02-21 | 2019-03-12 |  |  | 2019-03-12 | 2019-03-14 | 3 | 3 | 2019-04-05 | 2019-05-24 | 52 | 52 | 2019-05-24 | 1 | 1 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2021-03-08 | 312 | 312 | 505 | 505 | 143 | 143 | 2019-07-03 | 2019-07-30 | 2019-10-25 | 29 | 29 | 64 | 64 | 83 | 83 | 2019-10-07 | 97 | 97 | 2020-08-10 | 216 | 216 | 2019-07-30 | 2019-07-30 | 2021-03-08 | 2021-03-08 | 407 | 407 | 97 | 97 | 2020-08-06 |  | 2020-09-29 | 38 | 38 |  | 2020-06-26 | [11 empty] | 2020-10-09 |  |  |  |  | 2020-09-28 |  |  |  | 2020-12-23 | 60 | 60 | 2020-12-23 |  |  |  | 579 | 579 |  |  | 2020
320 | Simi Valley, 51 Tierra Rejada Rd (Phase 2) | 51 Tierra Rejada Rd | Simi Valley | 93065 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2018-07-16 |  |  |  | 2018-07-13
321 | Palm Desert, CA- 34-460 Monterey Ave Ste 100 (Desert Gateway) | 34-460 Monterey Ave Ste 100 | Palm Desert | 92211 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2018-09-21
322 | Lumber Yard | 3939 Cross Creek Rd | Malibu | 90265 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2017-02-08
323 | Baker, CA- 71808 Baker Blvd (Ultra Gas & Mart - Phase 2) | 71808 Baker Blvd EV2 | Baker | 92309 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 3198667 | 1936654 | 1966865 |  | 20 | NO |  | true |  |  |  |  | 2017-03-02 | [7 empty] | 2021-09-23 |  |  |  |  | 2021-10-20 | 1194 | 1194 | 2021-10-28 | 2021-11-04 | 2021-12-21 | 2021-12-17 | 40 | 40 | 2021-12-20 | 2022-02-15 | 40 | 40 | 2022-03-08 | 2022-03-30 | 31 | 31 | 2022-03-30 | 1 | 1 | 2022-03-30 | 2022-03-30 | 2022-09-23 | 2023-09-18 | 125 | 125 | 403 | 403 | 249 | 249 | 2022-03-09 | 2022-05-02 | 2022-05-23 | -16 |  | 16 | 16 | 54 | 54 | [6 empty] | 2022-05-02 |  | 2023-09-18 | [5 empty] | 2023-09-18 | 2023-09-19 | [16 empty] | 2023-10-02 |  |  |  |  | 2023-10-11 | 2023-12-16 | 46 | 46 | 2023-12-18 | 47 | 47 | 2023-12-18 |  |  |  | 1738 | 1738 | 545 | 545 | 2023
324 | Baldwin Park Target | 3100 Baldwin Park Blvd | Baldwin Park | 91706 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  |  | 2592435 | 1669821 |  |  | 5 |  |  | true | 2019-11-15 | 2019-12-09 | 17 | 17 | 2018-09-06 | 2018-09-07 | 327 | 327 | 2 | 2 |  | 2018-09-26 | 2018-09-26 | 14 | 14 | 1 | 1 | 2018-11-26 | 58 | 58 | 2018-11-26 |  | 2020-03-23 | 2020-03-24 | 344 | 344 | 2020-03-24 | 2020-04-08 | 12 | 12 | 2020-05-05 | 2020-05-19 | 30 | 30 | 2020-05-19 | 1 | 1 | 2020-07-10 | 2020-07-10 | 2020-07-10 | 2020-07-13 | 37 | 37 | 67 | 67 | 2 | 2 | 2020-07-10 | 2020-07-14 | 2020-09-09 | 37 | 37 | 41 | 41 | 43 | 43 | 2021-01-21 | 169 | 169 | 2021-02-19 | 21 | 21 | 2020-07-10 | 2020-07-10 | 2020-09-09 | 2021-02-19 | 153 | 153 | 169 | 169 | 2021-03-08 |  | 2021-05-13 | 49 | 49 | [13 empty] | 2021-06-10 |  |  |  |  | 2021-06-10 |  |  |  | 2021-07-20 | 28 | 28 | 2021-07-20 |  |  |  | 734 | 734 | 677 | 677 | 2021
325 | Porsche Experience Center | 19800 S. Main St. | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 2593035 | 1487610 |  |  | 18 |  |  | true | 2018-11-26 | 2018-11-26 | 1 | 1 | 2018-11-26 | 2018-11-26 | 1 | 1 | 1 | 1 | 2018-11-28 | [9 empty] | 2018-12-04 | 2018-12-14 |  | 2019-04-10 |  |  |  | 2019-04-18 | [10 empty] | 2019-07-29 |  | 2019-07-10 |  |  | 60 | 60 | [11 empty] | 2019-06-20 |  |  | 2019-06-27 | 6 | 6 | [13 empty] | 2019-09-27 | [12 empty] | 2020-01-07 | 72 | 72 |  |  | 2020-01-07 | [6 empty] | 2020-02-07 |  |  |  | 313 | 313 |  |  | 2020
326 | Long Beach, CA - 2270 N Bellflower Drive - Target | 2270 N. Bellflower Blvd | Long Beach | 90815 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2018-11-28 | 2019-05-08 | 116 | 116 | 2018-11-27 | 2018-11-28 | 116 | 116 | 2 | 2 |  |  | 2018-12-03
327 | Carson Target | 651 W Sepulveda Blvd | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 2599290 | 1480254 |  |  | 5 |  |  | NO | 2018-11-20 | 2018-12-10 | 15 | 15 | 2018-11-07 | [6 empty] | 2018-11-13 | 2018-11-14 |  |  | 2 | 2 | 2018-12-10 | 24 | 24 | 2018-12-11 | 2018-12-12 | 2019-01-14 | 2019-01-14 | 26 | 26 | 2019-01-14 | 2019-03-18 | 46 | 46 | 2019-04-10 | 2019-04-16 | 22 | 22 | 2019-04-16 | 1 | 1 | 2019-04-15 | 2019-04-26 | 2019-04-15 | 2019-10-10 | -2 |  | 149 | 149 | 129 | 129 | 2019-04-12 | 2019-04-30 | 2019-07-11 | -3 |  | 53 | 53 | 65 | 65 | 2019-10-10 | 128 | 128 | 2019-11-06 | 20 | 20 | 2019-04-15 | 2019-04-15 | 2019-10-10 | 2019-11-06 | 148 | 148 | 128 | 128 | [7 empty] | 2019-10-22 | [9 empty] | 2019-10-22 | 2019-10-28 |  |  | 5 | 5 | 2019-10-30 |  |  |  | 2019-12-05 | 27 | 27 | 2019-12-05 |  |  |  | 282 | 282 | 259 | 259 | 2019
328 | Camarillo, CA - 209 W Ventura Blvd | 209 Ventura Blvd | Camarillo | 93010 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 2742010 | 1602522 | [5 empty] | true | 2019-03-25 | 2019-04-04 | 9 | 9 | 2018-11-28 | 2018-11-28 | 92 | 92 | 1 | 1 |  |  | 2018-12-10 |  |  |  |  | 2019-08-27 | 195 | 195 | 2019-08-28 | 2019-09-05 | 2019-10-03 | 2019-10-03 | 28 | 28 | 2019-10-03 | 2019-10-16 | 10 | 10 | 2019-11-06 | 2019-10-18 | 3 | 3 | 2019-10-18 | 1 | 1
329 | Foothill Ranch Walmart | 26502 TOWNE CENTRE DRIVE | Foothill Ranch | 92610 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2594290 | 1507186 |  |  | 5 |  |  | NO | 2018-11-29 |  |  |  | 2018-09-06 | 2018-09-07 |  |  | 2 | 2 |  |  | 2018-11-04 |  |  |  |  | 2018-11-28 | 60 | 60 | 2018-11-29 | 2022-07-19 | 2018-12-28 | 2019-01-15 | 35 | 35 | 2019-01-16 | 2019-01-16 | 1 | 1 | 2019-02-07 | 2019-01-31 | 12 | 12 | 2019-01-31 | 1 | 1 | 2019-03-04 | 2019-03-12 | 2019-03-04 | 2019-04-04 | 23 | 23 | 57 | 57 | 24 | 24 | 2019-02-26 | 2019-03-14 | 2019-05-13 | 19 | 19 | 43 | 43 | 55 | 55 | 2019-08-30 | 152 | 152 | 2019-09-23 | 17 | 17 | 2019-03-04 | 2019-03-04 | 2019-05-13 | 2019-09-23 | 146 | 146 | 152 | 152 | 2019-08-27 |  | 2019-09-16 | 15 | 15 | [13 empty] | 2019-10-02 |  |  |  |  | 2019-10-11 |  |  |  | 2019-11-13 | 24 | 24 | 2019-11-13 |  |  |  | 310 | 310 | 251 | 251 | 2019
330 | Compton CVS | 909 S. Central Ave. | Compton | 90220 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2595990 | 1482694 |  |  | 4 |  |  | NO |  |  |  |  | 2018-08-31 | [7 empty] | 2018-10-04 |  |  |  |  | 2018-12-04 | 68 | 68 | 2018-12-05 |  | 2019-01-04 | 2019-01-23 | 37 | 37 | 2019-01-24 |  |  |  |  | 2019-03-07 |  |  | 2019-03-07 | 1 | 1 | 2019-05-28 | 2019-07-19 | 2019-05-28 | 2019-05-31 | 59 | 59 |  |  | 4 | 4 | [9 empty] | 2019-06-20 | 76 | 76 | [9 empty] | 76 | 76 | [18 empty] | 2019-07-08 |  |  |  |  | 2019-08-08 |  |  |  | 2019-09-09 | 23 | 23 | 2019-09-09 |  |  |  | 267 | 267 | 200 | 200 | 2019
331 | Baker Upgrade (Phase 2) | 72157 Baker Blvd | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2598110 | 1484248 |  |  | 6 |  |  | NO | 2018-11-26 | 2018-11-26 | 1 | 1 | 2018-12-06 | 2018-12-07 | -10 |  | 2 | 2 | [10 empty] | 2018-12-07 |  | 2019-01-08 | 2019-02-12 |  |  | 2019-02-12 |  |  |  |  | 2019-02-13 |  |  | 2019-02-14 | 2 | 2 | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-03-15 | 2 | 2 |  |  | 22 | 22 | [46 empty] | 2019-03-19 |  |  |  | 2019-04-16 | 21 | 21 | 2019-04-16 |  |  |  | 94 | 94 |  |  | 2019
332 | El Segundo Plaza | 700 S. Sepulveda Blvd. | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-11-29 | 2018-12-07 |  |  | 7 | 7 | 2018-12-12 | 2018-12-15 |  | 6 | 6
333 | Ontario Residence Inn | 2025 E Convention Center Dr | Ontario | 91764 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona |  |  | 2599020 | 1486787 |  |  | 2 |  |  | YES |  |  |  |  | 2018-10-26 | 2018-10-26 |  |  | 1 | 1 |  | 2018-11-01 | 2018-11-16 | 5 | 5 | 12 | 12 | 2018-12-07 | 31 | 31 | 2018-12-11 | 2018-12-12 | 2019-01-11 | 2019-01-11 | 26 | 26 | 2019-01-11 | 2019-01-29 | 13 | 13 | 2019-02-20 | 2019-02-25 | 20 | 20 | 2019-02-25 | 1 | 1 | 2019-02-25 | 2019-03-11 | 2019-02-25 | 2019-04-15 | 1 | 1 | 55 | 55 | 36 | 36 | [23 empty] | 2019-03-19 |  |  |  |  | 2019-02-25 | [12 empty] | 2019-04-08 | 31 | 31 |  |  | 2019-04-25 |  |  |  | 2019-05-31 | 27 | 27 | 2019-05-31 |  |  |  | 156 | 156 | 126 | 126 | 2019
334 | Corona Sierra del Oro Towne Centre Shopping Center | 2661 Green River Rd | Corona | 92882 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-09-30 | 16 | YES |  | NO | 2023-03-13 | 2023-04-24 | 31 | 31 | 2024-01-18 | 2024-01-18 | -186 |  | 1 | 1 | 2024-01-18 | 2024-01-23 | 2024-02-01 | 4 | 4 | 8 | 8
335 | Tustin, CA- 15160 Kensington Park Drive | 15164.5 Kensington Park Drive | Tustin | 92782 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2923888 | 1733943 |  |  | 8 |  |  | NO | 2019-03-25 | 2019-04-18 | 19 | 19 | 2018-12-03 | 2018-12-05 | 97 | 97 | 3 | 3 | 2021-06-09 |  | 2018-12-16 | [7 empty] | 2020-07-29 |  | 2020-09-02 | 2020-09-01 |  |  | 2020-09-01 | 2020-09-09 | 6 | 6 | 2020-10-05 | 2020-10-07 | 21 | 21 | 2020-10-08 | 2 | 2 | 2020-11-12 | 2021-02-19 | 2020-11-12 | 2021-03-17 | 26 | 26 | 129 | 129 | 84 | 84 | 2020-10-08 | 2020-12-30 | 2021-04-05 | 2 | 2 | 66 | 66 | 121 | 121 | [6 empty] | 2020-11-12 |  | 2021-04-05 | [11 empty] | 2021-06-15 | [10 empty] | 2021-08-09 | 2021-08-31 |  |  | 17 | 17 | 2021-09-21 |  |  |  | 2021-10-27 | 27 | 27 | 2021-10-27 |  |  |  | 742 | 742 |  |  | 2021
336 | Lancaster Hampton Inn | 2300 Double Play Way | Lancaster | 93536 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2599790 | 1479049 |  |  | 6 |  |  | NO |  |  |  |  | 2018-10-26 | 2018-10-29 |  |  | 2 | 2 | 2018-11-02 |  | 2018-11-08 | [7 empty] | 2018-12-12 |  | 2018-12-28 | 2018-12-17 |  |  | 2018-12-21 | 2019-01-14 | 17 | 17 | 2019-02-04 | [6 empty] | 2019-01-17 | 2019-02-06 | 2019-01-17 | 2019-04-15 |  |  | 66 | 66 | 63 | 63 | [28 empty] | 2019-02-15 |  | 2019-03-01 | [10 empty] | 2019-04-19 | 46 | 46 |  |  | 2019-05-29 |  |  |  | 2019-08-12 | 54 | 54 | 2019-08-12 |  |  |  | 207 | 207 |  |  | 2019
337 | Inyokern Brady's Mobile | 4467 US-395 | Inyokern | 93527 | Kern County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura |  |  | 2651368 | 1524085 |  |  | 3 |  |  | NO | 2019-01-02 | 2019-01-16 | 11 | 11 | 2018-12-04 | 2018-12-05 | 31 | 31 | 2 | 2 |  |  | 2018-12-29 | [7 empty] | 2019-03-20 |  | 2019-04-24 | 2019-04-16 |  |  | 2019-04-16 | 2019-05-02 | 13 | 13 | 2019-05-24 | 2019-05-06 | 3 | 3 | 2019-05-06 | 1 | 1 | 2019-05-31 | 2020-04-08 | 2019-05-31 | 2020-03-02 | 20 | 20 | 215 | 215 | 194 | 194 | 2019-05-06 | 2019-07-09 | 2020-07-23 | 1 | 1 | 268 | 268 | 314 | 314 | 2020-09-25 | 359 | 359 |  |  |  | 2019-05-31 | 2019-05-31 | 2020-07-23 |  |  |  | 359 | 359 | [18 empty] | 2021-01-26 |  |  |  |  | 2021-01-27 | [6 empty] | 2021-02-23 |  |  |  | 568 | 568 |  |  | 2021
338 | Los Angeles Bank of America | 4142 S Centinela St | Los Angeles | 90066 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2647770 | 1526903 |  |  | 4 |  |  | NO |  |  |  |  | 2018-12-07 | 2018-12-11 |  |  | 3 | 3 |  | 2019-01-02 | 2019-01-02 | 17 | 17 | 1 | 1 |  |  |  | 2019-03-13 |  | 2019-04-16 | 2019-04-15 |  |  | 2019-04-15 | 2019-09-24 | 117 | 117 | 2019-10-15 | 2019-05-10 | -98 |  | 2019-05-10 | 1 | 1 | 2019-05-10 | 2019-05-10 | 2019-05-10 | 2019-10-01 | 1 | 1 | 6 | 6 | 103 | 103 | 2019-05-10 | 2019-07-25 | 2019-10-16 | 1 | 1 | 60 | 60 | 114 | 114 | [6 empty] | 2019-05-10 |  | 2019-10-16 | [23 empty] | 2019-10-08 |  |  |  |  | 2019-10-25 |  |  |  | 2019-12-07 | 31 | 31 | 2019-12-07 |  |  |  | 261 | 261 |  |  | 2019
339 | Fountain Valley Arco | 18480 Brookhurst St | Fountain Valley | 92708 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 2600421 | 1495882 |  |  | 4 |  |  | NO |  |  |  |  | 2018-10-18 | 2018-10-18 |  |  | 1 | 1 |  | 2018-11-06 | 2018-11-06 | 14 | 14 | 1 | 1 | 2018-12-13 | 41 | 41 | 2018-12-13 |  | 2019-01-14 | 2019-01-30 | 35 | 35 | 2019-01-30 | 2019-02-07 | 7 | 7 | 2019-03-01 | 2019-06-12 | 90 | 90 | 2019-06-12 | 1 | 1 | 2020-03-03 | 2020-03-16 | 2019-06-21 | 2019-06-24 | 8 | 8 | 98 | 98 | 2 | 2 | 2019-06-12 | 2019-07-01 | 2019-07-17 | 1 | 1 | 13 | 13 | 26 | 26 | 2020-03-04 | 188 | 188 | 2020-03-12 | 7 | 7 | 2019-06-21 | 2019-06-21 | 2019-07-17 | 2020-03-12 | 187 | 187 | 188 | 188 | 2020-05-06 | 2020-05-21 | 2020-05-21 | 12 | 12 | 2020-03-02 | [11 empty] | 2020-06-02 | 2020-06-09 | 71 | 71 | 6 | 6 | 2020-06-11 | 2020-07-01 | 15 | 15 | 2020-07-02 | 16 | 16 | 2020-07-02 |  |  |  | 442 | 442 | 402 | 402 | 2020
340 | La Mirada PENSKE Truck Leasing | 15050 Northam Road | La Mirada | 90638 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2577700 | 1493873 |  |  | 4 |  |  | NO |  |  |  |  | 2018-10-19 | [15 empty] | 2018-12-12 |  |  | 2019-01-04 |  |  | 2019-01-04 | 2019-01-06 | 1 | 1 | [7 empty] | 2019-03-15 |  | 2019-03-15 | [47 empty] | 2019-03-08 | [5 empty] | 2019-04-02 | [6 empty] | 2019-04-12 |  |  |  | 126 | 126 |  |  | 2019
341 | Irvine, CA- Culver Dr. (Heritage Shopping Plaza) | 14200-14474 Culver Dr. | Irvine | 92604 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2765711 | 1613080 |  |  | 16 |  |  | true | 2019-03-25 | 2019-04-17 | 18 | 18 | 2018-12-05 | 2018-12-06 | 95 | 95 | 2 | 2 | 2018-12-18 |  | 2019-03-25 | [7 empty] | 2019-10-15 |  | 2019-12-16 | 2019-12-06 |  |  | 2019-12-06 | 2019-12-09 | 2 | 2 | 2019-12-30 | 2020-01-17 | 29 | 29 | 2020-01-17 | 1 | 1 | 2020-10-23 | 2020-11-19 | 2020-10-23 |  | 196 | 196 |  |  |  |  | 2020-02-07 | 2020-11-11 | 2021-01-07 | 15 | 15 | 37 | 37 | 231 | 231 | 2021-02-10 | 268 | 268 | 2021-02-17 | 5 | 5 | 2020-10-23 | 2020-10-23 |  |  |  |  | 268 | 268 | 2021-02-18 |  | 2021-03-02 | 9 | 9 | [13 empty] | 2021-03-05 | [8 empty] | 2021-04-15 |  |  | 2021-04-15 |  |  |  | 604 | 604 |  |  | 2021
342 | Nipton Shell | 65845 Cima Rd | Nipton | 92364 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO | [9 empty] | NO | 2019-01-11 | 2019-02-04 | 17 | 17 | 2018-12-10 | 2018-12-12 | 39 | 39 | 3 | 3 | 2018-12-17 |  | 2019-01-11
343 | Santa Clarita kohl's | 19307 Golden Valley Rd | Santa Clarita | 95008 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 2602343 | 1489187 |  |  | 4 |  |  | NO |  |  |  |  | 2018-11-30 | [7 empty] | 2018-12-14 | [7 empty] | 2018-12-17 |  | 2019-07-12 | 2019-06-21 |  |  | 2019-06-21 | 2019-06-21 | 1 | 1 | 2019-07-22 | 2019-06-24 | 2 | 2 | 2019-06-24 | 1 | 1 | 2019-07-19 | 2019-09-03 | 2019-07-19 | 2020-02-13 | 20 | 20 | 168 | 168 | 148 | 148 | 2019-07-17 | 2019-08-01 | 2020-02-21 | 18 | 18 | 144 | 144 | 155 | 155 | 2020-06-02 | 243 | 243 | 2020-06-23 | 16 | 16 | 2019-07-19 | 2019-07-19 | 2020-02-21 | 2020-06-23 | 239 | 239 | 243 | 243 | 2020-07-09 | 2020-07-23 | 2020-07-23 | 11 | 11 | 2020-06-01 | [11 empty] | 2020-06-23 | 2020-07-27 | 40 | 40 | 24 | 24 | 2020-07-27 | 2020-08-20 | 19 | 19 | 2020-08-21 | 20 | 20 | 2020-08-21 |  |  |  | 446 | 446 |  |  | 2020
344 | Penske Chino Facility | 13980 Magnolia St | Chino | 91710 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2575480 | 1458670 |  |  | 4 |  |  | true |  |  |  |  | 2018-10-03 | 2018-10-03 |  |  | 1 | 1 | 2018-10-08 | 2018-10-10 | 2018-10-17 | 6 | 6 | 6 | 6 |  |  |  | 2018-10-16 | 2018-10-17 | 2018-11-15 | 2018-11-15 |  |  | 2018-11-15 | 2018-11-29 | 11 | 11 | 2018-12-24 | 2018-12-24 | 18 | 18 | 2018-12-24 | 1 | 1 | 2018-12-26 |  | 2018-12-26 | 2018-12-26 | 3 | 3 | 20 | 20 | 1 | 1 | [28 empty] | 2018-12-31 | 2018-01-04 |  | 2018-12-31 | 1 | 1 | 2018-01-04 | -258 | [17 empty] | 2019-01-24 |  |  |  | 82 | 82 |  |  | 2019
345 | Camarillo Premium Outlets | 740 Ventura Blvd | Camarillo | 93010 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 2608884 | 1491284 |  |  | 9 |  |  | NO | 2018-11-29 |  |  |  | 2019-01-04 | [7 empty] | 2018-11-16 | [7 empty] | 2019-01-04 | 2019-01-07 | 2019-01-22 | 2019-02-04 |  |  | 2019-02-04 | 2019-08-23 | 145 | 145 | 2019-09-13 | 2019-09-12 | 15 | 15 | 2019-09-13 | 2 | 2 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-24 | 5 | 5 | 23 | 23 | 5 | 5 | 2019-03-08 | 2019-04-08 | 2019-11-12 | -135 |  | 157 | 157 | 178 | 178 | [6 empty] | 2019-04-08 |  | 2019-11-12 | [5 empty] | 2020-02-10 |  |  |  |  | 2019-12-17 | [12 empty] | 2020-03-09 | 57 | 57 |  |  | 2020-03-11 |  |  |  | 2020-05-05 | 40 | 40 | 2020-05-05 |  |  |  | 345 | 345 |  |  | 2020
346 | Culver City Senior Center | 4095 Overland Ave | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2644560 | 1525328 |  |  | 3 |  |  | NO |  |  |  |  | 2018-10-16 | 2018-10-17 |  |  | 2 | 2 |  | 2018-10-19 |  | 3 | 3 | [5 empty] | 2019-03-06 |  |  | 2019-04-05 |  |  | 2019-04-08 |  |  |  |  | 2019-05-23 |  |  | 2019-05-23 | 1 | 1 | 2019-07-09 | 2019-08-01 | [8 empty] | 2019-07-03 | 2019-07-16 | 2019-08-27 | 30 | 30 | 31 | 31 | 40 | 40 | [14 empty] | 2019-06-20 |  |  |  |  | 2019-05-23 |  | 2019-07-08 | [10 empty] | 2019-08-08 | 56 | 56 |  |  | 2019-08-28 |  |  |  | 2019-09-30 | 24 | 24 | 2019-09-30 |  |  |  | 250 | 250 |  |  | 2019
347 | Ventura Pacific View Mall | 3301 E. Maint St | Ventura | 93003 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura | [9 empty] | NO | 2018-12-28 | 2019-01-24 | 20 | 20 | 2018-12-28 | 2018-12-28 | 20 | 20 | 1 | 1 | 2019-01-03 |  | 2019-01-07
348 | Desert Hills Premium Outlets | 48400 Seminole Dr. | Cabazon | 92230 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO |  |  | 2613040 | 1490535 |  |  | 3 |  |  | NO | 2018-11-06 | 2018-11-27 | 16 | 16 | 2018-08-30 | 2018-08-30 | 64 | 64 | 1 | 1 |  |  | 2018-10-18 | [7 empty] | 2019-01-11 | 2019-01-16 | 2019-04-30 | 2019-04-23 |  |  | 2019-04-23 | 2019-04-23 | 1 | 1 | 2019-05-14 | 2019-05-30 | 28 | 28 | 2019-05-30 | 1 | 1 | 2019-05-30 | 2019-06-10 | 2019-05-30 | 2021-06-23 | 1 | 1 | 553 | 553 | 526 | 526 | 2019-05-14 | 2019-05-28 | 2019-09-23 | -13 |  | 85 | 85 | 95 | 95 | 2019-12-23 | 148 | 148 |  |  |  | 2019-05-28 | 2019-05-28 | 2021-06-23 |  |  |  | 148 | 148 |  |  | 2020-02-26 |  |  | 2019-06-18 |  | 2019-12-17 | [10 empty] | 2020-01-07 | 145 | 145 |  |  | 2020-01-16 |  |  |  | 2020-02-26 | 28 | 28 | 2020-02-26 |  |  |  | 387 | 387 |  |  | 2020
349 | Chino NFI Distribution Center | 15710 Mountain Ave | Chino | 91708 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2635430 | 1513866 | [5 empty] | NO |  |  |  |  | 2019-01-10 | 2019-01-10 |  |  | 1 | 1 |  | 2019-01-11 | 2019-01-11 | 2 | 2 | 1 | 1 |  |  |  | 2019-02-20 |  | 2019-03-25 | 2019-03-15 |  |  | 2019-03-15 | 2019-04-12 | 21 | 21 |  |  |  |  | 2019-05-08 |  |  | 2019-05-08 |  | 2019-05-08 | [7 empty] | 2019-06-11 |  | 2019-07-17 |  |  |  |  | 27 | 27 | [14 empty] | 2019-06-28 | [13 empty] | 2019-07-12 |  |  | 2019-07-12 | [12 empty] | 2019-08-02 |  |  |  | 147 | 147 |  |  | 2019
350 | Downey Apollo Center | 10335 Lakewood Blvd. "CS" | Downey | 90241 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2625217 | 1512141 |  |  | 3 |  |  | NO |  |  |  |  | 2019-01-17 | 2019-01-17 |  |  | 1 | 1 | 2019-01-23 | 2019-01-24 | 2019-01-24 | 6 | 6 | 1 | 1 |  |  |  | 2019-02-01 | 2019-02-05 | 2019-02-27 | 2019-03-08 |  |  | 2019-03-08 | 2019-03-19 | 8 | 8 | 2019-04-10 | 2019-04-29 | 30 | 30 | 2019-05-01 | 3 | 3 | 2019-05-01 | 2019-05-08 | 2019-05-01 | 2019-12-05 | 3 | 3 | 188 | 188 | 157 | 157 | 2019-05-15 | 2019-05-31 | 2019-06-21 | 13 | 13 | 16 | 16 | 28 | 28 | [6 empty] | 2019-05-01 |  | 2019-12-05 | [10 empty] | 2019-12-03 | [12 empty] | 2019-12-10 | 6 | 6 |  |  | 2020-01-30 | [6 empty] | 2020-03-02 |  |  |  | 290 | 290 |  |  | 2020
351 | El Segundo Hyatt House | 810 S. Douglas St. | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2620970 | 1507238 |  |  | 2 |  |  | NO |  |  |  |  | 2018-10-26 | 2018-10-26 |  |  | 1 | 1 | 2018-10-26 | 2018-10-31 | 2018-11-20 | 4 | 4 | 15 | 15 |  |  |  | 2019-01-25 |  | 2019-02-25 | 2019-03-04 |  |  | 2019-03-05 | 2019-03-07 | 3 | 3 | 2019-04-01 | [6 empty] | 2019-03-15 | 2019-05-15 | [8 empty] | 2019-03-11 | 2019-04-02 | 2019-04-15 |  |  | 10 | 10 | 26 | 26 | [14 empty] | 2019-04-30 | [5 empty] | 2019-04-11 | 2019-04-16 | [10 empty] | 2019-05-29 |  |  |  |  | 2019-05-31 | [6 empty] | 2019-06-24 |  |  |  | 172 | 172 |  |  | 2019
352 | Temple Shopping Center | 3130 Colima Rd | Hacienda Heights | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 2637996 | 1515816 |  |  | 6 |  |  | NO |  |  |  |  | 2019-01-14 | 2019-01-15 |  |  | 2 | 2 | 2019-01-16 |  | 2019-01-22 | [7 empty] | 2019-02-25 |  | 2019-03-21 | 2019-03-27 |  |  | 2019-03-28 | 2021-01-08 | 456 | 456 |  | 2021-02-05 | 20 | 20 | 2021-02-05 | 1 | 1 | 2021-02-05 | 2021-03-09 | 2021-02-05 | 2021-02-25 | 1 | 1 | 33 | 33 | 14 | 14 | 2021-02-11 | 2021-02-17 | 2021-02-26 | 5 | 5 | 8 | 8 | 11 | 11 | [6 empty] | 2021-02-05 |  | 2021-02-26 | [5 empty] | 2021-02-18 | 2021-02-24 | 2021-02-24 | 5 | 5 | [13 empty] | 2021-03-08 |  |  |  |  | 2021-03-16 | 2021-04-27 | 31 | 31 | 2021-04-27 | 31 | 31 | 2021-04-27 |  |  |  | 584 | 584 |  |  | 2021
353 | South Gate Sams Club | 5871 Firestone Blvd. | South Gate | 90280 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-01-25 | 2019-01-30 |  |  | 4 | 4 | 2019-01-31
354 | Chetonian Ultra Gas Mart | 71808 Baker Blvd | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2626796 | 1526397 |  |  | 12 |  |  | true | 2018-09-14 |  |  |  | 2018-08-30 | [7 empty] | 2018-09-15 | [7 empty] | 2019-02-04 |  | 2019-04-18 | 2019-04-16 |  |  | 2019-04-16 | 2019-06-20 | 48 | 48 | 2019-05-07 | 2019-06-25 | 4 | 4 | 2019-06-25 | 1 | 1 | 2019-06-28 | 2019-05-14 | 2019-06-28 | 2019-07-08 | 4 | 4 | 13 | 13 | 7 | 7 | 2019-04-24 | 2019-05-09 | 2019-05-20 | -45 |  | 8 | 8 | 19 | 19 | [6 empty] | 2019-05-09 |  | 2019-07-08 | [5 empty] | 2019-10-28 |  | 2019-11-19 | 17 | 17 |  |  | 2019-10-20 | [10 empty] | 2019-11-25 |  |  |  |  | 2019-12-05 |  |  |  | 2020-01-07 | 23 | 23 | 2020-01-07 |  |  |  | 353 | 353 |  |  | 2020
355 | Santa Barbara-La Cumbre Plaza | 121 South Hope Ave | Santa Barbara | 93105 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 2627980 | 1508307 | [5 empty] | NO | 2019-02-04 | 2019-02-20 | 13 | 13 | 2018-11-08 | [7 empty] | 2018-11-08 | [7 empty] | 2019-02-04 |  | 2019-03-01 | 2019-03-01 |  |  | 2019-03-04 | 2019-04-11 | 29 | 29 | 2019-05-02 | 2019-04-12 | 2 | 2 | 2019-04-12 | 1 | 1
357 | Costa Mesa Target | 3030 Harbor Blvd. Ste A. | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2019-01-30 | 2019-04-10 | 51 | 51 | 2019-01-29 | 2019-01-30 | 51 | 51 | 2 | 2 | 2019-02-04 |  | 2019-03-27
358 | Long Beach, CA - 6400 E. Marina Dr. (Alamitos Bay) | 6400 E. Marina Dr. | Long Beach CA | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2019-01-25 | 2019-04-10 | 54 | 54 | 2019-01-24 | 2019-01-25 | 54 | 54 | 2 | 2 |  | 2019-02-04 | 2019-02-04 | 7 | 7 | 1 | 1
359 | Temecula Tower Plaza | 27393 Ynez Rd. | Temecula CA | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2019-02-04 | 2019-02-04 |  |  | 1 | 1 | 2019-02-05
360 | Ontario Parking Concept, Inc. | 525 S. Vineyard Ave | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2663740 | 1539102 |  |  |  | NO |  | NO |  |  |  |  | 2019-02-06 | 2019-02-07 |  |  | 2 | 2 | 2019-02-08 |  | 2019-03-25 | [7 empty] | 2019-04-10 | 2019-04-11 | 2019-05-10 | 2019-05-09 |  |  |  | 2019-05-15 |  |  | 2019-06-05 | 2019-06-05 | 16 | 16 | 2019-06-07 | 3 | 3 | 2019-08-14 |  | 2019-08-14 |  | 51 | 51 |  |  |  |  | 2019-05-31 | 2019-11-19 | 2019-12-03 | -4 |  | 11 | 11 | 133 | 133 | [6 empty] | 2019-08-14
361 | Rolling Hills, CA - 550 Deep Valley Dr (Phase 2) | 550 Deep Valley Dr | Rolling Hills Estares | 90274 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Ventura | [9 empty] | NO |  |  |  |  | 2017-12-28
362 | Menifee, CA- 30340 Haun Rd (Target Phase 2) | 30340 Haun Rd. | Menifee | 92584 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2018-03-05
363 | Temecula Penske Truck Leasing | 42188 Winchester Rd | Temecula | 92590 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2640790 | 1525537 |  |  | 2 |  |  | NO |  |  |  |  | 2019-02-20 | 2019-02-20 |  |  | 1 | 1 |  |  | 2019-02-26 | [7 empty] | 2019-02-28 |  | 2019-03-29 | 2019-04-05 |  |  | 2019-04-05 |  |  |  |  | 2019-05-03 |  |  | 2019-05-03 | 1 | 1 | 2019-05-03 |  | 2019-05-03 |  | 1 | 1 |  |  |  |  | 2019-06-05 |  | 2019-06-10 | 24 | 24 |  |  | 4 | 4 | [14 empty] | 2019-07-11 | [22 empty] | 2019-07-26 | [6 empty] | 2019-08-16 |  |  |  | 128 | 128 |  |  | 2019
364 | Culver, CA - 8740 Washington Blvd. (Ivy Station) | 8740 Washington Blvd. | Culver City | 90232 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2019-01-15 |  |  |  | 2019-01-15 | 2019-01-15 |  |  | 1 | 1
365 | Culver City- Veterans Memorial Park | 4117 Overland Ave | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2638850 | 1517507 |  |  | 3 |  |  | NO |  |  |  |  | 2019-02-26 | [7 empty] | 2018-12-02 | [7 empty] | 2019-02-26 |  | 2019-03-25 | 2019-03-28 |  |  | 2019-03-28 | 2019-04-08 | 8 | 8 | 2019-05-06 | 2019-05-08 | 23 | 23 | 2019-05-10 | 3 | 3 | 2019-05-10 | 2019-05-20 | 2019-05-10 | 2019-05-13 | 3 | 3 | 26 | 26 | 2 | 2 | [23 empty] | 2019-06-19 | [5 empty] | 2019-05-17 | [11 empty] | 2019-08-13 |  |  |  |  | 2019-08-14 |  |  |  | 2019-09-11 | 21 | 21 | 2019-09-11 |  |  |  | 142 | 142 |  |  | 2019
366 | Huntington Beach Huntington Harbor | 16011 Bonaire Circle | Huntington Beach | 92649 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2019-02-26 | 2019-02-27 |  |  | 2 | 2 | 2019-02-28 |  | 2019-03-17
367 | Cerritos- Los Cerritos Center | 239 Los Cerritos Center | Cerritos | 90703 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 2677260 | 1562770 | [5 empty] | true | 2019-04-30 | 2019-05-02 | 3 | 3 | 2019-02-28 | 2019-03-04 | 44 | 44 | 3 | 3 |  |  | 2019-03-17 |  |  |  |  | 2019-04-30 | 44 | 44 | 2019-04-30 | 2019-05-01 | 2019-06-04
368 | Irvine Spectrum | 810 1/2 Spectrum Center Drive | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2832222 | 1664385 |  |  | 6 |  |  | NO | 2020-02-25 | 2020-03-19 | 18 | 18 | 2018-10-19 | 2019-03-07 | 268 | 268 | 100 | 100 |  | 2019-03-13 | 2020-02-20 | 5 | 5 | 244 | 244 | 2020-02-28 | 353 | 353 | 2020-03-02 | 2020-03-03 | 2020-04-03 | 2020-06-30 | 87 | 87 | 2020-06-30 | 2021-01-07 | 131 | 131 |  | 2021-02-01 | 17 | 17 | 2021-02-01 | 1 | 1 | 2021-01-11 | 2021-03-02 | 2021-01-11 | 2021-01-18 | -15 |  | 7 | 7 | 5 | 5 |  | 2021-01-04 | 2021-01-13 |  |  | 8 | 8 |  |  | 2021-05-27 | 83 | 83 | 2021-06-08 | 8 | 8 | 2021-01-04 | 2021-01-04 | 2021-01-18 | 2021-06-08 | 109 | 109 | 83 | 83 | [6 empty] | 2021-05-25 | [11 empty] | 2021-10-19 |  |  |  |  | 2021-10-27 |  |  |  | 2021-11-24 | 20 | 20 | 2021-11-24 |  |  |  | 792 | 792 | 440 | 440 | 2021
369 | Pacific Pines | 1117 Sepulveda Blvd | Torrance | 90502 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-02-19 | 2019-02-19 |  |  | 1 | 1 | 2019-02-20
370 | 4300 Long Beach | 4300 Long Beach Blvd | Long Beach | 90807 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2019-01-14 | 2019-01-15 |  |  | 2 | 2 | 2019-01-15 | 2019-01-22 |  | 6 | 6
371 | Lakewood Center Mall | 500 Lakewood Center Mall | Lakewood | 90712 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2019-10-08 | 2019-10-28 | 15 | 15 | 2018-11-08 | 2018-11-08 | 253 | 253 | 1 | 1 |  |  | 2020-02-05
372 | Mission Viejo Target | 24500 Alicia Parkway | Mission Viejo | 98027 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2774846 | 1627731 |  |  | 7 |  |  | NO | 2019-11-01 |  |  |  | 2018-11-21 | 2018-11-26 |  |  | 4 | 4 |  |  | 2019-08-13 |  |  |  |  | 2019-11-01 | 248 | 248 | 2019-11-01 | 2019-11-01 | 2019-12-06 | 2019-12-06 | 26 | 26 | 2019-12-06 | 2019-12-09 | 2 | 2 | 2019-12-30 | 2020-01-10 | 24 | 24 | 2020-01-10 | 1 | 1 | 2020-03-24 | 2021-01-13 | 2020-03-24 | 2020-03-31 | 51 | 51 | 79 | 79 | 6 | 6 |  | 2020-09-18 | 2020-12-22 |  |  | 65 | 65 |  |  | 2020-10-01 | 185 | 185 | 2020-12-29 | 60 | 60 | 2020-03-24 | 2020-03-24 | 2020-12-22 | 2020-12-29 | 194 | 194 | 185 | 185 | 2021-02-08 |  | 2021-02-26 | 14 | 14 | 2020-01-22 | [12 empty] | 2021-03-03 | 280 | 280 |  |  | 2021-03-04 |  |  |  | 2021-05-17 | 53 | 53 | 2021-05-17 |  |  |  | 636 | 636 | 389 | 389 | 2021
373 | Santa Monica Gelson's | 2627 Lincoln Blvd | Santa Monica | 90405 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-03-11 | 2019-03-12 |  |  | 2 | 2
374 | Ontario Target | 4200 East 4th Street | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2737980 | [6 empty] | NO |  |  |  |  | 2018-08-21 | 2018-08-22 |  |  | 2 | 2 |  |  | 2018-09-08 |  |  |  |  | 2019-08-19 | 260 | 260 | 2019-08-20 | 2019-08-21 | 2019-09-19 | 2019-09-18 | 23 | 23 | 2019-09-18
375 | Costa Mesa Target | 3030 Harbor Blvd Ste. A | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2018-08-21 | 2018-08-22 |  |  | 2 | 2 |  |  | 2018-08-30
376 | Redondo Beach Target | 1601 Kingsdale | Redondo Beach | 90278 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2018-08-21 | 2018-08-22 |  |  | 2 | 2
377 | Corona Kohls | 460 Hidden Valley Pkwy | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2689877 | 1562864 |  |  | 5 |  |  | NO |  |  |  |  | 2018-08-30 | [7 empty] | 2018-08-31 |  |  |  |  | 2019-05-20 | 188 | 188 | 2019-05-20 |  | 2019-06-24 | 2019-06-25 | 27 | 27 | 2019-06-25 | 2019-06-26 | 2 | 2 | 2019-07-19 | 2019-07-18 | 17 | 17 | 2019-07-18 | 1 | 1 | 2019-07-24 | 2019-12-11 | 2019-07-24 | 2019-12-11 | 5 | 5 | 121 | 121 | 101 | 101 | 2019-07-18 | 2019-08-07 | 2019-09-30 | 1 | 1 | 39 | 39 | 53 | 53 | [6 empty] | 2019-07-24 |  | 2019-12-11 | [5 empty] | 2019-12-03 |  |  |  |  | 2019-07-29 | 2019-11-14 | 2019-10-24 | [10 empty] | 2019-12-03 | 92 | 92 |  |  | 2019-12-16 |  |  |  | 2020-01-31 | 33 | 33 | 2020-01-31 |  |  |  | 370 | 370 | 183 | 183 | 2020
378 | Alhambra Kohl's | 1201 Fremont Ave. | Alhambra | 91803 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2689840 | 1558585 | [5 empty] | true |  |  |  |  | 2018-08-31 | 2018-08-31 |  |  | 1 | 1 |  |  | 2019-02-09 |  |  |  |  | 2019-05-17 | 186 | 186 | 2019-05-20 | 2019-05-22 | 2019-06-24 | 2019-06-20 | 25 | 25 | 2019-06-20 | 2019-06-21 | 2 | 2 | 2019-07-12
379 | Long Beach | 5689 Paramount Blvd | Long Beach | 90805 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2019-03-15 | 2019-03-26 | 8 | 8 | 2019-03-13 | 2019-03-15 | 8 | 8 | 3 | 3 |  |  | 2019-03-22
380 | Santa Ana E 5th St | 300 E 5th St | Santa Ana | 92701 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2740707 | 1595798 |  |  | 20 |  |  | NO | 2019-03-19 | 2019-04-24 | 27 | 27 | 2019-03-18 | 2019-03-19 | 27 | 27 | 2 | 2 |  |  | 2019-05-20 |  |  |  |  | 2019-08-19 | 111 | 111 | 2019-08-26 |  | 2019-10-02 | 2019-10-04 | 35 | 35 | 2019-10-04 | 2019-10-16 | 9 | 9 | 2019-11-06 | 2019-10-30 | 11 | 11 | 2019-10-30 | 1 | 1 | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-09-14 | 50 | 50 | 233 | 233 | 174 | 174 | 2019-11-01 | 2020-02-06 | 2020-05-14 | 3 | 3 | 70 | 70 | 137 | 137 | 2020-08-12 | 201 | 201 | 2020-08-17 | 4 | 4 | 2020-01-08 | 2020-01-08 | 2020-09-14 | 2020-09-14 | 174 | 174 | 201 | 201 | 2020-07-30 |  | 2020-08-20 | 16 | 16 | [13 empty] | 2020-09-14 |  |  |  |  | 2020-09-15 |  |  |  | 2020-11-12 | 42 | 42 | 2020-11-12 |  |  |  | 427 | 427 | 317 | 317 | 2020
381 | Torrance Union 76 Gas Station | 4000 Redondo Beach Blvd | Torrance | 90504 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2019-03-15 | 2019-03-18 |  |  | 2 | 2
382 | Long Beach, CA - 6521 E Pacific Coast Hwy (Marketplace) | 6521 E Pacific Coast Highway, EV1 | Long Beach | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3020648 | 1854522 |  |  | 20 |  |  | NO | 2019-03-21 | 2020-03-24 | 261 | 261 | 2019-03-20 | 2019-03-21 | 261 | 261 | 2 | 2 |  |  | 2020-04-08 | [7 empty] | 2021-01-19 |  | 2021-02-22 | 2021-05-28 |  |  | 2021-05-28 | 2021-06-11 | 10 | 10 | 2021-07-05 | 2021-07-13 | 22 | 22 | 2021-07-13 | 1 | 1 | 2021-07-13 | 2021-08-16 | 2021-07-13 |  | 1 | 1 | [5 empty] | 2021-08-04 | [7 empty] | 2022-01-18 | 130 | 130 | 2022-01-22 | 4 | 4 | 2021-07-13 | 2021-07-13 |  |  |  |  | 130 | 130 | 2022-01-13 | [17 empty] | 2022-03-31 |  |  |  |  | 2022-04-01 |  |  |  | 2022-05-12 | 30 | 30 | 2022-05-12 |  |  |  | 800 | 800 |  |  | 2022
383 | Grand Terrace Barton Rd. | 22795 Barton Rd. | Grand Terrace | 92313 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [14 empty] | 2019-03-21 | 2019-03-21 |  |  | 1 | 1 |  |  | 2019-04-02
384 | Fontana TCI Leasing | 14561 Merrill Ave #A | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2018-10-04 | 2018-10-10 |  |  | 5 | 5 | 2018-10-11
385 | San Bernardino Schneider | 1692 S. Auto Center Rd | San Bernardino | 92408 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | true | 2018-12-12 |  |  |  | 2018-10-04 | 2018-10-10 |  |  | 5 | 5 | 2018-10-11
386 | Santa Ana Bank of America | 2eE 17th Street | Santa Ana | 92705 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2677220 | 1554088 |  |  | 4 |  |  | NO | 2019-04-29 |  |  |  | 2019-04-03 | 2019-04-04 |  |  | 2 | 2 |  |  | 2019-04-19 |  |  |  |  | 2019-04-26 | 18 | 18 | 2019-04-30 | 2019-05-01 | 2019-06-04 | 2019-06-05 | 29 | 29 | 2019-06-05 | 2019-06-10 | 4 | 4 | 2019-07-01 | 2019-07-01 | 16 | 16 | 2019-07-09 | 7 | 7 | 2019-07-26 | 2019-08-12 | 2019-07-26 | 2019-10-10 | 20 | 20 | 89 | 89 | 55 | 55 | 2019-07-12 | 2019-07-30 | 2019-09-30 | 10 | 10 | 45 | 45 | 57 | 57 | 2019-09-18 | 52 | 52 | 2019-09-18 | 1 | 1 | 2019-07-26 | 2019-07-26 | 2019-10-10 | 2019-10-10 | 55 | 55 | 58 | 58 | [17 empty] | 2019-09-18 | 2019-09-27 |  |  | 8 | 8 | 2019-10-10 |  |  |  | 2019-12-05 | 41 | 41 | 2019-12-05 |  |  |  | 177 | 177 | 160 | 160 | 2019
387 | Culver City Super Petrol | 11272 Venice Blvd | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2680140 | [6 empty] | false | 2019-04-16 | 2019-04-17 | 2 | 2 | 2019-04-11 | 2019-04-11 | 5 | 5 | 1 | 1 |  |  | 2019-04-16 | [7 empty] | 2019-05-06 | 2019-05-07 | 2019-06-10 | 2019-07-09 |  |  | 2019-07-09 | 2019-07-12 | 4 | 4 | 2019-08-02
388 | Buena Park Courtyard Mariott | 7621 1/2 Beach Blvd | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2666010 | 1548138 |  |  | 2 |  |  | NO |  |  |  |  | 2018-10-26 | [7 empty] | 2018-11-16 |  |  |  |  | 2019-04-10 | 119 | 119 | 2019-04-12 | 2019-04-15 | 2019-05-14 | 2019-05-10 | 23 | 23 | 2019-05-10 | 2019-05-14 | 3 | 3 | 2019-06-05 | 2019-05-24 | 9 | 9 | 2019-05-28 | 3 | 3 | 2019-05-30 | 2019-06-07 | 2019-05-30 | 2019-10-04 | 5 | 5 | 104 | 104 | 92 | 92 | 2019-05-31 | 2019-06-28 | 2019-07-31 | 6 | 6 | 24 | 24 | 44 | 44 | [6 empty] | 2019-05-30 |  | 2019-10-04 | [5 empty] | 2019-08-28 |  | 2019-09-03 | 5 | 5 | 2019-07-22 | 2019-08-19 | 2019-08-19 | [9 empty] | 2019-08-29 | 2019-09-19 | 44 | 44 | 16 | 16 | 2019-10-18 | 2019-12-09 | 37 | 37 | 2019-12-09 | 37 | 37 | 2019-12-09 |  |  |  | 292 | 292 | 174 | 174 | 2019
389 | Ontario UPS | 3140 E Jurupa St | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2019-04-16 | 2019-04-16 |  |  | 1 | 1
390 | South Gate JB Hunt | 5650 Southern Ave | South Gate | 90280 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2019-04-16 | 2019-04-16 |  |  | 1 | 1 |  | 2019-04-25 | 2019-04-25 | 8 | 8 | 1 | 1
391 | Yorba Linda Center | 21480 Yorba Linda Blvd | Yorba Linda | 92887 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2723158 | 1602519 |  |  | 3 |  |  | NO | 2019-07-09 | 2019-07-23 | 11 | 11 | 2019-04-16 | 2019-04-16 | 71 | 71 | 1 | 1 |  |  | 2019-05-07 | [7 empty] | 2019-07-26 | 2019-07-29 | 2019-08-30 | 2020-01-13 |  |  | 2020-01-13 |  |  |  |  | 2020-03-04 |  |  | 2020-03-04 | 1 | 1 | 2020-03-04 | 2020-06-08 | 2020-03-04 | 2020-05-28 | 1 | 1 |  |  | 61 | 61 | 2020-03-06 |  | 2020-05-06 | 3 | 3 |  |  | 44 | 44 | 2020-05-14 | 52 | 52 | 2020-05-28 | 10 | 10 |  |  | 2020-05-28 | 2020-05-28 |  |  | 52 | 52 | 2020-05-18 | [17 empty] | 2020-06-26 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-06 | 26 | 26 | 2020-08-06 |  |  |  | 338 | 338 |  |  | 2020
392 | Yorba Linda- Yorba Canyon Center | 21480 Yorba Linda Blvd | Yorba Linda | 92887 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2723160 | 1602519 |  |  | 7 |  |  | NO |  |  |  |  | 2019-04-16 | 2019-04-16 |  |  | 1 | 1 |  |  | 2019-10-02 | [7 empty] | 2019-07-26 | 2019-07-29 |  | 2019-09-27 |  |  | 2019-10-02 | 2020-01-24 | 81 | 81 | 2020-02-14 | 2020-02-06 | 10 | 10 | 2020-02-06 | 1 | 1 | 2020-03-04 | 2020-06-25 | 2020-03-04 | 2020-05-28 | 19 | 19 | 88 | 88 | 61 | 61 |  | 2020-04-10 | 2020-05-06 |  |  | 19 | 19 |  |  | 2020-05-14 | 70 | 70 | 2020-05-28 | 10 | 10 | 2020-03-04 | 2020-03-04 | 2020-05-28 | 2020-05-28 | 61 | 61 | 70 | 70 | 2020-05-18 |  | 2020-06-04 | 13 | 13 | 2020-02-07 | [21 empty] | 2020-04-06 |  |  | 2020-04-06 |  |  |  | 252 | 252 |  |  | 2020
393 | Culver City Westfield Mall | 5800 S Sepulveda Blvd. | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-04-18 | 2019-04-19 |  |  | 2 | 2 |  |  | 2019-04-25
394 | Commerce Chevron Station | 2155 S Atlantic Blvd. | Commerce | 90040 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-04-19 | 2019-04-19 |  |  | 1 | 1 |  |  | 2019-04-25
395 | Whittier Parking Garage | 6729 Comstock Ave | Whittier | 90021 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | NO | 2019-05-02 |  |  |  | 2019-05-02 | 2019-05-02 |  |  | 1 | 1 | 2019-05-07
396 | Vidal, CA- 200 CA-62 | 200 CA-62 | Vidal | 92280 | San Bernardino County | 11. Cancelled | 87 - Blythe | Rurals | SBRO | [9 empty] | YES | 2019-05-01 | 2019-05-13 | 9 | 9 | 2019-04-30 | 2019-04-30 | 10 | 10 | 1 | 1
397 | Compton Knight | 2960 E Victoria St | Compton | 90221 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2019-05-14 |  |  |  | 2019-05-10
398 | Fontana Ryder | 13225 Jurupa Ave | Fontana | 92337 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO | [9 empty] | true | 2019-05-14 |  |  |  | 2018-10-04 | 2018-10-10 |  |  | 5 | 5
399 | Goleta Camino Real Marketplace | 7004 Market Place Drive | Goleta | 93117 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura |  |  | 2966259 | 1763527 |  |  | 6 |  |  | NO | 2019-05-23 | 2019-08-09 | 57 | 57 | 2018-08-23 | [5 empty] | 2021-06-30 |  | 2021-11-08 |  |  |  |  | 2020-10-04 | 546 | 546 | 2021-08-19 | 2020-10-14 | 2020-11-11 | 2020-11-16 | 30 | 30 | 2020-11-17 | 2021-04-06 | 95 | 95 | 2021-04-28 | 2021-05-03 | 20 | 20 | 2021-05-03 | 1 | 1 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-29 | 125 | 125 | 146 | 146 | 3 | 3 | 2020-12-22 | 2021-05-06 | 2021-05-12 | -91 |  | 5 | 5 | 98 | 98 | 2021-07-13 | 50 | 50 | 2021-09-16 | 47 | 47 | 2021-05-06 | 2021-05-06 | 2021-10-29 | 2021-10-29 | 124 | 124 | 50 | 50 | 2021-09-15 |  | 2021-10-15 | 23 | 23 | 2021-05-24 | 2021-07-01 | 2021-09-08 | [9 empty] | 2021-08-26 | 2021-11-08 | 118 | 118 | 52 | 52 | 2021-11-10 |  |  |  | 2022-01-07 | 39 | 39 | 2022-01-07 |  |  |  | 862 | 862 | 316 | 316 | 2022
400 | Bell, CA- 4410 Gage Ave | 4410 Gage Ave EV1 | Bell | 90201 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 2746534 | 1622397 |  |  | 8 |  |  | NO | 2019-05-23 | 2019-06-03 | 8 | 8 | 2019-05-21 | 2019-05-23 | 8 | 8 | 3 | 3 |  |  | 2019-06-13 |  |  |  |  | 2019-09-04 | 77 | 77 | 2019-09-06 |  | 2019-10-10 | 2019-10-08 | 25 | 25 | 2019-10-08 | 2019-10-21 | 10 | 10 | 2019-11-11 | 2019-12-14 | 40 | 40 | 2019-12-23 | 6 | 6 | 2019-12-23 | 2020-08-05 | 2019-12-23 | 2020-08-05 | 6 | 6 | 203 | 203 | 158 | 158 | 2020-07-15 | 2020-07-17 | 2020-10-21 | 148 | 148 | 68 | 68 | 70 | 70 | 2020-10-02 | 199 | 199 | 2020-11-23 | 36 | 36 | 2019-12-23 | 2019-12-23 | 2020-10-21 | 2020-11-23 | 234 | 234 | 204 | 204 | [18 empty] | 2021-01-22 |  |  |  |  | 2021-02-05 |  |  |  | 2021-03-17 | 28 | 28 | 2021-03-17 |  |  |  | 464 | 464 | 388 | 388 | 2021
401 | Malibu Village Cross Creek | 3862 Cross Creek Road | Malibu | 90265 | Los Angeles County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 2571130 | 1604937 |  |  | 3 |  |  | NO | 2019-05-24 |  |  |  | 2019-05-16 | [88 empty] | 2021-05-03 |  |  |  | 2021-05-22 | 15 | 15 | 2021-05-22 |  |  |  | 514 | 514 |  |  | 2021
402 | Santa Monica Civic Center Parking Lot | 1855 Main St. | Santa Monica | 90401 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2019-06-03 | 2019-05-23 |  |  | -8
403 | Lot 29 | 1636 5th St | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2825348 | 1665870 |  |  | 4 |  |  | NO | 2020-01-08 | 2020-01-15 | 6 | 6 | 2019-06-03 | 2019-05-23 | 169 | 169 | -8 |  | 2019-09-12 | 2019-09-20 | 2020-01-16 | 87 | 87 | 84 | 84 |  |  |  | 2020-02-20 |  |  | 2020-03-31 |  |  | 2020-03-31 | 2020-11-03 | 153 | 153 |  | 2020-12-02 | 19 | 19 | 2020-12-02 | 1 | 1 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-03-10 | 31 | 31 | 85 | 85 | 37 | 37 | 2020-12-31 | 2021-03-02 | 2021-05-17 | 21 | 21 | 55 | 55 | 95 | 95 | [6 empty] | 2021-01-15 |  | 2021-05-17 | [5 empty] | 2021-06-02 | 2021-06-02 | 2021-07-07 | 25 | 25 | 2021-05-17 | [12 empty] | 2021-07-14 | 41 | 41 |  |  | 2021-06-02 | 2021-07-12 | 28 | 28 | 2021-07-13 | 29 | 29 | 2021-07-13 |  |  |  | 537 | 537 |  |  | 2021
404 | Santa Monica Parking Structure #6 | 1431 2nd St | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-06-05 | 2019-05-23 |  |  | -10
405 | Santa Monica 9th St & Colorado Ave | 9th St & Colorado Ave | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-06-05 | 2019-05-23 |  |  | -10 |  |  |  | 2019-06-17
406 | Santa Monica Lot #12 | 1411 14th St | Santa Monica | 90404 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-06-05 | 2019-05-23 |  |  | -10 |  |  |  | 2019-06-17
407 | Grand Terrace City Hall | 22795 Barton Rd. | Grand Terrace | 92313 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2722649 | 1583879 |  |  | 2 |  |  | NO |  |  |  |  | 2019-05-31 | 2019-06-06 |  |  | 5 | 5 |  |  | 2019-06-19 |  |  |  |  | 2019-08-05 | 47 | 47 | 2019-08-06 |  | 2019-09-17 | 2019-08-21 | 13 | 13 | 2019-08-21 | 2019-08-29 | 7 | 7 |  | 2019-09-26 | 21 | 21 | 2019-09-26 | 1 | 1 |  | 2020-01-03 | 2019-09-30 | 2019-12-26 | 3 | 3 | 86 | 86 | 64 | 64 |  | 2020-01-13 | 2021-06-18 |  |  | 362 | 362 | [8 empty] | 2019-09-30 |  | 2021-06-18 | [5 empty] | 2019-12-03 |  | 2019-12-16 | 10 | 10 | 2019-09-30 | [12 empty] | 2020-02-03 | 89 | 89 |  |  | 2020-02-07 |  |  |  | 2020-03-24 | 32 | 32 | 2020-03-24 |  |  |  | 210 | 210 | 164 | 164 | 2020
408 | El Segundo, CA- 700 S Sepulveda Blvd (Plaza) | 700 S Sepulveda Blvd | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2019-06-10 | 2019-06-17 | 6 | 6 | 2019-06-10 | 2019-06-10 | 6 | 6 | 1 | 1
409 | Palos Verdes Library District Rolling Hills | 701 Silver Spur Road | Rolling Hills Estates | 90274 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 2720866 | 1589178 |  |  | 4 |  |  | NO |  |  |  |  | 2019-06-06 | 2019-06-07 |  |  | 2 | 2 | 2019-06-12 |  | 2019-06-21 |  |  |  |  | 2019-07-22 | 33 | 33 | 2019-07-22 |  | 2019-08-26 | 2019-08-27 | 27 | 27 | 2019-08-28 | 2020-05-14 | 184 | 184 | 2020-06-05 | 2020-07-27 | 51 | 51 | 2020-07-27 | 1 | 1 | 2020-07-27 | 2020-09-10 | 2020-07-27 | 2021-02-23 | 1 | 1 | 194 | 194 | 144 | 144 | 2020-07-24 | 2020-10-05 | 2020-11-30 | -2 |  | 38 | 38 | 88 | 88 | 2020-10-05 | 50 | 50 | 2020-10-21 | 13 | 13 | 2020-07-27 | 2020-07-27 | 2021-02-23 | 2021-02-23 | 144 | 144 | 50 | 50 | 2020-09-10 |  | 2020-11-19 | 50 | 50 | [13 empty] | 2021-02-22 |  |  |  |  | 2021-03-11 |  |  |  | 2021-05-01 | 37 | 37 | 2021-05-01 |  |  |  | 484 | 484 | 452 | 452 | 2021
410 | Glendora N Vista Bonita Ave | N Vista Bonita Ave | Glendora CA | 91741 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO | 2019-06-19 | 2019-07-11 | 17 | 17 | 2019-06-18 | 2019-06-19 | 17 | 17 | 2 | 2 | 2019-06-20
411 | Garden Grove | 9580 W. Garden Grove Blvd. 300 | Garden Grove | 92844 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2019-06-26 | 2019-06-26 |  |  | 1 | 1 |  |  | 2019-07-30
412 | Orange Bank of America | 941 N. Tustin St. | Orange | 92867 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2765781 | 1611737 |  |  | 5 |  |  | true | 2019-10-11 |  |  |  | 2019-06-20 | 2019-06-21 |  |  | 2 | 2 | 2019-06-25 |  | 2019-07-15 | [7 empty] | 2019-10-15 | 2019-10-17 | 2019-11-19 | 2019-11-19 |  |  | 2019-11-19 | 2020-01-17 | 43 | 43 | 2020-02-10 | 2020-02-28 | 29 | 29 | 2020-02-28 | 1 | 1 | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | 17 | 17 |  |  |  |  | 2020-02-24 | 2020-03-02 | 2020-03-17 | -5 |  | 12 | 12 | 17 | 17 | 2020-08-18 | 121 | 121 | 2020-08-20 | 3 | 3 | 2020-03-02 | 2020-03-02 |  |  |  |  | 121 | 121 | [18 empty] | 2020-10-26 |  |  |  |  | 2020-10-27 |  |  |  | 2020-12-18 | 36 | 36 | 2020-12-18 |  |  |  | 383 | 383 |  |  | 2020
413 | Temecula Bank of America | 27489 Ynez Rd. | Temecula CA | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2771460 | [6 empty] | NO | 2019-09-13 | 2019-10-25 | 31 | 31 | 2019-06-24 | 2019-06-25 | 89 | 89 | 2 | 2 |  |  | 2019-09-18 |  |  |  |  | 2019-09-12 | 59 | 59 | 2019-10-25 | 2019-10-29 | 2020-03-11
414 | La Canada, CA - 650 Foothill Blvd | 650 Foothill BLVD | La Canada Flintridge | 91011 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO | 2019-07-08 | 2020-07-13 | 261 | 261 | 2019-07-02 | 2019-07-03 | 264 | 264 | 2 | 2 | 2019-07-05 |  | 2020-06-24
415 | Fountain Valley Bank of America | 17468 Brookhurst | Fountain Valley | 92708 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2796784 | 1652938 |  |  | 5 |  |  | NO | 2019-12-23 | 2020-01-08 | 12 | 12 | 2019-07-10 | 2019-07-10 | 130 | 130 | 1 | 1 | 2019-07-11 |  | 2019-07-22 | [7 empty] | 2019-12-26 |  | 2020-03-19 | 2020-04-21 |  |  | 2020-04-21 | 2020-06-22 | 44 | 44 | 2020-07-13 | 2020-07-27 | 25 | 25 | 2020-07-27 | 1 | 1 | 2020-07-27 | 2020-07-27 | 2020-07-27 | 2020-08-17 | 1 | 1 | 40 | 40 | 16 | 16 | 2020-07-23 | 2020-08-10 | 2020-10-29 | -3 |  | 58 | 58 | 70 | 70 | [6 empty] | 2020-07-27 |  | 2020-10-29 | [5 empty] | 2021-01-11 | [17 empty] | 2021-02-16 |  |  |  |  | 2021-03-09 |  |  |  | 2021-04-12 | 25 | 25 | 2021-04-12 |  |  |  | 446 | 446 |  |  | 2021
416 | Los Angeles, CA- 6709 La Tijera Blvd (Ladera Center) | 6709 La Tijera Blvd | Los Angeles | 90045 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2019-07-18 | 2020-11-02 | 332 | 332 | 2019-07-10 | 2019-07-10 | 338 | 338 | 1 | 1 |  |  | 2019-07-17
417 | Whittier | 13211 Whittier Blvd | Whittier | 90602 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2733250 | 1592143 | [5 empty] | NO |  |  |  |  | 2019-07-15 | 2019-07-16 |  |  | 2 | 2 |  |  | 2019-07-15 |  |  |  |  | 2019-08-12 | 21 | 21 | 2019-08-13 |  | 2019-09-12 | 2019-09-11 | 23 | 23 | 2019-09-11
418 | Montclair, CA - 5060 E Montclair Plaza Ln | 5060 E. Montclair Plaza Lane | Montclair | 91763 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2808020 | 1652687 | [5 empty] | NO | 2019-07-15 | 2019-07-17 | 3 | 3 | 2019-07-15 | 2019-07-15 | 3 | 3 | 1 | 1 |  |  | 2019-07-22 |  |  |  |  | 2020-01-16 | 133 | 133 | 2020-01-17 | 2020-01-22 | 2020-02-17 | 2020-02-26 | 28 | 28 | 2020-02-26 |  |  |  |  | 2020-03-31 |  |  | 2020-03-31 | 1 | 1 | 2020-03-31 | 2020-03-31 | 2020-03-31 |  | 1 | 1 |  |  |  |  | 2020-05-14 | 2020-06-18 |  | 33 | 33 | [10 empty] | 2020-03-31
419 | Redlands, CA - 9900- 10080 Alabama St | 9900-10080 Alabama St | Redlands | 92374 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | true |  |  |  |  | 2019-07-17 | 2019-07-17 |  |  | 1 | 1
420 | Highland, CA- 27909 1/2 Highland Ave | 27909 1/2 Highland Ave | Highland | 92346 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2962475 | 1776502 |  |  | 8 |  |  | true | 2019-07-30 | 2019-08-06 | 6 | 6 | 2019-07-29 | 2019-07-30 | 6 | 6 | 2 | 2 | 2019-07-30 | [9 empty] | 2020-09-29 | 2020-10-06 | 2020-11-02 | 2020-12-23 |  |  | 2020-12-23 | 2021-01-04 | 7 | 7 | 2021-01-25 | 2021-02-23 | 35 | 35 | 2021-02-23 | 1 | 1 | 2021-02-25 | 2021-03-12 | 2021-02-25 | 2021-06-30 | 3 | 3 | 125 | 125 | 89 | 89 | 2021-02-01 | 2021-04-12 | 2021-04-19 | -16 |  | 6 | 6 | 55 | 55 | 2021-06-14 | 79 | 79 |  |  |  | 2021-02-25 | 2021-02-25 | 2021-06-30 |  |  |  | 79 | 79 |  |  | 2021-09-02 | [14 empty] | 2021-06-16 | 2021-07-14 |  |  | 20 | 20 | 2021-07-22 |  |  |  | 2021-09-02 | 31 | 31 | 2021-09-02 |  |  |  | 534 | 534 |  |  | 2021
421 | Palm Springs Bank of America | 588 S. Palm Canyon Dr. | Palm Springs | 92264 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2766089 | 1636776 |  |  | 4 |  |  | NO | 2019-10-11 |  |  |  | 2019-07-31 | 2019-08-01 |  |  | 2 | 2 | 2019-08-06 |  | 2019-09-10 | [7 empty] | 2019-10-16 | 2019-10-18 | 2020-03-06 | 2020-03-06 |  |  | 2020-03-06 | 2020-04-06 | 22 | 22 | 2020-04-27 | 2020-04-23 | 14 | 14 | 2020-04-23 | 1 | 1 | 2020-04-23 | 2020-08-12 | 2020-04-23 | 2020-04-28 | 1 | 1 | 17 | 17 | 4 | 4 | 2020-04-14 | 2020-07-13 | 2020-07-28 | -8 |  | 12 | 12 | 74 | 74 | [6 empty] | 2020-04-23 |  | 2020-07-28 | [5 empty] | 2020-08-13 |  | 2020-08-31 | 13 | 13 | 2020-07-13 | [12 empty] | 2020-09-08 | 41 | 41 |  |  | 2020-09-10 |  |  |  | 2020-11-02 | 38 | 38 | 2020-11-02 |  |  |  | 323 | 323 |  |  | 2020
422 | Westlake Lindero Canyon Bank of America | 30895 Thousand Oaks Blvd | Westlake Village | 91362 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2019-07-31 | 2019-08-01 |  |  | 2 | 2 |  |  | 2019-08-13
423 | Rosemead Walmart | 1827 Walnut Grove Ave | Rosemead | 91770 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona |  |  | 2742590 | 1603255 |  |  | 4 |  |  | NO | 2019-08-14 |  |  |  | 2019-08-02 | 2019-08-02 |  |  | 1 | 1 | 2019-08-06 |  | 2019-08-13 |  |  |  |  | 2019-08-28 | 19 | 19 | 2019-08-28 |  | 2019-09-27 | 2019-11-12 | 55 | 55 | 2019-11-12 | 2020-01-06 | 39 | 39 | 2020-01-27 | 2020-01-30 | 18 | 18 | 2020-01-30 | 1 | 1 | 2020-01-30 | 2020-03-02 | 2020-01-30 | 2020-02-19 | 1 | 1 | 31 | 31 | 14 | 14 | 2020-01-22 | 2020-02-06 | 2020-09-14 | -7 |  | 154 | 154 | 165 | 165 | 2020-07-14 | 116 | 116 | 2020-08-11 | 21 | 21 | 2020-01-30 | 2020-01-30 | 2020-09-14 | 2020-09-14 | 159 | 159 | 116 | 116 | 2020-07-17 | 2020-08-03 | 2020-08-03 | 12 | 12 | 2020-02-03 | 2020-07-06 | [11 empty] | 2020-08-24 | 143 | 143 |  |  | 2020-09-21 |  |  |  | 2020-10-30 | 30 | 30 | 2020-10-30 |  |  |  | 320 | 320 | 302 | 302 | 2020
424 | Pico Rivera Walmart | 8500 Washington Blvd. | Pico Rivera CA | 90660 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 2765873 | 1643171 |  |  | 5 |  |  | true | 2019-08-14 | 2019-08-28 | 11 | 11 | 2019-08-02 | 2019-08-02 | 19 | 19 | 1 | 1 | 2019-08-06 |  | 2019-08-13 |  |  |  |  | 2019-10-10 | 50 | 50 | 2019-10-15 |  | 2019-11-20 | 2019-11-21 | 31 | 31 | 2019-11-21 | 2019-12-02 | 8 | 8 | 2019-12-23 | 2020-01-17 | 34 | 34 | 2020-01-17 | 1 | 1 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-01 | 54 | 54 | 85 | 85 | -3 |  | 2020-03-06 | 2020-04-17 | 2020-09-21 | 34 | 34 | 109 | 109 | 139 | 139 | 2020-10-14 | 189 | 189 | 2020-11-20 | 27 | 27 | 2020-04-03 | 2020-04-03 | 2020-09-21 | 2020-11-20 | 162 | 162 | 189 | 189 | 2020-10-15 |  |  |  |  | 2020-01-23 | [11 empty] | 2020-12-18 | 2020-10-14 | 186 | 186 | -45 |  | 2020-10-20 |  |  |  | 2021-02-17 | 80 | 80 | 2021-02-17 |  |  |  | 391 | 391 | 342 | 342 | 2021
425 | Rancho Cucamonga Walmart | 12549 Foothill Blvd. | Rancho Cucamonga | 91739 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2743180 | [6 empty] | NO | 2019-08-29 | 2019-09-17 | 14 | 14 | 2019-08-02 | 2019-08-02 | 33 | 33 | 1 | 1 | 2019-08-06 |  | 2019-08-13 | [7 empty] | 2019-08-29
426 | Upland Town Center | 913 W. Foothill Blvd | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2771476 | 1623608 |  |  | 5 |  |  | NO | 2019-09-13 | 2019-10-25 | 31 | 31 | 2019-08-02 | 2019-08-02 | 61 | 61 | 1 | 1 | 2019-08-06 |  | 2019-08-19 |  |  |  |  | 2019-09-12 | 30 | 30 | 2019-10-25 |  | 2019-11-27 | 2019-12-02 | 58 | 58 | 2019-12-02 | 2019-12-04 | 3 | 3 | 2019-12-30 | 2020-01-24 | 36 | 36 | 2020-01-24 | 1 | 1 | 2020-01-24 | 2020-09-08 | 2020-01-24 | 2020-06-03 | 1 | 1 | 127 | 127 | 92 | 92 | 2020-02-07 | 2020-03-10 | 2020-04-08 | 11 | 11 | 22 | 22 | 43 | 43 | 2020-08-21 | 148 | 148 | 2020-08-28 | 6 | 6 | 2020-01-24 | 2020-01-24 | 2020-06-03 | 2020-08-28 | 153 | 153 | 148 | 148 | 2020-08-25 | [17 empty] | 2020-08-25 |  |  |  |  | 2020-09-08 |  |  |  | 2021-01-25 | 94 | 94 | 2021-01-25 |  |  |  | 375 | 375 | 346 | 346 | 2021
427 | Temecula, CA- Winchester Road | 39848 Winchester Rd #A | Temecula | 92591 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | YES | 2019-08-05 | 2019-09-03 | 22 | 22 | 2019-08-02 | 2019-08-05 | 22 | 22 | 2 | 2 | 2019-08-06 |  | 2019-08-13
428 | Brea, CA- 177 S Madrona Ave | 175 S Madrona Ave | Brea | 92821 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2938483 | 1746825 |  |  | 24 |  |  | YES | 2019-09-06 | 2019-11-12 | 48 | 48 | 2019-08-09 | 2019-09-06 | 48 | 48 | 21 | 21 |  |  | 2019-08-19 | [7 empty] | 2020-08-18 |  | 2020-09-21 | 2020-09-25 |  |  | 2020-09-25 | 2021-04-26 | 145 | 145 | 2021-05-17 | 2021-07-21 | 61 | 61 | 2021-07-21 | 1 | 1 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-21 | 43 | 43 | 104 | 104 | 2 | 2 | 2021-05-24 | 2021-06-01 | 2022-03-22 | -41 |  | 203 | 203 | 208 | 208 | 2021-05-24 | -41 |  |  |  |  | 2021-06-01 | 2021-05-24 | 2022-03-22 |  |  |  | -41 |  |  | 2022-07-15 | 2022-07-15 |  |  |  |  | 2021-07-06 | [10 empty] | 2022-07-19 |  |  |  |  | 2022-07-27 |  |  |  | 2022-10-12 | 55 | 55 | 2022-10-12 |  |  |  | 804 | 804 |  |  | 2022
429 | La Canada, CA - 1919 Verdugo Blvd | 1919 Verdugo Blvd. | La Canada Flintridge | 91011 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  |  | 3177520 | 1928289 | [5 empty] | true | 2021-04-22 |  |  |  | 2019-08-14 | 2019-08-15 |  |  | 2 | 2 | 2019-08-16 |  | 2019-09-13 | [7 empty] | 2021-09-23 | 2021-10-01 | 2021-11-15 | 2021-11-17 |  |  | 2021-11-19 | 2022-03-24 | 85 | 85 | 2022-04-14 | [6 empty] | 2022-05-12 |  | 2022-05-12 | [7 empty] | 2022-04-15
430 | Beaumont, CA - E 2nd St. | 1540 E. 2nd St. | Beaumont | 92223 | Riverside County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2765748 | 1611520 |  |  | 20 |  |  | NO | 2019-08-16 |  |  |  | 2019-08-16 | 2019-08-16 |  |  | 1 | 1 | 2019-08-19 |  | 2019-08-30 |  |  |  |  | 2019-10-03 | 35 | 35 | 2019-10-15 | 2019-10-18 | 2019-12-13 | 2019-12-05 | 46 | 46 | 2019-12-06 | 2019-12-09 | 2 | 2 | 2019-12-31 | 2019-12-26 | 14 | 14 | 2019-12-26 | 1 | 1 | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2020-01-21 | 1 | 1 | 30 | 30 | 17 | 17 | 2019-12-18 | 2020-02-04 | 2020-02-05 | -7 |  | 2 | 2 | 34 | 34 | 2020-01-14 | 13 | 13 | 2020-02-03 | 14 | 14 | 2019-12-26 | 2019-12-26 | 2020-02-05 | 2020-02-05 | 28 | 28 | 13 | 13 | 2020-02-24 |  | 2020-03-05 | 9 | 9 | [13 empty] | 2020-06-18 |  |  |  |  | 2020-02-06 |  |  |  | 2020-06-29 | 101 | 101 | 2020-06-29 |  |  |  | 223 | 223 | 189 | 189 | 2020
431 | Ontario Penske | 4015 Guati Road | Ontario | 91761 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2755450 | 1606980 |  |  | 8 |  |  | NO | 2019-08-26 | 2019-09-24 | 22 | 22 | 2019-08-26 | 2019-08-26 | 22 | 22 | 1 | 1 | 2019-08-27 | [9 empty] | 2019-09-24 | 2019-09-25 | 2019-10-23 | 2019-10-23 |  |  | 2019-10-23 | 2019-11-01 | 8 | 8 | [7 empty] | 2019-12-13 | 2019-12-23 | 2019-12-13 | 2020-02-04 |  |  | 66 | 66 | 36 | 36 | [23 empty] | 2020-01-14 | [16 empty] | 2020-01-04 | 2020-02-03 |  |  | 20 | 20
432 | San Bernardino Intermodal Yard CARB Elect. | 1863 West 4th St | San Bernardino | 92410 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 2743107 | 1642617 |  |  | 10 |  |  | YES |  |  |  |  | 2019-08-29 | 2020-01-16 |  |  | 100 | 100 | 2020-01-16 | [9 empty] | 2019-08-29 |  |  | 2019-09-30 |  |  | 2019-09-30 | 2019-12-12 | 54 | 54 | 2020-01-06 | 2020-01-09 | 20 | 20 | 2020-01-09 | 1 | 1 | 2020-01-30 | 2020-02-11 | 2020-01-30 | 2020-01-30 | 15 | 15 | 34 | 34 | 1 | 1 | [23 empty] | 2020-02-11 | [17 empty] | 2020-02-11 |  |  |  |  | 2020-03-04 |  |  |  | 2020-04-02 | 22 | 22 | 2020-04-02 |  |  |  | 153 | 153 |  |  | 2020
433 | Costa Mesa, CA-3303 Hyland Ave EV1 | 3303 Hyland Ave | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3088640 | 1861257 |  |  | 8 |  |  | NO | 2019-08-29 | 2020-10-23 | 296 | 296 | 2019-08-29 | 2019-08-29 | 296 | 296 | 1 | 1 | 2019-08-30 |  | 2019-09-18 | [7 empty] | 2021-05-11 | 2021-05-11 | 2021-06-11 | 2021-06-23 |  |  | 2021-06-23 | 2022-01-05 | 135 | 135 | 2022-01-26 | 2022-01-19 | 10 | 10 | 2022-01-19 | 1 | 1 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-27 | 61 | 61 | 79 | 79 | 10 | 10 | 2022-01-27 | 2022-02-17 | 2022-05-20 | 7 | 7 | 66 | 66 | 81 | 81 | 2022-11-18 | 213 | 213 | 2023-02-28 | 69 | 69 | 2022-02-17 | 2022-02-17 | 2022-05-20 | 2023-02-28 | 260 | 260 | 213 | 213 | 2022-11-17 | 2022-12-20 | 2022-12-20 | 22 | 22 | [12 empty] | 2023-02-06 | 2023-02-06 |  |  | 1 | 1 | 2023-02-10 | 2023-03-28 | 32 | 32 | 2023-04-15 | 45 | 45 | 2023-04-15 |  |  |  | 917 | 917 |  |  | 2023
434 | Brea | 160 N Brea Blvd | Brea | 92821 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2019-08-29 | 2019-08-30 |  |  | 2 | 2 | 2019-08-30 |  | 2019-09-18
435 | Redlands, CA - 100 West Stuart Avenue | 100 W Stuart Avenue | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | true | 2019-09-23 | 2019-10-25 | 25 | 25 | 2019-09-20 | 2019-09-20 | 26 | 26 | 1 | 1 | 2019-09-23 |  | 2019-09-30
436 | Whittier, CA | 11850 Whittier Blvd | Whittier | 90601 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | [9 empty] | true | 2019-10-08 | 2019-10-22 | 11 | 11 | 2019-10-03 | 2019-10-03 | 14 | 14 | 1 | 1 | 2019-10-04 |  | 2019-10-24
437 | Industry, CA- 18558 Gale Ave | 18558 Gale Ave | City of Industry | 91748 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 2952171 | 1765114 |  |  | 20 |  |  | true | 2019-10-08 | 2019-10-29 | 16 | 16 | 2019-10-08 | 2019-10-08 | 16 | 16 | 1 | 1 |  |  | 2019-10-24 |  |  |  |  | 2020-09-06 | 234 | 234 | 2020-09-08 | 2020-09-16 | 2020-10-12 | 2020-10-17 | 29 | 29 | 2020-10-19 | 2020-10-27 | 7 | 7 | 2020-11-23 | 2020-11-24 | 20 | 20 | 2020-11-24 | 1 | 1 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2021-01-13 | 19 | 19 | 52 | 52 | 15 | 15 | 2020-12-08 | 2021-01-14 | 2021-03-19 | 9 | 9 | 45 | 45 | 70 | 70 | 2021-04-21 | 101 | 101 | 2021-04-23 | 3 | 3 | 2020-12-22 | 2020-12-22 | 2021-03-19 | 2021-04-23 | 85 | 85 | 101 | 101 | 2021-05-06 |  | 2021-05-21 | 12 | 12 | 2021-03-30 | [11 empty] | 2021-05-24 | 2021-05-25 | 41 | 41 | 2 | 2 | 2021-05-11 |  |  |  | 2021-06-25 | 33 | 33 | 2021-06-25 |  |  |  | 435 | 435 | 201 | 201 | 2021
438 | San Gabriel, CA- 140 W Valley Blvd | 140 W Valley Blvd | San Gabriel | 91776 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2821705 | 1674354 |  |  | 20 |  |  | true | 2019-10-11 | 2019-11-12 | 23 | 23 | 2019-10-10 | 2019-10-10 | 24 | 24 | 1 | 1 | 2019-10-11 |  | 2019-10-24 |  |  |  |  | 2020-02-11 | 87 | 87 | 2020-02-18 |  | 2020-04-02 | 2020-04-16 | 47 | 47 | 2020-04-16 | 2020-05-18 | 23 | 23 |  | 2020-07-06 | 34 | 34 | 2020-07-06 | 1 | 1 | 2020-09-01 | 2020-09-01 | 2020-09-01 | 2020-09-06 | 42 | 42 | 78 | 78 | 4 | 4 | 2020-06-25 | 2020-09-18 | 2020-10-08 | -7 |  | 15 | 15 | 74 | 74 | 2021-04-02 | 187 | 187 | 2021-04-30 | 21 | 21 | 2020-09-01 | 2020-09-01 | 2020-10-08 | 2021-04-30 | 166 | 166 | 187 | 187 | [18 empty] | 2021-05-25 |  |  |  |  | 2021-05-27 |  |  |  | 2021-07-16 | 35 | 35 | 2021-07-16 |  |  |  | 447 | 447 | 361 | 361 | 2021
439 | El Segundo, CA | 2000 E El Segundo Blvd | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2019-10-10 | 2020-10-23 | 266 | 266 | 2019-10-09 | 2019-10-09 | 267 | 267 | 1 | 1 |  |  | 2019-10-24
440 | Irvine Orange Tree Square Shopping Ctr | 5406 Walnut Ave | Irvine | 92604 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2816570 | 1653218 |  |  | 8 |  |  | true | 2019-10-10 | 2019-10-28 | 13 | 13 | 2019-10-10 | 2019-10-10 | 13 | 13 | 1 | 1 | 2019-10-10 | 2019-10-22 | 2019-10-22 | 9 | 9 | 1 | 1 | 2020-02-05 | 83 | 83 | 2020-02-06 |  | 2020-03-16 | 2020-03-19 | 31 | 31 | 2020-03-19 | 2020-03-25 | 5 | 5 | 2020-04-15 | 2020-04-27 | 24 | 24 | 2020-04-06 | -16 |  | 2020-04-29 |  | 2020-04-29 | 2020-06-09 | 3 | 3 | 54 | 54 | 29 | 29 | 2020-04-23 | 2020-05-26 | 2020-07-01 | -3 |  | 27 | 27 | 49 | 49 | 2020-09-08 | 109 | 109 | 2020-09-18 | 9 | 9 | 2020-04-29 | 2020-04-29 | 2020-07-01 | 2020-09-18 | 100 | 100 | 94 | 94 | 2020-10-02 |  | 2020-10-23 | 16 | 16 | 2020-08-04 | 2020-09-03 | [11 empty] | 2020-10-26 | 59 | 59 |  |  | 2020-10-27 |  |  |  | 2020-12-01 | 23 | 23 | 2020-12-01 |  |  |  | 290 | 290 | 208 | 208 | 2020
441 | Fullerton, CA - 205 E Orangethorpe Ave | 205 E Orangethorpe Ave | Fullerton | 92832 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | true | 2019-10-24 | 2020-02-07 | 75 | 75 | 2019-10-11 | 2019-10-11 | 84 | 84 | 1 | 1 | 2019-10-15 | 2019-10-30 | 2019-10-30 | 14 | 14 | 1 | 1
442 | Redlands Bank of America | 305 E State Street | Redlands | 92373 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 2783925 | 1633059 |  |  | 4 |  |  | NO | 2019-10-25 | 2019-11-13 | 14 | 14 | 2019-10-16 | 2019-10-16 | 21 | 21 | 1 | 1 | 2019-10-16 |  | 2019-10-30 |  |  |  |  | 2019-11-21 | 27 | 27 | 2019-11-22 |  | 2020-01-06 | 2020-02-21 | 64 | 64 | 2020-02-21 | 2020-02-28 | 6 | 6 | 2020-03-20 | 2020-03-10 | 8 | 8 | 2020-03-10 | 1 | 1 | 2020-03-20 | 2020-06-19 | 2020-03-20 | 2020-04-16 | 9 | 9 | 35 | 35 | 20 | 20 | 2020-02-26 | 2020-04-06 | 2020-04-21 | -10 |  | 12 | 12 | 40 | 40 | 2020-05-18 | 50 | 50 | 2020-06-02 | 11 | 11 | 2020-03-20 | 2020-03-20 | 2020-04-21 | 2020-06-02 | 52 | 52 | 50 | 50 | 2020-06-04 |  | 2020-06-22 | 13 | 13 |  | 2020-05-27 | [10 empty] | 2020-06-23 | 2020-06-29 |  |  | 5 | 5 | 2020-07-06 |  |  |  | 2020-10-01 | 63 | 63 | 2020-10-01 |  |  |  | 246 | 246 | 220 | 220 | 2020
443 | Costa Mesa, CA- 3333 Bristol St | 3333 Bristol St | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2019-10-17 | 2019-10-17 |  |  | 1 | 1
444 | Irvine Dupont Drive | 2626 Dupont Dr | Irvine | 92612 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO | 2019-10-28 |  |  |  | 2019-10-17 | 2019-10-17 |  |  | 1 | 1 |  |  | 2019-10-27
445 | Costa Mesa, CA- 2937 Bristol St | 2937 Bristol St | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2019-10-21 | 2019-10-23 | 3 | 3 | 2019-10-21 | 2019-10-21 | 3 | 3 | 1 | 1
446 | Costa Mesa 2930 Bristol St | 2930 Bristol St | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2019-10-22 |  |  |  | 2019-10-21 | 2019-10-21 |  |  | 1 | 1 |  |  | 2019-11-05
447 | Huntington Beach, CA- 16400 Pacific Coast Hwy | 16400 Pacific Coast Hwy | Huntington Beach | 92649 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2019-11-18 | 2019-12-18 | 23 | 23 | 2019-11-15 | 2019-11-15 | 24 | 24 | 1 | 1 |  |  | 2019-12-03
448 | Los Angeles Vons 2270 | 4030 S Centinela Ave | Los Angeles | 90066 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2019-11-26 | 2019-11-26 | 1 | 1 | 2019-11-14 | 2019-11-14 | 9 | 9 | 1 | 1 | 2019-11-15 | 2019-11-18 | 2019-11-26 | 3 | 3 | 7 | 7
449 | Carson Albertson 3859 | 200 E Sepulveda Blvd | Carson | 90745 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2019-11-26 | 2019-12-04 | 7 | 7 | 2019-11-14 | 2019-11-14 | 15 | 15 | 1 | 1 | 2019-11-15 | 2019-11-18 | 2020-01-09 | 3 | 3 | 38 | 38
450 | Hawthorne FedEx | 12600 S Prairie Ave | Hawthorne | 90250 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2801780 | 1645759 |  |  | 24 |  |  | NO | 2019-11-13 | 2019-12-18 | 26 | 26 | 2019-11-13 | 2019-11-13 | 26 | 26 | 1 | 1 | 2019-11-14 |  | 2019-12-03 | [7 empty] | 2020-01-06 | 2020-01-10 | 2020-02-10 | 2020-01-24 |  |  | 2020-01-24 | 2020-01-24 | 1 | 1 |  | 2020-02-03 | 7 | 7 | 2020-02-03 | 1 | 1 | 2021-02-03 |  | 2021-02-03 | 2021-04-13 | 253 | 253 | 307 | 307 | 49 | 49 | [9 empty] | 2020-08-27 | 146 | 146 | 2020-12-30 | 85 | 85 | [6 empty] | 146 | 146 | 2021-02-05 | 2021-02-23 | 2021-02-23 | 12 | 12 | 2020-09-07 | [12 empty] | 2021-03-05 | 122 | 122 |  |  | 2021-04-15 | 2021-06-14 | 42 | 42 | 2021-06-15 | 43 | 43 | 2021-06-15 |  |  |  | 401 | 401 |  |  | 2021
451 | Fontana Volvo TEC | 14400 Randall Ave | Fontana | 92335 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2809066 | 1662858 |  |  | 4 |  |  | true |  |  |  |  | 2019-11-18 | 2019-11-19 |  |  | 2 | 2 | 2019-11-19 |  | 2019-12-03 | [7 empty] | 2020-01-21 | 2020-01-22 | 2020-02-21 | 2020-02-21 |  |  | 2020-02-21 | 2020-02-28 | 6 | 6 | 2020-03-20 | 2020-03-12 | 10 | 10 | 2020-03-12 | 1 | 1 | 2020-03-25 | 2020-03-31 | [31 empty] | 2020-04-03 |  | 2020-04-17 | 11 | 11 |  |  | 2020-04-23 | [9 empty] | 2020-04-23 | 2020-04-30 |  |  | 6 | 6 | 2020-05-01 |  |  |  | 2020-06-09 | 27 | 27 | 2020-06-09 |  |  |  | 143 | 143 |  |  | 2020
452 | Chino NFI Volvo EV | 15750 Mountain Ave | Chino | 91708 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2803675 | 1654154 |  |  | 19 |  |  | NO | 2019-11-20 | 2019-12-02 | 9 | 9 | 2019-11-19 | 2019-11-20 | 9 | 9 | 2 | 2 | 2019-11-19 |  | 2019-12-10 |  |  |  |  | 2019-12-31 | 31 | 31 | 2020-01-09 |  | 2020-02-07 | 2020-03-02 | 42 | 42 | 2020-03-02 | 2020-03-02 | 1 | 1 | 2020-03-27 | 2020-03-27 | 20 | 20 | 2020-03-27 | 1 | 1 | 2020-03-30 | 2020-04-03 | 2020-03-30 | 2020-03-30 | 2 | 2 | 21 | 21 | 1 | 1 | 2020-03-26 | 2020-07-09 | 2020-08-03 | -2 |  | 18 | 18 | 91 | 91 | 2020-04-03 | 6 | 6 | 2020-04-16 | 10 | 10 | 2020-03-30 | 2020-03-30 | 2020-08-03 | 2020-08-03 | 89 | 89 | 6 | 6 | 2020-07-16 |  | 2020-07-31 | 12 | 12 | 2020-05-14 | [12 empty] | 2020-10-28 | 117 | 117 |  |  | 2020-11-17 |  |  |  | 2021-02-12 | 59 | 59 | 2021-02-12 |  |  |  | 312 | 312 | 282 | 282 | 2021
453 | VW Test Center | 201 Del Norte Blvd | Oxnard | 93030 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2019-11-08 | 2019-11-08 |  |  | 1 | 1 | 2019-11-12 |  | 2019-12-04
454 | Ojai Boku Superfoods | 987 W Ojai Ave | Ojai | 93023 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 2837182 | 1676586 |  |  | 5 |  |  | NO |  |  |  |  | 2019-11-11 | 2019-11-11 |  |  | 1 | 1 |  |  | 2019-12-04 |  |  |  |  | 2020-03-11 | 85 | 85 | 2020-03-11 | 2020-03-14 | 2020-03-30 | 2020-04-08 | 21 | 21 | 2020-04-08 | 2020-04-14 | 5 | 5 | 2020-05-05 | 2020-04-15 | 2 | 2 | 2020-04-15 | 1 | 1 | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-12 | 17 | 17 | 21 | 21 | 4 | 4 | 2020-04-29 | 2020-06-01 | 2021-02-08 | 11 | 11 | 173 | 173 | 195 | 195 | [6 empty] | 2020-05-07 |  | 2021-02-08 | [5 empty] | 2020-10-18 | [17 empty] | 2020-11-09 |  |  |  |  | 2021-02-18 |  |  |  | 2021-03-24 | 25 | 25 | 2021-03-24 |  |  |  | 345 | 345 | 261 | 261 | 2021
455 | Irvine FedEx | 7000 Barranca Parkway | Irvine | 92618 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2801603 | 1678352 |  |  | 28 |  |  | true | 2019-11-20 | 2019-12-12 | 17 | 17 | 2019-11-19 | 2019-11-20 | 17 | 17 | 2 | 2 | 2019-11-22 | 2019-12-04 | 2019-12-11 | 11 | 11 | 6 | 6 |  |  |  | 2020-01-06 | 2020-01-06 | 2020-02-10 | 2020-05-04 |  |  | 2020-05-04 | 2020-06-04 | 23 | 23 |  | 2020-06-15 | 8 | 8 | 2020-06-15 | 1 | 1 | 2020-06-30 | 2020-09-15 | 2020-06-30 | 2020-09-17 | 12 | 12 | 74 | 74 | 56 | 56 | 2020-06-12 | 2020-07-27 | 2020-09-23 | -2 |  | 42 | 42 | 72 | 72 | 2020-08-25 | 51 | 51 | 2020-09-01 | 6 | 6 | 2020-06-30 | 2020-06-30 | 2020-09-23 | 2020-09-23 | 60 | 60 | 51 | 51 | 2021-02-11 | 2021-02-26 | 2021-02-26 | 11 | 11 | 2020-09-01 | [12 empty] | 2021-04-02 | 146 | 146 |  |  | 2021-04-19 | 2021-05-15 | 20 | 20 | 2021-05-16 | 20 | 20 | 2021-05-16 |  |  |  | 376 | 376 |  |  | 2021
456 | Culver City Westfield | 6000U Sepulveda Blvd EV2 | Culver City | 90230 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2856776 | 1691224 |  |  | 20 |  |  | NO | 2020-04-20 | 2020-04-20 | 1 | 1 | 2019-11-26 | 2019-12-04 | 96 | 96 | 7 | 7 | 2019-12-06 |  | 2020-01-02 | [7 empty] | 2020-04-20 | 2020-04-29 | 2020-05-22 | 2020-06-05 |  |  | 2020-06-05 | 2020-07-17 | 30 | 30 | 2020-08-07 | 2020-08-13 | 20 | 20 | 2020-08-13 | 1 | 1 | 2020-08-13 | 2020-08-13 | 2020-08-13 | 2020-09-02 | 1 | 1 | 34 | 34 | 15 | 15 | 2020-07-21 | 2020-09-11 | 2020-12-28 | -18 |  | 73 | 73 | 110 | 110 | 2021-03-15 | 145 | 145 |  |  |  | 2020-08-13 | 2020-08-13 | 2020-12-28 |  |  |  | 145 | 145 | [17 empty] | 2021-06-07 | 2021-06-07 |  |  | 1 | 1 | 2021-06-08 |  |  |  | 2021-09-27 | 78 | 78 | 2021-09-27 |  |  |  | 464 | 464 |  |  | 2021
457 | Stanton Garden Grove Blvd | 7949 Garden Grove Blvd | Garden Grove | 92841 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2019-11-25 |  |  |  | 2019-11-22 | 2019-11-25 |  |  | 2 | 2 |  |  | 2019-12-16
458 | Eastvale, CA- 12471 Limonite | 12471 Limonite Ave | Eastvale | 91752 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2919376 | 1726843 |  |  | 16 |  |  | NO | 2019-12-02 | 2019-12-19 | 14 | 14 | 2019-12-02 | 2019-12-02 | 14 | 14 | 1 | 1 | 2019-12-02 |  | 2019-12-18 |  |  |  |  | 2020-06-19 | 141 | 141 | 2020-06-22 | 2020-06-24 | 2020-07-24 | 2020-07-24 | 25 | 25 | 2020-07-24 | 2020-11-20 | 84 | 84 | 2020-12-11 | 2020-12-16 | 17 | 17 | 2020-12-17 | 2 | 2 | 2021-03-01 | 2021-03-01 | 2021-03-01 |  | 50 | 50 | [5 empty] | 2021-02-03 | 2021-03-30 |  |  | 39 | 39 | [8 empty] | 2021-02-03 | [7 empty] | 2021-04-14 |  | 2021-04-20 | 5 | 5 | [13 empty] | 2021-05-12 |  |  |  |  | 2021-05-13 |  |  |  | 2021-06-15 | 23 | 23 | 2021-06-15 |  |  |  | 388 | 388 | 248 | 248 | 2021
459 | Seal Beach Center | 901 Pacific Coast Hwy | Seal Beach | 90740 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2019-12-04 | 2019-12-04 |  |  | 1 | 1 | 2019-12-04 |  | 2019-12-09
460 | Long Beach Circle Center West | 1801 Ximeno Ave | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-12-04 | 2019-12-04 |  |  | 1 | 1 | 2019-12-04 |  | 2020-01-07
461 | Signal Hill, CA- 2450 Cherry Ave | 2450 Cherry Ave | Signal Hill | 90755 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2019-12-17 | 2019-12-17 |  |  | 1 | 1 | 2019-12-20
462 | Moreno Valley Mall | 22500 Town Cir | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 2874650 | 1707289 | [5 empty] | true |  |  |  |  | 2019-12-18 | 2019-12-18 |  |  | 1 | 1 | 2019-12-20 |  | 2020-04-06 | [7 empty] | 2020-05-22 | 2020-05-27 | 2020-06-24 | 2020-06-16 |  |  | 2020-06-16 | 2020-06-18 | 3 | 3 | 2020-07-09 | 2020-06-29 | 8 | 8 | 2020-06-29 | 1 | 1 | 2020-07-17 | [37 empty] | 2021-08-11 | 2021-08-31
463 | Thousand Oaks, CA- 2072 E Avenida de los Arboles | 2072 E. Avenida De Los Arboles | Thousand Oaks | 91362 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | true | 2019-12-23 | 2020-01-14 | 16 | 16 | 2019-12-19 | 2019-12-20 | 17 | 17 | 2 | 2 | 2019-12-30 |  | 2020-01-14
464 | Inglewood Bank of America | 11525 Crenshaw Blvd | Inglewood | 90303 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2818396 | 1661851 |  |  | 5 |  |  | true | 2020-01-14 | 2020-01-29 | 11 | 11 | 2020-01-02 | 2020-01-02 | 19 | 19 | 1 | 1 | 2020-01-02 |  | 2020-01-14 |  |  |  |  | 2020-02-06 | 25 | 25 | 2020-02-10 | 2020-02-19 | 2020-03-19 | 2020-04-30 | 60 | 60 | 2020-04-30 | 2020-05-04 | 3 | 3 | 2020-05-25 | 2020-06-01 | 20 | 20 | 2020-06-01 | 1 | 1 | 2020-06-01 | 2020-06-19 | 2020-06-01 | 2020-11-20 | 1 | 1 | 141 | 141 | 122 | 122 | 2020-06-16 | 2020-09-01 | 2020-10-22 | 12 | 12 | 37 | 37 | 91 | 91 | 2021-01-12 | 155 | 155 | 2021-01-25 | 9 | 9 | 2020-06-01 | 2020-06-01 | 2020-11-20 | 2021-01-25 | 163 | 163 | 155 | 155 | [5 empty] | 2020-08-24 | [12 empty] | 2020-11-17 | 60 | 60 |  |  | 2021-01-11 |  |  |  | 2021-03-06 | 38 | 38 | 2021-03-06 |  |  |  | 295 | 295 | 271 | 271 | 2021
465 | Temecula, CA- 30515 Temecula Pkwy | 30515 Temecula Pkwy | Temecula | 92592 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 2909332 | 1770335 |  |  | 8 |  |  | true | 2020-02-04 | 2020-02-04 | 1 | 1 | 2020-01-21 | 2020-01-21 | 11 | 11 | 1 | 1 | 2020-01-09 | [6 empty] | 2020-06-21 | 107 | 107 | 2020-07-06 | 2020-07-07 | 2020-08-07 | 2020-08-05 | 32 | 32 | 2020-08-05 | 2020-09-09 | 25 | 25 | 2020-10-05 | 2020-09-21 | 9 | 9 | 2020-09-21 | 1 | 1 | 2020-11-10 | 2020-11-19 | 2020-11-10 | 2020-12-11 | 37 | 37 | 65 | 65 | 21 | 21 | 2020-11-06 | 2020-12-29 | 2021-01-19 | 35 | 35 | 14 | 14 | 47 | 47 | 2021-04-19 | 144 | 144 | 2021-05-27 | 29 | 29 | 2020-11-10 | 2020-11-10 | 2021-01-19 | 2021-05-27 | 136 | 136 | 144 | 144 | 2021-05-21 |  | 2021-05-26 | 4 | 4 | 2021-02-23 | 2021-04-30 | 2021-05-20 | [9 empty] | 2021-06-08 | 2021-06-10 | 77 | 77 | 3 | 3 | 2021-06-14 |  |  |  | 2021-07-08 | 18 | 18 | 2021-07-08 |  |  |  | 370 | 370 | 263 | 263 | 2021
466 | Mission Viejo Ralph's | 27730 Santa Margarita Pkwy | Mission Viejo | 92691 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2883480 | [6 empty] | true | 2020-02-07 | 2020-06-04 | 83 | 83 | 2020-01-21 | 2020-01-21 | 96 | 96 | 1 | 1 | 2020-01-23 |  | 2020-01-28 |  |  |  |  | 2020-06-02 | 94 | 94 | 2020-06-04 | 2020-06-04 | 2020-07-08
467 | Monterey Park Ralphs 715 | 330 N Atlantic Blvd | Monterey Park | 91754 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2830224 | 1676430 |  |  | 5 |  |  | true | 2020-02-04 |  |  |  | 2020-01-24 | 2020-01-24 |  |  | 1 | 1 |  |  | 2020-02-09 |  |  |  |  | 2020-02-25 | 22 | 22 | 2020-02-26 | 2020-02-27 | 2020-03-31 | 2020-04-10 | 34 | 34 | 2020-04-10 | 2020-04-14 | 3 | 3 | 2020-05-11 | 2020-05-11 | 20 | 20 | 2020-05-11 | 1 | 1 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-05-28 | 1 | 1 | 32 | 32 | 13 | 13 | 2020-05-07 | 2020-05-21 | 2020-07-29 | -3 |  | 48 | 48 | 58 | 58 | 2020-10-05 | 103 | 103 |  |  |  | 2020-05-11 | 2020-05-11 | 2020-07-29 |  |  |  | 103 | 103 | 2020-09-11 |  | 2020-09-17 | 5 | 5 | [13 empty] | 2020-11-12 |  |  |  |  | 2020-11-13 |  |  |  | 2021-01-07 | 36 | 36 | 2021-01-07 |  |  |  | 241 | 241 | 220 | 220 | 2021
468 | Simi Valley, CA - 2902 Tapo Canyon Road | 2902 Tapo Canyon Rd | Simi Valley | 93063 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | true | 2020-01-30 | 2020-02-19 | 14 | 14 | 2020-01-28 | 2020-01-28 | 16 | 16 | 1 | 1 |  |  | 2020-02-19
469 | Garden Grove Ralphs | 12051 Euclid St | Garden Grove | 92840 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2826019 | 1662907 |  |  | 5 |  |  | NO | 2020-02-13 | 2020-02-28 | 11 | 11 | 2020-01-29 | 2020-01-29 | 22 | 22 | 1 | 1 |  |  | 2020-02-24 |  |  |  |  | 2020-02-18 | 14 | 14 | 2020-02-20 |  | 2020-06-01 | 2020-06-11 | 82 | 82 | 2020-06-11 | 2020-06-25 | 11 | 11 | 2020-07-16 | 2020-07-13 | 12 | 12 | 2020-07-14 | 2 | 2 | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2020-08-31 | 22 | 22 | 47 | 47 | 15 | 15 |  | 2020-07-27 | 2020-08-05 |  |  | 8 | 8 |  |  | 2020-10-05 | 59 | 59 |  |  |  | 2020-07-27 | 2020-07-27 | 2020-08-31 |  |  |  | 60 | 60 | 2020-10-02 |  |  |  |  | 2020-09-09 | [12 empty] | 2020-11-18 | 50 | 50 |  |  | 2020-11-20 |  |  |  | 2020-12-23 | 22 | 22 | 2020-12-23 |  |  |  | 229 | 229 | 216 | 216 | 2020
470 | Santa Clarita Expansion | 23965 Newhall Ranch Rd. | Santa Clarita | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 2816470 |  |  |  | 32 |  |  | true |  |  |  |  | 2020-02-05 | [15 empty] | 2020-02-05 | 2020-02-05 | 2020-02-25
471 | Costa Mesa, CA- 1350 Gisler Ave | 1350 Gisler Ave | Costa Mesa | 92626 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2020-02-13 | 2020-03-27 | 31 | 31 | 2020-02-11 | 2020-02-11 | 33 | 33 | 1 | 1
472 | Placentia Chevron | 313 1/2 W. Orangethorpe Ave. | Placentia | 92870 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2832519 | 1698878 |  |  | 2 |  |  | NO |  |  |  |  | 2020-02-18 | 2020-02-18 |  |  | 1 | 1 |  | 2020-02-26 | 2020-02-28 | 7 | 7 | 3 | 3 |  |  |  | 2020-03-02 | 2020-03-03 | 2020-04-03 | 2020-04-01 |  |  | 2020-04-01 | 2020-05-20 | 36 | 36 |  | 2020-06-10 | 15 | 15 | 2020-06-10 | 1 | 1 | 2020-07-06 | 2020-07-14 | 2020-07-06 | 2020-07-07 | 18 | 18 | 33 | 33 | 2 | 2 | 2020-07-30 | 2020-09-30 | 2020-10-15 | 36 | 36 | 12 | 12 | 55 | 55 | 2020-09-16 | 69 | 69 | 2020-09-21 | 4 | 4 | 2020-07-06 | 2020-07-06 | 2020-10-15 | 2020-10-15 | 73 | 73 | 69 | 69 | [5 empty] | 2020-09-14 | 2020-10-16 |  |  |  |  | 2020-10-21 | [6 empty] | 2020-12-14 | 63 | 63 |  |  | 2020-12-21 | [6 empty] | 2021-01-24 |  |  |  | 235 | 235 |  |  | 2021
473 | Santa Monica - Lot 27 | 1334 5th Street | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2851721 | 1692725 |  |  | 8 |  |  | NO | 2020-02-20 | 2020-03-04 | 10 | 10 | 2020-02-19 | 2020-02-20 | 10 | 10 | 2 | 2 | 2020-02-21 |  | 2020-03-02 | [7 empty] | 2020-04-07 | 2020-04-14 | 2020-05-21 | 2020-05-29 |  |  | 2020-05-29 | 2020-11-02 | 110 | 110 | 2020-11-23 | 2020-12-15 | 29 | 29 | 2020-12-15 | 1 | 1 | 2021-05-10 | 2021-07-29 | 2021-05-10 | 2021-05-13 | 101 | 101 | 132 | 132 | 4 | 4 | 2021-05-20 | 2021-06-16 | 2021-08-26 | 109 | 109 | 51 | 51 | 69 | 69 | 2021-08-06 | 163 | 163 | 2021-10-12 | 47 | 47 | 2021-05-10 | 2021-05-10 | 2021-08-26 | 2021-10-12 | 109 | 109 | 163 | 163 | 2022-02-28 | [6 empty] | 2020-05-20 | [9 empty] | 2022-03-08 | 2022-03-17 |  |  | 8 | 8 | 2022-03-24 | [6 empty] | 2022-06-16 |  |  |  | 587 | 587 |  |  | 2022
474 | Manhattan Beach Manhattan Village | 2610 N Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-03-03 | 2020-03-06 | 4 | 4 | 2020-03-02 | 2020-03-03 | 4 | 4 | 2 | 2
475 | Malibu | 30811 Pacific Coast Highway | Malibu Chevron | 90265 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | true |  |  |  |  | 2020-03-04 | 2020-03-04 |  |  | 1 | 1 | 2020-03-05
476 | Inyokern, CA- 6526 Locust Ave (Expansion) | 6526 Locust Ave | Inyokern | 93527 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 2924104 | 1734437 |  |  | 12 |  |  | NO | 2020-03-06 | 2020-03-17 | 8 | 8 | 2020-03-05 | 2020-03-05 | 9 | 9 | 1 | 1 | 2021-06-29 |  | 2020-03-23 |  |  |  |  | 2020-07-27 | 101 | 101 | 2020-07-29 | 2020-08-04 | 2020-09-02 | 2020-09-01 | 27 | 27 | 2020-09-01 | 2020-10-01 | 22 | 22 | 2020-10-26 | 2020-11-05 | 26 | 26 | 2020-11-05 | 1 | 1 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2021-02-03 | 5 | 5 | 84 | 84 | 55 | 55 | 2020-10-27 | 2020-11-23 | 2021-01-27 | -8 |  | 43 | 43 | 61 | 61 | 2021-05-10 | 126 | 126 | 2021-06-12 | 24 | 24 | 2020-11-12 | 2020-11-12 | 2021-02-03 | 2021-06-12 | 145 | 145 | 126 | 126 | [5 empty] | 2021-05-24 | 2021-06-16 | 2021-07-01 | [9 empty] | 2021-06-16 | 2021-07-13 | 35 | 35 | 19 | 19 | 2021-07-15 |  |  |  | 2021-08-13 | 22 | 22 | 2021-08-13 |  |  |  | 365 | 365 | 265 | 265 | 2021
477 | Santa Monica | 1944 Pico Blvd | Santa Monica | 90405 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2020-03-09 | 2020-03-09 |  |  | 1 | 1
478 | Lake Arrowhead, CA- 28200 CA-189 (Village) | 28202 CA-189 | Lake Arrowhead | 92352 | San Bernardino County | 9. Complete | 40 - Arrowhead | Rurals | SBRO |  |  | 2968912 | 1777682 |  |  | 8 |  |  | true | 2020-03-09 | 2020-03-16 | 6 | 6 | 2020-03-09 | 2020-03-09 | 6 | 6 | 1 | 1 |  |  | 2020-04-06 | [7 empty] | 2020-10-14 | 2020-10-21 | 2020-11-17 | 2020-11-19 |  |  | 2020-11-19 | 2020-11-20 | 2 | 2 | 2020-12-11 | 2020-12-24 | 23 | 23 | 2020-12-24 | 1 | 1 | 2020-12-28 | 2021-01-06 | 2020-12-28 | 2021-01-28 | 2 | 2 | 45 | 45 | 22 | 22 |  | 2021-01-20 | 2021-06-10 |  |  | 100 | 100 | [8 empty] | 2020-12-28 |  | 2021-06-10 | [5 empty] | 2021-08-11 |  | 2021-08-27 | 13 | 13 | 2021-07-01 | 2021-08-03 | [11 empty] | 2021-09-10 | 50 | 50 |  |  | 2021-09-29 |  |  |  | 2021-11-10 | 31 | 31 | 2021-11-10 |  |  |  | 425 | 425 |  |  | 2021
479 | Ontario DHE | 1351 S Campus Ave | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2838522 | 1677971 |  |  | 2 |  |  | NO | 2020-03-13 | 2020-03-25 | 9 | 9 | 2020-01-21 | 2020-01-22 | 45 | 45 | 2 | 2 |  |  | 2020-02-21 | [7 empty] | 2020-03-16 |  | 2020-04-17 | 2020-04-15 |  |  | 2020-04-15 | 2020-04-16 | 2 | 2 | 2020-05-07 | 2020-05-04 | 13 | 13 | 2020-05-04 | 1 | 1 | 2020-05-21 | 2020-05-21 | 2020-05-21 |  | 14 | 14 |  |  |  |  | 2020-06-16 | 2020-06-17 | 2020-07-06 | 31 | 31 | 13 | 13 | 14 | 14 | 2020-06-11 | 28 | 28 | 2020-06-24 | 10 | 10 | 2020-05-21 | 2020-05-21 |  |  |  |  | 28 | 28 | [5 empty] | 2020-05-14 | 2020-06-01 | 2020-06-30 | [10 empty] | 2020-12-08 | 143 | 143 |  |  | 2020-11-16 |  |  |  | 2020-12-11 | 18 | 18 | 2020-12-11 |  |  |  | 227 | 227 |  |  | 2020
480 | Culvery City Test Lab | 4333 Sepulveda Blvd | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-03-26 | 2020-03-27 | 2 | 2 | 2020-03-16 | 2020-03-16 | 10 | 10 | 1 | 1 | 2020-03-18 | 2020-03-26 |  | 9 | 9
481 | Long Beach Coffee Bean | 5865 E Spring Street | Long Beach | 90808 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2905950 | 1719993 |  |  | 4 |  |  | NO | 2020-03-26 |  |  |  | 2020-03-17 | 2020-03-17 |  |  | 1 | 1 | 2020-03-23 | 2020-03-26 | 2020-04-30 | 8 | 8 | 26 | 26 |  |  |  | 2020-06-30 |  | 2020-07-30 | 2020-07-21 |  |  | 2020-07-21 | 2020-07-21 | 1 | 1 |  | 2020-07-30 | 8 | 8 | 2020-07-30 | 1 | 1 | 2020-08-10 | 2020-08-10 | 2020-08-10 | 2020-08-11 | 8 | 8 | 16 | 16 | 2 | 2 | 2020-08-07 | 2020-09-13 | 2020-09-30 | 7 | 7 | 13 | 13 | 38 | 38 | 2020-10-26 | 62 | 62 | 2020-11-04 | 8 | 8 | 2020-08-10 | 2020-08-10 | 2020-09-30 | 2020-11-04 | 62 | 62 | 62 | 62 | 2021-02-04 | 2021-02-25 | 2021-02-25 | 15 | 15 | 2020-10-22 | [12 empty] | 2021-03-01 | 86 | 86 |  |  | 2021-03-02 | 2021-03-30 | 21 | 21 | 2021-03-31 | 22 | 22 | 2021-03-31 |  |  |  | 262 | 262 |  |  | 2021
482 | Redondo Beach Bank of America | 222 N Catalina Ave | Redondo Beach | 90277 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2020-03-20 |  |  |  | 2020-03-19 | 2020-03-19 |  |  | 1 | 1 | 2020-03-20 |  | 2020-03-26
483 | West Covina, CA - 112 Plaza Dr (Plaza West Covina) | 112 Plaza Dr | West Covina | 97190 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3096340 | 1867190 | [5 empty] | true | 2020-03-25 | 2020-04-17 | 18 | 18 | 2020-03-24 | 2020-03-24 | 19 | 19 | 1 | 1 |  |  | 2021-02-24 |  |  |  |  | 2021-05-19 | 292 | 292 | 2021-05-21 | 2021-05-27 | 2021-06-22 | 2021-06-24 | 26 | 26 | 2021-06-24
484 | Garden Grove, CA - 13861 Brookhurst St | 13861 Brookhurst St | Garden Grove | 92843 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2020-03-20 | 2020-04-06 | 12 | 12 | 2020-03-19 | 2020-03-19 | 13 | 13 | 1 | 1 |  |  | 2020-03-26
485 | Irvine | 7955 Irvine Center Dr | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | true | 2020-03-25 |  |  |  | 2020-03-23 | 2020-03-24 |  |  | 2 | 2 | 2020-03-25
486 | Montebello, CA - 801-1000 Via San Clemente | 801-1000 Via San Clemente | Montebello | 90640 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona | [9 empty] | true | 2020-03-25 | 2020-04-17 | 18 | 18 | 2020-03-24 | 2020-03-25 | 18 | 18 | 2 | 2
487 | Palm Desert Target | 72547 1/2 Highway 111 | Palm Desert | 92260 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 2859545 | 1694237 |  |  | 8 |  |  | true | 2020-03-30 | 2020-04-07 | 7 | 7 | 2020-03-27 | 2020-03-27 | 8 | 8 | 1 | 1 | 2020-03-30 |  | 2020-04-09 | [7 empty] | 2020-04-27 | 2020-04-30 | 2020-05-29 | 2020-05-22 |  |  | 2020-05-22 | 2020-06-16 | 17 | 17 | 2020-07-07 | 2020-07-08 | 16 | 16 | 2020-07-09 | 2 | 2 | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-27 | 12 | 12 | 29 | 29 | 3 | 3 | 2020-07-09 | 2020-07-24 | 2020-10-14 | 2 | 2 | 58 | 58 | 69 | 69 | [6 empty] | 2020-07-23 |  | 2020-10-14 | [5 empty] | 2021-01-08 |  | 2021-01-08 | 1 | 1 | [13 empty] | 2020-10-12 |  |  |  |  | 2020-10-21 |  |  |  | 2021-01-15 | 58 | 58 | 2021-01-15 |  |  |  | 203 | 203 |  |  | 2021
488 | Newport Beach, CA - 900 Newport Center Dr | 900 Newport Center Drive | Newport Beach | 92660 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true | 2020-03-23 | 2020-04-17 | 20 | 20 | 2020-03-23 | 2020-03-23 | 20 | 20 | 1 | 1
489 | Fullerton FedEx | 2500 Kimberly Ave | Fullerton | 92831 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2870994 | 1713711 |  |  | 11 |  |  | YES | 2020-04-21 | 2020-04-29 | 7 | 7 | 2020-04-07 | 2020-04-07 | 17 | 17 | 1 | 1 | 2020-04-09 | 2020-04-14 | 2020-04-21 | 6 | 6 | 6 | 6 |  |  |  | 2020-05-20 | 2020-05-21 | 2020-06-22 | 2020-06-24 |  |  | 2020-06-24 | 2020-06-30 | 5 | 5 |  | 2020-08-04 | 25 | 25 | 2020-08-04 | 1 | 1 | 2020-08-27 | 2020-09-15 | 2020-08-27 | 2020-09-17 | 18 | 18 | 56 | 56 | 15 | 15 | 2020-08-14 | 2020-10-09 | 2020-10-29 | 9 | 9 | 15 | 15 | 54 | 54 | [6 empty] | 2020-08-27 |  | 2020-10-29 | [5 empty] | 2020-11-24 | 2021-01-22 | 2021-01-22 | 39 | 39 | 2020-09-01 | 2020-11-09 | [11 empty] | 2021-01-27 | 100 | 100 |  |  | 2021-02-05 | 2021-03-14 | 25 | 25 | 2021-03-14 | 25 | 25 | 2021-03-14 |  |  |  | 234 | 234 |  |  | 2021
490 | West Hollywood, CA - 8550 Santa Monica Blvd | 8550 Santa Monica Blvd. | West Hollywood | 90069 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-04-13 | 2020-04-20 | 6 | 6 | 2020-04-13 | 2020-04-13 | 6 | 6 | 1 | 1 | 2020-04-15 |  | 2020-04-21
491 | Essex Sahara Oasis | 31251 Goffs Road EV1 | Essex Fenner | 92332 | San Bernardino County | 11. Cancelled | 84 - 29 Palms | Rurals | SBRO |  |  | 2861020 | 1713945 |  |  | 4 |  |  | true | 2020-04-28 | 2020-05-06 | 7 | 7 | 2020-04-02 | 2020-04-16 | 15 | 15 | 11 | 11 | 2020-04-17 |  | 2020-04-27 |  |  |  |  | 2020-04-02 | 1 | 1 | 2020-04-29 | 2020-04-30 | 2020-06-02 | 2020-07-14 | 72 | 72 | 2020-07-16 | 2020-07-16 | 1 | 1 |  | 2021-02-08 | 141 | 141 | 2021-02-08 | 1 | 1 | 2021-02-18 | 2021-05-13 | 2021-02-18 | 2021-02-22 | 8 | 8 | 150 | 150 | 3 | 3 | 2020-12-10 | 2020-12-14 | 2021-04-14 | -40 |  | 84 | 84 | 86 | 86 | 2021-02-09 | 2 | 2 | 2021-06-03 | 81 | 81 | 2020-12-14 | 2020-12-14 | 2021-04-14 | 2021-06-03 | 119 | 119 | 2 | 2 | 2020-11-23 | 2020-12-11 | 2020-12-11 | 13 | 13 | [13 empty] | 2021-04-08 |  |  |  |  | 2021-08-18 |  |  |  | 2022-04-07 | 160 | 160 | 2022-04-07 |  |  |  | 507 | 507 | 507 | 507 | 2022
492 | Long Beach, CA- 1650 Ximeno Ave | 1650 Ximeno Ave | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2924150 | 1748420 | [5 empty] | NO | 2020-04-24 |  |  |  | 2020-03-27 | 2020-04-15 |  |  | 14 | 14 | [7 empty] | 2020-07-27 | 85 | 85 | 2020-07-29 |  | 2020-08-02 | 2020-09-09 | 32 | 32 | 2020-09-09 | 2020-09-29 | 15 | 15 | 2020-10-20
493 | Long Beach, CA - 4571 E Los Coyotes | 4571 E Los Coyotes Diagnoal | Long Beach | 90815 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2020-04-07 |  |  |  | 2020-03-30 | 2020-04-07 |  |  | 7 | 7
494 | Diamond Bar Target Phase 2 | 747 Grand Avenue | Diamond Bar | 91765 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 2878070 | 1729384 |  |  | 5 |  |  | true | 2020-06-25 |  |  |  | 2020-04-15 | 2020-04-15 |  |  | 1 | 1 |  |  | 2020-04-29 | [7 empty] | 2020-05-29 | 2020-06-01 | 2020-07-10 | [8 empty] | 2020-07-30 |  |  | 2020-07-30 | 1 | 1 | 2020-07-30 | 2020-07-30 | [49 empty] | 2020-07-30 |  |  |  |  | 2020-07-31 |  |  |  | 2020-08-29 | 21 | 21 | 2020-08-29 |  |  |  | 96 | 96 |  |  | 2020
495 | Montebello Plaza Phase 2 | 2401 W Via Campo | Montebello | 90640 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona |  |  | 2875060 | 1714674 |  |  | 4 |  |  | true | 2020-06-25 |  |  |  | 2020-04-15 | 2020-04-15 |  |  | 1 | 1 |  |  | 2020-04-28 |  |  |  |  | 2020-05-20 | 26 | 26 | 2020-05-26 | 2020-05-27 | 2020-06-24 | 2020-06-25 | 26 | 26 | 2020-06-25 | 2020-06-25 | 1 | 1 | 2020-07-17 | [6 empty] | 2020-08-05 | 2020-08-05 | [54 empty] | 2020-08-06 |  |  |  | 2020-10-04 | 41 | 41 | 2020-10-04 |  |  |  | 120 | 120 | 95 | 95 | 2020
496 | Torrance Country Hills Phase 2 | 2965 Rolling Hills Rd | Torrance | 90505 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2875284 | 1722658 |  |  | 4 |  |  | NO | 2020-06-25 | 2020-07-01 | 5 | 5 | 2020-04-15 | 2020-04-15 | 55 | 55 | 1 | 1 |  |  | 2020-04-29 |  |  |  |  | 2020-05-20 | 26 | 26 | 2020-05-26 | 2020-05-27 | 2020-07-10 | 2020-07-12 | 36 | 36 | 2020-07-13 |  |  |  |  | 2020-07-12 |  |  | 2020-07-13 | 1 | 1 | 2020-08-11 | 2020-08-11 | [54 empty] | 2020-08-12 | [6 empty] | 2020-10-10 |  |  |  | 125 | 125 | 100 | 100 | 2020
497 | Gardena Target Phase 2 | 2169 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2874731 | 1716303 |  |  | 4 |  |  | true |  |  |  |  | 2020-04-15 | 2020-04-15 |  |  | 1 | 1 |  |  | 2020-04-28 |  |  |  |  | 2020-05-20 | 26 | 26 | 2020-05-22 | 2020-05-27 | 2020-06-24 | 2020-06-30 | 29 | 29 | 2020-06-30 | [10 empty] | 2020-08-13 | 2020-09-10 | [54 empty] | 2020-11-06 |  |  |  | 2021-01-10 | 41 | 41 | 2021-01-10 |  |  |  | 185 | 185 | 160 | 160 | 2021
498 | La Mirada Theather Phase 2 | 15210 La Mirada Blvd | La Mirada | 90638 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2877436 | 1715553 |  |  | 4 |  |  | true | 2020-06-25 | 2020-06-26 | 2 | 2 | 2020-04-15 | 2020-04-15 | 52 | 52 | 1 | 1 |  |  | 2020-04-28 | [7 empty] | 2020-05-28 | 2020-05-29 | 2020-07-10 | 2020-06-29 |  |  | 2020-06-30 |  |  |  |  | 2020-06-29 |  |  | 2020-06-30 | 2 | 2 | 2020-07-24 | 2020-11-23 | [36 empty] | 2020-11-18 | [17 empty] | 2021-01-05 |  |  |  | 2021-01-28 | 17 | 17 | 2021-01-28 |  |  |  | 198 | 198 |  |  | 2021
499 | Rancho Santa Margarita Target Phase 2 | 30602 Santa Margarita Pkwy | Rancho Santa Margarita | 92688 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2877502 | 1759845 |  |  | 4 |  |  | NO | 2020-06-25 |  |  |  | 2020-04-15 | 2020-04-15 |  |  | 1 | 1 |  |  | 2020-04-28 | [7 empty] | 2020-05-28 | 2020-05-29 | 2020-07-02 | 2020-06-26 |  |  | 2020-06-29 | 2020-09-16 | 56 | 56 | 2020-10-07 | 2020-10-21 | 26 | 26 | 2020-10-21 | 1 | 1 | 2020-10-28 | 2020-11-09 | [17 empty] | 2020-10-22 | 2 | 2 | 2020-10-23 | 2 | 2 | [6 empty] | 2 | 2 | [23 empty] | 2020-11-12 |  |  |  | 2020-12-04 | 15 | 15 | 2020-12-04 |  |  |  | 162 | 162 |  |  | 2020
500 | Barstow | 2845 Lenwood Rd | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 2989667 | 1811811 |  |  | 12 |  |  | YES | 2020-10-19 | 2021-01-21 | 63 | 63 | 2020-05-01 | 2020-05-01 | 181 | 181 | 1 | 1 | 2020-05-04 |  | 2021-02-17 | [7 empty] | 2020-11-20 | 2020-11-25 | 2020-02-25 |  |  |  |  | 2021-03-22 |  |  |  | 2021-05-20 | 44 | 44 | 2021-05-20 | 1 | 1 | 2021-05-20 | 2021-05-20 | 2021-05-20 | 2021-08-05 | 1 | 1 | 97 | 97 | 54 | 54 | 2021-05-04 | 2021-05-06 | 2021-05-18 | -13 |  | 9 | 9 | 11 | 11 | 2021-05-24 | 3 | 3 | 2021-07-01 | 28 | 28 | 2021-05-06 | 2021-05-06 | 2021-08-05 | 2021-08-05 | 64 | 64 | 3 | 3 | 2021-07-16 | 2021-08-04 | 2021-08-04 | 14 | 14 | 2021-05-11 | 2021-07-09 | [10 empty] | 2021-08-16 | 2021-09-10 | 86 | 86 | 19 | 19 | 2021-10-28 | 2021-11-29 | 20 | 20 | 2021-12-03 | 24 | 24 | 2021-12-03 |  |  |  | 400 | 400 |  |  | 2021
501 | Inglewood | 730 E La Palma Dr. | Inglewood | 90301 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2020-05-15 | 2020-05-21 | 5 | 5 | 2020-05-06 | 2020-05-07 | 11 | 11 | 2 | 2 |  |  | 2020-05-14
502 | Corona, CA- 450 Hidden Valley Pkwy (Plaza) | 450 Hidden Valley Pkwy | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | true | 2020-05-08 | 2020-07-17 | 49 | 49 | 2020-05-07 | 2020-05-07 | 50 | 50 | 1 | 1 | 2020-05-08
503 | El Segundo Plaza | 2004 Park Place | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2020-06-05 | 2020-06-30 | 18 | 18 | 2020-05-19 | 2020-05-21 | 28 | 28 | 3 | 3 | 2020-05-21 |  | 2020-06-02
504 | La Mirada TEC | 14790 Firestone Blvd. | La Mirada | 91708 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 2884289 | 1728106 |  |  | 7 |  |  | NO | 2020-05-22 | 2020-06-04 | 9 | 9 | 2020-05-22 | 2020-05-22 | 9 | 9 | 1 | 1 | 2020-05-26 |  | 2020-06-04 |  |  |  |  | 2020-05-21 | -2 |  | 2020-06-04 | 2020-06-05 | 2020-07-09 | 2020-07-06 | 31 | 31 | 2020-07-06 | 2020-07-08 | 3 | 3 | 2020-07-30 | 2020-08-07 | 23 | 23 | 2020-08-07 | 1 | 1 | 2020-08-07 | 2020-08-20 | 2020-08-07 | 2020-08-21 | 1 | 1 | 33 | 33 | 11 | 11 | 2020-07-24 | 2020-08-17 | 2021-02-10 | -11 |  | 121 | 121 | 137 | 137 | 2020-10-26 | 56 | 56 | 2020-11-02 | 6 | 6 | 2020-08-07 | 2020-08-07 | 2021-02-10 | 2021-02-10 | 127 | 127 | 56 | 56 | 2020-09-10 | [17 empty] | 2020-10-19 |  |  |  |  | 2020-10-26 |  |  |  | 2020-12-08 | 29 | 29 | 2020-12-08 |  |  |  | 137 | 137 | 138 | 138 | 2020
505 | Baldwin Park | 14477 Merced Ave | Baldwin Park | 91706 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 2888149 | 1727164 |  |  | 2 |  |  | YES | 2020-06-11 | 2020-06-24 | 10 | 10 | 2020-05-26 | 2020-05-26 | 22 | 22 | 1 | 1 | 2020-05-28 | 2020-06-03 | 2020-06-08 | 7 | 7 | 4 | 4 |  |  |  | 2020-06-09 |  | 2020-07-16 | 2020-08-19 |  |  | 2020-08-19 | 2020-08-21 | 3 | 3 |  | 2020-09-18 | 20 | 20 | 2020-09-18 | 1 | 1 | 2020-09-18 | 2020-10-02 | 2020-09-18 | 2020-09-29 | 1 | 1 | 27 | 27 | 8 | 8 | 2020-09-15 | 2020-09-29 | 2020-10-15 | -4 |  | 13 | 13 | 23 | 23 | 2020-11-18 | 43 | 43 |  |  |  | 2020-09-18 | 2020-09-18 | 2020-10-15 |  |  |  | 43 | 43 | 2021-04-08 |  |  |  |  | 2020-11-12 | [12 empty] | 2021-07-27 | 176 | 176 |  |  | 2021-08-17 | 2021-09-22 | 26 | 26 | 2021-09-23 | 27 | 27 | 2021-09-23 |  |  |  | 336 | 336 |  |  | 2021
506 | Chino Hills, CA- 4615 Chino Hills Pkwy (The Commons at Chino) | 4615 Chino Hills Pkwy | Chino Hills | 91709 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 3090810 | 1867321 | [5 empty] | true | 2020-05-19 | 2020-05-29 | 8 | 8 | 2020-05-15 | 2020-05-15 | 10 | 10 | 1 | 1 | 2020-05-18 |  | 2020-06-23 |  |  |  |  | 2021-05-10 | 247 | 247 | 2021-05-13 | 2021-05-19 | 2021-06-17 | 2021-06-23 | 32 | 32 | 2021-06-23 | 2021-06-29 | 5 | 5 | 2021-07-22 | 2021-07-23 | 18 | 18 | 2021-07-26 | 2 | 2 | 2021-08-25 | 2021-09-20 | 2021-08-25 | 2021-08-26 | 24 | 24 | 42 | 42 | 2 | 2 | 2021-08-20 | 2021-08-23 |  | 21 | 21 | [10 empty] | 2021-08-23
507 | Santa Ana Walmart Phase 2 | 3600 W McFadden Avenue | Santa Ana | 92704 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2914627 | 1725331 |  |  | 4 |  |  | NO | 2020-06-19 |  |  |  | 2020-05-29 | 2020-05-29 |  |  | 1 | 1 |  |  | 2020-06-04 | [7 empty] | 2020-07-13 |  | 2020-08-11 | [8 empty] | 2020-08-11 |  |  | 2020-08-11 | 1 | 1 | 2020-09-03 | 2020-09-03 | [49 empty] | 2021-02-17 |  |  |  |  | 2021-02-19 |  |  |  | 2021-04-10 | 36 | 36 | 2021-04-10 |  |  |  | 217 | 217 |  |  | 2021
508 | Signal Hill FedEx | 2451 Palm Dr | Signal Hills | 90755 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 2892228 | 1747217 |  |  | 9 |  |  | true | 2020-06-04 | 2020-06-29 | 18 | 18 | 2020-06-02 | 2020-06-02 | 20 | 20 | 1 | 1 | [10 empty] | 2020-06-15 | 2020-06-17 | 2020-07-20 | 2020-07-22 |  |  | 2020-07-22 | 2020-08-11 | 15 | 15 |  | 2020-09-11 | 23 | 23 | 2020-09-11 | 1 | 1 | 2020-09-11 | 2020-10-06 | 2020-09-11 | 2020-09-17 | 1 | 1 | 27 | 27 | 5 | 5 | 2020-09-02 | 2020-09-22 | 2020-10-19 | -7 |  | 20 | 20 | 33 | 33 | [6 empty] | 2020-09-11 |  | 2020-10-19 | [5 empty] | 2020-10-06 | 2020-10-20 | 2020-10-20 | 11 | 11 | 2020-09-01 | 2020-09-17 | 2020-09-29 |  |  |  | 2020-09-22 |  |  | 2020-10-06 | 6 | 6 | 2020-10-20 | 2020-10-30 | 43 | 43 | 9 | 9 | 2020-11-05 | 2021-01-10 | 42 | 42 | 2021-01-10 | 42 | 42 | 2021-01-10 |  |  |  | 152 | 152 |  |  | 2021
509 | Rancho Cucamonga, CA- Foothill Blvd | 12750 Foothill Blvd | Rancho Cucamonga | 91739 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 2986594 | 1791044 |  |  | 8 |  |  | true | 2020-06-03 | 2020-06-19 | 13 | 13 | 2020-06-03 | 2020-06-03 | 13 | 13 | 1 | 1 | 2020-06-03 |  | 2020-06-23 |  |  |  |  | 2020-11-06 | 111 | 111 | 2020-11-13 | 2020-11-19 | 2020-12-18 | 2020-12-21 | 29 | 29 | 2020-12-22 | 2020-12-23 | 2 | 2 | 2021-02-22 | 2021-02-22 | 40 | 40 | 2021-02-22 | 1 | 1 | 2021-03-11 | 2021-04-13 | 2021-03-11 | 2021-03-12 | 14 | 14 | 54 | 54 | 2 | 2 | 2021-03-05 | 2021-03-08 | 2021-05-05 | 10 | 10 | 43 | 43 | 44 | 44 | [6 empty] | 2021-03-08 |  | 2021-05-05 | [5 empty] | 2021-07-13 |  |  |  |  | 2021-05-24 | 2021-06-17 | [10 empty] | 2021-06-23 | 2021-08-10 | 55 | 55 | 34 | 34 | 2021-08-20 |  |  |  | 2021-09-21 | 22 | 22 | 2021-09-21 |  |  |  | 328 | 328 | 218 | 218 | 2021
510 | Diamond Bar, CA- 2785 S Diamond Bar Blvd (Plaza) | 2785-EV S Diamond Bar Blvd | Diamond Bar | 91765 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 2981860 | 1788786 |  |  | 24 |  |  | YES | 2020-06-08 | 2020-06-24 | 13 | 13 | 2020-06-08 | 2020-06-08 | 13 | 13 | 1 | 1 | 2020-06-09 |  | 2020-06-18 |  |  |  |  | 2020-11-04 | 106 | 106 | 2020-11-05 | 2020-11-12 | 2020-12-04 | 2020-12-15 | 27 | 27 | 2020-12-15 | 2021-01-06 | 15 | 15 | 2021-01-28 | 2021-02-01 | 18 | 18 | 2021-02-01 | 1 | 1 | 2021-03-17 | 2021-03-17 | 2021-03-17 | 2021-03-19 | 32 | 32 | 51 | 51 | 3 | 3 |  | 2021-03-03 | 2021-06-14 |  |  | 73 | 73 | [8 empty] | 2021-03-03 |  | 2021-06-14 | [10 empty] | 2021-07-23 | [17 empty] | 2021-10-19 |  |  |  | 2021-12-01 | 29 | 29 | 2021-12-01 |  |  |  | 373 | 373 | 268 | 268 | 2021
511 | Whole Foods Huntington Beach (HBC) | 10081 Adams Avenue | Huntington Beach | 92646 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2969200 | 1777642 |  |  |  | NO |  | NO | 2020-06-26 |  |  |  | 2020-06-15 | 2020-06-15 |  |  | 1 | 1 | 2020-06-16 | [9 empty] | 2020-10-14 |  | 2020-11-18 | 2020-11-17 |  |  | 2020-11-17 | 2020-11-23 | 5 | 5 |  | 2020-12-03 | 7 | 7 | 2020-12-16 | 10 | 10 | 2020-12-03 | 2021-04-02 | 2020-12-03 | 2021-03-10 | 1 | 1 | 72 | 72 | 66 | 66 | 2020-11-24 | 2021-02-12 |  | -6 | [11 empty] | 2020-12-03
512 | Orange, CA-1500 E Village Way | 1500 E Village Way | Orange | 92865 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES | 2020-06-17 |  |  |  | 2020-06-17 | 2020-06-17 |  |  | 1 | 1
513 | Laguna Beach | 104 N Coast Hwy | Laguna Beach | 92651 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 2911640 | 1776542 | [5 empty] | NO | 2020-07-01 | 2020-07-17 | 12 | 12 | 2020-06-22 | 2020-06-22 | 19 | 19 | 1 | 1 | 2020-06-23 | 2020-06-29 | 2020-07-07 | 6 | 6 | 6 | 6 |  |  |  | 2020-07-08 |  | 2020-08-11 | 2020-11-16 |  |  | 2020-11-16 | 2020-11-30 | 9 | 9 |  | 2020-12-03 | 4 | 4 | 2020-12-03 | 1 | 1 | 2020-12-29 |  | 2020-12-29 |  | 18 | 18 |  |  |  |  | 2020-12-10 | 2021-01-26 |  | 6 | 6 |  |  |  |  | 2021-08-05 | 170 | 170 | 2021-08-19 | 11 | 11 | 2020-12-29 | 2020-12-29 |  |  |  |  | 170 | 170
514 | Pomona Shell Station | 1518 Garey Ave | Pomona | 91767 | Los Angeles County | 4. Preliminary Design | 26 - Covina | Metro East | Pomona |  |  | 2911689 | 1735472 |  |  | 2 |  |  | NO |  |  |  |  | 2020-06-16 | 2020-06-23 |  |  | 6 | 6 | 2020-06-24 | 2020-07-02 | 2020-07-07 | 8 | 8 | 3 | 3 |  |  |  | 2020-07-08 |  | 2020-08-11 | 2020-08-10 |  |  | 2020-08-10 | 2020-12-17 | 90 | 90 |  | 2021-01-11 | 16 | 16 | 2021-01-12 | 2 | 2 | 2021-02-04 | 2021-03-11 | 2021-02-04 | 2021-03-09 | 18 | 18 | 55 | 55 | 23 | 23 | 2021-03-08 | 2021-04-13 | 2021-04-26 | 39 | 39 | 10 | 10 | 36 | 36 | 2021-02-02 | 15 | 15 |  |  |  | 2021-02-04 | 2021-02-02 | 2021-04-26 |  |  |  | 16 | 16 | 2021-03-01 | 2021-03-05 | 2021-03-05 | 5 | 5 |  | 2021-02-19 | [16 empty] | 2021-04-28 | 2021-05-27 | 22 | 22 | 2021-05-28 | 23 | 23 | 2021-05-28 |  |  |  | 240 | 240 |  |  | 2021
515 | San Dimas Shell | 630 W Bonita Ave | San Dimas | 91773 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 2911690 | 1735852 | [5 empty] | true |  |  |  |  | 2020-06-23 | 2020-06-23 |  |  | 1 | 1 | 2020-06-24 | 2020-07-02 | 2020-07-07 | 8 | 8 | 3 | 3 |  |  |  | 2020-07-08 |  | 2020-08-11 | 2020-08-12 |  |  | 2020-08-12 | [21 empty] | 2022-03-21
516 | Arcadia Westfield Santa Anita | 400 S Baldwin Ave EV | Arcadia | 91007 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 2915657 | 1740306 |  |  | 12 |  |  | true | 2020-06-30 | 2020-07-06 | 4 | 4 | 2020-06-23 | 2020-06-23 | 9 | 9 | 1 | 1 | 2020-06-23 |  | 2020-06-25 | [7 empty] | 2020-07-15 | 2020-07-22 | 2020-08-21 | 2020-08-19 |  |  | 2020-08-19 | 2020-08-25 | 5 | 5 | 2020-09-22 | 2020-09-25 | 23 | 23 | 2020-09-25 | 1 | 1 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-11-17 | 18 | 18 | 59 | 59 | 20 | 20 |  | 2020-12-11 | 2021-02-08 |  |  | 39 | 39 | [8 empty] | 2020-10-20 |  | 2021-02-08 | [22 empty] | 2021-07-20 | 2021-07-20 |  |  | 1 | 1 | 2021-08-05 |  |  |  | 2021-09-22 | 34 | 34 | 2021-09-22 |  |  |  | 315 | 315 |  |  | 2021
518 | Long Beach, CA- 5949 E. Spring St (Spring Street Pavillion) | 5949 E. Spring St | Long Beach | 90808 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2020-06-25 | 2020-07-17 | 16 | 16 | 2020-06-25 | 2020-06-25 | 16 | 16 | 1 | 1 | 2020-06-25 |  | 2020-07-06
519 | Mission Viejo Westwood Financial Olympiad Plaza | 23062 Alicia Pkwy | Mission Viejo | 92692 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3090990 | 1858248 |  |  |  | NO |  | true | 2020-07-06 | 2020-07-20 | 11 | 11 | 2020-06-09 | 2020-06-09 | 29 | 29 | 1 | 1 | 2020-06-10 |  | 2020-06-26 |  |  |  |  | 2021-05-13 | 234 | 234 | 2021-05-13 | 2021-05-14 | 2021-06-24 | 2021-06-15 | 23 | 23 | 2021-06-15 | 2021-06-16 | 2 | 2 | 2021-07-08 | 2021-07-08 | 16 | 16 | 2021-07-08 | 1 | 1 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-09 | 19 | 19 | 38 | 38 | 5 | 5 | 2021-07-22 | 2023-02-03 |  | 11 | 11 | [10 empty] | 2021-08-03
520 | West Hollywood, CA- 7377 Santa Monica Blvd (Plummer Park South) | 7377 Santa Monica Blvd | West Hollywood | 90046 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-06-30 | 2020-07-16 | 12 | 12 | 2020-06-30 | 2020-06-30 | 12 | 12 | 1 | 1 | 2020-07-07 |  | 2020-07-14
521 | West Hollywood Kings Rd Parking Garage | 8383 Santa Monica Blvd | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-06-30 |  |  |  | 2020-06-30 | 1930-06-30 01:00 |  |  | -23478 |  | 2020-07-07
522 | West Hollywood, CA- 901 Hancock Ave (WH Parking Garage) | 901 Hancock Ave | West Hollywood | 90069 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-06-30 | 2020-10-30 | 87 | 87 | 2020-06-30 | 2020-06-30 | 87 | 87 | 1 | 1 |  |  | 2020-07-16
523 | Culver City, CA- 8850 Washington Blvd (The Platform) | 8850 Washington Blvd EV | Culver City | 90232 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 2989753 | 1883629 |  |  | 8 |  |  | NO | 2020-06-30 | 2020-07-08 | 6 | 6 | 2020-06-30 | 2020-06-30 | 6 | 6 | 1 | 1 |  |  | 2020-07-27 |  |  |  |  | 2020-11-18 | 99 | 99 | 2020-11-20 | 2020-11-20 | 2020-12-23 | 2020-12-28 | 26 | 26 | 2020-12-28 | 2021-07-08 | 134 | 134 | 2021-07-29 | 2021-08-02 | 18 | 18 | 2021-08-02 | 1 | 1 | 2021-10-01 | 2021-10-01 | [17 empty] | 2021-08-04 | 3 | 3 | 2021-09-01 | 21 | 21 | [6 empty] | 3 | 3 | [5 empty] | 2021-10-06 | [12 empty] | 2021-10-20 | 11 | 11 |  |  | 2021-10-22 |  |  |  | 2021-11-22 | 21 | 21 | 2021-11-22 |  |  |  | 352 | 352 | 254 | 254 | 2021
524 | Orange | 615 S Tustin Ave | Orange | 92866 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2915809 | 1735825 |  |  | 2 |  |  | NO | 2020-07-14 | 2020-07-20 | 5 | 5 | 2020-07-07 | 2020-07-07 | 10 | 10 | 1 | 1 | 2020-07-07 | 2020-07-13 | 2020-07-14 | 5 | 5 | 2 | 2 |  |  |  | 2020-07-15 | 2020-07-16 | 2020-08-19 | 2020-08-19 |  |  | 2020-08-19 | 2020-08-28 | 8 | 8 |  | 2020-08-31 | 2 | 2 | 2020-08-31 | 1 | 1 | 2020-10-29 | 2020-11-16 | 2020-10-29 | 2020-10-30 | 43 | 43 | 45 | 45 | 2 | 2 | 2020-09-03 | 2020-11-02 | 2020-11-09 | 4 | 4 | 6 | 6 | 47 | 47 | 2021-01-12 | 91 | 91 | 2021-02-15 | 23 | 23 | 2020-10-29 | 2020-10-29 | 2020-11-09 | 2021-02-15 | 71 | 71 | 91 | 91 | [5 empty] | 2021-01-04 | [11 empty] | 2021-08-31 | 2021-09-27 | 186 | 186 | 19 | 19 | 2021-09-29 | 2021-11-17 | 35 | 35 | 2021-11-18 | 36 | 36 | 2021-11-18 |  |  |  | 346 | 346 |  |  | 2021
525 | Marina Del Rey | 13450 Maxella Ave | Marina Del Rey | 90292 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-06-30 |  |  |  | 2020-06-30 | 2020-06-30 |  |  | 1 | 1
526 | West Hollywood, CA- 625 N San Vincente Blvd (Park 5 Story/ Library) | 625 N San Vincente Blvd | West Hollywood | 90069 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-07-16 | 2020-07-10 | -5 |  | 2020-06-30 | 2020-06-30 | 8 | 8 | 1 | 1 | 2020-07-07 |  | 2020-07-14
527 | West Hollywood, CA- 8775 Sunset Blvd (Sunset Lot) | 8775 Sunset Blvd | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3063374 | 1853110 |  |  | 12 | NO |  | true | 2020-06-30 | 2020-07-10 | 8 | 8 | 2020-06-30 | 2020-06-30 | 8 | 8 | 1 | 1 |  |  | 2020-07-14 |  |  |  |  | 2021-03-24 | 183 | 183 | 2021-03-26 | 2021-03-29 | 2021-05-19 | 2021-05-21 | 43 | 43 | 2021-05-24 |  |  |  |  | 2021-07-21 |  |  | 2021-07-21 | 1 | 1 | 2021-10-07 |  | 2021-10-07 | 2021-10-13 | 56 | 56 |  |  | 5 | 5 |  | 2021-09-22 | 2021-11-19 |  |  | 42 | 42 | [8 empty] | 2021-09-22 |  | 2021-11-19 | [5 empty] | 2022-06-15 |  | 2022-06-28 | 10 | 10 | [13 empty] | 2022-07-18 |  |  |  |  | 2022-07-27 |  |  |  | 2022-09-02 | 28 | 28 | 2022-09-02 |  |  |  | 549 | 549 | 367 | 367 | 2022
528 | El Segundo, CA- 500 N Sepulveda blvd (Ralphs) | 500 N Sepulveda blvd | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Saddleback | [9 empty] | NO | 2020-07-13 | 2020-07-15 | 3 | 3 | 2020-07-09 | 2020-07-09 | 5 | 5 | 1 | 1 | 2020-07-10 |  | 2020-07-21
529 | Santa Ana Holiday Inn | 2726 S Grand Ave | Santa Ana | 92705 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2929351 | 1737760 |  |  | 4 |  |  | NO | 2020-07-30 | 2020-08-07 | 7 | 7 | 2020-07-03 | 2020-07-13 | 20 | 20 | 6 | 6 | 2020-07-14 | 2020-07-24 | 2020-07-30 | 10 | 10 | 5 | 5 |  |  |  | 2020-08-05 | 2020-08-06 | 2020-09-18 | 2020-09-18 |  |  | 2020-09-18 | 2020-11-24 | 47 | 47 |  | 2020-11-25 | 2 | 2 | 2020-11-25 | 1 | 1 | 2020-12-10 | 2020-12-22 | 2020-12-10 | 2021-02-02 | 10 | 10 | 46 | 46 | 36 | 36 | 2020-11-30 | 2020-12-17 | 2020-12-28 | 2 | 2 | 7 | 7 | 20 | 20 | [6 empty] | 2020-12-10 |  | 2021-02-02 | [5 empty] | 2021-03-01 | 2021-03-25 | 2021-03-25 | 19 | 19 | 2020-12-02 | [12 empty] | 2021-04-22 | 98 | 98 |  |  | 2021-04-23 | 2021-06-07 | 31 | 31 | 2021-06-07 | 31 | 31 | 2021-06-07 |  |  |  | 232 | 232 |  |  | 2021
530 | Orange Best Western | 720 The City Dr S | Orange | 92868 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 2941888 | 1755234 |  |  | 4 |  |  | NO | 2020-07-30 | 2020-08-14 | 12 | 12 | 2020-07-14 | 2020-07-14 | 24 | 24 | 1 | 1 | 2020-07-15 | 2020-07-24 | 2020-08-14 | 9 | 9 | 16 | 16 |  |  |  | 2020-08-25 |  | 2020-10-07 | 2020-10-07 |  |  | 2020-10-07 | 2020-10-30 | 18 | 18 |  | 2020-11-18 | 13 | 13 | 2020-11-18 | 1 | 1 | 2020-12-09 | 2020-12-22 | 2020-12-09 | 2021-02-02 | 14 | 14 | 62 | 62 | 37 | 37 | [23 empty] | 2020-12-17 | 2021-01-11 | 2021-01-11 | 16 | 16 | [12 empty] | 2021-03-01 | 2021-03-01 |  |  | 1 | 1 | 2021-03-01 | 2021-04-06 | 27 | 27 | 2021-04-06 | 27 | 27 | 2021-04-06 |  |  |  | 183 | 183 |  |  | 2021
531 | Tustin Shopping Center - Oak Tree Tustin LLC | 17582 17th St | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2957034 | 1774058 |  |  | 4 |  |  | true | 2020-07-30 | 2020-08-10 | 8 | 8 | 2020-07-14 | 2020-07-14 | 20 | 20 | 1 | 1 | 2020-07-15 | 2020-07-24 | 2020-08-14 | 9 | 9 | 16 | 16 |  |  |  | 2020-09-17 | 2021-07-15 | 2020-10-21 | 2021-11-04 |  |  | 2021-11-04 | 2021-11-04 | 1 | 1 |  | 2021-12-29 | 36 | 36 | 2021-12-29 | 1 | 1 | 2022-01-03 | 2022-01-03 | 2022-02-08 | 2022-02-08 | 29 | 29 | 64 | 64 | 1 | 1 | [41 empty] | 2022-04-13 |  |  |  |  | 2022-04-21 | 2022-05-06 | 12 | 12 | 2022-05-07 | 12 | 12 | 2022-05-07 |  |  |  | 457 | 457 |  |  | 2022
532 | West Hollywood, CA- 8120 Santa Monica Blvd (WeHo Lot) | 8120 Santa Monica Blvd | West Hollywood | 90069 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-07-15 | 2020-07-17 | 3 | 3 | 2020-07-14 | 2020-07-14 | 4 | 4 | 1 | 1 |  |  | 2020-07-27
533 | Yorba Linda AWSS | 19859 Esperanza Rd | Yorba Linda | 92886 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 2942353 | 1758418 |  |  | 2 |  |  | NO | 2020-07-31 | 2020-08-10 | 7 | 7 | 2020-07-20 | 2020-07-21 | 15 | 15 | 2 | 2 | 2021-06-10 | 2020-07-28 | 2020-08-14 | 6 | 6 | 14 | 14 |  |  |  | 2020-08-26 | 2020-08-26 | 2020-09-29 | 2020-09-29 |  |  | 2020-09-30 |  |  |  |  | 2021-03-03 |  |  | 2021-03-03 | 1 | 1 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-06 | 110 | 110 |  |  | 2 | 2 | [30 empty] | 2021-07-15 | [9 empty] | 2022-02-07 | 2022-02-27 |  |  | 14 | 14 | 2022-03-01 | 2022-03-31 | 23 | 23 | 2022-04-26 | 41 | 41 | 2022-04-26 |  |  |  | 445 | 445 |  |  | 2022
534 | Fullerton - Fueling Convenience | 1124 E Chapman Ave | Fullerton | 92831 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 2937648 | 1751561 |  |  | 2 |  |  | NO | 2020-07-30 | 2020-08-10 | 8 | 8 | 2020-07-20 | 2020-07-21 | 15 | 15 | 2 | 2 | 2020-07-21 | 2020-07-28 | 2020-08-14 | 6 | 6 | 14 | 14 |  |  |  | 2020-08-17 |  | 2020-09-18 | 2020-09-18 |  |  | 2020-09-21 | 2020-11-25 | 47 | 47 |  | 2020-12-30 | 23 | 23 | 2020-12-30 | 1 | 1 | 2021-08-17 | 2022-02-07 | 2021-08-17 | 2022-02-07 | 160 | 160 | 300 | 300 | 119 | 119 | 2021-01-05 | 2021-10-19 | 2021-11-16 | 4 | 4 | 20 | 20 | 220 | 220 | 2021-02-22 | 36 | 36 | 2022-03-08 | 263 | 263 | 2021-08-17 | 2021-02-22 | 2022-02-07 | 2022-03-08 | 263 | 263 | 36 | 36 | [7 empty] | 2021-07-15 | [10 empty] | 2022-02-28 |  |  |  |  | 2022-04-13 | 2022-05-04 | 16 | 16 | 2022-05-05 | 17 | 17 | 2022-05-05 |  |  |  | 452 | 452 |  |  | 2022
535 | Santa Monica Centinela | 1909 Centinela | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-31 | 2020-08-03 | 2 | 2 | 2020-07-23 | 2020-07-23 | 8 | 8 | 1 | 1 | 2020-07-24 | 2020-07-29 | 2020-08-17 | 5 | 5 | 14 | 14
536 | Irvine Spectrum | 670 Spectrum Center Drive | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3167170 | 1931195 | [5 empty] | true | 2020-07-24 | 2020-08-06 | 10 | 10 | 2020-07-24 | 2020-07-24 | 10 | 10 | 1 | 1 |  |  | 2020-08-07 | [7 empty] | 2021-09-09 | 2021-09-09 | 2021-09-23 | 2021-11-29 |  |  | 2021-11-29
537 | Tustin Market Place | 2961 El Camino Real | Tustin | 92782 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3066690 | 1849591 | [5 empty] | NO | 2020-07-24 | 2020-07-30 | 5 | 5 | 2020-07-24 | 2020-07-24 | 5 | 5 | 1 | 1 |  |  | 2020-08-07 | [7 empty] | 2021-04-01 | 2021-04-02 | 2021-05-06 | 2021-05-11 |  |  | 2021-05-12 | 2021-06-10 | 21 | 21 | 2021-07-01 | 2021-07-07 | 19 | 19 | 2021-07-07 | 1 | 1 | 2021-09-09 | 2021-09-09 | 2021-09-09 |  | 46 | 46 |  |  |  |  | 2021-09-03 | 2021-10-04 |  | 43 | 43 | [10 empty] | 2021-09-09
538 | Beverly Hills, CA- 321 S La Cienega | 321 S La Cienega Blvd | Beverly Hills | 90211 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 |  |  |  | 2020-07-24 | 2020-07-27 |  |  | 2 | 2 | 2020-07-29 | 2020-08-11 | 2020-08-27 | 12 | 12 | 13 | 13
539 | Beverly Hills, CA- 9560 Wilshire Blvd (Rodeo Plaza) | 9560 Wilshire Blvd | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 | 2020-08-24 | 20 | 20 | 2020-07-24 | 2020-07-27 | 21 | 21 | 2 | 2 | 2020-07-29
540 | Beverly Hills, CA- 216 S Beverly Dr | 216 S Beverly Dr | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 | 2020-08-07 | 9 | 9 | 2020-07-24 | 2020-07-27 | 10 | 10 | 2 | 2 | 2020-07-29 |  | 2020-08-14
541 | Beverly Hills, CA- 221 N Crescent Dr | 221 N Crescent Dr | Beverly Hills | 90210 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 | 2020-08-07 | 9 | 9 | 2020-07-24 | 2020-07-27 | 10 | 10 | 2 | 2 | 2020-07-29 |  | 2020-08-17
542 | Beverly Hills, CA- 450 N Rexford | 450 N Rexford Dr | Beverly Hills | 90210 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 | 2020-08-07 | 9 | 9 | 2020-07-24 | 2020-07-27 | 10 | 10 | 2 | 2 | 2020-07-29
543 | Beverly Hills, CA- 333 N Crescent Dr | 333 N Crescent Dr | Beverly Hills | 90210 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 | 2020-08-07 | 9 | 9 | 2020-07-24 | 2020-07-27 | 10 | 10 | 2 | 2 | 2020-07-29
544 | West Hollywood, CA- 7100 Santa Monica Blvd suite 70 (West Hollywood Gateway) | 7100 Santa Monica Blvd suite 70 | West Hollywood | 90046 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3181280 | [6 empty] | YES | 2020-07-28 | 2020-09-02 | 27 | 27 | 2020-07-24 | 2020-07-27 | 28 | 28 | 2 | 2 | 2021-08-06 |  | 2021-08-17 | [7 empty] | 2021-09-29 | 2021-10-01 | 2021-11-15
545 | Santa Monica, CA- 1819 Cloverfield Blvd | 1819 Cloverfield Blvd | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3086275 | 1855629 |  |  | 16 | NO |  | true | 2020-07-28 | 2020-08-03 | 5 | 5 | 2020-07-24 | 2020-07-27 | 6 | 6 | 2 | 2 | 2020-07-29 |  | 2020-08-17 | [7 empty] | 2021-05-07 | 2021-05-10 | 2021-06-09 | 2021-06-09 |  |  | 2021-06-09 | 2021-07-15 | 26 | 26 |  | 2021-12-22 | 111 | 111 | 2021-12-22 | 1 | 1 | 2021-12-22 | 2022-01-25 | 2021-12-22 | 2022-01-10 | 1 | 1 | 123 | 123 | 13 | 13 | 2021-12-16 | 2022-01-19 | 2022-02-14 | -5 |  | 19 | 19 | 41 | 41 | 2022-08-18 | 167 | 167 | 2022-08-23 | 4 | 4 | 2021-12-22 | 2021-12-22 | 2022-02-14 | 2022-08-23 | 170 | 170 | 167 | 167 |  |  | 2022-09-26 | [15 empty] | 2022-09-10 |  |  |  |  | 2022-08-19 |  |  |  | 2022-11-14 | 60 | 60 | 2022-11-14 |  |  |  | 581 | 581 |  |  | 2022
546 | Santa Monica, CA- 2437 Main St #B (Edgemar Center for the Arts) | 2437 Main St #B | Santa Monica | 90405 | Los Angeles County | 7. Civil Construction | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-07-29 | 2020-08-14 | 13 | 13 | 2020-07-28 | 2020-07-29 | 13 | 13 | 2 | 2 |  |  | 2020-09-08
547 | Marina Del Rey, CA-4637 Admiralty Way (Pier 44) | 4639U Admiralty Way | Marina Del Rey | 90292 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2986146 | 1776768 | 2127146 | 2024-04-30 | 10 | NO |  | true | 2020-07-29 | 2020-08-03 | 4 | 4 | 2020-07-28 | 2020-07-29 | 4 | 4 | 2 | 2 | 2020-07-31 | 2020-08-04 | 2020-08-25 | 5 | 5 | 16 | 16 | 2021-10-21 | 312 | 312 | 2021-10-25 | 2021-10-26 | 2021-12-13 | 2021-12-13 | 35 | 35 | 2021-12-13 | 2021-12-20 | 6 | 6 | 2022-01-13 | 2023-07-06 | 391 | 391 | 2022-01-19 | -371 |  | 2022-01-19 | 2023-03-28 | 2023-07-18 |  | 9 | 9 | [13 empty] | 2023-10-25 | 449 | 449 | 2023-11-22 | 21 | 21 | [6 empty] | 79 | 79 | [7 empty] | 2024-03-13 | [15 empty] | 2023-11-22
548 | San Dimas, CA- 856 W Arrow Hwy (Marketplace) | 856 W Arrow Hwy | San Dimas | 91773 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | true | 2020-07-29 | 2020-10-05 | 48 | 48 | 2020-07-22 | 2020-07-28 | 49 | 49 | 5 | 5
549 | Rialto, CA- 1309 W Renaissance Pkwy | 1309 W Renaissance Pkwy | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | true | 2020-07-28 | 2020-08-11 | 11 | 11 | 2020-07-23 | 2020-07-28 | 11 | 11 | 4 | 4 | 2020-07-28 |  | 2020-08-17
550 | Santa Ana | 1826 N Tustin Ave | Santa Ana | 92705 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2020-07-29 | 2020-08-12 | 11 | 11 | 2020-07-24 | 2020-07-24 | 14 | 14 | 1 | 1 | [10 empty] | 2020-11-05
551 | El Segundo | 138 Sheldon St | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2977915 | 1802160 |  |  | 4 |  |  | NO | 2020-09-09 | 2020-09-10 | 2 | 2 | 2020-08-06 | 2020-08-07 | 24 | 24 | 2 | 2 |  |  | 2020-09-08 | [7 empty] | 2020-10-28 | 2020-10-28 | 2020-12-01 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-03 | 22 | 22 | 2021-03-03 | 1 | 1 | 2021-03-03 | 2021-03-03 | 2021-09-21 | 2021-09-21 | 142 | 142 | 163 | 163 | 1 | 1 | 2021-03-08 | 2021-04-28 | 2021-05-03 | 4 | 4 | 4 | 4 | 41 | 41 | 2021-06-29 | 84 | 84 | 2021-07-23 | 18 | 18 | 2021-04-28 | 2021-04-28 | 2021-09-21 | 2021-09-21 | 102 | 102 | 84 | 84 | [5 empty] | 2021-07-06 | 2021-08-06 | [11 empty] | 2021-08-30 | 40 | 40 |  |  | 2021-09-15 | [6 empty] | 2021-10-07 |  |  |  | 295 | 295 |  |  | 2021
552 | City of Industry FedEx | 1081 Fullerton Rd | City of Industry | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 2933139 | 1750099 |  |  | 13 |  |  | true |  |  |  |  | 2020-08-10 | [15 empty] | 2020-08-10 |  | 2020-09-11 | 2020-09-11 |  |  | 2020-09-11 | 2020-09-11 | 1 | 1 | 2020-10-02 | 2020-10-02 | 16 | 16 |  |  |  | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2020-11-02 | 21 | 21 | 37 | 37 | 2 | 2 | [46 empty] | 2020-11-02 | [6 empty] | 2020-12-06 |  |  |  | 81 | 81 |  |  | 2020
553 | Ridgecrest Norma Street | 1400 N Norma Street | Ridgecrest | 93555 | Kern County | 9. Complete | 86 - Ridgecrest | Rurals | Ventura | [9 empty] | YES | 2020-08-07 | 2020-08-26 | 14 | 14 | 2020-08-07 | 2020-08-07 | 14 | 14 | 1 | 1 |  |  | 2020-08-31
554 | Santa Barbara, CA- 621 Anacapa St (Anacapa Ortega Garage) | 621 Anacapa St | Santa Barbara | 93101 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3087629 | 1852442 | [5 empty] | true | 2020-08-10 | 2020-08-31 | 16 | 16 | 2020-08-10 | 2020-08-10 | 16 | 16 | 1 | 1 | 2020-08-10 |  | 2020-08-24 | [7 empty] | 2021-05-10 | 2021-05-13 | 2021-07-14 | 2021-07-15 |  |  | 2021-07-15 | 2021-09-16 | 45 | 45 | 2021-10-07 | 2021-10-18 | 23 | 23 | 2021-10-18 | 1 | 1 | 2021-11-15 | 2021-12-02 | 2021-11-15 |  | 20 | 20 |  |  |  |  | 2021-11-10 | 2021-11-29 | 2022-07-29 | 18 | 18 | 170 | 170 | 180 | 180 | 2022-09-23 | 236 | 236 | 2023-04-18 | 143 | 143 | 2021-11-15 | 2021-11-15 |  |  |  |  | 236 | 236 | 2023-03-07 | [17 empty] | 2023-04-14 |  |  |  |  | 2023-04-24 |  |  |  | 2023-06-22 | 43 | 43
555 | Santa Barbara, CA- 914 Chapala St (City Lot 2) | 914 Chapala St | Santa Barbara | 93101 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | NO | 2020-08-10 | 2020-09-01 | 17 | 17 | 2020-08-10 | 2020-08-10 | 17 | 17 | 1 | 1 | 2020-08-10
556 | Beverly Hills, CA- 485 N Rodeo Dr | 485 N Rodeo Dr | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-07-28 |  |  |  | 2020-07-24 | 2020-07-27 |  |  | 2 | 2 | 2020-07-28
557 | Beverly Hills, CA- 485 Camden Dr | 485 Camden Dr | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-07-28 |  |  |  | 2020-07-24 | 2020-07-28 |  |  | 3 | 3 | 2020-07-28
558 | Beverly Hills, CA- 485 N Bedford Dr | 485 N Bedford Dr | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-07-28 |  |  |  | 2020-07-24 | 2020-07-28 |  |  | 3 | 3 | 2020-07-28
559 | Beverly Hills, CA- 485 N Roxbury Dr. | 485 N Roxbury Dr | Beverly Hills | 90212 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-07-28 | 2020-08-06 | 8 | 8 | 2020-07-24 | 2020-07-27 | 9 | 9 | 2 | 2 | 2020-07-28 |  | 2020-09-16
560 | Redondo Beach, CA- 4001 Inglewood Ave (Plaza) | 4001 Inglewood Ave | Redondo Beach | 90278 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2020-08-13 | 2020-09-01 | 14 | 14 | 2020-08-12 | 2020-08-12 | 15 | 15 | 1 | 1 | 2020-08-13 |  | 2020-08-31 | [9 empty] | 2021-10-05 | [52 empty] | 2022-02-18 | 2022-03-14
561 | Valencia Westfield Town Center | 24201 Valencia Blvd | Valencia | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 2950439 | 1749926 |  |  | 6 |  |  | true | 2020-09-02 |  |  |  | 2020-07-17 | 2020-07-17 |  |  | 1 | 1 | 2021-12-29 |  | 2020-08-23 |  |  |  |  | 2020-09-02 | 34 | 34 | 2020-09-03 | 2020-09-08 | 2020-10-08 | 2021-06-28 | 205 | 205 | 2021-06-28 | 2021-07-01 | 4 | 4 | 2021-07-22 | 2021-07-23 | 16 | 16 | 2021-07-26 | 2 | 2 | 2021-10-04 | 2021-10-04 | 2021-10-04 | 2021-10-18 | 51 | 51 | 76 | 76 | 11 | 11 | 2021-07-20 | 2021-08-09 | 2021-12-20 | -4 |  | 92 | 92 | 106 | 106 | 2022-01-07 | 115 | 115 | 2022-02-01 | 17 | 17 | 2021-08-09 | 2021-08-09 | 2021-12-20 | 2022-02-01 | 121 | 121 | 116 | 116 |  |  | 2022-06-10 |  |  | 2021-09-23 | 2022-03-23 | [11 empty] | 2022-06-21 | 187 | 187 | [6 empty] | 2022-06-29 |  |  | 2022-06-29 |  |  |  | 491 | 491 | 458 | 458 | 2022
562 | Culver City, CA- 9099 Washington Blvd | 9099 Washington Blvd | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-08-21 | 2020-09-02 | 9 | 9 | 2020-08-14 | 2020-08-14 | 14 | 14 | 1 | 1
563 | Culver City, CA- 3846 Cardiff Ave | 3846 Cardiff Ave | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-08-21 |  |  |  | 2020-08-14 | 2020-08-14 |  |  | 1 | 1 |  |  | 2020-09-01
564 | Culver City, CA- 3844 Watseka Ave | 3844 Watseka Ave | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-08-21 | 2020-09-02 | 9 | 9 | 2020-08-14 | 2020-08-14 | 14 | 14 | 1 | 1
565 | Culver City, CA - 10772 Jefferson Blvd (Ralph's #284) | 10772 Jefferson Blvd | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3093560 | 1880678 |  |  |  | NO |  | true | 2020-08-14 | 2020-08-27 | 10 | 10 | 2020-08-14 | 2020-08-14 | 10 | 10 | 1 | 1 |  |  | 2020-11-10 |  |  |  |  | 2023-06-22 | 719 | 719 | 2023-06-22 | 2023-06-23 | 2023-07-23
566 | Santa Monica, CA- 1225 Stanford St | 1225 Stanford St | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-08-21 | 2020-09-02 | 9 | 9 | 2020-08-14 | 2020-08-14 | 14 | 14 | 1 | 1
567 | Santa Monica, CA- 501 Santa Monica Blvd | 501 Santa Monica Blvd | Santa Monica Blvd | 90404 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2020-08-21 | 2020-09-02 | 9 | 9 | 2020-08-14 | 2020-08-14 | 14 | 14 | 1 | 1
568 | Costa Mesa Bristol | 2995 Bristol St | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 2966830 | 1770431 |  |  | 2 |  |  | YES |  |  |  |  | 2020-08-17 | 2020-08-17 |  |  | 1 | 1 |  |  | 2021-08-20 | [7 empty] | 2020-10-08 | 2020-10-12 | 2020-11-12 | 2020-10-30 |  |  | 2020-10-30 | 2020-11-04 | 4 | 4 |  | 2020-11-25 | 15 | 15 | 2020-11-25 | 1 | 1 | 2020-12-02 | 2020-12-18 | 2020-12-02 | 2020-12-04 | 4 | 4 | 20 | 20 | 3 | 3 | 2020-11-05 | 2020-12-09 | 2020-12-18 | -14 |  | 8 | 8 | 29 | 29 | [6 empty] | 2020-12-02 |  | 2020-12-18 | [5 empty] | 2021-05-03 | 2021-05-25 | 2021-05-25 | 17 | 17 | 2020-12-04 | 2021-04-12 | [10 empty] | 2021-08-04 | 2021-08-20 | 180 | 180 | 13 | 13 | 2021-09-10 | 2021-10-13 | 24 | 24 | 2021-10-13 | 24 | 24 | 2021-10-13 |  |  |  | 292 | 292 |  |  | 2021
569 | Laguna Hills, CA- 24301 Avenida De La Carlota (Oakbrook Village) | 24301 Avenida De La Carlota | Laguna Hills | 92653 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3063410 | 1837920 | [5 empty] | NO | 2020-08-19 | 2020-08-31 | 9 | 9 | 2020-08-18 | 2020-08-18 | 10 | 10 | 1 | 1 | 2020-08-19 |  | 2020-09-03 |  |  |  |  | 2021-03-25 | 150 | 150 | 2021-03-26 |  | 2021-05-10 | 2021-04-27 | 24 | 24 | 2021-04-27 | 2021-04-30 | 4 | 4 | 2021-05-21 | 2021-06-03 | 24 | 24 | 2021-06-03 | 1 | 1 | 2021-06-28 | 2021-08-06 | 2021-06-28 |  | 18 | 18 |  |  |  |  | 2021-06-11 | 2021-07-15 |  | 7 | 7 | [10 empty] | 2021-06-28
570 | Chino, CA- 3808 Grand Ave (Spectrum Marketplace) | 3808 Grand Ave | Chino | 91710 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO | 2020-08-19 |  |  |  | 2020-08-18 | 2020-08-18 |  |  | 1 | 1 | 2021-12-06 |  | 2021-12-27
571 | Garden Grove Lakeview Village Corp | 12879 Harbor Blvd | Garden Grove | 92840 | Orange County | 6. Requirements (permit, easment, etc.) | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2020-08-24 | 2020-08-24 |  |  | 1 | 1 | 2020-08-26 | 2020-08-31 | 2020-09-02 | 6 | 6 | 3 | 3
572 | Irvine, CA- 950 Spectrum Center Dr (Irvine Spectrum) R1 | 950 1/4 Spectrum Center Dr | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  | Schilling 12kV | 3409768 | 2066504 |  | 2024-07-08 | 16 | NO |  | YES | 2020-09-01 | 2020-10-21 | 36 | 36 | 2020-08-25 | 2020-08-25 | 41 | 41 | 1 | 1 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 6 | 6 | 4 | 4 | 2022-10-04 | 531 | 531 | 2023-09-25 | 2023-10-04 | 2023-11-10 | 2023-10-23 | 267 | 267 | 2023-11-06 | 2023-11-13 | 6 | 6 | 2023-12-05 | 2023-11-30 | 12 | 12 | 2023-11-30 | 1 | 1 | 2024-01-18 |  | 2024-01-18 | 2024-02-02 | 33 | 33 | 55 | 55 | 12 | 12 | 2022-12-16 | 2022-12-28 | 2024-02-28 | -243 |  | 295 | 295 | 303 | 303 | [6 empty] | 2022-12-28 |  | 2024-02-28
573 | Laguna Woods, CA- 24211 Paseo De Valencia (Bank of America) | 24211 Paseo De Valencia | Laguna Woods | 92637 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3079380 | 1854013 | [5 empty] | YES | 2020-09-01 | 2020-09-16 | 11 | 11 | 2020-08-27 | 2020-08-27 | 14 | 14 | 1 | 1 | 2020-09-02 |  | 2020-10-16 |  |  |  |  | 2021-04-26 | 165 | 165 | 2021-04-27 | 2021-04-27 | 2021-05-31 | 2021-06-03 | 28 | 28 | 2021-06-03 | 2021-06-22 | 14 | 14 | 2021-07-13 | 2021-07-02 | 9 | 9 | 2021-07-02 | 1 | 1 | 2021-07-22 |  | 2021-07-22 |  | 14 | 14 |  |  |  |  | 2021-07-13 |  |  | 7 | 7
574 | Laguna Beach, CA- 610 N Coast Hwy (Boat Canyon Center) | 610 N Coast Hwy | Laguna Beach | 92651 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 3016270 | 1822823 | [5 empty] | NO | 2020-09-01 | 2020-09-17 | 12 | 12 | 2020-08-27 | 2020-08-27 | 15 | 15 | 1 | 1 | 2020-09-01 |  | 2020-09-10 | [7 empty] | 2021-01-11 | 2021-01-12 | 2021-02-12 | 2021-03-29 |  |  | 2021-03-29 | 2021-03-29 | 1 | 1 | 2021-04-19 | 2021-05-14 | 35 | 35 | 2021-05-14 | 1 | 1 | 2021-06-09 |  | 2021-06-09 |  | 18 | 18 |  |  |  |  | 2021-05-20 | 2021-07-01 |  | 5 | 5 | [10 empty] | 2021-06-09
575 | Metro Pointe Parking West | 969 S Coast Dr | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3041741 | 1820758 |  |  | 4 |  |  | NO | 2020-09-01 | 2020-09-15 | 10 | 10 | 2020-09-01 | 2020-09-01 | 10 | 10 | 1 | 1 |  |  | 2020-10-08 | [7 empty] | 2021-02-22 | 2021-02-23 | 2021-03-26 | 2021-05-20 |  |  | 2021-05-20 | 2021-05-20 | 1 | 1 |  | 2021-06-04 | 11 | 11 | 2021-06-07 | 2 | 2 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 17 | 17 | 27 | 27 | 1 | 1 | 2021-06-07 | 2021-07-12 | 2021-10-04 | 2 | 2 | 60 | 60 | 84 | 84 | [6 empty] | 2021-06-28 |  | 2021-10-04 | [5 empty] | 2021-11-19 | 2021-11-30 | 2021-11-30 | 6 | 6 | 2021-07-30 | 2021-11-24 | [10 empty] | 2021-12-08 | 2021-12-14 | 94 | 94 | 5 | 5 | 2021-12-15 | 2022-01-21 | 26 | 26 | 2022-01-21 | 26 | 26 | 2022-01-21 |  |  |  | 348 | 348 |  |  | 2022
576 | Long Beach Ximeno Ave | 1800-2000 Ximeno Ave | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2020-09-01 |  |  |  | 2020-09-01 | 2020-09-01 |  |  | 1 | 1 | 2020-09-03 | 2020-09-09 | 2020-09-11 | 6 | 6 | 3 | 3
577 | Rancho Santa Margarita, CA- 30451-30465 Avenue de las Flores | 30451-30465 Ave de las Flores | Rancho Santa Margarita | 92688 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | true | 2020-08-04 |  |  |  | 2020-08-03 | 2020-08-03 |  |  | 1 | 1 |  |  | 2020-09-01
578 | Santa Ana, CA- 3301-3361 S Bristol St (Bristol Plaza) | 3301 Bristol St. | Santa Ana | 92704 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true | 2020-09-02 | 2020-09-25 | 17 | 17 | 2020-09-01 | 2020-09-01 | 18 | 18 | 1 | 1 |  |  | 2020-09-24
579 | Fountain Valley, CA- 18430 Brookhurst St (Garden Ctr) | 18430 Brookhurst St | Fountain Valley | 92708 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2020-09-02 | 2021-02-08 | 107 | 107 | 2020-09-01 | 2020-09-01 | 108 | 108 | 1 | 1 | 2020-09-03
580 | Torrance South Bay Village | 19330 Hawthrone Blvd | Torrance | 90503 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2020-09-02 | 2020-09-14 | 8 | 8 | 2020-08-31 | 2020-08-31 | 10 | 10 | 1 | 1 | 2020-09-09 |  | 2020-09-11
581 | Fountain Valley, CA- 17920 Brookhurst St (Black Angus) | 17920 Brookhurst St | Fountain Valley | 92708 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2020-09-09 | 2020-09-21 | 9 | 9 | 2020-09-08 | 2020-09-08 | 10 | 10 | 1 | 1 |  |  | 2020-09-28
582 | Anaheim Volvo Placentia | 2999 E La Jolla St | Anaheim | 92806 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | true |  |  |  |  | 2020-09-08 | 2020-09-08 |  |  | 1 | 1 | 2020-09-09 |  | 2020-09-28
583 | Seal Beach Center Regency | 1111 Pacific Coast Highway | Seal Beach | 90740 | Orange County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 3087672 | 1860443 |  |  | 4 |  |  | true | 2021-05-07 | 2021-05-17 | 7 | 7 | 2020-09-08 | 2020-09-08 | 173 | 173 | 1 | 1 | 2020-09-09 |  | 2020-10-07 | [7 empty] | 2021-05-10 | 2021-05-14 | 2021-06-15 | 2021-06-30 |  |  | 2021-06-30 | 2021-07-01 | 2 | 2 | 2021-07-22 | 2021-08-04 | 24 | 24 | 2021-08-04 | 1 | 1 | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-08-05 | 1 | 1 | 25 | 25 | 2 | 2 |  | 2021-08-30 | 2022-01-25 |  |  | 101 | 101 |  |  | 2021-10-20 | 55 | 55 | 2021-10-31 | 8 | 8 | 2021-08-04 | 2021-08-04 | 2022-01-25 | 2022-01-25 | 119 | 119 | 55 | 55 | [6 empty] | 2021-12-09 | 2021-12-14 | [9 empty] | 2021-12-14 | 2022-03-02 |  |  | 54 | 54 | 2022-03-04 |  |  |  | 2022-04-12 | 28 | 28 | 2022-04-12 |  |  |  | 400 | 400 |  |  | 2022
584 | Ventura Macerich Pacific View Mall | 3301 E Main St | Ventura | 93003 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 2999588 | 1794507 |  |  | 6 |  |  | true | 2020-09-11 | 2020-09-22 | 8 | 8 | 2020-09-10 | 2020-09-10 | 9 | 9 | 1 | 1 | 2020-09-11 |  | 2020-09-17 | [7 empty] | 2020-12-10 |  | 2021-01-06 | 2021-01-14 |  |  | 2021-01-14 | 2021-01-14 | 1 | 1 | 2021-02-04 | 2021-03-15 | 41 | 41 | 2021-03-15 | 1 | 1 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 29 | 29 | 70 | 70 | 2 | 2 | 2021-03-31 | 2021-04-05 | 2021-09-30 | 13 | 13 | 126 | 126 | 129 | 129 | [6 empty] | 2021-04-05 |  | 2021-09-30 | [5 empty] | 2021-11-08 | [5 empty] | 2021-09-22 | [11 empty] | 2022-01-28 |  |  |  |  | 2022-01-31 |  |  |  | 2022-03-26 | 39 | 39 | 2022-03-26 |  |  |  | 386 | 386 |  |  | 2022
585 | Long Beach Regency Vons Circle Center | 1800-2000 Ximeno Ave | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | true | 2020-10-08 |  |  |  | 2020-09-09 | 2020-09-09 |  |  | 1 | 1 | 2020-09-11
586 | Long Beach Regency Circle Marina | 4542-4800 Pacific Coast Hwy | Long Beach | 90804 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2020-10-08 |  |  |  | 2020-09-09 | 2020-09-09 |  |  | 1 | 1 | 2020-09-11
587 | Agoura Hills Twin Oaks | 5727 Kanan Rd | Agoura Hills | 91301 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | Malibu | Conejo 16KV | 3096352 | 1874485 |  |  | 4 | NO |  | YES | 2020-09-03 | 2020-09-15 | 8 | 8 | 2020-08-31 | 2020-08-31 | 11 | 11 | 1 | 1 | 2020-09-02 | 2020-09-11 | 2021-07-27 | 9 | 9 | 219 | 219 |  |  |  | 2021-05-21 | 2021-05-26 | 2021-07-28 | 2021-10-25 |  |  | 2021-10-25 | 2021-11-05 | 10 | 10 | 2021-12-03 | 2021-11-10 | 4 | 4 | 2021-11-10 | 1 | 1 | 2021-12-03 | 2022-01-10 | 2021-12-03 | 2021-12-16 | 15 | 15 | 27 | 27 | 10 | 10 | 2021-12-01 | 2022-09-15 | 2022-10-17 | 13 | 13 | 23 | 23 | 223 | 223 | 2023-02-07 | 312 | 312 | 2023-03-30 | 37 | 37 | 2021-12-03 | 2021-12-03 | 2022-10-17 | 2023-03-30 | 334 | 334 | 312 | 312 | 2023-04-27 | 2023-05-18 |  |  |  | 2022-08-23 | [17 empty] | 2023-06-06 |  |  |  | 2023-07-19 | 31 | 31 | 2023-07-19 |  |  |  | 726 | 726 |  |  | 2023
588 | Hermosa Beach Plaza Hermosa | 712 16th Street | Hermosa Beach | 90254 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3113500 | 1877836 |  |  | 6 | NO |  | true | 2020-09-11 | 2020-10-23 | 31 | 31 | 2020-09-09 | 2020-09-09 | 33 | 33 | 1 | 1 | 2020-09-11 | 2020-09-22 | 2020-09-30 | 10 | 10 | 7 | 7 | 2021-06-15 | 192 | 192 | 2021-06-17 |  | 2021-07-20 | 2021-07-21 | 26 | 26 | 2021-07-21 | 2021-08-06 | 13 | 13 | 2021-08-12 | 2021-08-20 | 11 | 11 | 2021-08-20 | 1 | 1 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-26 | 1 | 1 | 15 | 15 | 5 | 5 | 2021-08-27 | 2021-09-20 | 2022-02-03 | 6 | 6 | 94 | 94 | 109 | 109 | 2021-10-19 | 42 | 42 | 2021-11-05 | 14 | 14 | 2021-08-20 | 2021-08-20 | 2022-02-03 | 2022-02-03 | 114 | 114 | 42 | 42 | [6 empty] | 2021-11-29 | 2022-01-13 | [9 empty] | 2022-01-13 | 2022-04-11 |  |  | 61 | 61 | 2022-05-05 |  |  |  | 2022-07-28 | 59 | 59 | 2022-07-28 |  |  |  | 474 | 474 | 283 | 283 | 2022
589 | Palmdale Target | 38019 47th Street E | Palmdale | 93552 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 2991180 | 1782735 | [5 empty] | NO | 2020-09-15 |  |  |  | 2020-09-14 | 2020-09-15 |  |  | 2 | 2 | 2020-09-16 |  | 2020-09-25 | [7 empty] | 2020-11-24 | 2020-12-02 | 2020-12-28 | 2021-01-11 |  |  | 2021-01-11 | 2021-01-12 | 2 | 2 | 2021-02-03
590 | San Gabriel 76 Gas Station | 101 E Las Tunas Dr EV | San Gabriel | 91776 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 2966250 | 1898166 |  |  | 3 | NO |  | true |  |  |  |  | 2020-09-17 | 2020-09-18 |  |  | 2 | 2 | 2021-08-06 |  | 2020-10-02 | [7 empty] | 2020-10-07 |  | 2020-11-11 | 2020-11-03 |  |  | 2020-11-03 |  |  |  | 2022-11-29 | 2022-11-29 |  |  | 2022-11-30 | 2 | 2 | 2022-11-30 | 2022-12-07 | 2022-11-30 | 2022-12-01 | 2 | 2 |  |  | 2 | 2 | [9 empty] | 2021-11-18 | -259 |  | 2022-02-08 | 55 | 55 | [6 empty] | -258 | [19 empty] | 2022-12-05 |  |  |  |  | 2022-12-15 | 2023-01-17 | 23 | 23 | 2023-01-17 | 23 | 23
591 | Fountain Valley, CA- 17966 Brookhurst St (Plaza) | 17966 Brookhurst St | Fountain Valley | 92708 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true | 2020-09-21 | 2020-10-06 | 12 | 12 | 2020-09-18 | 2020-09-18 | 13 | 13 | 1 | 1 | 2020-09-21 | 2020-10-01 | 2020-10-14 | 10 | 10 | 10 | 10
592 | Fountain Valley, CA- 9430 Warner Ave (Plavan Plaza) | 9430 Warner Ave, Suite EV | Fountain Valley | 92708 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3066970 | 1835153 |  |  | 12 |  |  | NO | 2020-10-15 | 2020-11-09 | 18 | 18 | 2020-09-21 | 2020-09-21 | 36 | 36 | 1 | 1 | 2020-09-22 | 2020-10-01 | 2020-10-14 | 9 | 9 | 10 | 10 | 2021-04-01 | 132 | 132 | 2021-04-02 | 2021-04-02 | 2021-05-06 | 2021-04-29 | 21 | 21 | 2021-04-29 | 2021-05-13 | 11 | 11 | 2021-06-03 | [6 empty] | 2021-07-06 | 2021-07-06 | 2021-07-06 | 2021-09-20 |  |  | 90 | 90 | 54 | 54 |  | 2021-07-12 | 2021-09-20 |  |  | 50 | 50 | [8 empty] | 2021-07-06 |  | 2021-09-20 | [23 empty] | 2021-11-17 |  |  |  |  | 2021-11-19 |  |  |  | 2021-12-22 | 22 | 22 | 2021-12-22 |  |  |  | 315 | 315 | 184 | 184 | 2021
593 | Arcadia Santa Anita Westfield Mall | 400 S Baldwin Ave, Unit DCFC | Arcadia | 91007 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3154860 | 1910189 | [5 empty] | NO | 2020-09-22 |  |  |  | 2020-09-01 | 2020-09-01 |  |  | 1 | 1 | 2020-09-03 | 2020-09-21 | 2020-10-19 | 14 | 14 | 21 | 21 | 2021-08-18 | 242 | 242 | 2021-08-19 |  | 2021-09-29 | 2021-10-01 | 32 | 32 | 2021-10-01 | 2021-10-11 | 7 | 7 | 2021-11-02 | 2021-11-02 | 17 | 17 | 2021-11-02 | 1 | 1 | 2021-12-03
594 | La Quinta Inventrust Pavilion | 79220 Highway 111 | La Quinta | 92253 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2020-09-22 | 2020-09-22 |  |  | 1 | 1
595 | FedEx Ventura | 5198 Colt Street | Ventura | 93003 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 2970170 | 1771860 |  |  | 4 |  |  | true |  |  |  |  | 2020-09-17 | 2020-09-17 |  |  | 1 | 1 | 2020-09-18 | [9 empty] | 2020-10-16 |  | 2020-11-19 | 2020-11-18 |  |  | 2020-11-18 | 2020-11-23 | 4 | 4 |  | 2020-12-02 | 6 | 6 | 2020-12-02 | 1 | 1 | 2021-06-17 | 2021-07-14 | 2021-06-17 | 2021-06-22 | 137 | 137 | 145 | 145 | 4 | 4 | 2021-06-07 | 2021-06-22 | 2021-07-02 | 129 | 129 | 9 | 9 | 20 | 20 | 2021-01-15 | 31 | 31 | 2021-03-10 | 37 | 37 | 2021-06-17 | 2021-01-15 | 2021-07-02 | 2021-07-02 | 118 | 118 | 31 | 31 | 2021-07-01 | 2021-07-14 | 2021-07-15 | 10 | 10 | 2021-05-24 | 2021-07-19 | [10 empty] | 2021-08-03 | 2021-08-10 | 55 | 55 | 6 | 6 |  |  |  |  | 2021-10-07 |  |  | 2021-10-07 |  |  |  | 266 | 266 |  |  | 2021
596 | Westlake Village Agoura Rd | 2725 Agoura Rd | Westlake Village | 91361 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3097294 | 1868030 |  |  | 8 |  |  | YES | 2020-09-11 | 2020-10-23 | 31 | 31 | 2020-09-09 | 2020-09-11 | 31 | 31 | 3 | 3 | 2022-01-19 |  | 2020-09-23 | [7 empty] | 2021-06-17 | 2021-05-26 | 2021-07-20 | 2021-06-28 |  |  | 2021-06-28 | 2021-07-21 | 17 | 17 | 2021-08-11 | 2021-08-11 | 16 | 16 | 2021-08-16 | 4 | 4 | 2021-08-16 | 2021-08-31 | 2021-08-16 | 2021-08-19 | 4 | 4 | 22 | 22 | 4 | 4 | 2021-08-05 | 2021-08-25 | 2022-01-07 | -5 |  | 93 | 93 | 107 | 107 | 2022-01-11 | 102 | 102 |  |  |  | 2021-08-16 | 2021-08-16 | 2022-01-07 |  |  |  | 105 | 105 | 2022-01-31 |  |  |  |  | 2021-11-05 | 2021-11-29 | [11 empty] | 2022-03-08 | 82 | 82 |  |  | 2022-03-09 |  |  |  | 2022-04-29 | 38 | 38 | 2022-04-29 |  |  |  | 412 | 412 |  |  | 2022
597 | Stevenson Ranch Plaza | 24955 Pico Canyon Rd | Stevenson Ranch | 91381 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 3029032 | 1856459 |  |  | 4 |  |  | NO | 2020-10-23 | 2020-12-23 | 41 | 41 | 2020-09-22 | 2020-09-22 | 64 | 64 | 1 | 1 |  |  | 2020-09-29 | [7 empty] | 2021-02-01 | 2021-02-02 | 2021-03-04 | 2021-03-10 |  |  | 2021-03-10 | 2021-03-19 | 8 | 8 | 2021-04-09 | 2021-04-01 | 10 | 10 | 2021-04-01 | 1 | 1 | 2021-06-29 | 2022-03-14 | 2021-06-29 | 2022-04-05 | 63 | 63 | 264 | 264 | 193 | 193 | 2021-06-01 | 2021-07-22 | 2021-09-15 | 43 | 43 | 39 | 39 | 75 | 75 | 2021-11-22 | 164 | 164 | 2022-02-22 | 62 | 62 | 2021-06-29 | 2021-06-29 | 2022-04-05 | 2022-04-05 | 193 | 193 | 164 | 164 | 2022-03-05 | [5 empty] | 2022-01-03 | 2022-01-04 | [10 empty] | 2022-05-13 |  |  |  |  | 2022-04-13 |  |  |  | 2022-06-24 | 52 | 52 | 2022-06-24 |  |  |  | 442 | 442 |  |  | 2022
598 | Corona | 616 Paseo Grande | Corona | 92882 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 2971127 | 1779908 |  |  | 2 |  |  | true | 2020-09-28 | 2020-10-06 | 7 | 7 | 2020-09-22 | 2020-09-23 | 10 | 10 | 2 | 2 |  | 2020-09-30 | 2020-10-06 | 6 | 6 | 5 | 5 |  |  |  | 2020-10-19 |  | 2020-11-24 | 2020-11-24 |  |  | 2020-11-24 | 2021-04-01 | 87 | 87 |  | 2021-04-23 | 17 | 17 | 2021-04-23 | 1 | 1 | 2021-05-18 | 2021-06-21 | 2021-05-18 | 2021-06-28 | 18 | 18 | 62 | 62 | 29 | 29 | 2021-05-26 | 2021-10-26 | 2021-12-08 | 24 | 24 | 29 | 29 | 135 | 135 | 2022-01-04 | 176 | 176 | 2022-01-26 | 16 | 16 | 2021-05-18 | 2021-05-18 | 2021-12-08 | 2022-01-26 | 174 | 174 | 176 | 176 | 2022-03-03 | 2022-03-11 | 2022-03-11 | 7 | 7 | 2022-01-05 | [12 empty] | 2022-05-24 | 98 | 98 |  |  | 2022-05-25 | 2022-06-17 | 17 | 17 | 2022-06-22 | 20 | 20 | 2022-06-22 |  |  |  | 440 | 440 |  |  | 2022
599 | Pico Rivera, CA- 8800 Whittier Blvd (Crossroads Plaza) | 8800 Whittier Blvd | Pico Rivera | 90660 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | true | 2020-09-29 | 2020-10-21 | 17 | 17 | 2020-09-25 | 2020-09-25 | 19 | 19 | 1 | 1 | 2020-09-28
600 | Santa Fe Springs, CA- 10621 Carmenita Rd | 10621 Carmenita Rd | Santa Fe Springs | 90670 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 3094710 | 1862575 | [5 empty] | YES | 2020-09-29 | 2020-10-23 | 19 | 19 | 2020-09-25 | 2020-09-25 | 21 | 21 | 1 | 1 | 2020-09-28 |  | 2020-12-14 |  |  |  |  | 2021-05-17 | 160 | 160 | 2021-05-20 | 2021-05-20 | 2021-06-21 | 2021-06-18 | 24 | 24 | 2021-06-18 | 2021-07-26 | 26 | 26 | 2021-08-16 | 2021-08-20 | 20 | 20 | 2021-08-20 | 1 | 1 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-24 | 1 | 1 | 22 | 22 | 3 | 3 | 2021-08-20 | 2021-09-10 |  | 1 | 1 | [10 empty] | 2021-08-20
601 | La Mirada - S Beach Blvd | 13548U S Beach Blvd | La Mirada | 90638 | Los Angeles County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3013100 | 1811839 | 1983546 |  |  | NO |  | NO | 2020-09-28 | 2020-10-15 | 14 | 14 | 2020-09-28 | 2020-09-28 | 14 | 14 | 1 | 1 | 2020-09-28 | 2020-10-06 | 2020-10-20 | 7 | 7 | 11 | 11 |  |  |  | 2021-01-05 | 2021-01-07 | 2021-02-08 | 2021-02-23 |  |  | 2021-02-24 |  |  |  |  | 2021-04-23 |  |  | 2021-04-23 | 1 | 1 | 2021-06-16 | 2021-08-03 | 2021-06-16 | 2021-06-28 | 38 | 38 |  |  | 9 | 9 | 2021-06-10 | 2021-08-05 | 2022-02-04 | 34 | 34 | 126 | 126 | 165 | 165 | 2022-02-01 | 195 | 195 |  |  |  | 2021-06-16 | 2021-06-16 | 2022-02-04 |  |  |  | 195 | 195 | 2022-06-16 | 2022-06-16 | 2022-10-11 | 82 | 82 | 2022-01-07 | [11 empty] | 2022-11-18 | 2022-12-01 | 227 | 227 | 8 | 8 | 2022-12-09 | 2023-02-06 | 41 | 41 | 2023-02-06 | 41 | 41 | 2023-02-06 |  |  |  | 593 | 593 |  |  | 2023
602 | Hawaiian Gardens | 11807 E Carson St | Hawaiian Gardens | 90716 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2987400 | 1799706 |  |  | 2 |  |  | NO | 2020-09-28 | 2020-10-21 | 18 | 18 | 2020-09-28 | 2020-09-28 | 18 | 18 | 1 | 1 | 2020-09-28 | 2020-10-05 | 2020-10-21 | 6 | 6 | 13 | 13 |  |  |  | 2020-11-16 |  | 2020-12-18 |  |  |  |  | 2021-01-26 |  |  |  | 2021-02-18 | 17 | 17 | 2021-02-18 | 1 | 1 | 2021-03-10 | 2021-03-29 | 2021-03-10 | 2021-04-13 | 15 | 15 | 55 | 55 | 25 | 25 | 2021-05-10 | 2021-05-20 | 2021-06-10 | 58 | 58 | 15 | 15 | 23 | 23 | 2021-01-14 | -24 |  | 2021-07-24 | 133 | 133 | 2021-03-10 | 2021-01-14 | 2021-06-10 | 2021-07-24 | 133 | 133 | -24 |  | 2021-09-07 | 2021-10-06 | 2021-10-06 | 22 | 22 | 2021-06-04 | [12 empty] | 2021-10-25 | 100 | 100 |  |  | 2021-10-26 | 2021-11-30 | 23 | 23 | 2021-12-02 | 25 | 25 | 2021-12-02 |  |  |  | 296 | 296 |  |  | 2021
603 | Redondo Beach | 2714 Artesia Blvd | Redondo Beach | 90278 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 2970950 | 1799792 | [5 empty] | NO | 2020-09-28 | 2020-10-16 | 15 | 15 | 2020-09-28 | 2020-09-28 | 15 | 15 | 1 | 1 | 2020-09-28 | 2020-10-05 | 2020-10-17 | 6 | 6 | 10 | 10 |  |  |  | 2020-10-19 | 2020-10-20 | 2020-11-20
604 | Seal Beach | 13980 Seal Beach Blvd Unit D | Seal Beach | 90740 | Orange County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 2972101 | 1794911 |  |  | 2 |  |  | YES | 2020-09-28 | 2020-10-28 | 23 | 23 | 2020-09-28 | 2020-09-28 | 23 | 23 | 1 | 1 | 2022-01-12 | 2020-10-05 | 2020-10-20 | 6 | 6 | 12 | 12 |  |  |  | 2020-10-22 | 2020-10-23 | 2020-11-24 |  |  |  |  | 2021-03-17 |  |  |  | 2021-04-08 | 17 | 17 | 2021-04-08 | 1 | 1 | 2021-05-04 | 2021-05-18 | 2021-05-04 | 2021-05-13 | 19 | 19 | 42 | 42 | 8 | 8 | 2021-04-30 | 2021-06-01 | 2021-06-16 | 17 | 17 | 12 | 12 | 33 | 33 | 2021-08-10 | 87 | 87 | 2021-09-24 | 33 | 33 | 2021-05-04 | 2021-05-04 | 2021-06-16 | 2021-09-24 | 101 | 101 | 87 | 87 | [6 empty] | 2021-09-23 | [11 empty] | 2022-01-18 |  |  |  |  | 2022-01-20 | 2022-02-09 | 15 | 15 | 2022-02-18 | 22 | 22 | 2022-02-18 |  |  |  | 350 | 350 |  |  | 2022
606 | Santa Ana | 2120 E McFadden Ave | Santa Ana | 92705 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 2981801 | 1781966 |  |  |  | NO |  | true | 2020-09-28 |  |  |  | 2020-09-28 | 2020-09-28 |  |  | 1 | 1 | 2020-09-28 | 2020-10-15 | 2020-10-20 | 14 | 14 | 4 | 4 |  |  |  | 2020-11-05 | 2020-11-05 | 2020-12-04 | 2020-12-08 |  |  | 2020-12-08 | 2021-01-26 | 33 | 33 |  | 2021-02-16 | 15 | 15 | 2021-02-16 | 1 | 1 | 2021-06-28 | 2021-08-02 | 2021-06-28 | 2021-07-13 | 94 | 94 | 118 | 118 | 11 | 11 | 2021-03-18 | 2021-04-06 | 2022-06-15 | 23 | 23 | 302 | 302 | 315 | 315 | 2022-01-26 | 239 | 239 | 2022-02-09 | 11 | 11 | 2021-04-06 | 2021-04-06 | 2022-06-15 | 2022-06-15 | 302 | 302 | 239 | 239 | 2022-06-14 | 2022-06-29 | 2022-06-29 | 12 | 12 | 2022-02-01 | [12 empty] | 2022-07-27 | 124 | 124 |  |  | 2022-07-28 | 2022-08-30 | 24 | 24 | 2022-08-31 | 25 | 25 | 2022-08-31 |  |  |  | 485 | 485 |  |  | 2022
607 | Lake Elsinore Walmart | 29280 Central Ave | Lake Elsinore | 92532 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3020670 | [6 empty] | NO | 2020-09-29 |  |  |  | 2020-09-28 | 2020-09-29 |  |  | 2 | 2 | 2020-09-30 | [6 empty] | 2021-01-15 | 75 | 75 | 2021-01-19 | 2021-01-22 | 2021-02-23
608 | Inyokern Rd | 6525 W Inyokern Rd | Inyokern | 93527 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 3001175 | 1857996 |  |  | 10 |  |  | NO | 2020-10-22 | 2020-11-17 | 18 | 18 | 2020-09-29 | 2020-10-01 | 33 | 33 | 3 | 3 | 2020-10-01 | 2020-10-08 | 2020-10-23 | 6 | 6 | 12 | 12 |  |  |  | 2020-12-11 | 2020-12-14 | 2021-01-15 | 2021-01-12 |  |  | 2021-01-12 | 2021-05-04 | 79 | 79 | 2021-05-27 | 2021-05-28 | 19 | 19 | 2021-06-07 | 6 | 6 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 2021-08-02 | 43 | 43 | 63 | 63 | 3 | 3 | 2021-06-02 | 2021-06-24 | 2021-09-07 | 3 | 3 | 52 | 52 | 68 | 68 | [6 empty] | 2021-06-24 |  | 2021-09-07 | [10 empty] | 2021-07-12 | 2021-07-27 | 2021-07-06 | [9 empty] | 2021-06-16 | 2021-10-22 | 74 | 74 | 91 | 91 | 2021-10-25 | 2022-01-24 | 61 | 61 | 2022-01-31 | 66 | 66 | 2022-01-31 |  |  |  | 335 | 335 |  |  | 2022
609 | Santa Monica, CA- 800 Colorado Ave | 800 Colorado Ave | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2020-09-29 | 2020-09-29 |  |  | 1 | 1 | 2020-10-05
610 | Beverly Hills Olympic Blvd | 8955 Olympic Blvd | Beverly Hills | 90211 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-10-02 | 2020-10-13 | 8 | 8 | 2020-10-02 | 2020-10-02 | 8 | 8 | 1 | 1
611 | Compton, CA- 1621 S Alameda St (Gateway Towne Center) | 1621 S Alameda St | Compton | 90220 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 3162120 | 1949261 |  |  | 16 |  |  | YES | 2020-10-05 | 2021-04-05 | 124 | 124 | 2020-10-01 | 2020-10-01 | 126 | 126 | 1 | 1 | 2021-06-17 |  | 2021-06-23 | [7 empty] | 2021-08-31 | 2021-08-31 | 2022-01-25 | 2022-02-02 |  |  | 2022-02-07
612 | Oxnard Target | 2892 N Oxnard Blvd LND | Oxnard | 93036 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 2995678 | 1788119 |  |  | 6 |  |  | YES | 2020-10-05 | 2020-10-20 | 12 | 12 | 2020-09-30 | 2020-09-30 | 15 | 15 | 1 | 1 | 2020-10-01 |  | 2020-10-19 |  |  |  |  | 2020-12-03 | 44 | 44 | 2020-12-07 | 2020-12-10 | 2021-01-11 | 2021-01-13 | 28 | 28 | 2021-01-13 | 2021-01-25 | 8 | 8 | 2021-02-15 | 2021-02-01 | 6 | 6 | 2021-02-01 | 1 | 1 | 2021-03-08 | 2021-03-29 | 2021-03-08 | 2021-03-19 | 25 | 25 | 39 | 39 | 10 | 10 | 2021-03-05 | 2021-04-20 | 2021-07-12 | 24 | 24 | 58 | 58 | 90 | 90 | 2021-10-12 | 178 | 178 | 2022-03-01 | 95 | 95 | 2021-03-08 | 2021-03-08 | 2021-07-12 | 2022-03-01 | 248 | 248 | 178 | 178 | 2022-03-05 |  | 2022-03-25 | 15 | 15 | 2021-08-20 | 2021-09-23 | [10 empty] | 2022-03-17 | 2022-03-30 | 152 | 152 | 10 | 10 | 2022-03-31 |  |  |  | 2022-08-11 | 94 | 94 | 2022-08-11 |  |  |  | 469 | 469 | 426 | 426 | 2022
613 | Santa Monica Wilshire | 1101 Wilshire Blvd | Santa Monica | 90401 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | true | 2020-10-05 | 2020-10-22 | 14 | 14 | 2020-10-01 | 2020-10-01 | 16 | 16 | 1 | 1
614 | Irvine Northwood Town Center | 4800 Irvine Blvd (4800.75 Irvine Blvd) | Irvine | 92620 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 2993045 | 1795566 |  |  | 8 |  |  | true | 2020-10-08 | 2020-10-21 | 10 | 10 | 2020-09-09 | 2020-09-09 | 31 | 31 | 1 | 1 | 2020-09-11 | 2020-09-25 |  | 13 | 13 | [5 empty] | 2020-12-01 | 2020-12-02 | 2021-01-04 | 2021-01-14 |  |  | 2021-01-14 | 2021-01-14 | 1 | 1 | 2021-02-04 | 2021-03-18 | 44 | 44 | 2021-04-22 | 26 | 26 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-26 | 26 | 26 | 71 | 71 | 3 | 3 | 2021-03-26 | 2021-05-05 | 2021-08-20 | 7 | 7 | 76 | 76 | 104 | 104 | 2021-10-12 | 121 | 121 | 2021-10-22 | 9 | 9 | 2021-04-22 | 2021-04-22 | 2021-08-20 | 2021-10-22 | 129 | 129 | 146 | 146 | [5 empty] | 2021-06-18 | [11 empty] | 2021-12-09 | 2021-12-21 | 128 | 128 | 9 | 9 | 2021-12-22 |  |  |  | 2022-01-24 | 22 | 22 | 2022-01-24 |  |  |  | 344 | 344 |  |  | 2022
615 | Fontana Falcon Ridge | 15218 Summit Ave | Fontana | 92336 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | true | 2020-10-05 | 2020-10-21 | 13 | 13 | 2020-09-30 | 2020-09-30 | 16 | 16 | 1 | 1
616 | Beverly Hills Wilshire Blvd | 8833 Wilshire Blvd | Beverly Hills | 90211 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-10-05 | 2020-10-13 | 7 | 7 | 2020-10-02 | 2020-10-02 | 8 | 8 | 1 | 1
617 | Wildomar Bear Creek Village | 36010 Hidden Springs Rd; New: 36080 Hidden Springs Rd | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3098339 | 1912793 |  |  | 4 |  |  | NO | 2020-10-05 | 2020-10-16 | 10 | 10 | 2020-10-02 | 2020-10-02 | 11 | 11 | 1 | 1 | [10 empty] | 2021-05-25 | 2021-05-28 | 2021-06-28 | 2021-09-03 |  |  | 2021-09-07 |  |  |  |  | 2021-10-08 |  |  | 2021-10-08 | 1 | 1 | 2021-11-08 | 2021-12-06 | [9 empty] | 2021-12-03 | 2022-03-17 |  |  | 72 | 72 |  |  | 2022-01-07 | 62 | 62 | 2022-01-31 | 16 | 16 | [6 empty] | 62 | 62 | 2022-01-18 |  | 2022-03-11 | 38 | 38 |  | 2021-11-24 | 2022-01-06 | [9 empty] | 2022-03-31 | 2022-04-22 |  |  | 17 | 17 | 2022-04-25 |  |  |  | 2022-06-29 | 47 | 47 | 2022-06-29 |  |  |  | 437 | 437 |  |  | 2022
618 | Bridgeport Main | 453 Main St | Bridgeport | 93517 | Mono County | 3. Active | 85 - Bishop/Mammoth | Rurals | Ventura | [9 empty] | NO | 2020-11-17 | 2020-11-30 | 8 | 8 | 2020-10-06 | 2020-10-08 | 35 | 35 | 3 | 3 | 2020-10-06 | 2020-10-12 | 2020-10-23 | 3 | 3 | 10 | 10
619 | Tustin Shopping Center - Amana Corporation | 17602 17th St | Tustin | 92780 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2023-08-01 | 4 | YES | Level 3 | true |  |  |  |  | 2023-06-28 | 2023-06-28 |  |  | 1 | 1 | 2023-06-29 | 2023-07-05 | 2023-07-06 | 5 | 5 | 2 | 2
620 | Seal Beach Shops at Rossmoor | 12489 Seal Beach Blvd EV1 | Seal Beach | 90740 | Orange County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2991010 | 1792957 |  |  | 4 |  |  | true | 2020-10-08 | 2020-11-19 | 30 | 30 | 2020-09-09 | 2020-09-09 | 51 | 51 | 1 | 1 | 2021-06-29 | 2020-09-22 | 2020-10-07 | 10 | 10 | 12 | 12 | 2020-11-19 | 51 | 51 | 2020-11-24 |  | 2021-01-06 | 2021-01-27 | 45 | 45 | 2021-01-27 | 2021-02-24 | 20 | 20 | 2021-03-17 | 2021-03-18 | 17 | 17 | 2021-03-19 | 2 | 2 | 2021-05-05 | 2021-05-05 | 2021-05-05 | 2021-05-19 | 35 | 35 | 61 | 61 | 11 | 11 | 2021-04-22 | 2021-05-04 | 2021-06-15 | 26 | 26 | 30 | 30 | 38 | 38 | [6 empty] | 2021-05-04 |  | 2021-06-15 | [5 empty] | 2021-08-23 |  |  |  |  | 2021-06-08 | [11 empty] | 2021-09-09 | 2021-09-15 | 70 | 70 | 5 | 5 | 2021-10-20 |  |  |  | 2021-11-29 | 26 | 26 | 2021-11-29 |  |  |  | 306 | 306 | 256 | 256 | 2021
621 | El Segundo, CA- 390 N Pacific Coast Hwy | 390 N Pacific Coast Hwy | El Segundo | 90245 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2020-10-09 | 2020-10-21 | 9 | 9 | 2020-10-08 | 2020-10-08 | 10 | 10 | 1 | 1
622 | Santa Barbara Bank of America | 3790 State Street | Santa Barbara | 93105 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 2979124 | 1773907 |  |  | 4 |  |  | NO | 2020-10-09 |  |  |  | 2020-10-08 | 2020-10-08 |  |  | 1 | 1 | 2021-08-30 | [11 empty] | 2020-12-04 | 2020-12-04 |  |  | 2020-12-04 | 2020-12-07 | 2 | 2 | 2020-12-30 | 2021-03-23 | 73 | 73 | 2021-03-23 | 1 | 1 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-23 | 23 | 23 | 96 | 96 | 2 | 2 | 2021-03-31 | 2021-04-06 | 2021-04-28 | 7 | 7 | 17 | 17 | 21 | 21 | [6 empty] | 2021-04-06 |  | 2021-04-28 | [5 empty] | 2022-01-17 |  | 2022-02-03 | 13 | 13 | [12 empty] | 2022-03-18 | 2022-03-25 |  |  | 6 | 6 | 2022-03-29 |  |  |  | 2022-05-03 | 26 | 26 | 2022-05-03 |  |  |  | 393 | 393 |  |  | 2022
623 | Azusa, CA- 809 N Azusa Ave (Target) | 809 N Azusa Ave | Azusa | 91702 | Los Angeles County | 4. Preliminary Design | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2020-10-19 |  |  |  | 2020-10-09 | 2020-10-09 |  |  | 1 | 1 | 2020-10-12
624 | Temecula, CA- 27548 Ynez Rd Suite I-9 (Town Center) | 27548 Ynez Rd Suite I-9 | Temecula | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3289660 | 2007090 |  | 2024-11-15 | 24 | YES | Level 3 | true | 2022-04-04 | 2022-04-12 | 7 | 7 | 2023-03-14 | 2021-11-04 | 108 | 108 | -340 |  | 2021-11-10 | 2021-11-29 | 2021-12-04 | 15 | 15 | 5 | 5 | 2023-03-20 | 5 | 5 | 2023-03-21 |  | 2023-05-04 | 2023-05-12 | 40 | 40 | 2023-05-17 | [60 empty] | 2021-11-29
625 | Whittier, CA- 6531 Greenleaf Ave (Lot 12) | 6531 Greenleaf Ave | Whittier | 90601 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | true | 2020-10-22 | 2020-12-23 | 42 | 42 | 2020-10-19 | 2020-10-19 | 45 | 45 | 1 | 1 | 2020-10-19
626 | Beverly Hills, CA- 350 S Beverly Dr | 350 S Beverly Dr | Beverly Hills | 90212 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-10-26 | 2020-11-17 | 16 | 16 | 2020-10-21 | 2020-10-23 | 17 | 17 | 3 | 3
627 | Lee Vining | 133 Vista Point Drive | Lee Vining | 93541 | Mono County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  | 3140417 | 1890002 | 2071816 |  | 6 | YES | Level 3 | NO | 2020-11-02 | 2020-12-07 | 23 | 23 | 2020-10-14 | 2020-10-14 | 36 | 36 | 1 | 1 | 2020-10-19 | 2020-10-19 | 2020-10-23 | 4 | 4 | 5 | 5 | 2022-12-01 | 535 | 535 | 2022-12-01 | 2022-12-05 | 2023-01-26 | 2023-04-10 | 91 | 91 | 2023-04-10 | 2023-04-24 | 11 | 11 | 2023-04-24 | 2023-06-12 | 35 | 35 | 2023-06-12 | 1 | 1 | 2023-06-26 | 2023-09-28 | 2023-06-26 | 2023-07-11 | 11 | 11 | 55 | 55 | 11 | 11 | 2023-04-26 | 2023-05-12 | 2023-05-30 | -33 |  | 12 | 12 | 24 | 24 | [6 empty] | 2023-05-12 |  | 2023-07-11 | [5 empty] | 2023-08-01 | 2023-10-25 | 2023-11-14 | 75 | 75 | 2023-07-19 | 2023-10-24 | 2023-10-24 | 2023-07-26 | 6 | 6 | 2023-11-14 | 16 | 16 | 2023-11-14 | 16 | 16 | 2023-10-24 | 2023-11-14 | 84 | 84 | 16 | 16 | 2023-11-14 | 2023-11-23 | 7 | 7 | 2024-01-04 | 34 | 34 | 2024-01-04 | 2024-01-08 | 3 | 3 | 811 | 811 | 277 | 277 | 2024
628 | Alhambra | 1411 S Garfield Ave | Alhambra | 91803 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Alhambra |  |  | 2978330 | 1795849 |  |  | 2 |  |  | true |  |  |  |  | 2020-10-05 | 2020-10-05 |  |  | 1 | 1 | 2020-10-05 | 2020-10-07 | 2020-10-17 | 3 | 3 | 8 | 8 |  |  |  | 2020-10-28 |  | 2020-11-04 | 2020-12-09 |  |  | 2020-12-09 | 2020-12-09 | 1 | 1 |  | 2020-01-06 | -235 |  | 2020-01-06 | 1 | 1 | [50 empty] | 2021-08-20 | 2021-08-30 |  |  | 7 | 7 | [7 empty] | 2021-10-15 |  |  |  | 260 | 260 |  |  | 2021
629 | Santa Monica, CA- 1232 Harvard St | 1232 Harvard St | Santa Monica | 90404 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2020-10-28 | 2020-11-17 | 14 | 14 | 2020-10-28 | 2020-10-28 | 14 | 14 | 1 | 1 |  |  | 2021-03-09
630 | Santa Barbara Carrillo St | 32-36 W Carrillo St | Santa Barbara | 93101 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura |  |  | 3157067 | 1978717 |  | 2024-06-20 | 27 | NO | Level 3 | true | 2020-11-06 | 2020-12-24 | 32 | 32 | 2020-11-06 | 2020-11-06 | 32 | 32 | 1 | 1 | 2020-12-02 | 2020-12-04 | 2020-12-18 | 18 | 18 | 11 | 11 | 2021-08-23 | 198 | 198 | 2023-11-27 | 2023-11-27 | 2023-01-23 | 2023-01-23 | 357 | 357 | 2023-01-23 | 2023-01-23 | 1 | 1 | 2023-02-13 | 2023-01-05 | -12 |  | 2023-02-16 | 30 | 30 | 2024-02-02 |  | 2024-02-02 |  | 272 | 272 |  |  |  |  | 2022-05-16 | 2023-02-03 |  | -163 | [11 empty] | 2023-02-03
631 | Culver City, CA- 11924 Washington Blvd EV1 (Haven Culver) | 11924 Washington Blvd | Culver City | 90066 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3063272 | 1912677 |  |  | 8 |  |  | NO | 2020-11-12 | 2020-11-23 | 8 | 8 | 2020-11-10 | 2020-11-10 | 9 | 9 | 1 | 1 | 2020-11-13 | 2020-11-17 | 2020-12-14 | 5 | 5 | 18 | 18 |  |  |  | 2021-03-26 | 2021-03-26 | 2021-10-05 | 2021-09-09 |  |  | 2021-09-09 | 2021-09-15 | 5 | 5 | 2021-10-06 | 2021-10-07 | 17 | 17 | 2021-10-07 | 1 | 1 | 2021-11-03 | 2021-11-17 | 2021-11-03 | 2021-11-10 | 20 | 20 | 41 | 41 | 6 | 6 |  | 2021-10-25 | 2021-11-18 |  |  | 18 | 18 | [8 empty] | 2021-10-25 |  | 2021-11-18 | [23 empty] | 2022-01-21 |  |  |  |  | 2021-12-17 |  |  |  | 2022-02-15 | 41 | 41 | 2022-02-15 |  |  |  | 316 | 316 |  |  | 2022
632 | La Puente Pacific Place Shopping Center | 506 Workman Mill Rd | La Puente | 91746 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3005220 | 1804341 |  |  | 4 |  |  | NO | 2020-11-16 | 2020-11-20 | 5 | 5 | 2020-11-15 | 2020-11-16 | 5 | 5 | 1 | 1 | 2020-11-17 | [9 empty] | 2020-12-17 | 2020-12-23 | 2021-01-20 | 2021-01-25 |  |  | 2021-01-26 |  |  |  |  | 2021-02-23 |  |  | 2021-02-24 | 2 | 2 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 18 | 18 |  |  | 1 | 1 | 2021-03-10 | 2021-03-16 | 2021-03-22 | 12 | 12 | 5 | 5 | 9 | 9 | [6 empty] | 2021-03-16 |  | 2021-03-22 | [10 empty] | 2021-03-29 | [11 empty] | 2021-05-05 | 2021-05-19 | 38 | 38 | 11 | 11 | 2021-06-01 | 2021-06-30 | 22 | 22 | 2021-07-01 | 23 | 23 | 2021-07-01 |  |  |  | 157 | 157 |  |  | 2021
633 | Irvine Bowling Center | 3415 Michelson Dr | Irvine | 92612 | Orange County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 2991090 | 1795552 |  |  | 6 |  |  | NO | 2020-11-16 | 2020-12-04 | 13 | 13 | 2020-11-15 | 2020-11-16 | 13 | 13 | 1 | 1 | 2020-11-17 | [9 empty] | 2020-11-24 | 2020-11-30 | 2021-01-08 | 2021-01-27 |  |  | 2021-01-27 | 2021-02-01 | 4 | 4 |  | 2021-02-12 | 10 | 10 | 2021-02-16 | 2 | 2 |  | 2021-03-08 | 2021-03-08 | 2021-03-09 | 16 | 16 | 26 | 26 | 2 | 2 | 2021-03-16 | 2021-03-22 | 2021-04-12 | 22 | 22 | 16 | 16 | 20 | 20 | [6 empty] | 2021-03-08 |  | 2021-04-12 | [5 empty] | 2021-04-28 |  |  |  |  | 2021-02-24 | 2021-03-24 | 2021-04-01 | [10 empty] | 2021-04-27 | 45 | 45 |  |  | 2021-04-28 | 2021-05-26 | 21 | 21 | 2021-05-27 | 22 | 22 | 2021-05-27 |  |  |  | 133 | 133 |  |  | 2021
634 | Goleta FedEx | 495 S Fairview Dr | Goleta | 93117 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2020-11-15 | 2020-11-16 |  |  | 1 | 1
635 | Yorba Linda, CA- 18220 Yorba Linda Blvd (Packing House Square) | 18180 Yorba Linda Blvd | Yorba Linda | 92886 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3204007 | 1938637 |  |  | 8 | NO |  | true | 2020-11-17 | 2020-12-08 | 14 | 14 | 2020-11-16 | 2020-11-16 | 15 | 15 | 1 | 1 | 2020-11-17 |  | 2023-09-19 |  |  |  |  | 2021-11-04 | 245 | 245 | 2021-11-05 | 2021-11-08 | 2021-12-22 | 2022-02-01 | 59 | 59 | 2022-02-02 | 2022-02-18 | 13 | 13 | 2022-03-15 | 2022-03-19 | 20 | 20 | 2022-03-22 | 2 | 2 | 2022-03-22 | 2022-05-02 | 2022-03-22 | 2022-04-15 | 2 | 2 | 40 | 40 | 19 | 19 | 2022-03-07 | 2022-04-05 | 2022-06-09 | -10 |  | 47 | 47 | 68 | 68 | 2023-10-02 | 389 | 389 | 2023-11-01 | 23 | 23 | 2022-03-22 | 2022-03-22 | 2022-06-09 | 2023-11-01 | 411 | 411 | 390 | 390 | [5 empty] | 2023-06-20 |  |  | 2023-06-27 | 6 | 6 | [7 empty] | 2023-09-19 | 64 | 64 |  |  | 2023-11-02 | 2023-11-18 | 12 | 12 |  |  |  | 2023-11-20 |  |  |  | 760 | 760 | 516 | 516 | 2023
636 | Westlake Village, CA- 3825 Thousand Oaks Blvd (N Ranch Shopping Center) | 3825 Thousand Oaks Blvd | Westlake Village | 91350 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2020-11-19 | 2020-12-23 | 23 | 23 | 2020-11-17 | 2020-11-17 | 25 | 25 | 1 | 1 | 2020-11-20
637 | Ventura, CA- 42 N Chestnut St (Foster Library Parking Lot) | 42 N Chestnut St | Ventura | 93001 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | true | 2020-11-19 |  |  |  | 2020-11-17 | 2020-11-17 |  |  | 1 | 1 | 2020-11-20 |  | 2020-12-04
638 | Ventura, CA- 555 E Santa Clara St (Santa Clara parking Structure) | 555 E Santa Clara St | Ventura | 93001 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | true | 2020-11-19 |  |  |  | 2020-11-17 | 2020-11-17 |  |  | 1 | 1 |  |  | 2020-12-04
639 | Ventura, CA- 420 E Santa Clara St (Downtown Ventura Partners) | 420 E Santa Clara St | Ventura | 93001 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura | [9 empty] | NO | 2020-11-19 |  |  |  | 2020-11-17 | 2020-11-17 |  |  | 1 | 1 |  |  | 2020-12-04
640 | Chino Edison Ave | 4110 Edison Ave | Chino | 91710 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 2993470 | 1796915 |  |  | 3 |  |  | NO | 2020-10-28 |  |  |  | 2020-10-08 | 2020-10-13 |  |  | 4 | 4 | 2020-10-19 | 2020-10-23 | 2020-10-28 | 9 | 9 | 4 | 4 |  |  |  | 2020-12-02 | 2020-12-08 | 2021-01-07 | 2021-01-07 |  |  | 2021-01-08 | 2021-01-18 | 6 | 6 |  | 2021-02-10 | 17 | 17 | 2021-02-10 | 1 | 1 | 2021-02-10 | 2021-02-26 | 2021-02-10 | 2021-12-03 | 1 | 1 | 222 | 222 | 206 | 206 | 2021-06-16 | 2021-06-22 | 2021-09-29 | 89 | 89 | 70 | 70 | 74 | 74 | [6 empty] | 2021-02-10 |  | 2021-12-03 | [5 empty] | 2021-06-10 | 2021-06-14 | 2021-06-14 | 3 | 3 | [13 empty] | 2021-08-06 |  |  |  |  | 2021-11-10 | 2021-12-16 | 24 | 24 | 2021-12-17 | 25 | 25 | 2021-12-17 |  |  |  | 299 | 299 |  |  | 2021
641 | Santa Monica Los Amigos Park | 6th St (2420 1/2 6th St) | Santa Monica | 90405 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra |  |  | 3087750 | 1860822 |  |  |  | NO |  | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-15 | 2020-12-21 | 7 | 7 | 5 | 5 |  |  |  | 2021-05-10 | 2021-05-11 | 2021-06-09 | 2021-06-15 |  |  | 2021-06-23 | 2021-07-01 | 7 | 7 |  | 2021-08-23 | 37 | 37 | [22 empty] | 2022-03-14 | [11 empty] | 139 | 139 | [18 empty] | 2022-06-13 |  |  |  |  | 2022-06-15
642 | Santa Monica Joslyn Park | 7th Street | Santa Monica | 90405 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088090 | 1851531 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-15 | 2020-12-28 | 7 | 7 | 9 | 9 |  |  |  | 2021-05-11 | 2021-05-11 | 2021-06-10 | 2021-05-24 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-08-27 | 41 | 41
643 | Santa Monica Lot 9 Hill | Hill St | Santa Monica | 90405 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088120 | 1871869 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | [9 empty] | 2021-05-11 | 2021-05-11 | 2021-06-10 | 2021-07-07 |  |  | 2021-07-07 | 2021-07-08 | 2 | 2 |  | 2021-08-05 | 21 | 21
644 | Santa Monica Lot 26 Strand | Strand St | Santa Monica | 90405 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088130 | 1858897 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 |  |  | 2021-06-28 | [7 empty] | 2021-05-11 | 2021-05-11 | 2021-06-10 | 2021-06-08 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-09-17 | 55 | 55 | [22 empty] | 2024-03-25 | [11 empty] | 634 | 634
645 | Santa Monica Fairview Library | Ocean Park Place | Santa Monica | 90401 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088250 | 1858284 |  |  |  | NO |  | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-16 | 2020-12-28 | 8 | 8 | 8 | 8 |  |  |  | 2021-05-11 | 2021-05-12 | 2021-05-10 | 2021-06-09 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-08-25 | 39 | 39 |  |  |  |  | 2022-02-25 | [17 empty] | 2022-03-14 | [11 empty] | 137 | 137 | [23 empty] | 2022-06-21
646 | Santa Monica Montana Library | 17th St | Santa Monica | 90401 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088270 | 1863106 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-16 | 2020-12-28 | 8 | 8 | 8 | 8 |  |  |  | 2021-05-11 | 2021-05-12 | 2021-06-10 | 2021-06-14 |  |  | 2021-06-23 | 2021-07-01 | 7 | 7 |  | 2021-08-24 | 38 | 38
647 | Santa Monica California Ave | California Ave | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088280 | 1851534 |  |  |  | NO |  | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | [10 empty] | 2021-05-11 | 2021-05-12 | 2021-06-10 | 2021-05-27 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-07-14 | 9 | 9 | [22 empty] | 2022-03-15 | [11 empty] | 168 | 168 | [18 empty] | 2022-06-13 |  |  |  |  | 2022-06-15
648 | Santa Monica Idaho | Idaho St | Santa Monica | 90401 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088296 | 1948417 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-16 | 2020-12-28 | 8 | 8 | 8 | 8 |  |  |  | 2021-05-11 | 2021-05-12 | 2021-06-10 |  |  |  |  | 2022-01-19
649 | Santa Monica Reed Park | 7th St (1133 1/2 7th St) | Santa Monica | 90403 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088320 | 1878819 |  |  |  | NO |  | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | 2020-12-15 | 2020-12-29 | 7 | 7 | 10 | 10 |  |  |  | 2021-05-11 | 2021-05-13 | 2021-06-10 | 2021-07-26 |  |  | 2021-07-30 | 2021-08-02 | 2 | 2 |  | 2021-08-11 | 8 | 8 | [22 empty] | 2022-03-15 | [11 empty] | 148 | 148 | [18 empty] | 2022-06-10 |  |  |  |  | 2022-06-15
650 | Santa Monica Wilshire Blvd | Wilshire Blvd | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088360 | 1860218 | [5 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | [9 empty] | 2021-05-11 | 2021-05-13 | 2021-06-10 | 2021-06-08 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-08-30 | 42 | 42
651 | Santa Monica Lot 27 5th | 5th Street | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088380 | [6 empty] | NO |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | 2020-12-10 | [9 empty] | 2021-05-11 | 2021-05-13 | 2021-06-10
652 | Santa Monica Marine Park | Marine St | Santa Monica | 90401 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3088410 | 1862331 | [5 empty] | YES |  |  |  |  | 2020-12-03 | 2020-12-07 |  |  | 3 | 3 | [10 empty] | 2021-05-11 | 2021-05-17 | 2021-06-10 | 2021-06-09 |  |  | 2021-06-09 | 2021-07-01 | 17 | 17 |  | 2021-08-27 | 41 | 41
653 | Tustin, CA- 1705 Flight Way | 1705 Flight Way (New Address: 1773.5) | Tustin | 92782 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 3231349 | 1950079 |  |  | 12 | NO |  | NO | 2021-01-15 | 2021-05-14 | 84 | 84 | 2020-12-10 | 2020-12-10 | 108 | 108 | 1 | 1 | 2020-12-11 | 2022-09-16 | 2021-01-07 | 446 | 446 | -428 |  |  |  |  | 2022-01-03 | 2022-01-03 | 2022-02-15 | 2022-02-15 |  |  | 2022-02-15 | 2022-02-15 | 1 | 1 | 2022-03-09 | 2022-03-07 | 14 | 14 | 2022-03-09 | 3 | 3 | 2022-03-28 | 2022-04-27 | 2022-03-28 |  | 16 | 16 |  |  |  |  | 2022-03-21 | 2022-04-06 | 2022-05-24 | 11 | 11 | 35 | 35 | 47 | 47 | 2022-09-21 | 138 | 138 |  |  |  | 2022-03-28 | 2022-03-28 |  |  |  |  | 140 | 140 | 2022-09-27 | 2022-10-03 | 2022-10-03 | 5 | 5 | [13 empty] | 2022-09-16 |  |  |  |  | 2022-10-21 |  |  |  | 2022-12-18 | 38 | 38 | 2022-12-18 |  |  |  | 508 | 508 |  |  | 2022
654 | Tehachapi Surestay Hotel Best Western | 418 W Tehachapi Blvd | Tehachapi | 93561 | Kern County | 9. Complete | 52 - Tehachapi | North Valley | Ventura |  |  | 3024062 | 1817838 |  | 2023-05-05 | 12 |  |  | NO |  |  |  |  | 2020-12-09 | 2020-12-16 |  |  | 6 | 6 | [7 empty] | 2022-02-01 | 288 | 288 | 2022-02-01 | 2022-02-02 | 2022-03-04 | 2022-03-04 | 23 | 23 | 2022-03-05 | 2022-03-05 | 0 |  | 2022-03-21 | 2022-03-21 | 11 | 11 | 2022-03-22 | 2 | 2 | 2022-03-22 | 2022-07-06 | 2022-03-22 | 2022-03-23 | 2 | 2 | 13 | 13 | 2 | 2 | 2022-03-19 | 2022-04-28 | 2023-03-24 | -1 |  | 229 | 229 | 257 | 257 | 2022-04-05 | 11 | 11 | 2022-05-04 | 22 | 22 | 2022-03-22 | 2022-03-22 | 2023-03-24 | 2023-03-24 | 256 | 256 | 12 | 12 | [5 empty] | 2022-03-31 |  | 2023-01-30 | 2022-04-04 | 3 | 3 |  |  |  | 2023-02-06 | 6 | 6 | 2023-02-17 | 2023-02-17 | 225 | 225 | 1 | 1 | 2023-03-24 | 2023-05-18 | 40 | 40 | 2023-05-18 | 40 | 40 | 2023-05-18 |  |  |  | 616 | 616 | 329 | 329 | 2023
655 | Tehachapi Baymont by Wyndham | 500 E Steuber Rd | Tehachapi | 93561 | Kern County | 11. Cancelled | 52 - Tehachapi | North Valley | Ventura |  |  | 3030264 | 1812616 |  |  | 14 | NO |  | NO |  |  |  |  | 2020-12-09 | 2020-12-16 |  |  | 6 | 6 | 2022-02-01 |  | 2021-01-29 | [7 empty] | 2021-09-01 | 2021-09-04 | 2021-10-05 | 2021-10-05 |  |  |  | 2021-10-19 |  |  | 2021-11-12 | 2021-12-01 | 29 | 29 | 2021-12-01 | 1 | 1 | 2022-04-26 |  | 2022-04-26 | 2022-05-05 | 102 | 102 | 137 | 137 | 8 | 8 | 2021-11-30 | 2021-12-30 | 2022-07-22 | -2 |  | 143 | 143 | 164 | 164 | 2022-04-13 | 93 | 93 |  |  |  | 2021-12-30 | 2021-12-30 | 2022-07-22 |  |  |  | 93 | 93 | 2022-04-21 |  |  |  |  | 2021-12-21 | 2022-01-27 | 2022-02-02 | [10 empty] | 2023-02-01 | 282 | 282 |  |  | 2023-04-12 | [6 empty] | 2023-06-28 |  |  |  | 644 | 644 |  |  | 2023
656 | Simi Valley Amazon | 1757 Tapo Canyon Rd | Simi Valley | 93063 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2020-12-17 |  |  |  | 2020-12-17 | 2020-12-17 |  |  | 1 | 1
657 | South Gate Amazon | 9350 Rayo Ave | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2020-12-16 |  |  |  | 2020-12-16 | 2021-01-08 |  |  | 16 | 16 | 2021-01-11
658 | Mission Viejo Amazon | 25725 Jeronimo Rd | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO | 2020-12-16 | 2021-01-06 | 14 | 14 | 2020-12-16 | 2021-01-08 | -3 |  | 16 | 16 | 2021-01-11
659 | Valencia Amazon | 28820 Chase Place | Valencia | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO | 2020-12-17 |  |  |  | 2020-12-16 | 2020-12-17 |  |  | 2 | 2
660 | Camarillo Amazon | 3001-3175 Mission Oaks Blvd | Camarillo | 93012 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2020-12-16 |  |  |  | 2020-12-16 | 2020-12-16 |  |  | 1 | 1
661 | Santa Ana Rona Plaza | 2003 1st St | Santa Ana | 92703 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 3018010 | 1812008 |  |  |  | NO |  | NO | 2020-12-29 |  |  |  | 2020-12-28 | 2020-12-29 |  |  | 2 | 2 | 2020-12-29 | 2021-01-06 | 2021-01-11 | 6 | 6 | 4 | 4 |  |  |  | 2021-01-13 | 2021-01-13 | 2021-02-16 | 2021-02-26 |  |  | 2021-02-26 | 2021-03-02 | 3 | 3 |  | 2021-03-25 | 18 | 18 | 2021-03-25 | 1 | 1 | 2021-05-27 | 2021-09-27 | 2021-05-27 | 2021-10-19 | 46 | 46 | 163 | 163 | 101 | 101 | 2021-05-17 | 2021-07-02 |  | 38 | 38 |  |  |  |  | 2021-11-15 | 164 | 164 |  |  |  | 2021-05-27 | 2021-05-27 |  |  |  |  | 164 | 164
662 | Valencia Crossroads | 24290 Valencia Blvd | Valencia | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 3041859 | 1825836 |  |  | 6 |  |  | NO | 2020-12-29 |  |  |  | 2020-12-28 | 2020-12-29 |  |  | 2 | 2 | 2020-12-29 | 2021-01-07 | 2021-01-11 | 7 | 7 | 3 | 3 | 2021-03-23 | 59 | 59 | 2021-02-22 | 2021-02-23 | 2021-03-26 | 2021-03-22 | -2 |  | 2021-06-07 | 2021-06-09 | 3 | 3 | 2021-07-02 | 2021-07-06 | 19 | 19 | 2021-07-06 | 1 | 1 | 2021-08-03 | 2021-08-03 | 2021-08-03 | 2021-08-04 | 21 | 21 | 40 | 40 | 2 | 2 | 2021-06-28 | 2021-07-30 | 2021-12-21 | -6 |  | 99 | 99 | 122 | 122 | 2021-12-16 | 114 | 114 | 2021-12-17 | 2 | 2 | 2021-07-30 | 2021-07-30 | 2021-12-21 | 2021-12-21 | 99 | 99 | 114 | 114 | 2022-02-09 | 2022-02-22 | 2022-02-23 | 10 | 10 | 2021-12-07 | 2022-01-04 | [10 empty] | 2022-03-03 | 2022-03-30 | 79 | 79 | 20 | 20 | 2022-04-05 | 2022-05-03 | 21 | 21 | 2022-05-03 | 21 | 21 | 2022-05-03 |  |  |  | 340 | 340 | 282 | 282 | 2022
663 | Gardena Plaza | 1420 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3025680 | 1812119 |  |  | 4 |  |  | true | 2020-12-29 | 2021-01-15 | 13 | 13 | 2020-12-28 | 2020-12-29 | 13 | 13 | 2 | 2 | 2020-12-29 | 2021-01-06 | 2021-01-20 | 6 | 6 | 10 | 10 |  |  |  | 2021-01-28 | 2021-01-29 | 2021-03-02 | 2021-02-24 |  |  | 2021-02-24 | 2021-02-24 | 1 | 1 |  | 2021-03-03 | 6 | 6 | 2021-03-04 | 2 | 2 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-21 | 34 | 34 | 41 | 41 | 3 | 3 | 2021-03-12 | 2021-03-17 | 2021-04-15 | 8 | 8 | 22 | 22 | 25 | 25 | [6 empty] | 2021-03-17 |  | 2021-04-21 | [10 empty] | 2021-03-11 | 2021-05-26 | 2021-05-25 | [9 empty] | 2021-05-28 | 2021-06-17 | 70 | 70 | 14 | 14 | 2021-06-18 | 2021-07-20 | 22 | 22 | 2021-07-26 | 26 | 26 | 2021-07-26 |  |  |  | 146 | 146 |  |  | 2021
664 | Spring Plaza | 5900 Springs St EV | Long Beach | 90815 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra |  |  | 3055240 | 1838447 |  |  | 4 |  |  | NO | 2020-12-29 | 2021-01-22 | 17 | 17 | 2020-12-28 | 2020-12-29 | 17 | 17 | 2 | 2 | 2020-12-29 | 2021-01-06 | 2021-01-20 | 6 | 6 | 10 | 10 |  |  |  | 2021-03-15 | 2021-06-17 | 2021-04-19 | 2021-04-22 |  |  | 2021-04-23 | 2021-04-29 | 5 | 5 | 2021-05-20 | 2021-05-24 | 18 | 18 | 2021-05-24 | 1 | 1 | 2021-07-27 | 2021-10-26 | 2021-07-27 | 2021-08-09 | 45 | 45 | 71 | 71 | 10 | 10 | 2021-05-28 | 2021-06-08 | 2021-10-21 | 5 | 5 | 96 | 96 | 102 | 102 | 2021-07-29 | 47 | 47 | 2021-08-18 | 15 | 15 | 2021-06-08 | 2021-06-08 | 2021-10-21 | 2021-10-21 | 96 | 96 | 47 | 47 | 2021-08-17 | 2021-09-01 | 2021-09-01 | 12 | 12 | 2021-08-03 | [11 empty] | 2021-09-03 | 2021-09-27 | 39 | 39 | 16 | 16 | 2021-10-27 | 2021-12-02 | 24 | 24 | 2021-12-03 | 25 | 25 | 2021-12-03 |  |  |  | 236 | 236 |  |  | 2021
665 | Ralph's #269 - 11873 S. Hawthorne Blvd | 11873 Hawthorne Blvd | Hawthorne | 90250 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3034620 | 1824736 |  | 2024-11-21 | 6 |  |  | NO | 2020-12-29 | 2021-01-15 | 13 | 13 | 2020-12-28 | 2020-12-29 | 13 | 13 | 2 | 2 | 2020-12-29 | 2021-01-06 | 2021-01-20 | 6 | 6 | 10 | 10 | 2021-01-20 | 16 | 16 | 2021-02-10 | 2021-02-10 | 2021-03-16 | 2021-03-12 | 37 | 37 | 2021-03-15 | 2021-03-15 | 1 | 1 |  | 2021-04-09 | 20 | 20 | 2021-04-12 | 2 | 2 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2021-04-12 | 2 | 2 | 21 | 21 | 1 | 1 | 2021-04-09 | 2021-06-04 |  | 1 | 1 | [10 empty] | 2021-04-12
666 | Cypress Katella | 6400 Katella Ave | Cypress | 90630 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3051270 | 1831801 | [5 empty] | NO | 2020-12-31 | 2021-02-11 | 29 | 29 | 2020-12-30 | 2020-12-31 | 29 | 29 | 2 | 2 | 2021-01-05 | [9 empty] | 2021-03-09 | 2021-03-09 | 2021-04-14 | [14 empty] | 2021-05-03 | 2021-06-21 | [9 empty] | 2021-06-17 | 2021-07-07 |  |  | 14 | 14 |  |  | 2021-05-17 |  |  | 2021-07-12 | 39 | 39 | [31 empty] | 2021-08-27
667 | Claremont Star | 415 W Foothill Blvd | Claremont | 91711 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3041755 | 1842116 |  |  | 4 |  |  | NO | 2021-01-04 | 2021-01-12 | 7 | 7 | 2021-01-04 | 2021-01-04 | 7 | 7 | 1 | 1 | 2021-01-05 | 2021-01-08 | 2021-01-21 | 5 | 5 | 9 | 9 |  |  |  | 2021-02-22 | 2021-02-23 | 2021-03-26 | 2021-05-10 |  |  | 2021-05-10 | 2021-07-29 | 57 | 57 | 2021-08-19 | 2021-09-01 | 25 | 25 | 2021-09-01 | 1 | 1 | 2021-09-23 | 2021-10-14 | 2021-09-23 | 2021-10-11 | 16 | 16 | 52 | 52 | 13 | 13 | 2021-08-20 | 2021-09-14 | 2021-09-20 | -9 |  | 5 | 5 | 21 | 21 | 2021-09-23 | 16 | 16 |  |  |  | 2021-09-14 | 2021-09-14 | 2021-10-11 |  |  |  | 16 | 16 | 2021-11-29 | 2021-12-06 | 2021-12-14 | 12 | 12 | 2021-09-21 | [11 empty] | 2021-12-13 | 2021-12-27 | 66 | 66 | 10 | 10 | 2021-12-29 | 2022-02-07 | 28 | 28 | 2022-02-08 | 29 | 29 | 2022-02-08 |  |  |  | 277 | 277 |  |  | 2022
668 | Westminster | 6777 Westminster Blvd | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3029000 | 1818519 | [5 empty] | NO | 2021-01-04 | 2021-01-30 | 19 | 19 | 2021-01-04 | 2021-01-04 | 19 | 19 | 1 | 1 | 2021-01-05 | 2021-01-12 | 2021-01-13 | 7 | 7 | 2 | 2 |  |  |  | 2021-02-01 | 2021-02-01 | 2021-03-04 | 2021-03-12 |  |  | 2021-03-12 | 2021-03-14 | 1 | 1 |  | 2021-05-13 | 44 | 44 | 2021-05-13 | 1 | 1 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 5 | 5 |  |  |  |  | 2021-04-15 | 2021-06-03 |  | -21 | [11 empty] | 2021-05-19
669 | Towne Center East | 2450 Cherry Ave | Signal Hill | 90755 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2021-01-04 | 2021-01-15 | 10 | 10 | 2021-01-04 | 2021-01-04 | 10 | 10 | 1 | 1 | 2021-01-05 | 2021-01-07 | 2021-01-21 | 4 | 4 | 10 | 10
670 | Laguna Niguel Alicia | 27320 Alicia Pkwy | Laguna Niguel | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO | 2021-01-04 | 2021-01-26 | 16 | 16 | 2021-01-04 | 2021-01-04 | 16 | 16 | 1 | 1 | 2021-01-05 | 2021-01-11 | 2021-01-11 | 6 | 6 | 1 | 1
671 | Mission Viejo Marguerite | 26022 Marguerite Pkwy | Mission Viejo | 92692 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2021-01-04 |  |  |  | 2021-01-04 | 2021-01-04 |  |  | 1 | 1 | 2021-01-05
672 | Los Altos Market Center | 2080 N Bellflower Blvd | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2021-01-08 | 2021-02-17 | 27 | 27 | 2021-01-08 | 2021-01-07 | 28 | 28 | -2 |  | 2021-01-08 |  | 2022-01-24
673 | Fountain Valley, CA Talbert Ave Expansion | 11179 Talbert Ave | Fountain Valley | 92708 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2021-01-15 | 2021-02-07 | 15 | 15 | 2021-01-06 | 2021-01-11 | 19 | 19 | 4 | 4 | 2021-02-19 | 2021-02-25 | 2021-03-08 | 32 | 32 | 8 | 8
674 | Bishop Cottonwood Plaza | 785 N Main St | Bishop | 93514 | Inyo County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  | 3061700 | 1845305 |  |  | 6 |  |  | true | 2021-01-20 | 2021-02-09 | 15 | 15 | 2020-11-05 | 2020-11-05 | 63 | 63 | 1 | 1 | 2020-11-09 | 2020-11-18 | 2020-11-22 | 9 | 9 | 3 | 3 |  |  |  | 2021-03-23 | 2021-03-30 | 2021-05-07 | 2021-05-03 |  |  | 2021-05-03 | 2021-05-03 | 1 | 1 |  | 2021-06-23 | 37 | 37 | 2021-06-23 | 1 | 1 | 2021-07-19 | 2021-07-19 | 2021-07-19 | 2021-08-05 | 18 | 18 | 67 | 67 | 14 | 14 | 2021-07-21 | 2021-07-23 | 2021-08-23 | 20 | 20 | 22 | 22 | 24 | 24 | 2021-08-10 | 34 | 34 | 2021-08-24 | 11 | 11 | 2021-07-19 | 2021-07-19 | 2021-08-23 | 2021-08-24 | 27 | 27 | 34 | 34 | 2021-09-22 | 2021-11-05 | 2021-11-05 | 33 | 33 | 2021-08-27 | 2021-09-08 | [10 empty] | 2021-11-29 | 2021-12-02 | 66 | 66 | 4 | 4 | 2022-01-07 |  |  |  | 2022-05-06 | 84 | 84 | 2022-05-06 |  |  |  | 376 | 376 |  |  | 2022
675 | Moreno Valley Mall | 22500 Town Circle | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3039110 | 1863446 |  |  | 4 |  |  | NO | 2021-01-14 | 2021-02-16 | 22 | 22 | 2021-01-14 | 2021-01-14 | 22 | 22 | 1 | 1 | 2021-01-15 | [9 empty] | 2021-03-22 | 2021-03-23 | 2021-04-20 | 2021-06-15 |  |  | 2021-06-15 | 2021-06-18 | 4 | 4 | 2021-07-13 | 2021-07-19 | 21 | 21 | 2021-07-20 | 2 | 2 | 2021-08-12 | 2021-09-10 | 2021-08-12 | 2021-08-20 | 19 | 19 | 45 | 45 | 7 | 7 | 2021-08-13 | 2021-09-08 | 2021-11-17 | 20 | 20 | 50 | 50 | 67 | 67 | [6 empty] | 2021-08-12 |  | 2021-11-17 | [5 empty] | 2021-09-06 | 2021-09-08 | 2021-09-08 | 2 | 2 |  |  | 2021-09-13 | [9 empty] | 2021-09-13 | 2021-09-20 |  |  | 6 | 6 | 2021-09-21 |  |  |  | 2021-10-27 | 27 | 27 | 2021-10-27 |  |  |  | 200 | 200 |  |  | 2021
676 | Castaic | 31739 Castaic Rd | Castaic | 91384 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 59 - Valencia | North Valley | Ventura |  |  | 3072350 | [6 empty] | NO | 2021-01-20 | 2021-02-02 | 10 | 10 | 2021-01-07 | 2021-01-07 | 18 | 18 | 1 | 1 | 2021-01-08 | 2021-01-21 | 2021-01-22 | 10 | 10 | 2 | 2 |  |  |  | 2021-04-14 | 2021-04-22 | 2021-05-19
677 | Mojave Airport | 16999 Airport Blvd | Mojave | 93501 | Kern County | 11. Cancelled | 52 - Tehachapi | North Valley | Ventura |  |  | 3029759 | 1823006 |  | 2024-12-01 |  | NO |  | NO |  |  |  |  | 2021-01-12 | 2021-01-12 |  |  | 1 | 1 | 2021-01-13 |  | 2021-01-29 | [7 empty] | 2021-02-02 | 2021-02-09 | 2021-03-08 | 2021-03-08 |  |  | 2021-03-08 | 2021-03-15 | 6 | 6 |  | 2023-10-10 | 652 | 652 | 2021-04-13 | -631 |  | 2023-10-11 | 2021-05-14 | 2023-10-11 |  | 2 | 2
678 | San Bernardino | 555 W 2nd St | San Bernardino | 92401 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | YES | 2021-02-02 | 2021-02-08 | 5 | 5 | 2021-01-26 | 2021-01-26 | 10 | 10 | 1 | 1 | 2021-01-27 | 2021-02-05 | 2021-02-09 | 9 | 9 | 3 | 3
679 | Perris, CA Plaza de Perris 1688 | 1686 N Perris Blvd | Perris | 92571 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3255460 | 2128786 |  | 2024-01-19 | 12 | NO |  | NO | 2021-01-28 | 2023-03-22 | 542 | 542 | 2021-01-27 | 2021-01-27 | 543 | 543 | 1 | 1 | 2021-01-28 | 2021-06-21 | 2021-06-21 | 102 | 102 | 1 | 1 | 2022-02-14 | 265 | 265 | 2023-04-18 | 2023-04-19 | 2023-06-01 | 2023-06-01 | 329 | 329 | 2023-06-02 | 2023-06-28 | 19 | 19 | 2023-08-09 | 2023-08-09 | 30 | 30 | 2023-08-09 | 1 | 1 | 2023-08-22 | 2023-08-22 | 2023-08-22 | 2023-09-14 | 10 | 10 | 55 | 55 | 17 | 17 | 2023-07-21 | 2023-08-03 | 2023-08-21 | -14 |  | 13 | 13 | 22 | 22 | [6 empty] | 2023-08-03 |  | 2023-09-14 | [5 empty] | 2023-10-18 | 2023-10-26 | 2023-10-31 | 10 | 10 | 2023-09-29 |  |  | 2023-10-05 | 5 | 5 | [6 empty] | 2023-11-01 | 2023-11-09 | 30 | 30 | 7 | 7 | 2023-12-04 | 2024-01-16 | 29 | 29 | 2024-01-16 | 29 | 29 | 2024-01-16 |  |  |  | 749 | 749 | 485 | 485 | 2024
680 | Santa Clarita, CA- Valencia Market Place | 25888 The Old Rd | Stevenson Ranch | 91381 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO | 2021-02-01 | 2021-02-19 | 14 | 14 | 2021-01-29 | 2021-01-29 | 15 | 15 | 1 | 1
681 | Newport Beach, CA (Via Lido Plaza) | 3425 Via Lido | Newport Beach | 92663 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2021-02-01 | 2021-02-22 | 15 | 15 | 2021-02-01 | 2021-02-01 | 15 | 15 | 1 | 1 | 2021-02-01 |  | 2021-02-12
682 | Fontana - Slover Ave | 16880 Slover Ave | Fontana | 92337 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3041891 | 1826100 | 1863960 | 2024-06-01 |  | NO |  | true | 2021-02-01 | 2021-02-03 | 3 | 3 | 2021-02-01 | 2021-02-01 | 3 | 3 | 1 | 1 | 2021-02-02 | 2021-02-10 | 2021-02-15 | 8 | 8 | 3 | 3 |  |  |  | 2024-03-20 | 2024-03-20 | 2024-04-17 | 2021-03-22 |  |  | 2021-03-22 | 2022-04-07 | 265 | 265 | 2022-04-28 | 2022-04-27 | 15 | 15 | 2022-04-27 | 1 | 1 | 2022-05-20 | 2022-06-07 | 2022-05-20 | 2022-05-31 | 18 | 18 | 38 | 38 | 7 | 7 | 2021-07-29 | 2022-05-16 | 2023-02-08 | -188 |  | 186 | 186 | 386 | 386 | [6 empty] | 2022-05-16 |  | 2023-02-08 | [10 empty] | 2024-02-14
683 | Santa Barbara, CA - Paseo Nuevo | 716 Chapala St | Santa Barbara | 93101 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | NO | 2021-02-09 | 2021-04-23 | 53 | 53 | 2021-02-08 | 2021-02-09 | 53 | 53 | 2 | 2 | 2021-02-09
684 | Moreno Valley, CA Centerpoint Dr (Towngate Plaza) | 22880 Centerpoint Dr | Moreno Valley | 92553 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES | 2021-02-16 |  |  |  | 2021-02-12 | 2021-02-12 |  |  | 1 | 1 | 2021-02-16
685 | Yorba Linda, CA - 18601 Yorba Linda Blvd (Home Ranch) | 18601 Yorba Linda Blvd Suite EV | Yorba Linda | 92886 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3094304 | 1854363 |  |  | 8 | NO |  | true | 2021-02-17 | 2021-03-09 | 15 | 15 | 2021-02-16 | 2021-02-16 | 16 | 16 | 1 | 1 | 2021-02-17 | 2021-02-23 | 2021-03-08 | 6 | 6 | 10 | 10 |  |  |  | 2021-05-19 |  | 2021-08-02 | 2021-08-30 |  |  | 2021-08-30 | 2021-08-31 | 2 | 2 | 2021-09-22 | 2021-09-16 | 12 | 12 | 2021-09-17 | 2 | 2 | 2022-08-29 | 2021-11-17 | 2022-08-29 | 2022-09-07 | 240 | 240 | 257 | 257 | 7 | 7 | 2021-09-10 | 2021-09-29 | 2022-12-06 | -5 |  | 298 | 298 | 311 | 311 | 2023-03-07 | 369 | 369 | 2023-03-31 | 19 | 19 | 2021-09-29 | 2021-09-29 | 2022-12-06 | 2023-03-31 | 379 | 379 | 370 | 370 | [18 empty] | 2023-03-06 |  |  |  |  | 2023-03-29 |  |  |  | 2023-05-19 | 38 | 38 | 2023-05-19 |  |  |  | 572 | 572 |  |  | 2023
686 | Castaic, CA - 29461 Castaic Creek Plaza | 29461 The Old Rd | Castaic | 91384 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 3156056 | 1900572 |  |  | 12 |  |  | true | 2021-02-22 | 2021-04-08 | 34 | 34 | 2021-02-19 | 2021-02-19 | 35 | 35 | 1 | 1 | 2021-02-23 |  | 2021-03-03 | [7 empty] | 2021-08-20 |  | 2021-09-24 | 2021-11-23 |  |  | 2021-11-29 | 2021-12-03 | 5 | 5 | 2021-12-27 | 2022-01-07 | 25 | 25 | 2022-01-11 | 3 | 3 | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-05-23 | 3 | 3 | 119 | 119 | 93 | 93 |  | 2022-02-07 | 2022-02-28 |  |  | 15 | 15 | [5 empty] | 2022-07-07 |  |  | 2022-01-11 |  | 2022-05-23 | 2022-07-07 | [6 empty] | 2022-06-20 |  |  | 2022-04-11 | [17 empty] | 2022-07-01 |  |  |  | 2022-08-11 | 29 | 29 | 2022-08-11 |  |  |  | 374 | 374 |  |  | 2022
687 | West Hollywood | 7351 Santa Monica Blvd | West Hollywood | 90046 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2021-02-23 | 2021-03-11 | 13 | 13 | 2021-02-22 | 2021-02-22 | 14 | 14 | 1 | 1 |  |  | 2021-03-15
688 | Torrance, CA - Knox St | 1441 W Knox St | Torrance | 90501 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | true | 2021-02-25 |  |  |  | 2021-02-24 | 2021-02-24 |  |  | 1 | 1 | 2021-03-01
689 | Gardena Grove, CA Valley View St (Bridgecreek Business Park) | 2752 Valley View St | Garden Grove | 92845 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | true | 2021-03-25 | 2021-04-07 | 10 | 10 | 2021-02-25 | 2021-02-25 | 30 | 30 | 1 | 1 | 2021-02-25 | 2021-03-04 | 2021-03-09 | 6 | 6 | 4 | 4
690 | Santa Clarita, CA The Old Rd (Sunset Pointe Plaza) | 25269 The Old Rd | Santa Clarita | 91381 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2021-03-01 | 2021-04-08 | 29 | 29 | 2021-02-25 | 2021-02-25 | 31 | 31 | 1 | 1 | 2021-02-26 |  | 2021-03-03
691 | Ontario, CA - Ontario Mills Pkwy | 4450 Ontario Mills Parkway | Ontario | 91764 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | true | 2021-03-01 | 2021-03-19 | 15 | 15 | 2021-02-25 | 2021-02-25 | 17 | 17 | 1 | 1 | 2021-12-23 |  | 2021-12-28
692 | Ontario, CA - E C St | 127 E C St | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [6 empty] | 12 |  |  | NO | 2021-03-01 | 2021-03-16 | 12 | 12 | 2021-02-25 | 2021-02-25 | 14 | 14 | 1 | 1 | 2021-03-01 | [86 empty] | 2022-06-08 |  |  | 2022-06-08 |  |  |  | 325 | 325 |  |  | 2022
693 | Palm Desert | 69050 Vista Chino | Cathedral City | 92234 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | true | 2021-03-02 | 2021-03-12 | 9 | 9 | 2021-02-26 | 2021-02-26 | 11 | 11 | 1 | 1 | 2021-03-02 | 2021-03-10 | 2021-03-12 | 9 | 9 | 3 | 3
694 | Hungtington Beach Kimco Marina Village Phase 2 | 5922 Edinger Ave, Unit EV | Huntington Beach | 92649 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 3078650 | 1846505 |  |  | 7 |  |  | true | 2021-03-01 | 2021-03-19 | 15 | 15 | 2021-02-23 | 2021-02-25 | 17 | 17 | 3 | 3 | 2021-03-01 | [6 empty] | 2021-04-23 | 44 | 44 | 2021-04-26 | 2021-04-26 | 2021-05-28 | [8 empty] | 2021-06-01 |  |  | 2021-06-01 | 1 | 1 | 2021-06-01 | 2021-06-01 | [54 empty] | 2021-06-02 |  |  |  | 2021-06-23 | 16 | 16 | 2021-06-23 |  |  |  | 86 | 86 | 43 | 43 | 2021
695 | Cabazon Morongo Trail | 48540 Morongo Trail | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3069617 | 1846984 |  |  | 12 |  |  | YES | 2021-03-01 | 2021-03-03 | 3 | 3 | 2021-02-24 | 2021-02-24 | 6 | 6 | 1 | 1 | 2021-09-30 |  | 2021-04-07 | [7 empty] | 2021-04-09 | 2021-04-14 | 2021-05-16 | 2021-05-17 |  |  | 2021-05-17 | 2021-06-18 | 24 | 24 | 2021-07-09 | 2021-07-27 | 27 | 27 | 2021-07-27 | 1 | 1 | 2021-08-05 | 2021-08-05 | 2021-08-05 | 2021-08-09 | 8 | 8 | 36 | 36 | 3 | 3 | 2021-07-27 |  | 2021-09-20 | 1 | 1 |  |  | 39 | 39 | [8 empty] | 2021-09-20 | [10 empty] | 2021-09-23 | [11 empty] | 2021-11-24 | 2021-12-01 | 47 | 47 | 4 | 4 | 2021-12-01 |  |  |  | 2022-02-02 | 44 | 44 | 2022-02-02 |  |  |  | 238 | 238 |  |  | 2022
696 | Long Beach, CA - E Willow St | 101 E Willow St | Long Beach | 90806 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2021-03-01 | 2021-03-05 | 5 | 5 | 2021-02-26 | 2021-02-26 | 6 | 6 | 1 | 1 | 2021-03-01 |  | 2021-03-16
697 | Fairfield Inn & Suites Tustin | 15011 Newport Ave | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3059200 | 1837161 |  |  | 6 |  |  | NO | 2021-03-03 | 2021-03-16 | 10 | 10 | 2021-03-03 | 2021-03-03 | 10 | 10 | 1 | 1 | 2021-07-23 | 2021-03-15 | 2021-03-19 | 9 | 9 | 5 | 5 | 2021-03-23 | 15 | 15 | 2021-03-23 | 2021-03-24 | 2021-05-04 | 2021-05-18 | 41 | 41 | 2021-05-18 | 2021-05-19 | 2 | 2 |  | 2021-06-18 | 22 | 22 | 2021-06-18 | 1 | 1 | 2021-06-18 | 2021-06-18 | 2021-06-18 | 2021-06-21 | 1 | 1 | 23 | 23 | 2 | 2 | 2021-06-08 | 2021-06-10 | 2021-06-21 | -9 |  | 8 | 8 | 10 | 10 | [6 empty] | 2021-06-10 |  | 2021-06-21 | [5 empty] | 2021-09-01 | 2021-09-23 | 2021-09-24 | 17 | 17 | 2021-07-09 | 2021-08-31 | 2021-08-27 | [9 empty] | 2021-09-23 | 2021-10-08 | 65 | 65 | 12 | 12 | 2021-10-19 | 2021-12-03 | 31 | 31 | 2021-12-03 | 31 | 31 | 2021-12-03 |  |  |  | 192 | 192 | 178 | 178 | 2021
698 | Covina | 105 N Vincent Ave | Covina | 91722 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2021-03-03 | 2021-03-15 | 9 | 9 | 2021-03-03 | 2021-03-03 | 9 | 9 | 1 | 1 | 2021-07-23 |  | 2021-07-28
699 | Manhattan Village | 3200 N Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3126580 | 1931618 |  |  | 2 | NO |  | NO | 2021-03-03 | 2021-03-11 | 7 | 7 | 2021-03-03 | 2021-03-03 | 7 | 7 | 1 | 1 | 2021-03-05 | 2021-03-16 | 2021-11-23 | 10 | 10 | 177 | 177 |  |  |  | 2021-07-07 | 2021-07-08 | 2021-08-09 | 2021-08-09 |  |  |  | 2021-12-22 |  |  | 2022-01-20 | 2022-06-01 | 112 | 112 | 2022-06-01 | 1 | 1 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-02 | 1 | 1 | 113 | 113 | 2 | 2 | 2022-01-28 | 2022-07-19 | 2022-07-28 | -87 |  | 8 | 8 | 127 | 127 | [6 empty] | 2022-06-01 |  | 2022-07-28 | [5 empty] | 2022-10-12 |  | 2022-11-08 | 20 | 20 | 2022-08-02 |  |  | 2022-09-21 | 36 | 36 | [6 empty] | 2022-12-07 | 2023-01-09 | 111 | 111 | 24 | 24 | 2023-01-13 | 2023-02-05 | 15 | 15 | 2023-02-06 | 16 | 16 | 2023-02-06 |  |  |  | 488 | 488 |  |  | 2023
700 | Redondo Beach Plaza | 4001 Inglewood Ave | Redondo Beach | 90278 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-03-03 | 2021-03-03 |  |  | 1 | 1
701 | Albertsons Gardena #108 | 1735 W Artesia Blvd | Gardena | 90248 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3245560 | [6 empty] | NO | 2022-01-24 | 2022-01-28 | 5 | 5 | 2021-03-03 | 2022-03-08 | -27 |  | 256 | 256 | 2022-03-08 | 2022-03-25 | 2022-04-11 | 14 | 14 | 12 | 12 | 2022-01-21 | 225 | 225 | 2022-01-31 | 2022-02-02
702 | Ralphs Camarillo #741 | 674 Las Posas Rd | Camarillo | 93010 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3172610 | 1920602 | [5 empty] | NO | 2022-12-21 |  |  |  | 2022-11-09 | 2022-11-09 |  |  | 1 | 1 | 2022-11-14 | 2022-11-17 | 2022-11-18 | 6 | 6 | 2 | 2 |  |  |  | 2021-09-16 | 2021-09-21 | 2021-11-03 | 2021-11-03 |  |  | 2021-11-03 | 2021-11-05 | 3 | 3 | 2021-12-01 | 2021-12-14 | 25 | 25 | 2021-12-14 | 1 | 1
703 | Ventura Ralphs | 1776 S Victoria Ave | Ventura | 93003 | Ventura County | 10. Customer Hold | 39 - Ventura | North Coast | Ventura | [9 empty] | NO | 2021-03-03 |  |  |  | 2021-03-03 | 2021-03-03 |  |  | 1 | 1 | 2021-03-05 | 2021-03-08 | 2021-03-09 | 4 | 4 | 2 | 2
704 | Ralphs Fresh Fare Malibu #731 | 23841 Malibu Rd | Malibu | 90265 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-03-03 | 2021-03-19 | 13 | 13 | 2021-03-03 | 2021-03-03 | 13 | 13 | 1 | 1 | 2021-03-05 | 2021-03-11 | 2021-03-12 | 7 | 7 | 2 | 2
705 | Mountain Vista Plaza | 1425 Bradbury Ave | Duarte | 91010 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  |  | 3090777 | 1861541 |  |  | 10 | NO |  | NO | 2021-03-03 |  |  |  | 2021-03-03 | 2021-03-03 |  |  | 1 | 1 | 2021-03-05 | 2021-03-18 | 2021-04-02 | 12 | 12 | 12 | 12 |  |  |  | 2021-05-13 | 2021-05-18 | 2021-06-16 | 2021-06-15 |  |  | 2021-06-16 | 2021-06-18 | 3 | 3 | 2021-07-12 | 2021-07-12 | 16 | 16 | 2021-07-12 | 1 | 1 | 2021-08-04 | 2021-09-10 | 2021-08-04 | 2021-10-11 | 18 | 18 | 80 | 80 | 48 | 48 | 2021-07-16 | 2021-08-09 | 2021-11-18 | 5 | 5 | 72 | 72 | 88 | 88 | 2021-11-17 | 91 | 91 | 2022-06-08 | 140 | 140 | 2021-08-04 | 2021-08-04 | 2021-11-18 | 2022-06-08 | 213 | 213 | 91 | 91 | 2022-05-03 | 2022-05-31 | 2022-05-31 | 20 | 20 | 2022-02-18 |  |  | 2022-02-23 | 3 | 3 | [7 empty] | 2022-06-13 | 80 | 80 |  |  | 2022-06-17 | 2022-07-16 | 20 | 20 | 2022-07-24 | 25 | 25 | 2022-07-24 |  |  |  | 352 | 352 |  |  | 2022
706 | Mountain Meadow Plaza | 4227 1/2 Tierra Rejada Rd | Moorpark | 93021 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3069551 | 1850898 |  |  | 4 | NO |  | NO | 2021-03-03 | 2021-03-19 | 13 | 13 | 2021-03-03 | 2021-03-03 | 13 | 13 | 1 | 1 | 2021-03-05 | 2021-03-10 | 2021-03-11 | 6 | 6 | 2 | 2 |  |  |  | 2021-04-09 | 2021-04-13 | 2022-01-03 | 2021-06-17 |  |  | 2021-06-18 | 2022-01-28 | 154 | 154 | 2022-02-22 | 2022-01-31 | 2 | 2 | 2022-01-31 | 1 | 1 | 2022-02-24 |  | 2022-02-24 | 2022-02-28 | 18 | 18 | 21 | 21 | 3 | 3 | 2021-06-28 | 2021-07-22 |  | -149 | [5 empty] | 2022-03-31 | 43 | 43 |  |  |  | 2021-07-22 | 2021-07-22 |  |  |  |  | 43 | 43 | 2022-05-13 |  |  |  |  | 2022-03-17 | 2022-03-23 | 2022-05-03 | 2022-03-22 | 4 | 4 | [6 empty] | 2022-06-06 | 2022-06-14 | 63 | 63 | 7 | 7 | 2022-07-07 | 2022-08-21 | 32 | 32 | 2022-08-22 | 33 | 33 | 2022-08-22 |  |  |  | 373 | 373 |  |  | 2022
707 | Santa Ana - Centre on 17th | 2000 E 17th St | Santa Ana | 92705 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 3083945 | 1849305 |  |  | 8 |  |  | YES | 2021-03-03 | 2021-03-16 | 10 | 10 | 2021-03-03 | 2021-03-03 | 10 | 10 | 1 | 1 | 2021-03-05 | [9 empty] | 2021-05-04 | 2021-05-05 | 2021-06-08 | 2021-10-04 |  |  | 2021-10-04 | 2021-10-06 | 3 | 3 | 2021-11-01 | 2022-01-04 | 61 | 61 | 2022-01-05 | 2 | 2 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-06 | 2 | 2 | 63 | 63 | 2 | 2 | 2021-11-09 | 2021-11-11 | 2021-12-06 | -37 |  | 15 | 15 | 17 | 17 | 2022-01-21 | 12 | 12 | 2022-02-15 | 18 | 18 | 2021-11-11 | 2021-11-11 | 2022-01-06 | 2022-02-15 | 64 | 64 | 13 | 13 |  |  | 2022-04-22 |  |  | 2022-01-06 |  |  | 2022-01-10 | 3 | 3 | 2022-02-14 | 25 | 25 | 2022-04-14 |  |  | 2022-04-20 | 2022-05-04 | 83 | 83 | 11 | 11 | 2022-05-05 | 2022-06-19 | 31 | 31 | 2022-06-20 | 32 | 32 | 2022-06-20 |  |  |  | 329 | 329 |  |  | 2022
708 | South Bay Plaza | 2216 Sepulveda Blvd | Torrance | 90501 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | Walteria | Blocker 16kv | 3096312 | 1874506 |  |  | 4 | NO |  | NO | 2021-03-03 | 2021-03-17 | 11 | 11 | 2021-03-03 | 2021-03-03 | 11 | 11 | 1 | 1 | 2021-03-05 | 2021-03-17 | 2021-04-07 | 11 | 11 | 16 | 16 |  |  |  | 2021-05-21 | 2021-05-25 | 2021-06-22 | 2021-07-12 |  |  | 2021-07-12 | 2021-07-19 | 6 | 6 | 2021-08-09 | 2021-08-12 | 19 | 19 | 2021-08-12 | 1 | 1 | 2021-08-17 | 2021-09-10 | 2021-08-17 | 2021-08-28 | 4 | 4 | 30 | 30 | 9 | 9 | 2021-09-22 | 2021-09-29 | 2022-08-12 | 29 | 29 | 220 | 220 | 225 | 225 | 2021-11-17 | 68 | 68 | 2022-03-18 | 83 | 83 | 2021-08-17 | 2021-08-17 | 2022-08-12 | 2022-08-12 | 250 | 250 | 68 | 68 | [5 empty] | 2022-03-24 | [12 empty] | 2022-07-28 | 89 | 89 |  |  | 2022-08-17 | 2022-10-04 | 34 | 34 | 2022-10-04 | 34 | 34 | 2022-10-04 |  |  |  | 403 | 403 |  |  | 2022
709 | Investec -Downey Landing Shopping Center | 12076 – 12156 Lakewood Blvd | Downey | 90242 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES | 2021-03-03 | 2021-03-10 | 6 | 6 | 2021-03-03 | 2021-03-03 | 6 | 6 | 1 | 1 | 2021-03-05 |  | 2021-03-19
710 | Ontario Plaza | 920-1070 N Mountain Ave | Ontario | 91762 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2021-03-03 | 2021-03-15 | 9 | 9 | 2021-03-03 | 2021-03-03 | 9 | 9 | 1 | 1 | 2021-03-05 | 2021-03-23 | 2021-03-24 | 15 | 15 | 2 | 2
711 | Culver City Ralphs | 10772 Jefferson Blvd | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 226676 | 1903279 |  |  |  | NO |  | true | 2021-03-03 | 2021-03-11 | 7 | 7 | 2021-03-03 | 2021-03-03 | 7 | 7 | 1 | 1 | 2021-03-05 |  | 2021-06-07 | [7 empty] | 2021-08-16 | 2021-08-17 | 2021-09-16 | 2021-09-16 |  |  | 2021-09-16 | 2022-08-02 | 221 | 221 | 2022-08-30 | 2022-09-01 | 23 | 23 | 2022-09-01 | 1 | 1 | 2022-12-01 |  | 2022-12-01 |  | 62 | 62 |  |  |  |  | 2022-08-25 |  |  | -6 | [36 empty] | 2021-06-05 | 2021-05-28 |  |  | -5
712 | Hampton by Hilton Inn LA-Orange County-Cypress | 10900 Yamaha Way | Cypress | 90630 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3084867 | 1863110 |  |  | 6 |  |  | YES | 2021-03-03 | 2021-04-08 | 27 | 27 | 2021-03-03 | 2021-03-03 | 27 | 27 | 1 | 1 | 2021-03-05 | 2021-03-15 | 2021-03-19 | 9 | 9 | 5 | 5 |  |  |  | 2021-05-05 | 2021-06-03 | 2021-06-08 | 2021-06-30 |  |  | 2021-07-06 | 2021-07-19 | 10 | 10 | 2021-08-09 | 2021-08-05 | 14 | 14 | 2021-08-09 | 3 | 3 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-30 | 16 | 16 | 31 | 31 | 3 | 3 | 2021-08-10 | 2021-09-03 | 2021-09-15 | 4 | 4 | 8 | 8 | 26 | 26 | 2021-10-06 | 42 | 42 | 2021-10-28 | 17 | 17 | 2021-08-26 | 2021-08-26 | 2021-09-15 | 2021-10-28 | 45 | 45 | 44 | 44 | 2022-01-19 | 2022-01-28 | 2022-01-28 | 8 | 8 | 2021-11-29 | 2021-11-29 |  | 2021-11-30 | 2 | 2 | [6 empty] | 2022-01-05 | 2022-02-11 | 53 | 53 | 27 | 27 | 2022-02-15 | 2022-03-21 | 24 | 24 | 2022-03-21 | 24 | 24 | 2022-03-24 |  |  |  | 268 | 268 |  |  | 2022
713 | Dunhil - Shoppes at Chino Hills | 4200 Chino Hills Pkwy | Chino Hills | 91709 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona |  |  | 3061760 | 1849326 | [5 empty] | YES | 2021-03-03 | 2021-03-15 | 9 | 9 | 2021-03-03 | 2021-03-03 | 9 | 9 | 1 | 1 | 2021-03-05 |  | 2021-03-23 | [7 empty] | 2021-03-25 | 2021-03-30 | 2021-05-07 | 2021-05-11 |  |  | 2021-05-11 | 2021-05-12 | 2 | 2 |  | 2021-06-06 | 17 | 17 | 2021-06-06 | 0 |  | 2021-06-29 | 2021-08-19 | 2021-06-29 | 2021-06-29 | 17 | 17 | 34 | 34 | 1 | 1 | 2021-06-25 | 2021-07-28 |  | 15 | 15 | [10 empty] | 2021-06-29
714 | Haagen Redondo Beach (RDB) | 302 Beryl St | Redondo Beach | 90277 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | Victoria | Carnelian 16kV | 3193949 | 1933199 |  |  | 6 | NO |  | NO | 2021-03-08 | 2021-03-29 | 16 | 16 | 2021-03-05 | 2021-03-05 | 17 | 17 | 1 | 1 | 2021-03-05 | 2021-03-10 | 2021-03-26 | 4 | 4 | 13 | 13 | 2021-10-13 | 156 | 156 | 2023-01-31 | 2023-02-01 | 2023-03-16 | 2022-08-04 | 204 | 204 | 2022-08-04 | 2022-08-04 | 1 | 1 | 2022-08-31 | 2023-02-24 | 141 | 141 | 2023-02-27 | 2 | 2 | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-03-06 | 2 | 2 | 147 | 147 | 6 | 6 | 2023-03-17 | 2023-03-23 | 2023-04-24 | 16 | 16 | 23 | 23 | 27 | 27 | 2023-05-25 | 64 | 64 | 2023-06-12 | 12 | 12 | 2023-02-27 | 2023-02-27 | 2023-04-24 | 2023-06-12 | 75 | 75 | 65 | 65 | [5 empty] | 2022-10-14 | 2023-03-20 |  | 2022-10-25 | 8 | 8 | 2023-03-27 | 105 | 105 |  |  |  | 2023-04-25 | 2023-05-10 | 144 | 144 | 12 | 12 | 2023-05-16 | [6 empty] | 2023-06-19 |  |  |  | 579 | 579 | 424 | 424 | 2023
715 | Redondo Beach Plaza | 4001 Inglewood Ave | Redondo Beach | 90278 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3150168 | 1898589 |  |  | 6 |  |  | true | 2021-03-03 |  |  |  | 2021-03-03 | 2021-03-03 |  |  | 1 | 1 | 2021-03-05 | [9 empty] | 2021-08-13 | 2021-08-13 | 2021-09-14 | 2021-09-14 |  |  | 2021-09-14 | 2021-09-14 | 1 | 1 |  | 2021-10-01 | 14 | 14 | 2021-10-11 | 7 | 7 | 2021-10-18 | 2021-11-29 | 2021-10-18 | 2021-10-19 | 12 | 12 | 26 | 26 | 2 | 2 | 2021-10-27 | 2021-11-05 | 2022-02-14 | 19 | 19 | 67 | 67 | 74 | 74 | [6 empty] | 2021-10-18 |  | 2022-02-14 | [5 empty] | 2022-04-08 | 2022-04-22 | 2022-04-25 | 12 | 12 | 2022-02-16 |  | 2022-04-20 | 2022-02-22 | 4 | 4 |  |  |  | 2022-04-28 | 7 | 7 | 2022-04-20 | 2022-05-06 | 57 | 57 | 13 | 13 | 2022-05-13 | [6 empty] | 2022-06-28 |  |  |  | 335 | 335 |  |  | 2022
716 | Santa Monica, CA - 700 Wilshire Blvd | 700 Wilshire Blvd | Santa Monica | 90401 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2021-03-05 | 2021-04-07 | 24 | 24 | 2021-03-03 | 2021-03-03 | 26 | 26 | 1 | 1 | 2021-03-05 |  | 2021-03-31
717 | Long Beach, CA -Shoreline Village Drive | 429 Shoreline Village Drive | Long Beach | 90802 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3307490 | [6 empty] | YES | 2021-03-05 | 2021-03-31 | 19 | 19 | 2021-03-03 | 2021-03-03 | 21 | 21 | 1 | 1 | 2022-04-12 | 2022-04-14 | 2021-03-29 | 283 | 283 | -265 |  | 2022-05-11 | 302 | 302 | 2022-05-11 | 2022-05-13 | 2022-06-27 | 2022-08-02 | 58 | 58 | 2022-08-02
718 | Long Beach, CA - 1990 Ximeno | 1990 Ximeno Ave | Long Beach | 90815 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2021-03-05 | 2021-03-31 | 19 | 19 | 2021-03-03 | 2021-03-03 | 21 | 21 | 1 | 1 | 2021-03-05 |  | 2021-03-31
719 | San Bernardino Block | 1930 S Waterman Ave | San Bernardino | 92408 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO |  |  | 3091020 | 1854716 |  |  |  | NO |  | NO |  |  |  |  | 2021-03-04 | 2021-03-04 |  |  | 1 | 1 | 2021-03-05 |  | 2021-03-24 | [7 empty] | 2021-05-13 | 2021-05-17 | 2021-06-14 | 2021-06-15 |  |  | 2021-06-15 | 2021-06-29 | 11 | 11 | 2021-07-21 | 2021-07-15 | 12 | 12 | 2021-07-16 | 2 | 2 | 2021-07-16 | 2021-08-24 | 2021-07-16 | 2021-08-24 | 2 | 2 | 40 | 40 | 28 | 28 | 2021-08-25 | 2021-09-16 | 2022-01-20 | 30 | 30 | 86 | 86 | 101 | 101 | [6 empty] | 2021-07-16 |  | 2022-01-20 | [10 empty] | 2022-02-22
720 | Ontario 4th Block | 2160 S Euclid Ave | Ontario | 91762 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-03-04 | 2021-03-04 |  |  | 1 | 1 | 2021-03-05 |  | 2021-03-25
721 | Buena Park | 6392 1/2 Beach Blvd | Buena Park | 90621 | Orange County | 10. Customer Hold | 48 - Fullerton | Orange | Saddleback |  |  | 3065910 | 2130019 |  | 2024-07-12 | 0 | NO |  | NO |  |  |  |  | 2021-03-04 | 2021-03-04 |  |  | 1 | 1 | 2021-03-05 | 2023-03-10 | 2023-03-10 | 510 | 510 | 1 | 1 | 2023-03-30 | 524 | 524 | 2023-03-30 | 2023-03-31 | 2023-05-12 | 2023-06-28 | 64 | 64 | 2023-06-28 | 2023-07-05 | 5 | 5 | 2023-07-27 | 2023-10-04 | 65 | 65 | 2023-10-04 | 1 | 1 | 2023-10-04 |  | 2023-10-04 | 2023-10-05 | 1 | 1 | 66 | 66 | 2 | 2 | 2023-10-14 | 2023-11-28 | 2024-01-11 | 8 | 8 | 31 | 31 | 60 | 60 | [6 empty] | 2023-10-04 |  | 2024-01-11
722 | Arcadia | 102 E Duarte Rd | Arcadia | 91006 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 27 - Monrovia | Metro East | Pomona |  |  | 3090590 | 1855541 | [5 empty] | NO |  |  |  |  | 2021-03-04 | 2021-03-04 |  |  | 1 | 1 | 2021-03-05 |  | 2021-04-01 | [8 empty] | 2021-05-18 | 2021-06-16 | 2021-06-16 |  |  | 2021-06-16 | 2021-07-06 | 14 | 14 | 2021-07-27 | 2021-07-29 | 18 | 18 | 2021-07-29 | 1 | 1 | 2021-08-24 |  | 2021-08-24 |  | 19 | 19 |  |  |  |  | 2021-11-22 | 2021-11-29 |  | 81 | 81 | [10 empty] | 2021-08-24
723 | Ventura Hydrogen R1 | 2121 E Harbor Blvd | Ventura | 93001 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 3076549 | 1853079 |  | 2025-01-10 | 0 | NO |  | NO |  |  |  |  | 2021-03-04 | 2021-03-04 |  |  | 1 | 1 | 2021-03-05 |  | 2021-03-22 |  |  |  |  | 2021-04-21 | 35 | 35 | 2023-09-19 | 2023-09-20 | 2023-10-31 | 2023-10-24 | 635 | 635 | 2023-10-24 | 2023-11-07 | 11 | 11 | 2023-12-04 | 2023-12-15 | 27 | 27 | 2023-12-18 | 2 | 2 | 2023-12-18 |  | 2023-12-18 | 2023-12-21 | 2 | 2 | 31 | 31 | 4 | 4 | 2024-01-03 | 2024-01-10 |  | 12 | 12 | [10 empty] | 2023-12-18 | [12 empty] | 2023-06-22
724 | San Gabriel Sunny Plaza | 529 E Valley Blvd | San Garbiel | 91776 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Alhambra |  |  | 3088437 | 1918051 |  |  | 3 | NO |  | true |  |  |  |  | 2021-03-08 | 2021-03-16 |  |  | 7 | 7 | 2021-03-16 | [9 empty] | 2021-05-11 | 2021-05-18 | 2021-09-02 | 2021-10-20 |  |  | 2021-10-20 | 2021-10-20 | 1 | 1 |  | 2021-10-22 | 3 | 3 | 2021-10-22 | 1 | 1 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2022-11-22 | 20 | 20 | 275 | 275 | 254 | 254 | [28 empty] | 2021-12-08 | [12 empty] | 2022-04-19 | 92 | 92 |  |  | 2022-08-02 | [6 empty] | 2022-06-27 |  |  |  | 331 | 331 |  |  | 2022
725 | Santa Monica Business Park | 3100 Ocean Park Blvd | Santa Monica | 90405 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [6 empty] | 6 |  |  | NO | 2021-03-17 | 2021-03-25 | 7 | 7 | 2021-03-17 | 2021-03-17 | 7 | 7 | 1 | 1 | 2021-03-25 | 2021-03-25 | 2021-03-30 | 7 | 7 | 4 | 4
726 | Inglewood | 300 W Century Blvd | Inglewood | 90303 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2021-03-17 |  |  |  | 2021-03-16 | 2021-03-17 |  |  | 2 | 2 | 2021-03-18
727 | Five Points Plaza (El Monte) | 12030 Valley Blvd | El Monte | 91732 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona |  |  | 3084028 | 1857347 |  |  | 4 |  |  | YES | 2021-03-17 | 2021-04-06 | 15 | 15 | 2021-03-16 | 2021-03-16 | 16 | 16 | 1 | 1 | 2021-03-18 |  | 2021-04-08 | [7 empty] | 2021-05-04 | 2021-05-11 | 2021-06-09 | 2021-06-09 |  |  | 2021-06-10 | 2021-12-16 | 131 | 131 | 2022-01-13 | 2022-01-11 | 18 | 18 | 2022-01-12 | 2 | 2 | 2022-01-27 | 2022-02-24 | 2022-01-27 | 2022-02-04 | 12 | 12 | 35 | 35 | 7 | 7 | 2022-01-19 | 2022-04-29 | 2022-05-19 | 6 | 6 | 15 | 15 | 86 | 86 | 2022-04-11 | 62 | 62 | 2022-05-18 | 28 | 28 | 2022-01-27 | 2022-01-27 | 2022-05-19 | 2022-05-19 | 80 | 80 | 63 | 63 | 2022-04-08 | 2022-04-25 | 2022-04-25 | 12 | 12 | 2022-02-21 |  |  | 2022-02-25 | 4 | 4 | [6 empty] | 2022-04-15 | 2022-05-02 | 50 | 50 | 12 | 12 | 2022-05-11 | 2022-06-13 | 23 | 23 | 2022-06-15 | 25 | 25 | 2022-06-15 |  |  |  | 317 | 317 |  |  | 2022
728 | Diamond Creek Village Shopping Center | 21080 Golden Springs | Diamond Bar | 91768 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3151610 | 1910997 |  |  | 4 | NO |  | NO | 2021-03-17 | 2021-04-01 | 12 | 12 | 2021-03-16 | 2021-03-16 | 13 | 13 | 1 | 1 | 2021-03-18 |  | 2021-03-30 | [7 empty] | 2021-08-16 | 2021-09-03 | 2021-11-22 | 2021-12-01 |  |  | 2021-12-01 | 2021-12-03 | 3 | 3 | 2021-12-28 | 2021-12-27 | 16 | 16 | 2021-12-28 | 2 | 2 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-02-04 | 16 | 16 | 44 | 44 | 14 | 14 | 2022-01-04 | 2022-02-11 | 2022-02-22 | 7 | 7 | 7 | 7 | 34 | 34 | 2022-02-24 | 41 | 41 | 2022-04-11 | 33 | 33 | 2022-01-18 | 2022-01-18 | 2022-02-22 | 2022-04-11 | 59 | 59 | 42 | 42 | [5 empty] | 2022-02-11 |  |  | 2022-02-15 | 3 | 3 | [6 empty] | 2022-05-25 | [5 empty] | 2022-06-22 | 2022-07-30 | 27 | 27 | 2022-07-31 | 27 | 27 | 2022-07-31 |  |  |  | 348 | 348 |  |  | 2022
729 | Smart and Final Center | 21608 S Vermont Ave | Torrance | 90502 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2021-03-16 |  |  |  | 2021-03-16 | 2021-03-16 |  |  | 1 | 1 | 2021-03-18 |  | 2021-04-02
730 | Garden Grove Torwn & Country | 12879 Harbor Blvd | Garden Grove | 92840 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2021-03-17 | 2021-04-07 | 16 | 16 | 2021-03-16 | 2021-03-16 | 17 | 17 | 1 | 1 | 2021-03-18
732 | Montclair East Shopping Center | 9197 Central Ave | Montclair | 91763 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3096273 | 1869262 |  |  | 4 |  |  | NO | 2021-03-22 | 2021-04-07 | 13 | 13 | 2021-03-22 | 2021-03-22 | 13 | 13 | 1 | 1 | 2021-03-29 |  | 2021-04-02 | [7 empty] | 2021-05-21 | 2021-05-27 | 2021-06-21 | 2021-06-28 |  |  | 2021-06-28 | 2021-06-28 | 1 | 1 | 2021-07-20 | 2021-07-21 | 17 | 17 | 2021-07-21 | 1 | 1 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 2021-08-19 | 22 | 22 | 38 | 38 | 1 | 1 | 2021-09-28 | 2021-09-30 | 2021-10-18 | 49 | 49 | 13 | 13 | 15 | 15 | 2021-12-16 | 103 | 103 | 2022-01-06 | 15 | 15 | 2021-08-19 | 2021-08-19 | 2021-10-18 | 2022-01-06 | 96 | 96 | 103 | 103 | [5 empty] | 2021-12-02 | 2022-02-08 |  | 2021-12-14 | 9 | 9 | [6 empty] | 2022-03-18 | 2022-04-05 | 86 | 86 | 13 | 13 | 2022-04-29 | [6 empty] | 2022-06-02 |  |  |  | 304 | 304 |  |  | 2022
733 | Downey Crossroads | 9501 Lakewood Blvd | Downey | 90242 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 3207804 | 1941182 |  |  |  | NO |  | true | 2021-11-12 | 2021-11-15 | 2 | 2 | 2021-03-25 | 2021-03-25 | 164 | 164 | 1 | 1 | 2021-03-29 | 2021-04-01 | 2021-04-08 | 6 | 6 | 6 | 6 |  |  |  | 2021-11-15 | 2021-11-16 | 2022-08-24 | 2022-08-29 |  |  | 2022-08-29 | 2022-08-31 | 3 | 3 | 2022-09-23 | 2022-09-06 | 4 | 4 | 2022-09-08 | 3 | 3 | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2022-10-07 | 23 | 23 | 27 | 27 | 2 | 2 | 2022-09-28 | 2023-04-04 |  | 17 | 17 | [10 empty] | 2022-10-06
734 | Mammoth Lakes Expansion | 437 Old Mammoth Rd | Mammoth Lakes | 93546 | Mono County | 11. Cancelled | 85 - Bishop/Mammoth | Rurals | Ventura | [9 empty] | YES | 2021-03-31 | 2021-04-06 | 5 | 5 | 2021-03-31 | 2021-03-31 | 5 | 5 | 1 | 1 | 2021-04-02
735 | Santa Barbara La Cumbre Plaza | 121 S Hope Ave | Santa Barbara | 93105 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3189976 | 1921934 |  |  |  | NO |  | YES | 2021-04-07 | 2021-04-14 | 6 | 6 | 2021-04-07 | 2021-04-07 | 6 | 6 | 1 | 1 | 2021-04-08 |  | 2021-04-14 | [7 empty] | 2021-10-15 | 2021-10-19 | 2022-06-23 | 2022-06-23 |  |  | 2022-06-23 | 2022-06-23 | 1 | 1 | 2022-07-18 | 2022-07-21 | 20 | 20 | 2022-07-21 | 1 | 1 | 2023-06-26 |  | 2023-06-26 |  | 236 | 236 |  |  |  |  | 2022-07-21 | 2022-08-01 | 2023-05-31 | 1 | 1 | 211 | 211 | 218 | 218 | [6 empty] | 2022-08-01
737 | Arcadia, CA - Baldwin Ave Westfield Santa Anita | 400 S Baldwin Ave | Arcadia | 91007 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3141030 | 1890739 | [5 empty] | YES | 2021-04-19 | 2021-05-17 | 21 | 21 | 2021-04-10 | 2021-04-10 | 26 | 26 | 0 |  | 2021-04-12 |  | 2021-04-30 |  |  |  |  | 2021-07-27 | 75 | 75 | 2021-07-29 | 2021-08-06 | 2021-08-31 | 2021-09-02 | 28 | 28 | 2021-09-02 | 2021-10-20 | 34 | 34 | 2021-11-12 | 2021-11-03 | 11 | 11 | 2021-11-04 | 2 | 2 | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2021-12-13 | 24 | 24 | 36 | 36 | 3 | 3
738 | Hemet, CA- 12899 S Sanderson (Page Plaza) | 1191 S Sanderson Ave | Hemet | 92545 | Riverside County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar |  |  | 3194520 | 1920437 | [5 empty] | YES | 2021-04-20 | 2021-05-06 | 13 | 13 | 2021-04-12 | 2021-04-12 | 19 | 19 | 1 | 1 | 2021-04-13 |  | 2021-05-06 | [7 empty] | 2021-10-21 | 2021-10-22 | 2021-12-08
739 | West Covina Emanate Queen of the Valley | 1115 S Sunset Ave | West Covina | 91790 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3279372 | 1999717 |  | 2024-08-01 |  |  |  | YES | 2021-05-07 |  |  |  | 2021-04-13 | 2021-04-13 |  |  | 1 | 1 | 2021-04-15 |  | 2021-05-02 |  |  |  |  | 2022-03-22 | 237 | 237 | 2022-03-29 | 2022-09-12 | 2022-06-07 | 2022-06-07 | 55 | 55 | 2022-06-13 | 2022-10-21 | 93 | 93 | 2022-06-22 | 2022-07-28 | -61 |  | 2022-07-29 | 2 | 2 | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-11-08 | 73 | 73 | 13 | 13 | 1 | 1
740 | Covina Emanante Intercommunity | 212 W San Bernardino Rd | Covina | 91723 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3189578 | 1930517 |  |  | 8 | NO | Level 3 | NO | 2021-05-07 |  |  |  | 2021-04-13 | 2021-04-13 |  |  | 1 | 1 | 2021-04-15 |  | 2021-05-02 |  |  |  |  | 2021-10-05 | 123 | 123 | 2021-10-13 | 2021-10-19 | 2021-12-03 | 2021-11-23 | 35 | 35 | 2021-12-01 | 2021-12-02 | 2 | 2 | 2021-12-27 | 2021-12-28 | 18 | 18 | 2021-12-28 | 1 | 1 | 2022-04-11 | 2022-04-14 | 2022-04-11 | 2022-04-12 | 73 | 73 | 91 | 91 | 2 | 2 |  | 2022-03-25 | 2022-04-29 |  |  | 26 | 26 |  |  | 2023-04-04 | 321 | 321 | 2023-08-09 | 90 | 90 | 2022-03-25 | 2022-03-25 | 2022-04-29 | 2023-08-09 | 349 | 349 | 321 | 321 | [5 empty] | 2022-04-12 | 2022-08-02 | 2022-09-21 | [10 empty] | 2023-04-30 | 266 | 266 |  |  | 2023-08-21 | 2023-09-18 | 20 | 20 | 2023-09-19 | 21 | 21 | 2023-09-20 | 2023-09-21 | 2 | 2 | 617 | 617 | 495 | 495 | 2023
741 | Glendora Foothill Presbyterian Hospital previously 250 S Grand Ave | 256 S Grand Ave | Glendora | 91741 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3203787 | 1942690 |  |  | 4 | NO | Level 1 | NO | 2021-05-07 |  |  |  | 2021-04-13 | 2021-04-13 |  |  | 1 | 1 | 2021-04-15 |  | 2021-10-26 |  |  |  |  | 2021-11-02 | 143 | 143 | 2021-11-05 | 2021-11-09 | 2021-12-17 | 2022-01-03 | 41 | 41 | 2022-01-03 | 2022-01-25 | 16 | 16 | 2022-02-17 | [6 empty] | 2022-03-01 | 2022-09-09 | [31 empty] | 2023-04-11 | 2023-04-25 | 2023-04-25 | 11 | 11 |  | 2022-09-28 | [10 empty] | 2023-05-11 | 2023-06-01 |  |  | 15 | 15 | 2023-07-11 | 2023-08-10 | 23 | 23 | 2023-08-10 | 23 | 23 | 2023-08-10 | 2023-08-11 | 2 | 2 | 589 | 589 | 447 | 447 | 2023
742 | Long Beach 7-Eleven | 602 E Anaheim St | Long Beach | 90813 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3078823 | 1877394 |  |  | 2 | NO |  | YES | 2021-04-26 | 2021-05-17 | 16 | 16 | 2021-04-16 | 2021-04-16 | 22 | 22 | 1 | 1 | 2021-04-19 | 2021-11-17 | 2021-11-22 | 150 | 150 | 4 | 4 |  |  |  | 2021-04-26 | 2021-04-27 | 2021-05-26 | 2021-05-17 | [7 empty] | 2021-05-21 |  |  | 2021-05-21 | 1 | 1 | 2021-05-21 | 2021-06-22 | 2021-05-21 | 2021-09-08 | 1 | 1 |  |  | 76 | 76 | 2021-07-19 | 2021-08-02 | 2021-08-30 | 40 | 40 | 21 | 21 | 31 | 31 | 2021-09-08 | 76 | 76 | 2021-09-09 | 2 | 2 | 2021-05-21 | 2021-05-21 | 2021-09-08 | 2021-09-09 | 77 | 77 | 76 | 76 | 2021-10-11 | 2021-11-01 | 2021-11-01 | 16 | 16 | 2021-09-02 | [12 empty] | 2021-11-22 | 56 | 56 |  |  | 2021-11-24 | 2022-01-04 | 27 | 27 | 2022-01-05 | 28 | 28 | 2022-01-05 |  |  |  | 182 | 182 |  |  | 2022
743 | Menifee, CA -Newport Rd | Corner of Calle Tomas and Newport Rd | Menifee | 92584 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES | 2021-04-21 | 2021-05-14 | 18 | 18 | 2021-04-16 | 2021-04-16 | 21 | 21 | 1 | 1 | 2021-04-19
744 | Culver City, CA - 6000 Sepulveda Blvd | 6000 Sepulveda Blvd | Culver City | 90230 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3243230 | 1958783 | [5 empty] | YES | 2021-04-12 | 2022-01-19 | 195 | 195 | 2021-04-12 | 2021-04-12 | 195 | 195 | 1 | 1 | 2021-04-15 |  | 2021-04-30 |  |  |  |  | 2022-01-25 | 199 | 199 | 2022-01-26 | 2022-01-27 | 2022-03-14 | 2022-03-07 | 29 | 29 | 2022-03-09
745 | Palmdale, CA - 849 W Rancho Vista | 849 W Rancho Vista Blvd (mtr address is 815 W Rancho Vista Blvd | Palmdale | 93551 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 3250936 | 1957317 |  |  | 24 |  |  | YES | 2021-04-21 | 2021-04-29 | 7 | 7 | 2021-04-19 | 2021-04-19 | 9 | 9 | 1 | 1 | 2021-04-21 | 2021-05-04 | 2021-05-14 | 12 | 12 | 9 | 9 | 2022-01-26 | 195 | 195 | 2022-02-09 | 2022-02-09 | 2022-03-25 | 2022-03-24 | 41 | 41 | 2022-03-24 | 2022-04-12 | 14 | 14 | 2022-05-03 | 2022-05-24 | 31 | 31 | 2022-05-24 | 1 | 1 | 2022-08-16 | 2022-08-16 | 2022-08-16 | 2022-12-12 | 59 | 59 | 169 | 169 | 81 | 81 | 2022-05-23 | 2022-06-03 | 2022-06-22 | -2 |  | 14 | 14 | 22 | 22 | 2022-09-22 | 85 | 85 | 2022-11-02 | 30 | 30 | 2022-06-03 | 2022-06-03 | 2022-12-12 | 2022-12-12 | 132 | 132 | 85 | 85 | [17 empty] | 2022-12-22 | 2022-12-22 |  |  | 1 | 1 | 2022-12-05 |  |  |  | 2023-01-27 | 39 | 39 | 2023-01-27 |  |  |  | 449 | 449 | 255 | 255 | 2023
746 | Fullerton, CA- 203 E Orangethorpe Suite EV | 203 E Orangethorpe Ave Suite EV | Fullerton | 92832 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3166143 | 1899686 |  |  | 16 |  |  | true | 2021-04-20 | 2021-05-11 | 16 | 16 | 2021-04-14 | 2021-04-14 | 20 | 20 | 1 | 1 | 2021-04-19 |  | 2021-04-26 |  |  |  |  | 2021-09-03 | 101 | 101 | 2021-09-08 | 2021-09-08 | 2021-10-06 | 2021-10-07 | 24 | 24 | 2021-10-07 | 2021-10-08 | 2 | 2 | 2021-11-01 | 2021-11-03 | 19 | 19 | 2021-11-03 | 1 | 1 | 2021-12-01 | 2021-12-15 | 2022-02-23 | 2022-03-15 | 75 | 75 | 107 | 107 | 15 | 15 | 2021-11-16 | 2021-12-03 | 2022-03-01 | 9 | 9 | 60 | 60 | 71 | 71 |  |  |  | 2022-07-18 |  |  | 2021-12-03 |  | 2022-03-15 | 2022-07-18 | [22 empty] | 2022-08-11 |  |  |  |  | 2022-08-29 |  |  |  | 2022-09-30 | 24 | 24 | 2022-09-30 |  |  |  | 371 | 371 | 271 | 271 | 2022
747 | South Gate, CA - Firestone Blvd | 5811 Firestone Blvd | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | YES | 2021-04-21 | 2021-05-10 | 14 | 14 | 2021-04-20 | 2021-04-20 | 15 | 15 | 1 | 1 | 2021-04-21 |  | 2021-05-03
748 | Castaic, CA - 31724 Castaic Rd (Denny's) | 31724 Castaic Rd | Castaic | 91384 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2021-04-21 | 2021-05-06 | 12 | 12 | 2021-04-20 | 2021-04-20 | 13 | 13 | 1 | 1 | 2021-04-21 |  | 2021-05-02
749 | Manhattan Beach - El Segundo | 1800 Rosecrans Ave Ste E | Manhattan Beach | 90266 | Los Angeles County | 5. Final Design | 44 - South Bay | Metro West | Alhambra |  |  | 3203280 | 1940819 |  | 2024-05-31 |  | NO | Level 3 | YES | 2021-04-29 | 2021-05-11 | 9 | 9 | 2021-04-20 | 2021-04-22 | 14 | 14 | 3 | 3 | 2021-04-23 | 2021-04-29 | 2021-04-29 | 6 | 6 | 1 | 1 |  |  |  | 2021-11-04 | 2021-11-05 | 2021-12-23 | 2021-12-22 |  |  | 2021-12-22 | 2022-02-09 | 34 | 34 | 2022-03-03 | 2022-03-18 | 27 | 27 | 2022-03-18 | 1 | 1 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-06-09 | 2 | 2 | 85 | 85 | 58 | 58 | 2023-08-09 | 2023-08-09 | 2023-12-26 | 354 | 354 | 96 | 96 | 96 | 96 | [6 empty] | 2022-03-21 |  | 2023-12-26
750 | Ventura - old address 3301 E Main Street | 3283 E Main St | Ventura | 93003 | Ventura County | 4. Preliminary Design | 39 - Ventura | North Coast | Ventura |  |  | 3634460 | 2218765 | 2217357 | 2024-09-01 | 8 | YES | Level 3 | YES | 2023-06-15 | 2023-09-06 | 58 | 58 | 2021-04-20 | 2021-04-20 | 602 | 602 | 1 | 1 | 2021-04-21 | 2021-04-22 | 2021-04-25 | 3 | 3 | 2 | 2 | 2023-11-14 | 651 | 651 | 2023-11-14 | 2023-11-14 | 2023-12-29 | 2024-02-06 | 56 | 56 | 2024-02-06 | 2024-03-13 | 26 | 26 | 2024-04-04 | [44 empty] | 2021-07-29
751 | Thousand Oaks - W Hillcrest Dr | 350 W Hillcrest Drive, EV2 | Thousand Oaks | 91360 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3698245 |  |  | 2024-10-24 | 12 | YES | Level 3 | YES | 2024-01-24 | 2024-03-01 | 27 | 27 | 2022-12-08 | 2023-02-20 | 260 | 260 | 51 | 51 | 2023-02-20 | 2023-02-22 | 2023-03-07 | 2 | 2 | 10 | 10 | 2024-03-21 | 325 | 325 | 2024-03-22 | 2024-03-22 | 2024-05-03
752 | Beaumont, CA - Oak Valley Pkwy | 1815 Oak Valley Pkwy | Beaumont | 92223 | Riverside County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3176120 | 1915576 |  | 2022-11-18 | 24 | NO |  | true | 2021-04-21 | 2021-05-03 | 9 | 9 | 2021-04-16 | 2021-04-16 | 12 | 12 | 1 | 1 | 2022-08-05 | 2021-05-20 | 2021-06-05 | 25 | 25 | 11 | 11 | 2021-09-21 | 110 | 110 | 2021-09-22 | 2021-09-23 | 2021-10-25 | 2021-10-27 | 27 | 27 | 2021-10-27 | 2021-12-03 | 25 | 25 | 2021-12-23 | 2022-01-20 | 33 | 33 | 2022-01-20 | 1 | 1 | 2022-01-31 | 2022-01-31 | 2022-01-31 | 2022-02-09 | 8 | 8 | 47 | 47 | 8 | 8 | 2022-01-18 | 2022-02-03 | 2022-04-05 | -3 |  | 43 | 43 | 55 | 55 | 2022-09-21 | 171 | 171 | 2022-10-31 | 29 | 29 | 2022-01-31 | 2022-01-31 | 2022-04-05 | 2022-10-31 | 192 | 192 | 171 | 171 | [6 empty] | 2022-08-29 | [10 empty] | 2022-10-10 | 2022-10-25 |  |  | 12 | 12 | 2022-10-26 |  |  |  | 2022-12-07 | 28 | 28 | 2022-12-07 |  |  |  | 414 | 414 | 305 | 305 | 2022
753 | Thousand Oaks, CA - Moorpark Rd | 173 N Moorpark Rd | Thousand Oaks | 91360 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-04-26 | 2021-05-26 | 23 | 23 | 2021-04-26 | 2021-04-26 | 23 | 23 | 1 | 1 | 2021-04-28 | 2021-05-06 | 2021-05-18 | 9 | 9 | 9 | 9
754 | Westlake Village, CA - Lindero Canyon Rd | 5776 Lindero Canyon Rd | Westlake Village | 91362 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | true | 2021-04-26 | 2021-05-26 | 23 | 23 | 2021-04-26 | 2021-04-26 | 23 | 23 | 1 | 1 | 2021-04-28
755 | Westlake Village, CA – 30805 Thousand Oaks Blvd | 30805 Thousand Oaks Blvd | Westlake Village | 91362 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2021-04-26 | 2021-05-26 | 23 | 23 | 2021-04-26 | 2021-04-26 | 23 | 23 | 1 | 1 | 2021-04-28 | 2021-05-06 | 2021-05-18 | 9 | 9 | 9 | 9
756 | Calabasas, CA – Mullholland Hwy | 22277 Mulholland Hwy | Calabasas | 91302 | Los Angeles County | 10. Customer Hold | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2021-04-26 | 2021-04-26 |  |  | 1 | 1
757 | Irvine - Alton Parkway | Alton Parkway | Irvine | 92571 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3176790 | 1924337 | [5 empty] | NO | 2021-04-27 |  |  |  | 2021-04-27 | 2021-04-27 |  |  | 1 | 1 | [10 empty] | 2021-09-23 | 2021-09-23 | 2021-10-08 | 2021-11-05 |  |  | 2021-11-05 | 2022-01-18 | 48 | 48
758 | Temecula - Winchester Rd | 40820 Winchester Rd | Temecula | 92591 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3158100 | [6 empty] | YES |  |  |  |  | 2021-04-27 | 2021-04-27 |  |  | 1 | 1 | 2021-04-22 | 2021-05-04 | 2021-05-07 | 6 | 6 | 4 | 4 |  |  |  | 2021-08-25 | 2021-08-26 | 2021-09-27
759 | Monterey Park, CA - Garvey Ave (99 Ranch) | 771 W Garvey Ave | Monterey Park | 91754 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona | [9 empty] | true | 2021-04-27 | 2021-05-07 | 9 | 9 | 2021-04-27 | 2021-04-27 | 9 | 9 | 1 | 1 | 2021-04-28 |  | 2021-05-04
760 | Rancho Las Palmas Shopping Center-Phase 2 | 42370 Bob Hope Dr | Rancho Mirage | 92270 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3151226 | 1909618 |  |  | 4 |  |  | true | 2021-04-29 | 2021-05-10 | 8 | 8 | 2021-04-29 | 2021-04-29 | 8 | 8 | 1 | 1 | 2022-01-12 | [9 empty] | 2021-08-16 | 2021-08-19 | 2021-10-21 | 2021-10-22 |  |  | 2021-10-22 | 2021-10-29 | 6 | 6 | 2021-11-22 | 2021-12-28 | 39 | 39 | 2021-12-28 | 1 | 1 | 2022-01-27 | 2022-02-24 | 2022-01-27 | 2022-02-04 | 22 | 22 | 66 | 66 | 7 | 7 | 2021-12-29 | 2022-01-24 | 2022-02-09 | 2 | 2 | 13 | 13 | 30 | 30 | [6 empty] | 2022-01-24 |  | 2022-02-09 | [5 empty] | 2022-02-17 | 2022-03-03 | 2022-03-04 | 11 | 11 | 2021-11-10 | [11 empty] | 2022-03-03 | 2022-03-18 | 87 | 87 | 12 | 12 | 2022-03-21 | 2022-05-16 | 41 | 41 | 2022-05-17 | 42 | 42 | 2022-05-17 |  |  |  | 265 | 265 |  |  | 2022
761 | El Segundo, CA -Maple Ave (AC Hotel) | 2130 E Maple Ave | El Segundo | 90245 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3162400 | [6 empty] | YES | 2021-05-03 | 2021-05-07 | 5 | 5 | 2021-04-30 | 2021-04-30 | 6 | 6 | 1 | 1 | 2021-05-03 | 2021-05-11 | 2021-05-13 | 8 | 8 | 3 | 3 |  |  |  | 2021-08-31
762 | Long Beach, CA - Atlantic Ave (Aldi Grocery) | 4580 Atlantic Ave | Long Beach | 90807 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2021-05-03 | 2021-05-20 | 14 | 14 | 2021-04-30 | 2021-04-30 | 15 | 15 | 1 | 1 | 2021-05-03 |  | 2021-05-13
763 | West Hollywood, CA - N La Peer Dr (La Peer Hotel) | 627 N La Peer Dr | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2021-05-03 | 2021-05-14 | 10 | 10 | 2021-04-30 | 2021-04-30 | 11 | 11 | 1 | 1 | 2021-05-03
764 | Long Beach, CA - 4040 Atlantic Ave | 4000-4040 Atlantic Ave | Long Beach | 90807 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2021-05-03 | 2021-05-24 | 16 | 16 | 2021-04-30 | 2021-04-30 | 17 | 17 | 1 | 1 | 2021-05-19 |  | 2021-05-13
765 | Long Beach, CA - 4280 Long Beach Blvd (Trader Joe) | 4280 Long Beach Blvd | Long Beach | 90807 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2021-05-03 | 2021-05-24 | 16 | 16 | 2021-04-30 | 2021-04-30 | 17 | 17 | 1 | 1 | 2021-05-19 |  | 2021-06-10
766 | Lancaster, CA - 2058 W Ave J | 2058 W Ave J | Lancaster | 93536 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | YES | 2021-05-03 | 2021-05-06 | 4 | 4 | 2021-05-03 | 2021-05-03 | 4 | 4 | 1 | 1 | 2021-05-18 |  | 2021-05-25
767 | Victorville, CA - 14598 7th St. Victorville, CA | 14598 7th St EV1 | Victorville | 92395 | San Bernardino County | 10. Customer Hold | 73 - Victorville | Rurals | SBRO |  |  | 3202620 | 1943800 |  |  | 16 |  |  | YES | 2021-05-03 | 2021-05-25 | 17 | 17 | 2021-05-03 | 2021-05-03 | 17 | 17 | 1 | 1 | 2021-05-18 | 2021-05-20 | 2021-05-21 | 14 | 14 | 2 | 2 | 2021-11-01 | 128 | 128 | 2021-11-04 | 2021-11-10 | 2022-01-13 | 2022-01-13 | 50 | 50 | 2022-01-13 | 2022-05-03 | 77 | 77 | 2022-05-24 | 2022-08-10 | 70 | 70 | 2022-08-10 | 1 | 1 | 2022-08-11 | 2022-08-11 | 2022-08-11 | 2022-08-19 | 2 | 2 | 77 | 77 | 7 | 7 |  |  | 2022-07-05 | [6 empty] | 2022-09-08 | 21 | 21 | 2022-10-26 | 35 | 35 |  |  | 2022-08-19 | 2022-10-26 |  |  | 21 | 21 | [18 empty] | 2022-10-31 |  |  |  |  | 2022-10-25 |  |  |  | 2022-11-30 | 24 | 24 | 2022-11-30 |  |  |  | 398 | 398 | 271 | 271 | 2022
768 | Buena Park Holiday Inn | 7000 Beach Blvd | Buena Park | 90620 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [9 empty] | YES | 2021-05-07 |  |  |  | 2021-03-31 | 2021-04-19 |  |  | 14 | 14 | 2021-04-21 | 2021-04-30 | 2021-05-04 | 10 | 10 | 3 | 3
769 | Newport Beach, CA - 401 Newport Center Dr (Fashion Island) | 401 Newport Center Dr | Newport Beach | 92660 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [6 empty] | 32 |  |  | true |  |  |  |  | 2023-12-28 | 2023-11-28 |  |  | -22 |  | 2023-11-28 | 2023-11-30 | 2023-12-05 | 3 | 3 | 4 | 4
770 | Irvine, CA - Lake Forest Drive (Irvine Best Buy) | 16171 Lake Forest Dr | Irvine | 92618 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2021-05-07 | 2021-05-21 | 11 | 11 | 2021-05-05 | 2021-05-05 | 13 | 13 | 1 | 1 | 2021-05-07
771 | Laguna Hills, CA - Moulton Parkway | 23702 Moulton Pkwy | Laguna Hills | 92653 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback |  |  | 3458505 | 2111079 |  | 2023-12-15 | 16 | YES | Level 2 | YES | 2023-01-10 | 2023-01-20 | 8 | 8 | 2023-03-23 | 2021-05-05 | 432 | 432 | -475 |  | 2021-05-07 | 2021-05-17 | 2021-05-21 | 9 | 9 | 5 | 5 | 2023-03-23 | 1 | 1 | 2023-03-23 | 2023-03-23 | 2023-05-05 | 2023-04-26 | 25 | 25 | 2023-04-26 | 2023-05-16 | 15 | 15 | 2023-06-07 | 2023-07-03 | 34 | 34 | 2023-06-01 | -23 | [11 empty] | 2023-06-16 | 2023-06-24 | 2023-06-29 | -12 |  | 4 | 4 | 10 | 10 | 2023-06-12 | 8 | 8 | 2023-08-28 | 55 | 55 | [6 empty] | -16 |  | 2023-07-27 | 2023-08-28 | 2023-10-04 | 49 | 49 | 2023-07-06 | 2023-09-15 |  | 2023-07-18 | 9 | 9 | [7 empty] | 2023-09-18 | 52 | 52 |  |  | 2023-10-05 | 2023-10-31 | 19 | 19 | 2023-11-01 | 20 | 20 | 2023-11-01 | 2023-11-03 | 3 | 3 | 157 | 157 | 157 | 157 | 2023
772 | Westminster, CA - 6777 Westminster Blvd (Westminster Center) | 6777 Westminster Blvd | Westminster | 92683 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback |  |  | 3672292 |  |  |  | 16 | YES | Level 3 | YES | 2024-01-10 | 2024-01-24 | 10 | 10 | 2023-08-30 | 2023-08-30 | 100 | 100 | 1 | 1 | 2023-08-31 | 2023-09-05 | 2023-09-19 | 4 | 4 | 11 | 11 | 2024-01-25 | 101 | 101 | 2024-02-01
773 | Temecula, CA - 41301 Margarita Rd (Bel Villaggio Center) R1 | 41277 Margarita Rd | Temecula | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3176010 | 2209930 | 2205457 | 2024-06-01 | 20 | YES | Level 3 | true | 2021-05-07 | 2021-05-26 | 14 | 14 | 2021-05-07 | 2021-05-07 | 14 | 14 | 1 | 1 | 2021-05-18 | 2023-01-09 | 2023-04-20 | 422 | 422 | 72 | 72 | 2023-10-18 | 619 | 619 | 2023-10-18 | 2023-10-20 | 2023-12-06 | 2023-12-05 | 33 | 33 | 2023-12-11 | 2023-12-13 | 3 | 3 | 2024-01-09 | 2024-01-18 | 24 | 24 | 2024-01-18 | 1 | 1 | 2024-01-18 | 2024-03-25 | 2024-01-18 |  | 1 | 1 |  |  |  |  | 2023-12-14 | 2023-12-27 | 2024-02-23 | -23 |  | 40 | 40 | 48 | 48 | 2024-03-26 | 48 | 48 |  |  |  | 2023-12-27 | 2023-12-27 |  |  |  |  | 48 | 48
774 | Temecula, CA - Rancho California Rd (Palomar Shopping Ctr) | 30640 Rancho CA Road | Temecula | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | true | 2021-05-10 | 2021-05-26 | 13 | 13 | 2021-05-10 | 2021-05-10 | 13 | 13 | 1 | 1 | 2021-05-18 |  | 2021-05-26
775 | Malibu, CA - 22523 Pacific Coast Hwy (Colony House Liquor) | 22523 Pacific Coast Hwy | Malibu | 90265 | Los Angeles County | 3. Active | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-05-07 |  |  |  | 2021-05-07 | 2021-05-07 |  |  | 1 | 1 | 2021-05-11 | 2021-05-18 | 2021-05-23 | 8 | 8 | 4 | 4
776 | Malibu, CA - 30745 Pacific Coast Hwy EV-1 (Trancas Country Market) | 30745 Pacific Coast Hwy EV-1 | Malibu | 90265 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3142110 | 1892814 |  | 2023-06-21 |  |  |  | YES | 2021-05-07 | 2021-05-26 | 14 | 14 | 2021-05-07 | 2021-05-07 | 14 | 14 | 1 | 1 | 2021-05-11 |  | 2021-05-23 |  |  |  |  | 2021-07-27 | 56 | 56 | 2023-01-31 | 2023-01-31 | 2023-03-15 | 2023-04-10 | 430 | 430 | 2023-04-10
777 | Malibu, CA - Malibu Rd | 23705 Malibu Rd | Malibu | 90265 | Los Angeles County | 3. Active | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-05-07 | 2021-05-26 | 14 | 14 | 2021-05-07 | 2021-05-07 | 14 | 14 | 1 | 1 | 2021-05-11 |  | 2021-05-23
778 | Malibu, CA - 30745 Pacific Coast Hwy EV-2 (Trancas Overflow) | 30745 Pacific Coast Hwy EV-2 | Malibu | 90265 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3142677 | 1892813 |  | 2024-10-23 |  | YES | Level 3 | YES | 2021-05-07 | 2021-05-26 | 14 | 14 | 2021-05-07 | 2021-05-07 | 14 | 14 | 1 | 1 | 2021-05-11 |  | 2021-05-23 |  |  |  |  | 2021-07-27 | 56 | 56 | 2023-01-31 | 2023-01-31 | 2023-03-15 | 2023-04-10 | 430 | 430 | 2023-04-10
779 | Huntington Beach, CA - 19640 Beach Blvd (Newland Center) | 19640 Beach Blvd | Huntington Beach | 92648 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | true | 2021-05-14 | 2021-06-02 | 13 | 13 | 2021-05-12 | 2021-05-12 | 15 | 15 | 1 | 1 | 2021-05-13 |  | 2021-06-05 | [74 empty] | 2021-06-05 | 2021-05-27 |  |  | -6
780 | La Canada Flintridge, CA - 920 Foothill Blvd (Sprouts) | 920 Foothill Blvd | La Canada Flintridge | 91011 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona | [9 empty] | YES | 2021-05-06 | 2021-05-21 | 12 | 12 | 2021-05-03 | 2021-05-03 | 15 | 15 | 1 | 1 |  | 2021-06-01 | 2021-06-07 | 21 | 21 | 5 | 5
781 | Victorville, CA - 11604 Amargosa Rd | 11604 Amargosa Rd EV1 | Victorville | 92392 | San Bernardino County | 9. Complete | 73 - Victorville | Rurals | SBRO |  |  | 3176303 | 1928080 |  |  | 16 |  |  | NO | 2021-05-13 | 2021-05-26 | 10 | 10 | 2021-05-11 | 2021-05-11 | 12 | 12 | 1 | 1 | 2021-05-12 | 2021-05-20 | 2021-05-21 | 8 | 8 | 2 | 2 | 2021-09-20 | 92 | 92 | 2021-09-22 |  | 2021-11-17 | 2021-12-02 | 51 | 51 | 2021-12-03 | 2021-12-15 | 9 | 9 | 2022-01-10 | 2022-02-25 | 50 | 50 | 2022-02-25 | 1 | 1 | 2022-08-11 |  | 2022-08-11 | 2022-08-23 | 118 | 118 | 175 | 175 | 9 | 9 | 2022-01-14 | 2022-09-06 | 2022-09-09 | -29 |  | 4 | 4 | 166 | 166 | 2022-11-02 | 176 | 176 | 2022-12-22 | 34 | 34 | 2022-08-11 | 2022-08-11 | 2022-09-09 | 2022-12-22 | 92 | 92 | 176 | 176 |  |  | 2022-10-14 | [14 empty] | 2022-11-16 | 2022-12-06 |  |  | 13 | 13 | 2022-12-05 |  |  |  | 2023-01-09 | 26 | 26 | 2023-01-09 |  |  |  | 420 | 420 | 329 | 329 | 2023
782 | Tustin - 17th St - Oak Tree Tustin LLC | 17612 17th St | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3118549 | 1868308 |  |  | 4 | NO |  | YES |  |  |  |  | 2021-05-13 | 2021-05-13 |  |  | 1 | 1 | 2021-05-14 |  | 2021-06-18 | [7 empty] | 2021-06-24 | 2021-06-25 | 2021-07-29 | 2021-09-01 |  |  | 2021-09-01 |  |  |  |  | 2021-10-28 |  |  | 2021-10-28 | 1 | 1 | 2021-11-02 | 2021-11-04 | 2021-11-02 |  | 4 | 4 | [13 empty] | 2022-01-05 | 46 | 46 | 2022-01-11 | 5 | 5 | [6 empty] | 46 | 46 | [5 empty] | 2021-09-16 | [12 empty] | 2022-01-05 | 76 | 76 |  |  | 2022-01-06 | 2022-01-26 | 14 | 14 | 2022-01-26 | 14 | 14 | 2022-01-26 |  |  |  | 177 | 177 |  |  | 2022
783 | Buena Park, CA Artesia BLVD | 6050 Artesia Blvd | Buena Park | 90622 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | YES | 2021-05-14 | 2021-06-01 | 12 | 12 | 2021-05-13 | 2021-05-13 | 13 | 13 | 1 | 1 | 2021-05-14 | 2022-11-15 | 2022-12-05 | 381 | 381 | 13 | 13 | [70 empty] | 2021-06-05 | 2021-05-27 |  |  | -6
784 | Lawndale, CA (Smart & Final) | 15215U Hawthorne Blvd | Lawndale | 90260 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 44 - South Bay | Metro West | Alhambra |  |  | 3188982 | 1930480 |  |  | 8 | NO |  | YES | 2021-05-17 | 2021-05-20 | 4 | 4 | 2021-05-14 | 2021-05-14 | 5 | 5 | 1 | 1 |  |  | 2021-06-05 |  |  |  |  | 2021-10-06 | 101 | 101 | 2021-10-13 | 2021-10-15 | 2021-12-02 | 2021-12-01 | 38 | 38 | 2021-12-01 | 2021-12-15 | 11 | 11 | 2022-01-14 | 2022-01-28 | 31 | 31 | 2022-01-28 | 1 | 1 | 2022-08-04 | 2022-01-28 | 2022-01-28 | 2023-02-01 | 1 | 1 | 286 | 286 | 256 | 256 | 2022-01-28 | 2022-03-09 | 2023-03-13 | 1 | 1 | 256 | 256 | 283 | 283 | [6 empty] | 2022-01-28 |  | 2023-03-13 | [5 empty] | 2023-05-17 | 2023-06-07 | 2023-06-07 | 15 | 15 | [12 empty] | 2021-06-05 | 2023-06-13 |  |  | 510 | 510 | 2023-07-13 | 2023-08-14 | 23 | 23 | 2023-09-02 | 37 | 37 | 2023-09-02 |  |  |  | 582 | 582 | 482 | 482 | 2023
785 | Costa Mesa, CA - S Coast Dr (IKEA) | 3201 Susan St, #EM, Costa Mesa, CA 92626 | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3198040 | 1944114 |  | 2024-05-31 |  | NO |  | true | 2021-05-20 | 2021-06-02 | 9 | 9 | 2021-05-18 | 2021-05-18 | 11 | 11 | 1 | 1 | 2021-05-20 |  | 2021-06-10 |  |  |  |  | 2021-10-13 | 104 | 104 | 2021-10-27 | 2021-10-28 | 2021-12-14 | 2022-01-20 | 67 | 67 | 2022-01-20 | 2022-02-11 | 17 | 17 | 2022-03-07 | 2022-06-10 | 84 | 84 | 2022-06-10 | 1 | 1 |  |  | 2022-06-23 | 2022-11-01 | 10 | 10 | 184 | 184 | 92 | 92 |  | 2022-08-09 | 2023-04-14 |  |  | 173 | 173 |  |  | 2023-09-05 | 313 | 313 |  |  |  | 2022-06-23 | 2022-06-23 | 2023-04-14 |  |  |  | 313 | 313
786 | Palm Desert CAL State SB Palm Desert Campus | 37500 Cook St | Palm Desert | 92211 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2021-05-19 | 2021-05-20 |  |  | 2 | 2 | 2021-05-21
787 | Valencia, CA - 27634 The Old Rd (Valencia Crossing) | 27634U The Old Rd | Valencia | 91355 | Los Angeles County | 4. Preliminary Design | 59 - Valencia | North Valley | Ventura |  |  | 3248470 | 1955003 |  |  | 8 |  |  | YES | 2021-05-19 | 2021-06-09 | 15 | 15 | 2021-05-18 | 2021-05-18 | 16 | 16 | 1 | 1 | 2021-05-21 |  | 2021-05-26 |  |  |  |  | 2022-02-02 | 179 | 179 | 2022-02-04 | 2022-02-04 | 2022-03-22 | 2022-03-22 | 34 | 34 | 2022-03-23 | 2022-03-28 | 4 | 4 | 2022-04-18 | 2022-04-28 | 24 | 24 | 2022-04-28 | 1 | 1 | 2022-04-28 | 2022-05-20 | 2022-04-28 |  | 1 | 1 |  |  |  |  | 2022-04-26 | 2022-05-26 | 2022-08-08 | -3 |  | 51 | 51 | 73 | 73 | 2022-09-14 | 97 | 97 | 2022-09-22 | 7 | 7 | 2022-04-28 | 2022-04-28 |  |  |  |  | 97 | 97 | 2022-09-13 | [17 empty] | 2022-11-07 |  |  |  |  | 2022-11-10 |  |  |  | 2022-12-09 | 19 | 19 | 2022-12-09 |  |  |  | 394 | 394 | 216 | 216 | 2022
788 | Covina, CA - S Barranca Ave (Ikea) R1 | 854 S Barranca Ave, Suite EV | Covina | 91723 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3324952 | 2012601 |  | 2024-05-08 |  | NO |  | YES | 2021-05-25 | 2021-06-09 | 11 | 11 | 2021-05-20 | 2021-05-21 | 13 | 13 | 2 | 2 |  |  | 2021-06-01 |  |  |  |  | 2024-01-19 | 672 | 672 | 2024-02-20 |  | 2024-04-22 | [14 empty] | 2023-08-21 | 2022-09-28 | 2023-08-21 | [8 empty] | 2022-09-20 | 2023-05-01 |  |  | 155 | 155 |  |  | 2023-09-27 | [5 empty] | 2022-09-20 | 2022-09-20 | [11 empty] | 2023-10-04
789 | Ikea Carson (E Dominguez St) | 20700 S Avalon Blvd | Carson | 90746 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3181120 | [6 empty] | YES | 2021-05-25 | 2021-06-10 | 12 | 12 | 2021-05-21 | 2021-05-21 | 14 | 14 | 1 | 1 | 2021-11-29 |  | 2021-06-10 |  |  |  |  | 2021-09-27 | 89 | 89 | 2021-09-29 | 2021-10-01 | 2021-11-15 | 2021-11-16 | 36 | 36 | 2021-11-17
790 | Previous address 850 E Central San Bernardino | 1110 E Central Ave | San Bernardino | 92405 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3156702 | 1921689 |  |  |  | NO | Level 3 | YES |  | 2021-06-17 |  |  | 2021-05-27 | 2021-05-28 | 14 | 14 | 2 | 2 |  |  | 2021-06-13 | [7 empty] | 2021-08-24 |  | 2021-10-29 | 2021-11-03 |  |  | 2021-11-03 | 2021-11-09 | 5 | 5 | 2021-12-03 | 2022-01-04 | 37 | 37 | 2022-01-04 | 1 | 1 | 2023-09-14 | 2023-09-15 | 2023-09-14 | 2023-09-15 | 430 | 430 | 467 | 467 | 2 | 2 | 2021-11-18 | 2021-12-27 | 2022-06-27 | -31 |  | 128 | 128 | 152 | 152 | 2023-08-29 | 419 | 419 | 2023-09-20 | 16 | 16 | 2021-12-27 | 2021-12-27 | 2023-09-15 | 2023-09-20 | 440 | 440 | 419 | 419 | 2023-05-01 | 2023-05-19 | 2023-09-08 | 92 | 92 | 2023-05-04 |  |  | 2023-05-16 | 9 | 9 | [6 empty] | 2023-08-16 | 2023-08-24 | 79 | 79 | 7 | 7 | 2023-09-21 | 2023-10-31 | 29 | 29 | 2023-11-03 | 32 | 32 | 2023-11-03 |  |  |  | 617 | 617 |  |  | 2023
791 | City of Santa Barbara | 621 Anacapa St | Santa Barbara | 93101 | Ventura County | 6. Requirements (permit, easment, etc.) | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2021-05-11
792 | Covina, CA - S Barranca Ave (Ikea) | 852 S Barranca Ave | Covina | 91723 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | Cortez | Barbossa 12kv | 3309511 | 2044193 |  | 2024-06-28 | 6 | NO |  | YES | 2021-07-15 | 2021-07-27 | 9 | 9 | 2021-06-01 | 2021-05-21 | 46 | 46 | -7 |  |  |  | 2021-06-01 |  |  |  |  | 2022-05-13 | 241 | 241 | 2022-05-16 | 2022-05-18 | 2022-06-30 | 2022-07-13 | 42 | 42 | 2022-07-14 | 2022-08-04 | 16 | 16 | 2022-08-25 | 2022-11-18 | 75 | 75 |  |  |  | 2022-11-18 | 2023-03-17 | 2022-11-18 | 2023-02-17 | 1 | 1 | 137 | 137 | 63 | 63 | 2022-10-03 | 2022-10-20 | 2023-04-24 | -34 |  | 128 | 128 | 141 | 141 | 2023-11-08 | [5 empty] | 2022-10-20 | 2022-10-20 | 2023-04-24 |  |  |  | 247 | 247 | 2023-11-08 | 2023-11-08 |  |  |  | 2023-11-08
793 | Montclair - Moreno St | 5483 Moreno St | Montclair | 91763 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona |  |  | 3268880 | [6 empty] | YES | 2021-06-02 |  |  |  | 2021-06-02 | 2021-06-02 |  |  | 1 | 1 | 2021-06-02 | 2021-06-04 | 2021-06-07 | 3 | 3 | 2 | 2 |  |  |  | 2021-09-27
794 | Yucca Valley, CA - 57552 29 Palms Hwy (Joshua Village) | 57552 29 Palms Hwy | Yucca Valley | 92284 | San Bernardino County | 9. Complete | 84 - Yucca Valley | Rurals | SBRO | [5 empty] | 2025-03-01 | 16 | YES | Level 2 | YES | 2023-12-21 |  |  |  | 2023-08-28 | 2023-08-28 |  |  | 1 | 1 | 2023-09-21 | 2023-09-28 | 2023-10-26 | 23 | 23 | 21 | 21
795 | Yucca Valley, CA - 57220 29 Palms Hwy (Desert Hills Plaza) | 57220 29 Palms Hwy | Yucca Valley | 92284 | San Bernardino County | 11. Cancelled | 84 - 29 Palms | Rurals | SBRO |  |  | 3167220 | 1918059 |  |  | 16 | NO |  | true |  | 2021-06-18 |  |  | 2021-06-02 | 2021-06-02 | 13 | 13 | 1 | 1 | 2021-06-03 |  | 2021-06-18 |  |  |  |  | 2021-09-08 | 69 | 69 | 2021-09-09 |  | 2021-10-18 | 2021-11-02 | 40 | 40 | 2021-11-02 | 2021-11-03 | 2 | 2 | 2021-12-03 | 2021-12-08 | 23 | 23 | 2021-12-08 | 1 | 1 | 2021-12-09 | 2022-01-04 | 2021-12-09 | 2022-01-05 | 2 | 2 | 42 | 42 | 19 | 19 | 2021-12-03 | 2021-12-30 | 2022-01-10 | -4 |  | 8 | 8 | 26 | 26 | 2022-07-05 | 145 | 145 | 2022-08-26 | 39 | 39 | 2021-12-09 | 2021-12-09 | 2022-01-10 | 2022-08-26 | 182 | 182 | 145 | 145 | [18 empty] | 2022-08-15 |  |  |  |  | 2022-08-16 |  |  |  | 2022-09-16 | 23 | 23 | 2022-09-16 |  |  |  | 327 | 327 | 259 | 259 | 2022
796 | Paramount | 7209 Rosecrans Ave | Paramount | 90723 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | true | 2021-06-03 | 2021-06-17 | 11 | 11 | 2021-06-02 | 2021-06-02 | 12 | 12 | 1 | 1 |  |  | 2021-06-18
797 | Beaumont | 253 E 1st Street | Beaumont | 92223 | Riverside County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | YES | 2021-06-03 | 2021-06-10 | 6 | 6 | 2021-06-03 | 2021-06-03 | 6 | 6 | 1 | 1 | 2021-06-03 |  | 2021-06-21
798 | Visalia, CA - 6603 Betty Dr (Valley Travel Plaza) | 6603 Betty Dr | Visalia | 93291 | Tulare County | 6. Requirements (permit, easment, etc.) | 51 - Tulare | San Joaquin | Ventura |  |  | 3181890 | 1921478 |  |  | 19 | NO |  | NO | 2021-06-03 | 2021-06-14 | 8 | 8 | 2021-06-03 | 2021-06-03 | 8 | 8 | 1 | 1 | 2021-06-07 |  | 2021-06-14 |  |  |  |  | 2021-09-29 | 83 | 83 | 2021-09-30 | 2021-10-05 | 2021-11-17 | 2021-11-17 | 35 | 35 | 2021-11-18 | 2021-12-14 | 17 | 17 | 2022-01-07 | 2022-01-10 | 19 | 19 | 2022-01-10 | 1 | 1 | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-02-01 | 12 | 12 | 34 | 34 | 5 | 5 | 2022-01-18 | 2022-02-15 |  | 6 | 6 |  |  |  |  | 2022-06-03 | 102 | 102 |  |  |  | 2022-01-26 | 2022-01-26 |  |  |  |  | 102 | 102 | 2022-06-06 |  | 2022-06-14 | 7 | 7 | [13 empty] | 2022-07-30 |  |  |  |  | 2022-08-01 |  |  |  | 2022-10-04 | 46 | 46 | 2022-10-04 |  |  |  | 338 | 338 | 256 | 256 | 2022
799 | Colton | 1900 S Riverside Avenue | Colton | 92324 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3146673 | 1921567 |  | 2024-08-01 | 6 | NO |  | NO |  |  |  |  | 2021-06-08 | 2021-06-08 |  |  | 1 | 1 | 2021-07-21 | [9 empty] | 2021-08-06 | 2021-08-12 | 2021-09-10 | 2021-10-29 |  |  | 2021-11-01 | 2021-11-07 | 5 | 5 |  | 2023-12-11 | 527 | 527 | 2023-12-11 | 1 | 1 | 2023-12-20 | 2024-02-01 | 2023-12-20 | 2024-01-05 | 8 | 8 | 544 | 544 | 11 | 11 | [28 empty] | 2022-07-08 |  |  | 2022-07-27 | 14 | 14 | [6 empty] | 2022-07-21
800 | Santa Monica, CA - 500 Broadway | 500 Broadway | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2020-09-29
801 | Long Beach Transit Station | 1963 E. Anaheim Street | Long Beach | 90813 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | true | 2021-06-10 |  |  |  | 2021-06-10
802 | Cypress, CA - 5995 Katella Ave | 5995 Katella Ave | Cypress | 90630 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | true | 2021-06-14 | 2021-07-09 | 19 | 19 | 2021-06-14 | 2021-06-14 | 19 | 19 | 1 | 1 |  |  | 2021-07-18
803 | El Segundo the Point | 850 S Pacific Coast Highway | El Segundo | 90245 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true |  |  |  |  | 2021-06-14 | 2021-06-14 |  |  | 1 | 1
804 | Palm Springs Windmills Tour | 62950 20th Ave | Palm Springs | 92258 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | true |  |  |  |  | 2021-06-14 | 2021-06-14 |  |  | 1 | 1 |  |  | 2021-07-06
805 | Costa Mesa - Briggs Ave | 261 Briggs Avenue | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3127975 | 1879380 |  |  | 2 |  |  | NO | 2021-06-16 | 2021-06-21 | 4 | 4 | 2021-05-24 | 2021-05-24 | 20 | 20 | 1 | 1 | 2021-05-24 |  | 2021-05-24 | [7 empty] | 2021-07-08 | 2021-07-08 | 2021-08-10 | 2021-08-23 |  |  | 2021-08-23 |  |  |  |  | 2021-09-10 |  |  | 2021-09-10 | 1 | 1 | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-22 | 56 | 56 |  |  | 16 | 16 | 2021-10-04 | 2021-11-03 | 2021-11-18 | 17 | 17 | 11 | 11 | 33 | 33 | [6 empty] | 2021-11-03 |  | 2021-12-22 | [10 empty] | 2021-10-04 | [11 empty] | 2022-04-04 | 2022-05-02 | 145 | 145 | 21 | 21 | 2022-05-03 | 2022-06-03 | 23 | 23 | 2022-06-03 | 23 | 23 | 2022-06-03 |  |  |  | 260 | 260 |  |  | 2022
806 | Gateway Towncenter Compton | 1621 S Alameda St | Compton | 90220 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3150020 | 1900824 | [5 empty] | NO | 2021-06-17 | 2021-06-30 | 10 | 10 | 2021-06-17 | 2021-06-17 | 10 | 10 | 1 | 1 | 2021-06-18 |  | 2021-07-02 | [7 empty] | 2021-08-12 | 2021-08-13 | 2021-09-14 | 2021-09-15 |  |  | 2021-09-15
807 | Whittier Telegraph Rd | 13417 Telegraph Rd | Whittier | 90605 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-06-18 | 2021-06-18 |  |  | 1 | 1 | 2021-06-21
808 | Santa Ana Downtown R29 | 301 E 1st St-EV | Santa Ana | 92701 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3247907 | 2085400 |  | 2024-02-08 | 4 | YES | Level 1 | NO | 2022-01-24 | 2022-02-02 | 8 | 8 | 2022-12-14 | 2021-06-18 | 157 | 157 | -375 |  | 2021-06-21 |  | 2021-07-06 |  |  |  |  | 2022-12-16 | 3 | 3 | 2022-12-16 | 2023-01-11 | 2023-02-03 | 2023-01-23 | 26 | 26 | 2023-01-23 | 2023-01-25 | 3 | 3 | 2023-02-17 |  |  |  | 2023-01-30 |  |  | 2022-06-29 | 2022-07-29 | 2022-06-29 | 2022-07-10 |  |  | -138 |  | 7 | 7 | 2023-02-01 | 2023-02-06 | 2023-02-09 |  |  | 4 | 4 | 7 | 7 | 2023-01-21 | -6 |  | 2023-03-22 | 42 | 42 | 2022-06-29 | 2022-06-29 | 2023-02-09 | 2023-03-22 | 184 | 184 |  |  | 2023-10-17 | 2024-01-03 | 2024-01-08 | 56 | 56 | 2023-02-15 |  |  | 2023-02-21 | 4 | 4 | [6 empty] | 2024-01-08 | 2024-01-11 | 229 | 229 | 4 | 4 | 2024-02-01 | 2024-03-13 | 29 | 29 | 2024-03-16 | 31 | 31 | 2024-03-16 |  |  |  | 317 | 317 | 315 | 315 | 2024
809 | San Dimas Plaza | 877 W Arrow Hwy | San Dimas | 91773 | Los Angeles County | 7. Civil Construction | 27 - Monrovia | Metro East | Pomona |  |  | 3202840 | [6 empty] | NO | 2021-06-21 | 2021-06-29 | 7 | 7 | 2021-06-21 | 2021-06-21 | 7 | 7 | 1 | 1 | 2021-06-21 |  | 2021-07-06 | [7 empty] | 2021-11-04 | 2021-11-09 | 2021-12-24 | 2021-12-27 |  |  | 2021-12-28 | 2022-02-23 | 40 | 40 | 2022-03-22
810 | Puente Hills Town Center - old address 17416 Colima | 17342 Colima Rd | Rowland Heights | 91748 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona |  |  | 3150082 | 1904171 |  | 2024-04-29 | 6 | NO |  | YES | 2021-06-21 | 2021-06-22 | 2 | 2 | 2021-06-21 | 2021-12-20 | -125 |  | 126 | 126 | 2021-12-21 | 2021-12-28 | 2022-01-03 | 6 | 6 | 5 | 5 | 2022-08-12 | 290 | 290 | 2021-08-12 | 2021-08-19 | 2021-11-17 | 2021-11-18 | -185 |  | 2021-11-19 | 2021-12-06 | 10 | 10 | 2022-01-03 | 2022-01-03 | 20 | 20 | 2022-01-05 | 3 | 3 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2022-02-07 | 273 | 273 | 44 | 44 | -249 |  | 2023-02-15 | 2023-02-28 | 2023-08-01 | 284 | 284 | 109 | 109 | 117 | 117 | 2023-08-28 | 417 | 417 | 2023-09-08 | 9 | 9 | 2023-01-31 | 2023-01-31 | 2023-08-01 | 2023-09-08 | 155 | 155 | 419 | 419 | 2023-12-14 | 2024-01-08 | 2024-01-11 | 19 | 19 | 2022-09-29 |  |  | 2022-10-06 | 6 | 6 | [6 empty] | 2024-01-15 | 2024-01-22 | 330 | 330 | 5 | 5
811 | Carson Ralphs & Abalone #132 | 1770 W Carson St. | Torrance | 90501 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3542805 | 2147750 |  | 2025-04-02 | 8 | YES | Level 2 | YES | 2023-06-06 |  |  |  | 2022-12-08 | 2022-12-08 |  |  | 1 | 1 | 2022-12-13 | 2022-12-15 | 2023-01-06 | 6 | 6 | 17 | 17 | 2023-06-01 | 123 | 123 | 2023-06-01 | 2023-06-06 | 2023-07-19 | 2023-07-10 | 27 | 27 | 2023-07-11 | [60 empty] | 2021-06-28
812 | Park Plaza Shopping Center (Pico Rivera) | 6101 Rosemead Blvd | Pico Rivera | 90660 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 3127393 | 1918061 |  |  | 4 | NO |  | NO | 2021-06-18 | 2021-07-07 | 13 | 13 | 2021-06-18 | 2021-06-18 | 13 | 13 | 1 | 1 |  |  | 2021-07-06 | [7 empty] | 2021-07-08 | 2021-07-09 | 2022-03-21 | 2022-07-19 |  |  | 2022-07-25 | 2022-08-04 | 9 | 9 | 2022-08-26 | 2022-08-09 | 4 | 4 | 2022-08-09 | 1 | 1 | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-09-09 | 22 | 22 | 26 | 26 | 2 | 2 | 2021-11-15 | 2022-09-01 | 2022-09-09 | -185 |  | 6 | 6 | 207 | 207 | 2023-04-05 | 166 | 166 | 2023-05-01 | 19 | 19 | 2022-09-01 | 2022-09-01 | 2022-09-09 | 2023-05-01 | 167 | 167 | 166 | 166 | [5 empty] | 2022-04-01 | 2022-04-07 | 2022-04-07 | [10 empty] | 2023-03-10 | 238 | 238 |  |  | 2023-03-15 | 2023-05-03 | 36 | 36 | 2023-05-04 | 37 | 37 | 2023-05-04 |  |  |  | 474 | 474 |  |  | 2023
813 | Torrance - Hawthorne Blvd | 19800 Hawthorne Blvd | Torrance | 90503 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2021-06-22 | 2021-06-25 | 4 | 4 | 2021-06-21 | 2021-06-22 | 4 | 4 | 2 | 2 |  |  | 2021-07-07
814 | Dunhill - Shoppes at Chino Hills Chino Hills, CA 91709 | 13920 City Center Dr | Chino Hills | 91709 | San Bernardino County | 10. Customer Hold | 34 - Ontario | Metro East | Pomona |  |  | 3151737 | 1925842 |  |  | 6 | NO |  | NO | 2021-06-18 | 2021-06-21 | 2 | 2 | 2021-06-21 | 2021-06-21 | 1 | 1 | 1 | 1 | 2021-06-22 |  | 2021-07-01 |  |  |  |  | 2022-08-22 | 296 | 296 | 2022-08-25 | 2022-08-25 | 2022-10-14 | 2022-10-15 | 39 | 39 | 2022-10-24 | 2022-11-16 | 17 | 17 | 2022-12-13 | 2023-01-09 | 37 | 37 | 2023-01-11 | 3 | 3 | 2023-01-11 | 2023-03-03 | 2023-01-11 | 2023-02-06 | 3 | 3 | 56 | 56 | 18 | 18 | 2023-01-25 | 2023-01-25 | 2023-02-03 | 12 | 12 | 8 | 8 | 8 | 8 | 2023-06-27 | 117 | 117 | 2023-07-11 | 10 | 10 | 2023-01-11 | 2023-01-11 | 2023-02-06 | 2023-07-11 | 126 | 126 | 119 | 119 | 2023-06-09 | 2023-06-23 | 2023-06-19 | 7 | 7 | 2023-03-21 |  | 2023-05-04 | 2023-04-03 | 10 | 10 |  |  |  | 2023-05-15 | 8 | 8 | 2023-06-22 | 2023-06-29 | 72 | 72 | 6 | 6 | 2023-07-10 | 2023-08-07 | 21 | 21 | 2023-08-08 | 22 | 22 | 2023-08-08 |  |  |  | 539 | 539 | 244 | 244 | 2023
815 | Mission Viejo - La Paz Rd | 26137 La Paz Rd | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3164090 | 1899692 | [5 empty] | NO |  |  |  |  | 2021-06-18 | 2021-06-21 |  |  | 2 | 2 |  |  | 2021-07-06 | [7 empty] | 2021-09-02 | 2021-09-02
816 | South Gate Tweedy Blvd | 3848 Tweedy Blvd | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3191390 | [6 empty] | NO | 2021-06-22 | 2021-07-02 | 9 | 9 | 2021-06-22 | 2021-06-22 | 9 | 9 | 1 | 1 |  |  | 2021-07-14 | [7 empty] | 2021-10-15 | 2021-10-18
817 | Huntington Beach Yorktown Main | 7051 Yorktown/Main St | Huntington Beach | 92648 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-06-18 | 2021-06-18 |  |  | 1 | 1 | 2021-06-18 |  | 2021-07-01
818 | Grand Terrace Barton Rd | 22441 Barton Rd | Grand Terrace | 92313 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3149910 | 1899291 | [5 empty] | YES | 2021-06-22 | 2021-07-01 | 8 | 8 | 2021-06-22 | 2021-06-22 | 8 | 8 | 1 | 1 | 2021-06-23 |  | 2021-07-01 | [7 empty] | 2021-08-12 | 2021-08-12 | 2021-10-01 | 2021-10-22 |  |  | 2021-10-22 |  |  |  |  | 2021-11-17 |  |  | 2021-11-17 | 1 | 1 | 2021-11-17 | 2021-11-17 | 2021-11-17 | 2021-11-30 | 1 | 1 |  |  | 8 | 8 | 2021-11-05 | 2021-12-06 |  | -8 | [11 empty] | 2021-11-17
819 | Gateway Plaza Santa Fe Springs | 10639 Carmenita Rd | Santa Fe Springs | 90670 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 3280719 | 1990369 | 2023009 | 2025-05-15 | 4 | NO |  | YES | 2021-06-23 | 2021-07-12 | 13 | 13 | 2021-06-23 | 2021-06-23 | 13 | 13 | 1 | 1 | 2021-06-24 | 2021-06-29 | 2021-07-20 | 5 | 5 | 15 | 15 | 2022-03-17 | 184 | 184 | 2022-03-30 | 2022-04-01 | 2022-06-07 | 2022-06-06 | 57 | 57 | 2022-06-06 | 2022-06-13 | 6 | 6 | 2022-08-09 | 2023-08-11 | 296 | 296 | 2023-06-29 | -31 |  | 2023-08-11 | 2023-09-25 | 2023-08-11 | 2023-08-15 | 1 | 1 | 298 | 298 | 3 | 3 | 2023-07-07 |  |  | -26 | [27 empty] | 2023-01-20
820 | Huntington Beach, CA - 5141 Warner Ave | 5141 Warner Ave | Huntington Beach | 92649 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3243990 | [6 empty] | YES | 2021-06-23 | 2021-07-07 | 10 | 10 | 2021-06-22 | 2021-06-23 | 10 | 10 | 2 | 2 | 2021-06-23 | 2022-05-13 | 2021-07-07 | 225 | 225 | -216 |  | 2022-01-25 | 149 | 149 | 2022-01-27 | 2022-01-27 | 2022-03-11 | 2022-04-13 | 56 | 56 | 2022-04-13
821 | Riverside, CA - Van Buren Blvd | 22400 Van Buren Blvd | Riverside | 92518 | Riverside County | 5. Final Design | 31 - Redlands | Desert | SBRO |  | Ironwood 33kV | 3392298 | 2048090 |  | 2024-12-15 |  | NO |  | YES |  |  |  |  | 2021-06-28 | 2021-06-28 |  |  | 1 | 1 | 2021-06-29 |  | 2021-07-23 |  |  |  |  | 2022-09-23 | 314 | 314 | 2022-09-26 |  |  | 2022-11-22 | 42 | 42 | 2022-11-30
822 | Tesla Corona - W 6th Street | 1341 W 6th St | Corona | 92882 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona |  | Cupples 33kV | 3295692 | 2219993 | 2219995 |  |  | YES | Level 3 | YES | 2021-07-07 | 2021-07-19 | 9 | 9 | 2021-06-29 | 2021-06-29 | 14 | 14 | 1 | 1 |  |  | 2022-03-04 |  |  |  |  | 2021-10-22 | 82 | 82 | 2021-10-22 |  |  | 2022-10-26 | 255 | 255 | 2022-10-26 | 2023-09-21 | 229 | 229 | 2023-10-13 | [6 empty] | 2023-05-08 |  | 2023-05-08
823 | Murrieta - 24530 Village Walk Pl, EV-1- R2 | 24530 Village Walk Pl, EV-1 | Murrieta | 92562 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3352929 | 2132373 |  | 2024-01-26 | 12 | YES | Level 2 | true | 2021-06-29 | 2021-07-27 | 20 | 20 | 2021-06-29 | 2021-06-29 | 20 | 20 | 1 | 1 | 2021-06-29 | 2021-06-29 | 2021-07-23 | 1 | 1 | 18 | 18 | 2022-03-08 | 173 | 173 | 2023-03-22 |  | 2023-05-16 | 2023-05-30 | 312 | 312 | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-06-28 | 2023-07-19 | 36 | 36 | 2023-07-19 | 1 | 1 | [10 empty] | 2023-07-03 | 2023-07-20 | 2023-08-07 | -12 |  | 13 | 13 | 25 | 25 | 2023-08-03 | 12 | 12 | 2023-09-19 | 33 | 33 | [6 empty] | 12 | 12 | 2023-09-20 | 2023-10-09 | 2023-10-23 | 24 | 24 | 2023-09-06 |  |  | 2023-09-22 | 13 | 13 | [6 empty] | 2023-11-08 | 2023-11-26 | 56 | 56 | 11 | 11 | 2023-12-12 | 2024-01-11 | 21 | 21 | 2024-01-11 | 21 | 21 | 2024-01-11 | 2024-01-18 | 5 | 5 | 640 | 640 | 468 | 468 | 2024
824 | Arcadia - Joseph Street | 35 W Joseph St | Arcadia | 91007 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3152570 | [6 empty] | YES |  |  |  |  | 2021-06-29 | 2021-07-01 |  |  | 3 | 3 | 2021-07-02 |  | 2021-08-16 | [7 empty] | 2021-08-17 |  | 2021-09-10
825 | Calimesa - Sandalwood Travel Center | Sandalwood Dr & 17th Street | Calimesa | 92320 | Riverside County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [7 empty] | NO |  | true | 2021-06-29 | 2021-07-14 | 11 | 11 | 2021-06-29
826 | Menifee, CA - Bradley Rd | Bradley Rd & Newport Rd | Menifee | 92584 | Riverside County | 7. Civil Construction | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES | 2021-06-30 | 2021-07-27 | 19 | 19 | 2021-06-30
827 | Long Beach - Port of Long Beach | 200 Pier S Ave | Long Beach | 90802 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | Dike | Ford 12 kv | 3355414 | 2019391 |  | 2024-02-01 | 30 | NO |  | YES | 2021-06-30 | 2021-07-27 | 19 | 19 | 2021-06-30 | 2021-06-30 | 19 | 19 | 1 | 1 | 2021-06-30 |  | 2021-07-10 |  |  |  |  | 2022-04-18 | 201 | 201 | 2022-04-25 | 2022-04-26 | 2022-06-09 | 2022-08-15 | 84 | 84 | 2022-08-15 | 2022-08-17 | 3 | 3 | 2023-09-12 | 2023-10-13 | 294 | 294 | 2023-10-16 | 2 | 2 | 2023-10-23 | 2024-03-11 | 2023-10-23 | 2023-10-30 | 7 | 7 | 305 | 305 | 6 | 6 | 2023-01-05 |  | 2023-10-31 | -197 |  |  |  | 209 | 209 | 2023-07-19 | -63 |  | 2023-10-31 | 74 | 74 |  |  | 2023-10-31 | 2023-10-31 |  |  | -62 |  | 2023-11-06 |  |  |  |  | 2023-10-31 |  |  | 2023-11-06 | 5 | 5 | [6 empty] | 2024-02-26 | 2024-02-28 | 81 | 81 | 3 | 3
828 | Chino Hills - Grand Ave | 3560 Grand Avenue | Chino Hills | 91709 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2021-06-30 | 2021-07-06 | 4 | 4 | 2021-06-30 | [7 empty] | 2021-07-13
829 | Santa Monica, CA-1401 S/M Blvd - Phase 2 | 1401 Santa Monica Blvd | Santa Monica | 90404 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra |  |  | 3086229 | 1847955 |  |  | 36 |  |  | YES | 2020-01-31 | 2020-02-13 | 10 | 10 | 2021-07-01 | 2021-07-01 | -349 |  | 1 | 1 | 2021-12-02 | [26 empty] | 2021-07-19 | 2021-08-11 | 2021-07-19 | 2021-07-28 |  |  |  |  | 8 | 8 |  | 2021-10-28 | [13 empty] | 2021-07-19 | [7 empty] | 2022-05-19 |  | 2022-06-10 | 16 | 16 | 2022-04-04 | [11 empty] | 2021-12-29 | 2021-12-29 | -67 |  | 1 | 1 | 2022-06-20 |  |  |  | 2022-09-01 | 53 | 53 | 2022-09-01 |  |  |  | 296 | 296 |  |  | 2022
830 | Rialto - Stonehurst Drive (Green Cities) Previously 2298 | 2290 West Stonehurst Drive | Rialto | 92377 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO | Alder | Lytle 12 KV | 3295989 | 2003202 |  |  | 14 | NO | Level 3 | YES | 2021-07-07 | 2021-07-15 | 7 | 7 | 2021-06-29 | 2021-06-29 | 12 | 12 | 1 | 1 | 2021-06-30 |  | 2021-07-07 |  |  |  |  | 2022-04-19 | 203 | 203 | 2022-04-22 | 2022-04-28 | 2022-06-09 | 2022-09-07 | 99 | 99 | 2022-09-07 | 2022-10-11 | 25 | 25 | 2022-11-30 | 2023-07-06 | 186 | 186 | 2023-06-15 | -15 |  | 2023-07-07 | 2023-07-07 | 2023-07-07 | 2023-07-17 | 2 | 2 | 193 | 193 | 7 | 7 | 2023-06-20 | 2023-07-06 | 2023-07-31 | -12 |  | 18 | 18 | 29 | 29 | 2023-09-11 | 61 | 61 | 2023-09-27 | 13 | 13 | 2023-07-06 | 2023-07-06 | 2023-07-31 | 2023-09-27 | 59 | 59 | 47 | 47 |  | 2023-08-14 | 2023-12-18 |  |  | 2023-07-07 | 2023-08-28 | 2023-12-04 | 2023-07-12 | 4 | 4 |  |  |  | 2023-12-15 | 10 | 10 |  | 2023-11-06 | 86 | 86 |  |  | 2023-11-08 | 2024-01-22 | 49 | 49 | 2024-02-04 | 58 | 58 | 2024-02-04 |  |  |  | 655 | 655 | 453 | 453 | 2024
831 | Rule 29 Hesperia, CA - Main Street (Topaz Marketplace) | 14135 1/2 Main St | Hesperia | 92345 | San Bernardino County | 4. Preliminary Design | 73 - Victorville | Rurals | SBRO |  | Sluice 12kV | 3380062 | 2038409 | 2053301 | 2024-01-12 | 16 | YES | Level 3 | YES | 2021-07-07 | 2021-07-27 | 15 | 15 | 2022-09-07 | [12 empty] | 2022-09-07 | 1 | 1 | 2022-09-07 |  | 2022-11-01 | 2022-11-30 | 58 | 58 | 2022-11-30 | 2023-01-31 | 44 | 44 |  | 2023-07-25 | 123 | 123 | 2023-05-24 | -43 |  | 2023-07-25 | 2023-07-25 | 2023-07-25 | 2023-07-31 | 1 | 1 | 127 | 127 | 5 | 5 | 2023-06-09 | 2023-06-15 | 2023-06-20 | -32 |  | 4 | 4 | 8 | 8 | 2023-07-31 | 47 | 47 | 2023-09-28 | 43 | 43 | 2023-06-15 | 2023-06-15 | 2023-07-31 | 2023-09-28 | 74 | 74 | 5 | 5 | 2023-09-29 | 2023-12-04 | 2024-01-26 | 81 | 81 | 2023-07-19 | [12 empty] | 2024-01-12 | 123 | 123 |  |  | 2024-02-08 | 2024-03-14 | 25 | 25 | 2024-03-15 | 26 | 26 | 2024-03-15 | 2024-03-26 | 8 | 8 | 384 | 384 | 384 | 384 | 2024
833 | Phelan, CA - 3230 Wagon Train Rd (McDonald's) | 3230 Wagon Train Rd | Phelan | 92371 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 3267873 | 1972748 | [5 empty] | YES | 2021-07-07 | 2021-07-27 | 15 | 15 | 2021-07-07 | 2021-07-07 | 15 | 15 | 1 | 1 | 2021-07-12 |  | 2021-07-16 |  |  |  |  | 2022-03-07 | 167 | 167 | 2022-03-10 | 2022-03-15 | 2022-04-22 | 2022-04-12 | 27 | 27 | 2022-04-12
834 | In and Out Valencia | 27430 The Old Road | Valencia | 91355 | Los Angeles County | 10. Customer Hold | 59 - Valencia | North Valley | Ventura | [9 empty] | NO | 2021-07-07 | 2021-08-04 | 21 | 21 | 2021-07-07 | 2021-07-07 | 21 | 21 | 1 | 1 | 2021-07-13 |  | 2021-07-28
835 | County of Ventura - County APCD Phase 2 | 4567 Telephone Road | Ventura | 93003 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3148690 | [6 empty] | YES |  |  |  |  | 2021-07-12 | 2021-07-12 |  |  | 1 | 1 | 2021-07-13 | 2021-07-13 | 2021-07-23 | 2 | 2 | 9 | 9 | 2021-08-06 | 20 | 20 | 2021-08-10 |  | 2021-09-14
836 | Montevista - Montevista Avenue | 9143 Montevista Avenue | Montclair | 91763 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | true | 2021-06-23 | 2021-07-27 | 24 | 24 | 2021-06-23 | 2021-06-23 | 24 | 24 | 1 | 1
837 | Robbie Barker - Trona | 82740 Trona Rd | Trona | 93562 | San Bernardino County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 3155929 | 1902835 |  |  | 2 |  |  | true |  |  |  |  | 2021-07-08 | 2021-07-08 |  |  | 1 | 1 | 2021-07-08 |  | 2021-07-14 | [7 empty] | 2021-08-20 | 2021-10-27 | 2021-12-13 | 2021-11-17 |  |  | 2021-11-18 | 2021-11-18 | 1 | 1 | 2021-12-13 | 2021-12-14 | 17 | 17 | 2021-12-14 | 1 | 1 | 2022-03-02 | 2022-03-02 | 2022-03-02 | 2022-03-10 | 54 | 54 | 76 | 76 | 7 | 7 | 2022-03-01 | 2022-03-29 | 2022-04-04 | 53 | 53 | 5 | 5 | 25 | 25 | [6 empty] | 2022-03-02 |  | 2022-04-04 | [10 empty] | 2021-12-09 | [11 empty] | 2022-03-24 | 2022-04-01 | 79 | 79 | 7 | 7 | 2022-04-04 | 2022-06-08 | 47 | 47 | 2022-06-10 | 49 | 49 | 2022-06-10 |  |  |  | 234 | 234 |  |  | 2022
838 | Carson - Avalon Blvd (Ikea) Carson - 20700 Avalon Blvd (IKEA) Carson, CA 90746 CA 90746 | 20700 Avalon Blvd Carson, CA 90746 | Carson | 90746 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3203630 | [6 empty] | YES | 2021-07-13 | 2021-07-27 | 11 | 11 | 2021-07-13 | [15 empty] | 2021-11-05 | 2021-11-08 | 2021-12-22
839 | Huntington Beach Target - Phase 2 | 9882 Adams Avenue | Huntington Beach | 92646 | Orange County | 7. Civil Construction | 43 - Saddleback | Orange | Saddleback |  |  | 3134919 | 1882471 | [5 empty] | NO | 2021-07-13 | 2021-07-16 | 4 | 4 | 2021-07-13 | 2021-07-13 | 4 | 4 | 1 | 1 | 2021-07-13 |  | 2021-07-20 | [10 empty] | 2021-08-27 |  |  | 2021-08-27 | [10 empty] | 2022-07-06 | 2022-07-06 | 2022-07-06 | 2022-07-06 |  |  |  |  | 1 | 1 | [40 empty] | 2022-09-07 | 2022-09-15 |  |  | 7 | 7 | 2022-09-15 |  |  |  | 2022-10-24 | 28 | 28 | 2022-10-24 |  |  |  | 325 | 325 |  |  | 2022
840 | Mana Investment Company Old address 11951 Beach - New address 11953 | 11953 Beach Blvd | Stanton | 90680 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3143756 | 2056918 |  | 2024-03-01 | 8 | YES | Level 1 | YES |  |  |  |  | 2021-07-13 | 2021-07-13 |  |  | 1 | 1 | 2021-07-14 | 2021-07-19 | 2021-07-23 | 5 | 5 | 5 | 5 | 2022-11-02 | 332 | 332 | 2022-11-02 | 2022-11-03 | 2022-12-12 | 2022-11-21 | 13 | 13 | 2022-11-21 | 2022-11-21 | 1 | 1 | 2022-12-12 | 2022-12-16 | 18 | 18 | 2022-12-16 | 1 | 1 |  | 2023-07-13 |  | 2024-02-28 |  |  | 320 | 320 |  |  | 2022-12-15 | 2022-12-29 | 2023-05-18 | -2 |  | 99 | 99 | 109 | 109 | [8 empty] | 2024-02-28 | [5 empty] | 2024-02-19 | 2024-03-04 | 2024-03-06 | 12 | 12 | [9 empty] | 2024-03-06 |  |  |  | 2024-02-19
841 | Mojave, CA - 16870 CA-14 R1 | 16870 UNIT B Highway 14 | Mojave | 93501 | Kern County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  |  | 3202376 | 1926712 |  |  | 20 | NO |  | YES | 2021-07-15 | 2021-07-26 | 8 | 8 | 2021-07-14 | [5 empty] | 2021-07-15 |  | 2021-07-23 |  |  |  |  | 2021-10-25 | 73 | 73 | 2021-11-03 | 2021-11-10 | 2021-12-28 | 2022-01-07 | 51 | 51 | 2022-01-07 | 2023-03-16 | 300 | 300 | 2023-04-13 | [6 empty] | 2023-05-10 | 2023-06-21 | 2023-05-10 | 2023-06-22 |  |  | 70 | 70 | 31 | 31 | 2023-04-14 |  | 2023-05-31 |  |  |  |  | 33 | 33 | 2023-08-30 |  |  | 2023-09-06 | 5 | 5 |  |  | 2023-06-22 | 2023-09-06 |  |  |  |  | 2023-08-01 | 2023-08-04 | 2023-10-16 | 54 | 54 | 2023-07-21 |  |  | 2023-07-26 | 4 | 4 | [6 empty] | 2023-09-22 | 2023-10-11 | 58 | 58 | 14 | 14 | 2023-09-26 | 2023-10-05 | 8 | 8 |  |  |  | 2023-10-16 |  |  |  | 571 | 571 | 499 | 499 | 2023
842 | Pasadena, CA - E Colorado Blvd | 3498U East Colorado Blvd | Pasadena | 91107 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 27 - Monrovia | Metro East | Pomona |  |  | 3202219 | 1942411 |  |  | 16 |  |  | YES | 2021-07-14 | 2021-07-30 | 13 | 13 | 2021-07-14 | 2022-04-04 | -170 |  | 182 | 182 | 2022-04-04 |  | 2021-07-27 |  |  |  |  | 2021-11-01 | 78 | 78 | 2021-11-03 | 2021-11-09 | 2021-12-20 | 2021-12-29 | 39 | 39 | 2021-12-29 | 2022-01-07 | 8 | 8 | 2022-01-31 | 2022-02-02 | 18 | 18 | 2022-02-07 | 4 | 4 | 2022-02-23 | 2022-02-23 | 2022-10-13 | 2022-10-26 | 178 | 178 | 204 | 204 | 10 | 10 | 2022-02-11 | 2022-03-23 | 2022-10-17 | 8 | 8 | 146 | 146 | 173 | 173 | [6 empty] | 2022-03-23 |  | 2022-10-26 | [7 empty] | 2023-02-23 | [15 empty] | 2023-02-22 |  |  |  |  | 2023-02-23 |  |  |  | 2023-03-27 | 23 | 23 | 2023-03-27 |  |  |  | 429 | 429 | 352 | 352 | 2023
843 | Costa Mesa - Ikea | 3203 Susan St EM | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | Gisler | Klingon 12 kv | 3190989 | 1936701 |  | 2024-05-15 | 6 | NO |  | YES | 2021-07-15 | 2021-07-20 | 4 | 4 | 2021-07-16 | 2021-07-16 | 3 | 3 | 1 | 1 | 2021-07-16 |  | 2021-07-21 |  |  |  |  | 2021-10-13 | 63 | 63 | 2021-10-14 | 2021-10-15 | 2021-12-01 | 2022-01-19 | 66 | 66 | 2022-01-20 |  |  |  |  | 2022-08-30 |  |  | 2022-08-30 | 1 | 1 | 2022-08-30 | 2024-03-01 | 2022-08-30 | 2023-11-15 | 1 | 1 |  |  | 308 | 308 |  | 2022-07-12 | 2023-04-21 |  |  | 198 | 198 | [8 empty] | 2022-07-12 |  | 2023-11-15
844 | Whittier, CA - 15225 Whittier Blvd | 15225 Whittier Blvd | Whittier | 90603 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES | 2021-07-16 | 2021-07-27 | 8 | 8 | 2021-07-15 | 2021-07-15 | 9 | 9 | 1 | 1 | 2021-07-22 |  | 2021-07-31
845 | Commerce, CA - 6131 Telegraph Rd | 6131 Telegraph Rd | Commerce | 90040 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 3203712 | 1929197 |  |  | 40 | NO |  | YES | 2021-07-16 | 2021-07-30 | 11 | 11 | 2021-07-15 | [7 empty] | 2021-07-31 |  |  |  |  | 2021-11-03 | 79 | 79 | 2021-11-05 | 2021-11-08 | 2021-12-24 | 2021-12-23 | 34 | 34 | 2021-12-23 | 2022-03-30 | 67 | 67 | 2022-04-20 | 2022-05-05 | 27 | 27 | 2022-05-05 | 1 | 1 | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2023-01-23 | 27 | 27 | 207 | 207 | 155 | 155 | 2022-05-05 | 2022-06-06 |  | 1 | 1 |  |  |  |  | 2022-09-22 | 98 | 98 | 2023-01-27 | 88 | 88 | 2022-06-06 | 2022-06-06 |  |  |  |  | 98 | 98 | 2022-08-25 | 2022-10-04 | 2022-10-04 | 28 | 28 | [13 empty] | 2023-01-24 |  |  |  |  | 2023-01-25 |  |  |  | 2023-03-16 | 36 | 36 | 2023-03-16 |  |  |  | 421 | 421 | 343 | 343 | 2023
846 | Huntington Beach Target Phase 2 | 9882 Adams Avenue | Huntington Beach | 92646 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3134920 | 1882471 |  |  | 6 | NO |  | true | 2021-07-13 | 2021-07-20 | 6 | 6 | 2021-07-13 | [5 empty] | 2022-08-05 | [9 empty] | 2021-07-21 | 2021-07-21 | 2021-08-19 | 2021-08-27 |  |  | 2021-08-27 | [60 empty] | 2022-08-05 | 2022-09-15 |  |  | 29 | 29 | 2022-09-15 |  |  |  | 2022-10-24 | 28 | 28
847 | Cypress Target 200061 - Phase 2 | 6835 Katella Avenue | Cypress | 90630 | Orange County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2021-07-19 | 2021-08-04 | 13 | 13 | 2021-07-19 | 2021-07-19 | 13 | 13 | 1 | 1 |  |  | 2021-07-21 |  |  |  |  | 2021-08-05 | 14 | 14
848 | Stanton - Old Address 7135 Katella - Mana Investment | 7153 Katella Ave | Stanton | 90680 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3143560 | 1902265 |  |  | 4 | NO | Level 1 | NO |  |  |  |  | 2021-07-20 | 2021-07-20 |  |  | 1 | 1 | 2021-07-22 |  | 2021-08-02 | [7 empty] | 2021-08-03 | 2021-08-03 | 2021-09-12 | 2021-09-14 |  |  | 2021-09-14 | 2021-09-14 | 1 | 1 |  | 2021-11-10 | 42 | 42 | 2021-11-10 | 1 | 1 | 2021-11-15 | 2021-12-09 | 2022-04-20 |  | 110 | 110 | [5 empty] | 2021-11-11 | 2022-01-18 |  |  | 44 | 44 | [8 empty] | 2021-11-11 | [7 empty] | 2022-03-10 | 2022-04-01 | 2022-04-01 | 17 | 17 |  |  | 2022-02-03 | [9 empty] | 2023-01-30 | 2023-05-30 |  |  | 85 | 85 | 2023-09-07 | 2023-10-12 | 26 | 26 | 2023-10-13 | 27 | 27 | 2023-12-12 |  |  |  | 606 | 606 |  |  | 2023
849 | Stanton - Old Address 7155 Katella Avenue (Mana LLC) | 7105 Katella Ave | Stanton | 90680 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3143462 | 1902437 |  |  | 4 | NO | Level 1 | NO |  |  |  |  | 2021-07-20 | 2021-07-20 |  |  | 1 | 1 | 2021-07-22 |  | 2021-08-02 | [7 empty] | 2021-08-03 | 2021-08-03 | 2021-09-12 | 2021-09-14 |  |  | 2021-09-14 | 2021-09-14 | 1 | 1 |  | 2021-11-10 | 42 | 42 | 2021-11-10 | 1 | 1 | 2021-11-15 | 2021-12-09 | 2022-04-20 | 2022-04-28 | 110 | 110 | 157 | 157 | 7 | 7 | [23 empty] | 2022-03-10 | 2022-04-01 | 2022-04-01 | 17 | 17 | [12 empty] | 2023-01-30 | 2023-05-30 |  |  | 85 | 85 | 2023-08-31 | 2023-10-12 | 30 | 30 | 2023-10-13 | 31 | 31 | 2023-10-13 |  |  |  | 566 | 566 |  |  | 2023
850 | Covina - Vincent Avenue | 103 N Vincent Avenue | Covina | 91722 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3144276 | 1929864 |  |  | 4 | NO |  | YES |  |  |  |  | 2021-07-22 | 2021-07-22 |  |  | 1 | 1 | [10 empty] | 2021-08-04 | 2021-08-10 | 2021-09-08 | 2021-09-08 |  |  | 2021-09-08 | 2021-10-28 | 37 | 37 | 2021-11-19 | 2021-11-19 | 16 | 16 | 2021-11-22 | 2 | 2 | 2021-12-27 | 2022-05-04 | 2021-12-27 | 2022-04-18 | 24 | 24 | 117 | 117 | 79 | 79 | 2021-12-15 | 2021-12-22 | 2022-01-17 | 17 | 17 | 17 | 17 | 22 | 22 | 2022-07-19 | 165 | 165 | 2022-08-08 | 15 | 15 | 2021-12-22 | 2021-12-22 | 2022-04-18 | 2022-08-08 | 159 | 159 | 166 | 166 | [18 empty] | 2023-04-19 |  |  |  |  | 2023-04-20 | 2023-05-22 | 23 | 23 | 2023-05-25 | 26 | 26 | 2023-05-25 |  |  |  | 466 | 466 |  |  | 2023
851 | Mammoth Lakes - Old Mammoth Rd | 686 Old Mammoth Road | Mammoth Lakes | 93546 | Mono County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  |  | 1847167 | [5 empty] | YES |  |  |  |  | 2021-07-26
852 | WinCo Foods - Lakewood #107 | 3400 E South St | Lakewood | 90805 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3150210 | 1900266 |  |  | 3 | NO |  | YES | 2021-07-27 | 2021-08-11 | 12 | 12 | 2021-07-27 | 2021-07-27 | 12 | 12 | 1 | 1 | 2021-07-27 |  | 2021-08-06 | [7 empty] | 2021-08-12 | 2021-08-13 | 2021-09-15 | 2021-09-14 |  |  | 2021-09-14 | 2021-10-19 | 26 | 26 | 2021-11-09 | 2021-11-08 | 15 | 15 | 2021-11-09 | 2 | 2 | 2021-11-09 | 2022-02-03 | 2021-11-09 | 2021-11-10 | 2 | 2 | 17 | 17 | 2 | 2 | 2021-12-21 | 2022-01-20 | 2022-03-21 | 29 | 29 | 42 | 42 | 62 | 62 | 2022-05-25 | 136 | 136 |  |  |  | 2021-11-09 | 2021-11-09 | 2022-03-21 |  |  |  | 137 | 137 | 2022-05-10 | 2022-05-25 | 2022-05-25 | 12 | 12 | 2022-03-23 |  |  | 2022-03-31 | 7 | 7 | [6 empty] | 2022-05-25 | [5 empty] | 2022-07-01 |  |  |  | 2022-08-15 | 31 | 31 | 2022-08-15 |  |  |  | 266 | 266 |  |  | 2022
853 | Hesperia, CA - 13401 Main St | 13401 Main St | Hesperia | 92345 | San Bernardino County | 10. Customer Hold | 73 - Victorville | Rurals | SBRO |  |  | 3205400 | 1941750 | [5 empty] | false | 2021-07-30 | 2021-08-17 | 13 | 13 | 2021-07-29 | 2021-07-29 | 14 | 14 | 1 | 1 | 2021-08-04 |  | 2021-08-23 |  |  |  |  | 2021-11-05 | 71 | 71 | 2021-11-09 | 2021-11-10 | 2021-12-29 | 2022-01-05 | 40 | 40 | 2022-01-06 | 2022-01-11 | 4 | 4 | 2022-02-02 | 2022-02-16 | 26 | 26 | 2022-02-16 | 1 | 1 | 2022-02-16 |  | 2022-02-16 |  | 1 | 1 |  |  |  |  | 2022-01-25 | 2022-03-14 |  | -17 | [11 empty] | 2022-02-16
854 | County of Ventura County APCD Mtr Only | 4567 Telephone Road | Ventura | 93003 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3140270 | [6 empty] | false |  |  |  |  | 2021-07-12 | 2021-07-12 |  |  | 1 | 1 | 2021-07-13 |  | 2021-07-23 | [7 empty] | 2021-07-28 | 2021-08-01 | 2021-08-30 | [8 empty] | 2021-09-16
855 | Santa Monica - Shore Hotel | 1515 Ocean Ave | Santa Monica | 90401 | Los Angeles County | 10. Customer Hold | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2022-01-13 | 2022-01-18 | 3 | 3 | 2021-08-02 | [5 empty] | 2021-08-03 |  | 2021-08-17 |  |  |  |  | 2022-01-13 | 114 | 114
856 | Whittier - Los Olivos Apartments | 14300 Mulberry Drive | Whittier | 90604 | Los Angeles County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3183050 | 1935646 | [5 empty] | NO |  |  |  |  | 2021-08-03 | 2021-08-03 |  |  | 1 | 1 | [10 empty] | 2021-10-01 | 2021-10-04 | 2022-01-04 | 2022-01-10 |  |  | 2022-01-10 |  |  |  |  | 2022-01-18
857 | Norwalk - Imperial Palm Apartments | 12016 Imperial Highway | Norwalk | 90650 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra |  |  | 3247950 | 1972171 | [5 empty] | NO |  |  |  |  | 2021-08-03 | 2021-08-03 |  |  | 1 | 1 | [10 empty] | 2022-02-03 | 2022-02-08 | 2022-03-21 | 2022-03-24 |  |  | 2022-03-24 |  |  |  |  | 2022-03-24
858 | Buena Park - Executive Park Apartments (old address 7601 Franklin, new address 7601 1/2 Franklin) | 7601 1/2 Franklin Street | Buena Park | 90621 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3182123 | 1927632 |  | 2024-03-31 | 2 | NO |  | NO |  |  |  |  | 2021-08-03 | 2021-08-03 |  |  | 1 | 1 |  |  | 2021-08-16 | [7 empty] | 2021-09-30 | 2021-09-30 | 2022-05-23 | 2022-06-07 |  |  | 2022-06-07 | 2022-08-31 | 61 | 61 | 2022-09-21 | 2022-09-27 | 19 | 19 | [13 empty] | 2022-08-30 |  |  | -20 | [5 empty] | 2024-02-05 |  |  | 2024-02-26 | 15 | 15 | [6 empty] | 342 | 342 | [18 empty] | 2024-02-07 |  |  |  |  | 2024-02-28 | 2024-03-13 | 11 | 11 | 2024-03-13 | 11 | 11 | 2024-03-13 |  |  |  | 658 | 658 |  |  | 2024
859 | Kaykel Investments - Fueling Convenience | 16125 Baseline Ave, Unit 2 | Fontana | 92336 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 3151325 | 1930450 |  |  | 2 |  |  | true |  |  |  |  | 2021-08-05 | 2021-08-05 |  |  | 1 | 1 |  |  | 2021-08-13 | [7 empty] | 2021-08-16 | 2021-08-19 | 2021-09-17 | 2021-09-21 |  |  | 2021-09-21 | 2021-09-27 | 5 | 5 | 2021-10-18 | 2021-12-01 | 45 | 45 | 2021-12-01 | 1 | 1 | 2021-12-01 | 2022-01-24 | 2021-12-01 | 2022-03-02 | 1 | 1 | 107 | 107 | 63 | 63 | [23 empty] | 2022-01-04 | 2022-01-20 | 2022-01-20 | 12 | 12 |  |  | 2021-12-03 | [9 empty] | 2022-03-03 | 2022-03-08 |  |  | 4 | 4 | 2022-03-14 | 2022-04-20 | 28 | 28 | 2022-04-21 | 29 | 29 | 2022-04-21 |  |  |  | 179 | 179 |  |  | 2022
860 | Santa Monica Place - Phase 2 | 395 Santa Monica Place | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 2394020 | 1885124 |  |  | 6 |  |  | NO |  |  |  |  | 2021-08-04 | 2021-08-03 |  |  | -2 |  | 2021-08-03 | [12 empty] | 2021-08-04 |  |  | 2021-08-04 |  |  |  |  | 2021-08-05 |  |  | 2021-08-05 | 1 | 1 | 2021-08-16 | 2021-08-18 | [17 empty] | 2021-08-06 | 2 | 2 | 2021-09-14 | 27 | 27 | [6 empty] | 2 | 2 | [23 empty] | 2021-09-15 |  |  |  | 2021-10-15 | 23 | 23 | 2021-10-15 |  |  |  | 52 | 52 |  |  | 2021
861 | Tower Market Rancho Mirage | 37800 Monterey Ave | Rancho Mirage | 92270 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO |  |  | 3156410 | 1918848 | [5 empty] | YES |  |  |  |  | 2021-08-05 | 2021-08-05 |  |  | 1 | 1 | 2021-08-06 |  | 2021-08-20 | [7 empty] | 2021-08-23 | 2021-09-02 | 2021-10-01 | 2021-10-22 |  |  | 2021-10-22
862 | Santa Paula Center - 210536 Brixmor | 542 W Main St | Santa Paula | 93060 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3189663 | 1918326 |  | 2023-12-15 | 4 | NO | Level 3 | NO | 2021-08-06 | 2021-08-21 | 11 | 11 | 2021-08-06 | 2021-08-06 | 11 | 11 | 1 | 1 | 2021-08-06 |  | 2021-08-18 |  |  |  |  | 2021-10-01 | 40 | 40 | 2023-10-16 | 2023-10-19 | 2021-11-24 | 2021-12-06 | 44 | 44 | 2021-12-08 | 2022-01-26 | 34 | 34 | 2023-11-13 | 2023-11-13 | 457 | 457 | 2023-11-13 | 1 | 1 | 2022-02-24 | 2022-02-24 | 2023-10-31 | 2023-11-15 | -10 |  | 459 | 459 | 12 | 12 | 2022-02-17 | 2022-03-02 | 2022-05-10 | -441 |  | 50 | 50 | 58 | 58 | [6 empty] | 2022-03-02 |  | 2023-11-15 | [23 empty] | 2023-11-06 |  |  |  |  | 2023-11-15 | 2023-11-30 | 10 | 10 |  |  |  | 2023-12-19 |  |  |  | 598 | 598 | 559 | 559 | 2023
863 | City Hall & City Hall West | 6615 Passons Blvd | Pico Rivera | 90660 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-08-09
864 | South Gate, CA - Firestone Blvd | 4635 Firestone Blvd | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | true | 2021-08-16 | 2021-08-30 | 11 | 11 | 2021-08-09 | 2021-08-09 | 16 | 16 | 1 | 1 | 2021-08-09 |  | 2021-08-27
865 | Bellflower, CA - Rosecrans Ave | 9045 Rosecrans Avenue | Bellflower | 90706 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | true | 2021-08-06 | 2021-08-25 | 14 | 14 | 2021-08-09 | 2021-08-09 | 13 | 13 | 1 | 1 | 2021-08-09 |  | 2021-08-27
866 | Torrance, CA - 20715 Hawthorne Blvd | 20715 Hawthorne Blvd | Torrance | 90503 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2021-08-17 | 2021-08-24 | 6 | 6 | 2021-08-09 | 2021-08-09 | 12 | 12 | 1 | 1 | 2021-08-09 |  | 2021-08-25
867 | Torrance, CA - 22929 Hawthorne Blvd | 22929 Hawthorne Blvd | Torrance | 90505 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2021-08-25 | 2021-08-25 | 1 | 1 | 2021-08-09 | 2021-08-09 | 13 | 13 | 1 | 1 | 2021-08-09 |  | 2021-08-25
868 | FAT2 Riggen Visalia | 8730 W Riggin Ave | Visalia | 92391 | Tulare County | 10. Customer Hold | 51 - Tulare | San Joaquin | Ventura |  |  | 3164860 | 1916380 |  |  | 10 | NO |  | NO |  |  |  |  | 2021-08-12 | 2021-08-12 |  |  | 1 | 1 | 2021-08-12 |  | 2021-08-26 | [7 empty] | 2021-09-03 | 2021-09-08 | 2021-10-06 | 2021-10-20 |  |  | 2021-10-20 | 2021-10-25 | 4 | 4 |  | 2021-11-15 | 15 | 15 | 2021-11-15 | 1 | 1 | 2022-11-29 | 2022-11-29 | 2022-11-29 | 2022-12-09 | 261 | 261 | 283 | 283 | 9 | 9 | 2021-12-09 | 2022-01-07 | 2022-06-20 | 17 | 17 | 114 | 114 | 134 | 134 | 2022-08-02 | 180 | 180 | 2022-08-10 | 7 | 7 | 2022-01-07 | 2022-01-07 | 2022-12-09 | 2022-12-09 | 233 | 233 | 180 | 180 | 2023-07-14 | 2023-07-27 | 2023-08-01 | 13 | 13 | 2021-11-18 |  |  | 2021-11-24 | 5 | 5 | [7 empty] | 2023-07-08 | 412 | 412 |  |  | 2023-08-21 | 2023-11-01 | 52 | 52 | 2023-11-02 | 53 | 53 | 2023-11-02 |  |  |  | 563 | 563 |  |  | 2023
869 | Camarillo - Petit St | 2911 Petit St | Camarillo | 93012 | Ventura County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3182040 | 1912899 | [5 empty] | YES |  |  |  |  | 2021-08-16 | 2021-08-18 |  |  | 3 | 3 | 2021-08-18 |  | 2021-08-23 | [7 empty] | 2021-09-30 | 2021-10-05 | 2021-11-19 | 2021-11-18 |  |  | 2021-11-18 | 2021-11-29 | 6 | 6 | 2021-12-23 | 2021-12-27 | 20 | 20 | 2022-01-04 | 7 | 7 | 2022-01-10 | 2022-01-19 | 2022-01-10 |  | 11 | 11 | [32 empty] | 2022-02-23
870 | City of Industry, CA - old address 17501 Colima Rd | 17501 1/2 Colima Rd | City of Industry | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3255119 | 1976793 |  |  | 12 | NO |  | YES | 2021-08-18 | 2021-08-30 | 9 | 9 | 2021-08-18 | 2021-08-18 | 9 | 9 | 1 | 1 | 2021-08-18 |  | 2021-08-27 |  |  |  |  | 2022-02-11 | 122 | 122 | 2022-02-16 | 2022-02-28 | 2022-04-01 | 2022-04-11 | 41 | 41 | 2022-04-11 | 2022-06-08 | 42 | 42 | 2022-07-11 | [6 empty] | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-27 |  |  | 35 | 35 | 11 | 11 | 2022-11-18 | 2022-11-21 | 2022-12-14 |  |  | 16 | 16 | 17 | 17 | 2023-08-10 |  |  | 2023-08-25 | 12 | 12 | 2022-07-13 | 2022-07-13 | 2022-12-14 | 2023-08-25 | 285 | 285 |  |  | 2023-08-11 | 2023-09-12 | 2023-09-12 | 22 | 22 | 2023-05-15 | 2023-09-18 | 2023-09-12 | 2023-06-13 | 21 | 21 |  |  |  | 2023-09-12 | 1 | 1 | 2023-09-18 | 2023-09-22 | 92 | 92 | 5 | 5 | 2023-09-29 | [6 empty] | 2023-11-14 |  |  |  | 567 | 567 | 446 | 446 | 2023
871 | Upland, CA - 1234 W Foothill Blvd | 1234 W Foothill Blvd | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO | 2021-08-18 | 2021-09-20 | 23 | 23 | 2021-08-18 | 2021-08-19 | 22 | 22 | 2 | 2 | 2021-08-19 | 2021-10-05 | 2021-10-18 | 33 | 33 | 10 | 10
872 | Montebello - Taylor Ave | 400 S Taylor Avenue | Montebello | 90640 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-08-18 | 2021-08-18 |  |  | 1 | 1 | 2021-08-19 |  | 2021-08-30
873 | F&E Signal Hill #1278 R29 | 2475 Cherry Ave-EV | Signal Hill | 90755 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3544693 | 2145252 | 2145673 | 2024-07-24 | 8 | YES | Level 3 | NO | 2023-04-17 | 2023-05-31 | 32 | 32 | 2023-03-13 | 2023-03-24 | 48 | 48 | 10 | 10 | 2023-03-27 | 2023-04-03 | 2023-04-15 | 7 | 7 | 10 | 10 | 2023-04-17 | 26 | 26 | 2023-06-06 | 2023-06-07 | 2023-07-21 | 2023-07-18 | 65 | 65 | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-08-29 | 2023-09-06 | 35 | 35 | 2023-09-07 | 2 | 2 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-27 | 14 | 14 | 50 | 50 | 3 | 3 | 2023-11-20 | 2023-12-01 |  | 54 | 54 | [10 empty] | 2023-09-25
874 | WinCo Foods Ventura | 4750 Telephone Rd | Ventura | 93003 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  |  | 3196661 |  |  |  |  | NO |  | true |  |  |  |  | 2021-08-18 | 2021-08-18 |  |  | 1 | 1 | 2021-08-18 |  | 2021-08-23 |  |  |  |  | 2022-05-19 | 190 | 190 | 2021-10-26 | 2021-10-28 | 2022-07-11 | 2021-11-26 | -121 |  |  | 2022-06-23 |  |  | 2022-08-16 | 2022-07-22 | 21 | 21 | 2022-10-21 | 65 | 65 | 2022-10-21 | 2023-01-17 | 2022-10-21 | 2023-01-13 | 65 | 65 | 142 | 142 | 58 | 58 | 2022-09-27 | 2022-10-07 |  | 47 | 47 | [10 empty] | 2022-10-07
875 | Diamond Bar - Diamond Hills Plaza | 2825 S Diamond Bar Blvd | Diamond Bar | 91765 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3202487 | 1953201 |  |  | 8 |  |  | YES |  |  |  |  | 2021-08-19 | 2021-08-19 |  |  | 1 | 1 | 2021-08-19 |  | 2021-08-31 | [7 empty] | 2021-11-03 | 2021-11-09 | 2021-12-24 | 2021-12-24 |  |  |  | 2022-02-02 |  |  | 2022-02-25 | 2022-03-04 | 22 | 22 | 2022-03-07 | 2 | 2 | 2022-03-09 | 2022-03-29 | 2022-03-09 | 2022-03-14 | 4 | 4 | 28 | 28 | 4 | 4 | [23 empty] | 2022-04-12 | 2022-04-22 | 2022-04-22 | 9 | 9 |  |  | 2022-04-06 | [6 empty] | 2022-04-11 | 4 | 4 | 2022-04-25 | 2022-05-05 |  |  | 9 | 9 | 2022-05-06 | [6 empty] | 2022-06-08 |  |  |  | 202 | 202 |  |  | 2022
876 | Green Tree Inn | 14173 Green Tree Blvd | Victorville | 92395 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 3194061 | 1921902 |  |  | 6 | NO |  | NO | 2021-08-19 | 2021-08-27 | 7 | 7 | 2021-08-19 | 2021-08-19 | 7 | 7 | 1 | 1 | 2021-08-19 |  | 2021-08-30 | [7 empty] | 2021-10-20 | 2021-10-20 | 2022-04-11 | 2021-11-22 |  |  |  | 2022-06-21 |  |  | 2022-07-15 | 2022-07-25 | 24 | 24 | 2022-07-25 | 1 | 1 | 2022-09-08 | 2022-09-08 | 2022-09-08 | 2022-09-27 | 33 | 33 | 69 | 69 | 14 | 14 | 2022-07-27 | 2022-08-01 | 2022-10-07 | 3 | 3 | 49 | 49 | 52 | 52 | [6 empty] | 2022-08-01 |  | 2022-10-07 | [5 empty] | 2022-10-12 | 2022-10-20 | 2022-10-20 | 7 | 7 | 2022-08-09 | [11 empty] | 2022-10-20 | 2022-11-04 | 63 | 63 | 12 | 12 | 2022-11-07 | 2023-01-12 | 46 | 46 | 2023-01-13 | 47 | 47 | 2023-01-13 |  |  |  | 354 | 354 |  |  | 2023
877 | Signal Hill - Cerritos Ave | 2421 Cerritos Ave | Signal Hill | 90755 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 3281760 | 1975414 | [5 empty] | NO | 2021-08-26 | 2021-09-13 | 12 | 12 | 2021-08-25 | 2021-08-25 | 13 | 13 | 1 | 1 | 2021-08-26 | 2021-08-26 | 2021-09-07 | 2 | 2 | 8 | 8 |  |  |  | 2021-09-16 | 2021-09-17 | 2022-03-30 | 2022-03-31 |  |  | 2022-03-31
878 | Casa Moreno Apartments | 13705 Sunkist Drive | La Puente | 91746 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona |  | 10417 | 3182975 | 1929716 |  |  |  | NO |  | NO |  |  |  |  | 2021-08-25 | 2021-08-25 |  |  | 1 | 1 | 2021-08-26 |  | 2021-09-07 | [7 empty] | 2021-10-01 | 2021-10-07 | 2021-11-23 | 2021-11-23 |  |  |  | 2021-12-06 |  |  | 2021-12-28 | [56 empty] | 2022-09-19 | 2022-09-19 |  |  | 1 | 1 | 2022-09-20
879 | Valencia - Creekside Rd | 24055 Creekside Rd | Valencia | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 3302820 | 2003286 |  |  |  | NO |  | YES | 2021-09-27 | 2021-10-05 | 7 | 7 | 2021-08-25 | 2021-08-26 | 28 | 28 | 2 | 2 | 2021-08-26 |  | 2021-08-31 |  |  |  |  | 2022-04-29 | 171 | 171 | 2021-09-09 | 2021-09-13 | 2022-06-17 | 2022-06-20 | 36 | 36 | 2022-06-21 | 2022-07-19 | 20 | 20 | 2022-08-18 | [6 empty] | 2022-08-18 | 2022-12-09 | 2022-08-18 | 2022-08-22 |  |  | 25 | 25 | 3 | 3 | 2022-11-29 | 2022-12-06 | 2022-12-08 |  |  | 3 | 3 | 8 | 8 | [6 empty] | 2022-08-18 |  | 2022-12-08 | [10 empty] | 2022-12-15 |  |  | 2022-12-20 | 4 | 4
880 | Valencia, CA - 28273 Newhall Ranch Rd | 28241.5 Newhall Ranch Rd | Santa Clarita | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  | Nighthawk 16KV | 3424828 | 2062942 |  |  | 24 | NO |  | NO | 2021-08-26 | 2022-11-15 | 308 | 308 | 2021-08-26 | 2021-08-30 | 306 | 306 | 3 | 3 | 2021-08-30 |  | 2021-09-27 | [7 empty] | 2022-11-17 | 2022-11-17 |  | 2023-01-08 |  |  | 2023-01-10 | 2023-02-08 | 21 | 21 | 2023-03-02 | 2023-07-06 | 104 | 104 | 2023-04-05 | -65 |  | 2023-07-10 | 2023-08-08 | 2023-07-10 | 2023-07-27 | 3 | 3 | 119 | 119 | 14 | 14 | 2023-04-04 | 2023-05-15 | 2023-05-15 | -66 |  | 1 | 1 | 30 | 30 | 2023-09-18 | 116 | 116 | 2023-09-21 | 4 | 4 | 2023-05-15 | 2023-05-15 | 2023-07-27 | 2023-09-21 | 91 | 91 | 52 | 52 | 2023-09-21 | 2023-10-09 | 2023-10-10 | 14 | 14 | 2023-07-14 |  |  | 2023-07-19 | 4 | 4 | [6 empty] | 2023-10-11 | 2023-10-22 | 70 | 70 | 8 | 8 | 2023-10-26 | 2023-11-30 | 24 | 24 | 2023-12-01 | 25 | 25
881 | Chetonian Ultra Gas Mart - Phase 2 | 71808 Baker Blvd | Baker | 92309 | San Bernardino County | 7. Civil Construction | 72 - Barstow | Rurals | SBRO |  |  | 3160172 | 1915560 |  |  | 24 |  |  | YES |  |  |  |  | 2021-08-27 | 2022-03-07 |  |  | 130 | 130 | 2022-03-07 | [9 empty] | 2021-08-27 | 2021-09-02 | 2021-10-18 | 2021-10-18 |  |  | 2021-10-18 | 2021-11-01 | 11 | 11 | 2021-11-24 | 2021-12-01 | 20 | 20 | 2021-12-01 | 1 | 1 | 2021-12-03 | 2021-12-03 | [37 empty] | 2022-03-04 | [11 empty] | 2022-05-04 |  |  |  |  | 2022-05-19 |  |  |  | 2022-06-14 | 18 | 18 | 2022-06-14 |  |  |  | 200 | 200 |  |  | 2022
882 | Shoshone - Highway 127 | 491 State Hwy 127 | Shoshone | 92384 | Inyo County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 3263660 | 1995200 | 2174764 | 2024-04-30 |  | NO | Level 3 | YES | 2021-08-30 | 2021-09-30 | 23 | 23 | 2021-08-10 | 2021-08-18 | 31 | 31 | 7 | 7 | 2021-08-18 | 2021-08-30 | 2021-08-30 | 9 | 9 | 1 | 1 |  |  |  | 2022-03-03 | 2022-03-07 | 2022-05-11 | 2022-07-20 |  |  | 2022-07-21 | 2022-07-21 | 1 | 1 | 2022-08-12 | 2022-08-12 | 17 | 17 | 2022-08-10 | -3 |  | 2022-11-21 | 2022-08-21 | 2022-11-21 | 2022-11-29 | 70 | 70 | 90 | 90 | 5 | 5 | 2022-08-25 | 2022-09-26 | 2023-01-16 | 10 | 10 | 77 | 77 | 98 | 98 | [6 empty] | 2022-09-26 |  | 2023-01-16 | [10 empty] | 2024-01-08 |  |  | 2024-01-23 | 11 | 11
883 | Lakewood, CA- 5923U South Street | 5923U South Street | Lakewood | 90713 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3228325 | 1951012 |  |  | 25 |  |  | NO | 2021-08-30 | 2021-09-14 | 11 | 11 | 2021-08-30 | 2021-08-30 | 11 | 11 | 1 | 1 |  |  | 2021-09-13 |  |  |  |  | 2021-12-10 | 71 | 71 | 2021-12-22 | 2021-12-28 | 2022-02-09 | 2022-02-02 | 37 | 37 | 2022-02-02 | 2022-02-07 | 4 | 4 | 2022-03-03 | 2022-03-16 | 27 | 27 | 2022-03-16 | 1 | 1 | 2022-04-12 | 2022-04-12 | 2022-04-12 | 2022-04-25 | 20 | 20 | 55 | 55 | 10 | 10 | 2022-03-16 | 2022-04-20 | 2022-05-31 | 1 | 1 | 29 | 29 | 54 | 54 | 2022-09-21 | 133 | 133 | 2022-10-25 | 25 | 25 | 2022-04-12 | 2022-04-12 | 2022-05-31 | 2022-10-25 | 138 | 138 | 133 | 133 | [18 empty] | 2022-10-16 |  |  |  |  | 2022-10-26 |  |  |  | 2022-12-02 | 25 | 25 | 2022-12-02 |  |  |  | 317 | 317 | 247 | 247 | 2022
884 | Brea - W Imperial Highway | 305 W Imperial Hwy | Brea | 92621 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2021-08-31 | [5 empty] | 2021-09-02 | 2021-09-07
885 | Yucca Valley - 29 Palms Highway | 57677 29 Palms Highway | Yucca Valley | 92284 | San Bernardino County | 11. Cancelled | 84 - 29 Palms | Rurals | SBRO | [9 empty] | YES |  | 2021-10-20 |  |  | 2021-09-01 | 2021-09-02 | 34 | 34 | 2 | 2 | 2021-09-02 |  | 2021-09-16
886 | La Puente - Hacienda Blvd | 1801 N Hacienda Blvd | La Puente | 91744 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2021-09-01 | 2021-09-03 | 3 | 3 | 2021-09-02 | 2021-09-02 | 2 | 2 | 1 | 1 | 2021-09-02 |  | 2021-09-17
887 | La Crescenta Ralphs | 2675 Foothill Blvd EV | La Crescenta | 91214 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3447958 | 2097349 |  | 2023-09-11 |  | NO |  | YES | 2023-01-04 | 2023-01-12 | 7 | 7 | 2021-09-02 | 2021-09-02 | 343 | 343 | 1 | 1 | 2021-09-02 |  | 2021-09-18 |  |  |  |  | 2023-01-04 | 337 | 337 | 2023-01-04 | 2023-01-09 | 2023-02-23 | 2023-02-23 | 35 | 35 | 2023-02-23 | 2023-02-27 | 3 | 3 | 2023-03-20 | 2023-03-21 | 17 | 17 | 2023-03-21 | 1 | 1 | 2023-04-25 |  | 2023-04-25 |  | 26 | 26
888 | Corona - Limonite Ave | 12660 Limonite Ave | Corona | 92880 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2021-09-01 | 2021-09-16 | 11 | 11 | 2021-09-02 | 2021-09-02 | 10 | 10 | 1 | 1 | 2021-09-02
889 | Friendly Hills Marketplace-Whittier R29 | 15311 Whittier Blvd | Whittier | 90603 | Los Angeles County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | Telegraph | Mercado 12kV | 3267799 | 2029706 | 2020698 |  | 8 | YES | Level 3 | YES | 2022-03-07 | 2022-03-09 | 3 | 3 | 2022-07-12 | 2021-09-02 | 128 | 128 | -215 |  | 2021-09-02 | 2021-09-02 | 2021-09-13 | 1 | 1 | 7 | 7 | 2022-07-12 | 1 | 1 | 2022-07-12 | 2022-07-15 | 2022-08-26 | 2022-08-29 | 35 | 35 | 2022-08-30 | 2022-08-30 | 1 | 1 | 2022-09-26 | 2022-09-20 | 15 | 15 | 2022-09-20 | 1 | 1 | 2022-11-09 | 2023-01-18 | 2022-11-09 |  | 37 | 37 |  |  |  |  | 2022-09-20 | 2022-09-23 | 2022-10-14 | 1 | 1 | 16 | 16 | 19 | 19 | 2022-10-12 | 17 | 17 | 2022-11-15 | 24 | 24 | 2022-09-23 | 2022-09-23 |  |  |  |  | 17 | 17 | 2022-11-22 | 2022-12-08 | 2023-01-11 | 35 | 35 | 2022-09-07 | 2022-11-09 | 2022-12-07 | 2022-09-19 | 9 | 9 | 2022-11-17 | 6 | 6 | 2022-12-13 | 5 | 5 | 2023-02-02 | 2023-02-13 | 110 | 110 | 8 | 8 | 2023-02-15 | 2023-04-06 | 36 | 36 | 2023-04-06 | 36 | 36 | 2023-04-06 |  |  |  | 187 | 187 | 187 | 187 | 2023
890 | Garrison Equity-Mountain Shadows Plaza R29 | 3693 E Highland Ave | Highland | 92346 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  | Goldbuckle 12kv | 3348366 |  |  |  | 5 | YES |  | YES | 2023-05-01 | 2023-05-02 | 2 | 2 | 2023-04-13 | 2023-04-13 | 14 | 14 | 1 | 1 | 2023-04-17 | 2023-04-25 | 2023-04-28 | 9 | 9 | 4 | 4 | 2023-04-12 | -2 |  | 2023-05-17 | 2023-05-22 | 2023-07-05 |  |  |  |  | 2022-11-03
891 | Ontario, CA - 2920 S Archibald Ave | 2920 S Archibald Ave | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2021-09-02 | 2021-09-16 | 10 | 10 | 2021-09-02 | 2021-09-02 | 10 | 10 | 1 | 1 | 2021-09-02 |  | 2021-09-23
892 | Brea, CA - 2435 E Imperial Hwy | 2435 E Imperial Hwy | Brea | 92821 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | YES | 2021-09-02 | 2021-10-06 | 24 | 24 | 2021-09-02 | 2021-09-02 | 24 | 24 | 1 | 1 | 2021-09-02 |  | 2021-09-22
893 | San Gabriel, CA - 301 W Valley Blvd | 301 W Valley Blvd | San Gabriel | 91776 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | YES | 2021-09-02 |  |  |  | 2021-09-02 | 2021-09-02 |  |  | 1 | 1 | 2021-09-02
894 | Fontana, CA - 16833 Valley Blvd | 16833 Valley Blvd | Fontana | 92335 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO | [9 empty] | NO | 2021-09-02 | 2021-09-07 | 3 | 3 | 2021-09-02 | 2021-09-02 | 3 | 3 | 1 | 1 | 2021-09-02 |  | 2021-09-27
895 | Moorpark - Moorpark Ave | 530 Moorpark Ave | Moorpark | 93021 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3206151 | 1928825 |  |  | 4 | NO |  | NO |  |  |  |  | 2021-09-02 | 2021-09-02 |  |  | 1 | 1 | 2021-09-02 |  | 2021-09-15 | [7 empty] | 2021-11-10 | 2021-11-12 | 2021-12-30 | 2022-01-03 |  |  | 2022-01-04 | 2022-01-05 | 2 | 2 | 2022-01-31 | 2022-02-01 | 19 | 19 | 2022-02-03 | 3 | 3 | 2022-02-03 | 2022-02-24 | 2022-02-03 | 2022-02-03 | 3 | 3 | 21 | 21 | 1 | 1 | 2022-02-03 | 2022-04-22 | 2022-06-20 | 3 | 3 | 41 | 41 | 96 | 96 | 2022-10-10 | 174 | 174 |  |  |  | 2022-02-03 | 2022-02-03 | 2022-06-20 |  |  |  | 176 | 176 | 2022-10-13 | 2022-10-26 |  |  |  | 2022-06-07 |  | 2022-10-04 | [9 empty] | 2022-10-04 | 2022-10-26 | 100 | 100 | 17 | 17 | 2022-11-01 |  |  |  | 2023-05-11 | 133 | 133 | 2023-05-11 |  |  |  | 426 | 426 |  |  | 2023
896 | Redondo Beach - PCH | 1800 S Pacific Coast Highway | Redondo Beach | 90277 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2021-09-02 | 2021-09-13 | 7 | 7 | 2021-09-02 | 2021-09-02 | 7 | 7 | 1 | 1 | 2021-09-02
897 | Thousand Oaks - Canejo Gateway Plaza | 699 Wendy DR | Thousand Oaks | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3227068 | 1943793 |  |  | 8 | NO |  | YES | 2021-12-20 | 2021-12-21 | 2 | 2 | 2021-09-02 | 2021-09-02 | 75 | 75 | 1 | 1 | 2021-09-02 | 2022-09-02 | 2021-09-13 | 253 | 253 | -247 |  | 2021-09-15 | 9 | 9 | 2021-12-20 | 2021-12-21 | 2022-02-07 | 2022-02-04 | 98 | 98 | 2022-02-07 | 2022-02-09 | 3 | 3 | 2022-03-04 | 2022-03-09 | 20 | 20 | 2022-03-10 | 2 | 2 | 2022-10-21 | 2022-03-29 | 2022-10-21 | 2022-03-14 | 160 | 160 | 23 | 23 | -157 |  | 2022-03-02 | 2022-10-07 | 2022-10-31 | -6 |  | 17 | 17 | 171 | 171 | 2022-07-12 | 87 | 87 | 2022-09-13 | 45 | 45 | 2022-10-07 | 2022-07-12 | 2022-10-31 | 2022-10-31 | 79 | 79 | 88 | 88 | [5 empty] | 2022-09-27 |  |  | 2022-10-13 | 13 | 13 | 2022-10-04 | -8 |  |  |  |  | 2022-11-04 | 2022-11-18 | 38 | 38 | 10 | 10 | 2022-11-21 | 2023-01-12 | 37 | 37 | 2023-01-13 | 38 | 38 | 2022-12-29 |  |  |  | 333 | 333 | 325 | 325 | 2022
898 | El Segundo, CA - 2200 E Imperial Hwy | 2200 E Impeerial Highway | El Segundo | 90245 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2021-09-02 | 2021-09-13 | 7 | 7 | 2021-09-02 | 2021-09-03 | 6 | 6 | 2 | 2 | 2021-09-02 |  | 2021-09-15
899 | Santa Barbara - Turnpike Rd | 191 S Turnpike Rd | Santa Barbara | 93111 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3280786 | 1986927 |  |  |  | NO |  | YES | 2022-02-23 | 2022-03-09 | 11 | 11 | 2021-09-02 | 2022-02-14 | 17 | 17 | 112 | 112 | 2022-02-15 | 2022-02-22 | 2022-02-23 | 6 | 6 | 2 | 2 | 2022-02-11 | 111 | 111 | 2023-01-24 | 2022-03-31 | 2022-05-12 | 2022-05-27 | 75 | 75 | 2022-05-31 | 2022-06-01 | 2 | 2 | 2022-06-24 | 2022-07-07 | 26 | 26 | 2022-07-12 | 4 | 4 | 2022-07-12 | 2022-08-23 | 2022-07-12 | 2022-07-21 | 4 | 4 | 36 | 36 | 8 | 8 | 2022-07-08 | 2022-08-31 | 2022-09-22 | 2 | 2 | 16 | 16 | 54 | 54 | [6 empty] | 2022-07-12 |  | 2022-09-22
900 | Redlands - N Orange St | 550 N Orange Street | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | YES | 2021-09-02 | 2021-09-07 | 3 | 3 | 2021-09-02 | 2021-09-03 | 2 | 2 | 2 | 2 | 2021-09-03 |  | 2021-09-17
901 | Lake Forest - El Toro Rd | 23716 El Toro Rd | Lake Forest, CA 92630 | 92630 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2021-09-02 | 2021-09-15 | 9 | 9 | 2021-09-02 | 2021-09-07 | 7 | 7 | 3 | 3 | 2021-09-07 |  | 2021-09-20
902 | Goleta Fairview Center | 125 N Fairview Ave | Goleta | 93117 | Santa Barbara County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura | Vegas | Gaucho 16kv | 3349527 |  |  | 2024-08-30 | 4 | YES | Level 3 | YES | 2022-07-12 | 2022-07-15 | 4 | 4 | 2023-06-30 | 2023-06-30 | -244 |  | 1 | 1 | 2023-07-05 | 2023-07-06 | 2023-08-02 | 4 | 4 | 20 | 20
903 | Ventura, CA - 4095 Telegraph Rd | 43 N Ashwood Ave, #US | Ventura | 93003 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3255539 | 1965132 |  |  | 12 | NO |  | YES | 2021-09-07 | 2021-09-15 | 7 | 7 | 2021-09-07 | 2021-09-07 | 7 | 7 | 1 | 1 | 2021-09-08 |  | 2021-09-20 |  |  |  |  | 2022-02-15 | 111 | 111 | 2022-08-05 | 2022-08-05 | 2022-04-12 | 2022-04-12 | 40 | 40 | 2022-04-13 | 2022-04-13 | 1 | 1 | 2022-05-04 | 2022-05-04 | 16 | 16 | 2023-04-19 | 243 | 243 | 2023-04-19 |  | 2023-04-19 |  | 243 | 243 |  |  |  |  | 2022-06-06 | 2022-10-24 | 2022-12-12 | 23 | 23 | 33 | 33 | 131 | 131 | 2023-04-13 | -5 |  | 2023-05-16 | 24 | 24 | 2022-10-24 | 2022-10-24 |  |  |  |  | 239 | 239 | [5 empty] | 2023-01-03 | [12 empty] | 2023-04-14 | 72 | 72 |  |  | 2023-05-15 | 2023-05-23 | 7 | 7 | 2023-06-27 | 31 | 31
904 | Redondo Beach - 1611 S Catalina Ave | 1611 S Catalina Ave | Redondo Beach | 90277 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-12-21 |  |  |  | YES |  |  |  |  | 2023-05-02 | 2023-05-02 |  |  | 1 | 1 | 2023-05-02 | 2023-05-10 | 2023-05-26 | 7 | 7 | 13 | 13
905 | Oxnard - Esplanade Shopping Center | 369 W Esplanade Dr - EV | Oxnard | 93036 | Ventura County | 10. Customer Hold | 39 - Ventura | North Coast | Ventura |  |  | 3259650 | 1963770 |  | 2024-11-14 | 4 |  |  | YES | 2022-02-09 | 2022-02-23 | 10 | 10 | 2023-06-27 | 2023-07-14 | -353 |  | 13 | 13 | 2023-07-19 | 2023-07-20 | 2023-07-22 | 5 | 5 | 2 | 2 | 2022-09-13 | -200 |  | 2022-02-24 | 2022-02-24 | 2022-04-11 | 2022-10-31 | 35 | 35 | 2022-11-01
906 | Rancho Cucamonga - Foothill Blvd | 9339 Foothill Blvd Ste E | Rancho Cucamonga | 91730 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO | [9 empty] | NO | 2021-09-07 |  |  |  | 2021-09-07 | 2021-09-07 |  |  | 1 | 1 | 2021-09-07 |  | 2021-09-30
907 | Norwalk - Civic Center Plaza | 12241 E Imperial Highway | Norwalk | 90650 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 3229260 | 1949951 |  |  | 6 | NO |  | YES |  | 2021-12-28 |  |  | 2021-09-07 | 2021-09-07 | 77 | 77 | 1 | 1 | 2021-09-07 |  | 2021-09-14 |  |  |  |  | 2021-12-22 | 74 | 74 | 2021-12-27 | 2021-12-27 | 2022-02-11 | 2022-02-03 | 30 | 30 | 2022-02-03 | 2022-02-09 | 5 | 5 | 2022-03-10 | 2022-04-26 | 54 | 54 | 2022-04-27 | 2 | 2 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 126 | 126 | 179 | 179 | 1 | 1 | 2022-10-11 | 2022-10-19 | 2023-03-23 | 118 | 118 | 107 | 107 | 113 | 113 | [6 empty] | 2022-10-19 |  | 2023-03-23 | [5 empty] | 2022-12-12 | 2022-12-28 |  |  |  | 2022-10-14 |  |  | 2022-10-25 | 8 | 8 | [7 empty] | 2023-02-16 | 86 | 86 |  |  | 2023-03-27 | 2023-05-23 | 42 | 42 | 2023-05-23 | 42 | 42 | 2023-05-23 |  |  |  | 432 | 432 | 359 | 359 | 2023
908 | Mission Viejo Foothill Marketplace | 28715 Los Alisos Blvd-EV | Mission Viejo | 92692 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | Chiquita | Fizz 12kV | 3342983 |  |  | 2023-12-24 |  | YES |  | YES | 2022-06-29 | 2022-07-08 | 7 | 7 | 2021-09-07 | 2021-09-07 | 211 | 211 | 1 | 1 | 2021-09-07 |  | 2021-09-13 |  |  |  |  | 2023-05-05 | 420 | 420 | 2023-05-12 | 2023-05-12 | 2023-06-27
909 | Whittier, CA - 13809 Whittier Blvd | 13809 Whittier Blvd | Whittier | 90605 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES | 2021-09-09 |  |  |  | 2021-09-09 | [7 empty] | 2021-09-24
910 | West Covina, CA - 2650 E Garvey Ave S | 2650 E Garvey Ave S, Unit EV | West Covina | 91791 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3227489 | 1948589 |  |  | 16 |  |  | YES | 2021-09-09 | 2021-09-20 | 8 | 8 | 2021-09-09 | 2021-09-09 | 8 | 8 | 1 | 1 | 2021-09-09 |  | 2021-09-24 |  |  |  |  | 2021-12-16 | 68 | 68 | 2021-12-21 | 2022-12-23 | 2022-02-07 | 2022-02-04 | 35 | 35 | 2022-02-08 | 2022-02-16 | 7 | 7 | 2022-03-15 | 2022-03-15 | 19 | 19 | 2022-03-16 | 2 | 2 | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-25 | 16 | 16 | 48 | 48 | 15 | 15 | 2022-03-19 | 2022-05-02 | 2022-05-20 | 4 | 4 | 15 | 15 | 45 | 45 | 2022-09-09 | 125 | 125 | 2022-09-19 | 7 | 7 | 2022-04-05 | 2022-04-05 | 2022-05-20 | 2022-09-19 | 117 | 117 | 126 | 126 | 2022-08-05 |  | 2022-09-07 | 23 | 23 | [13 empty] | 2022-09-07 |  |  |  |  | 2022-09-16 |  |  |  | 2022-10-31 | 32 | 32 | 2022-10-31 |  |  |  | 289 | 289 | 222 | 222 | 2022
911 | Rancho Cucamonga, CA - 8635 Baseline Rd | 8635 Baseline Road | Rancho Cucamonga | 91730 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | YES | 2021-09-09 | 2021-10-11 | 23 | 23 | 2021-09-09 | 2021-09-09 | 23 | 23 | 1 | 1 | 2021-09-09 |  | 2021-10-26
912 | Covina, CA - 903 N Grand Ave | 903 N Grand Avenue | Covina | 91724 | Los Angeles County | 5. Final Design | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2021-09-09 | 2021-09-21 | 9 | 9 | 2021-09-09 | 2021-09-09 | 9 | 9 | 1 | 1 | 2021-09-09
913 | Ontario, CA - 1 Mills Circle | 1 Mills Circle | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3262738 | 1980575 |  | 2024-10-21 |  | YES | Level 3 | NO | 2021-09-09 | 2021-09-23 | 11 | 11 | 2021-09-09 | 2021-09-09 | 11 | 11 | 1 | 1 | 2021-09-09 |  | 2021-09-22 | [7 empty] | 2023-03-23 |  | 2023-05-06 | 2023-05-10 |  |  | 2023-05-10 | 2024-02-14 | 193 | 193 | 2024-03-12
914 | Rosamond - Rosamond Blvd | 2536 Rosamond Blvd | Rosamond | 93560 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura |  |  | 3282240 | 1985953 | [5 empty] | NO |  |  |  |  | 2021-09-13 | 2021-09-14 |  |  | 2 | 2 | 2021-09-14 |  | 2021-09-21 | [7 empty] | 2021-10-19 | 2021-10-21 | 2022-06-06 | 2022-05-12 |  |  | 2022-05-12
915 | Huntington Beach - Yorktown Ave | 7051 Yorktown Avenue | Huntington Beach | 92648 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3173890 | 1941179 | [5 empty] | NO |  |  |  |  | 2021-09-15 | 2021-09-02 |  |  | -9 |  | 2021-09-07 | 2021-09-10 | 2021-09-15 | 6 | 6 | 4 | 4 |  |  |  | 2021-09-17 | 2021-09-20 | 2021-10-04 | 2021-12-29 | [7 empty] | 2021-12-29 |  |  | 2022-01-05 | 6 | 6 | 2022-01-05 | 2022-01-05
916 | Inglewood - Century Blvd | 3540 E Century Blvd | Inglewood | 90303 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  | 2021-11-05 |  |  | 2021-09-17 | 2021-09-17 | 36 | 36 | 1 | 1 | 2021-09-22 |  | 2021-11-04
917 | Lakewood 2700 Carson St | 2724 Carson St | Lakewood | 90712 | Los Angeles County | 4. Preliminary Design | 46 - Long Beach | Metro West | Alhambra |  |  | 3203162 | 1938662 |  |  | 6 | NO |  | YES | 2021-09-20 | 2021-09-20 | 1 | 1 | 2021-09-17 | 2021-09-21 | -2 |  | 3 | 3 | 2021-09-22 | 2021-09-27 | 2021-09-30 | 5 | 5 | 4 | 4 |  |  |  | 2021-11-04 | 2021-11-05 | 2021-12-23 | 2021-12-22 |  |  | 2021-12-22 | 2022-02-16 | 39 | 39 | 2022-03-10 | 2022-04-14 | 41 | 41 | 2022-04-14 | 1 | 1 | 2022-10-18 | 2022-05-17 | 2022-10-18 | 2022-10-27 | 131 | 131 | 178 | 178 | 8 | 8 | 2022-04-01 | 2022-05-03 | 2022-06-17 | -10 |  | 33 | 33 | 55 | 55 | [6 empty] | 2022-05-03 |  | 2022-10-27 | [5 empty] | 2022-09-12 | 2022-09-27 | 2022-09-27 | 12 | 12 | 2022-09-12 | 2022-10-13 |  | 2022-09-27 | 12 | 12 | 2022-10-27 | 23 | 23 |  |  |  | 2022-09-28 | 2022-12-29 | 76 | 76 | 64 | 64 | 2022-12-30 | 2023-02-02 | 24 | 24 | 2023-02-03 | 25 | 25 | 2023-02-03 |  |  |  | 348 | 348 |  |  | 2023
918 | Bellflower, CA – 17102 Clark Ave R1 | 17102 Clark Ave EV1 | Bellflower | 90706 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 3243970 | 1965183 |  | 2024-07-06 |  | YES |  | YES | 2023-12-14 |  |  |  |  | 2023-12-14 | [11 empty] | 2022-01-25 |  |  | 2024-02-21 | 2022-01-31 | 2024-04-03
919 | Long Beach, CA - 6590 Long Beach Blvd | 6590 1/2 Long Beach Blvd | Long Beach | 90805 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3229744 | 1954554 |  |  | 8 |  |  | YES | 2021-09-20 | 2021-09-23 | 4 | 4 | 2021-09-20 | 2021-09-20 | 4 | 4 | 1 | 1 | 2021-09-21 |  | 2021-10-06 |  |  |  |  | 2021-12-22 | 65 | 65 | 2021-12-28 | 2021-12-30 | 2022-02-14 | 2022-02-15 | 38 | 38 | 2022-02-15 | 2022-05-24 | 70 | 70 | 2022-06-14 | [6 empty] | 2022-10-12 | 2022-11-08 | 2022-10-12 | [8 empty] | 2022-07-27 | 2022-08-01 |  |  | 4 | 4 |  |  | 2023-01-05 |  |  | 2023-03-01 | 38 | 38 | 2022-07-27 | 2022-07-27 | [24 empty] | 2023-02-28 |  |  |  |  | 2023-03-08 |  |  |  | 2023-04-13 | 27 | 27 | 2023-04-13 |  |  |  | 395 | 395 | 331 | 331 | 2023
920 | Brea, CA - 735 E Birtch St | 735 E Birch St | Brea | 92821 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO | 2021-09-27 | 2021-10-13 | 13 | 13 | 2021-09-21 | [7 empty] | 2021-09-27
921 | La Habra - La Habra Hills | 841 W La Habra Blvd | La Habra | 90631 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3213428 | 1950950 | [5 empty] | NO |  |  |  |  | 2021-09-21 | 2021-09-21 |  |  | 1 | 1 | 2021-09-30 | 2021-10-05 | 2021-10-12 | 11 | 11 | 6 | 6 |  |  |  | 2021-11-23 | 2021-11-24 | 2022-01-13 | 2022-01-26 |  |  | 2022-01-26 |  |  |  |  | 2022-02-09 | [56 empty] | 2023-06-30 |  |  |  |  | 2023-09-19
922 | Covina Palms Apartments | 1343 W San Bernardino Rd | Covina | 91722 | Los Angeles County | 10. Customer Hold | 26 - Covina | Metro East | Pomona |  |  | 3213820 | 1945655 |  |  | 2 | NO |  | NO |  |  |  |  | 2021-09-21 | 2021-09-29 |  |  | 7 | 7 | 2021-09-30 | 2021-10-04 | 2021-10-07 | 4 | 4 | 4 | 4 |  |  |  | 2021-11-17 | 2021-12-06 | 2022-01-14 | 2022-01-19 |  |  | 2022-01-19 |  |  |  |  | 2022-02-24 | [61 empty] | 2023-04-03 | 2023-04-06 | 4 | 4 | 2023-04-06 | 4 | 4 | 2023-04-06 |  |  |  | 389 | 389 |  |  | 2023
923 | Bellflower - Sierra Gardens | 16245 Lakewood Blvd | Bellflower | 90706 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3214040 | 1949886 | [5 empty] | YES |  |  |  |  | 2021-09-21 | [15 empty] | 2021-11-24 | 2021-11-29 | 2022-01-12 | 2022-01-12 |  |  | 2022-01-12 |  |  |  |  | 2022-01-13
924 | Beverly Hills, CA - N Crescent Dr | 427 N Crescent Dr | Beverly Hills | 90210 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2021-09-23 | 2021-10-04 | 8 | 8 | 2021-09-23 | 2021-09-23 | 8 | 8 | 1 | 1 | 2021-09-24 |  | 2021-10-18
925 | Santa Clarita, CA - 18655 Soledad Canyon Rd | 18655 Soledad Canyon Rd | Santa Clarita | 91351 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2021-09-23 |  |  |  | 2021-09-23 | 2021-09-23 |  |  | 1 | 1 |  |  | 2021-10-04
926 | West Covina, CA - 2753 E Eastland Center Dr | 2753 E Eastland Center Dr EV | West Covina | 91791 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3414399 | 2077004 |  | 2023-11-08 | 24 | NO |  | YES | 2021-09-23 | 2021-09-29 | 5 | 5 | 2021-09-23 | 2021-09-24 | 4 | 4 | 2 | 2 | 2021-09-24 | 2021-10-06 | 2021-10-19 | 9 | 9 | 10 | 10 |  |  |  | 2022-10-31 | 2022-11-01 | 2022-12-19 | 2022-12-29 |  |  | 2022-12-30 | 2023-01-06 | 6 | 6 | 2023-02-07 | 2023-02-14 | 27 | 27 | 2023-02-14 | 1 | 1 | 2023-02-22 | 2023-09-13 | 2023-02-22 | 2023-09-06 | 6 | 6 | 169 | 169 | 138 | 138 |  | 2023-03-03 | 2023-05-02 |  |  | 43 | 43 |  |  | 2023-09-27 | 158 | 158 | 2023-10-27 | 23 | 23 | 2023-02-22 | 2023-02-22 | 2023-09-06 | 2023-10-27 | 175 | 175 | 158 | 158 | 2023-08-03 | 2023-09-21 | 2023-09-21 | 35 | 35 | 2023-07-11 |  |  | 2023-07-25 | 11 | 11 | [7 empty] | 2023-09-21 | 52 | 52 |  |  | 2023-10-24
927 | San Bernardino, CA - 1170 W 3rd St | 1170 W 3rd St | San Bernardino | 92410 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | [9 empty] | YES | 2021-09-24 | 2021-09-29 | 4 | 4 | 2021-09-23 | 2021-09-23 | 5 | 5 | 1 | 1 | 2021-09-24 | 2021-10-06 | 2021-10-08 | 10 | 10 | 3 | 3
928 | Alhambra, CA - 2400 W Commonwealth Ave | 2400 W Commonwealth Ave | Alhambra | 91803 | Los Angeles County | 9. Complete | 22 - Montebello | Metro East | Pomona |  |  | 3324046 | 2013379 |  |  | 12 | NO |  | YES | 2021-09-24 | 2021-10-26 | 23 | 23 | 2021-09-24 | 2021-09-24 | 23 | 23 | 1 | 1 | 2021-09-24 | 2022-04-15 | 2022-04-15 | 140 | 140 | 1 | 1 | 2022-06-06 | 175 | 175 | 2022-06-09 |  | 2022-07-26 | 2022-08-01 | 40 | 40 | 2022-08-02 | 2022-08-19 | 14 | 14 | 2022-09-16 | 2022-12-02 | 72 | 72 | 2022-12-02 | 1 | 1 | 2022-12-02 | 2023-02-08 | 2022-12-02 | 2023-01-20 | 1 | 1 | 106 | 106 | 35 | 35 | 2022-11-18 | 2022-11-29 | 2023-01-10 | -9 |  | 31 | 31 | 36 | 36 |  |  |  | 2023-05-19 |  |  | 2022-11-29 |  | 2023-01-20 | 2023-05-19 |  |  |  |  | 2023-05-26 | 2023-06-01 | 2023-06-05 | 6 | 6 | [13 empty] | 2023-06-19 |  |  |  |  | 2023-07-03 | 2023-07-26 | 17 | 17 | 2023-08-16 | 32 | 32 | 2023-08-16 |  |  |  | 478 | 478 | 304 | 304 | 2023
929 | In-N-Out Valencia | 27510 Old Road | Valencia | 91355 | Los Angeles County | 9. Complete | 59 - Valencia | North Valley | Ventura |  |  | 3201226 | 1957676 |  |  | 4 | NO |  | NO | 2021-09-27 | 2021-10-07 | 9 | 9 | 2021-09-27 | 2021-09-27 | 9 | 9 | 1 | 1 | 2021-09-27 |  | 2021-09-29 | [7 empty] | 2022-01-26 | 2022-01-27 | 2022-03-14 | 2022-03-11 |  |  | 2022-03-11 | 2022-03-14 | 2 | 2 | 2022-04-08 | 2022-03-21 | 6 | 6 | 2022-03-21 | 1 | 1 | 2022-03-22 | 2022-03-30 | 2022-03-22 | 2022-03-23 | 2 | 2 | 8 | 8 | 2 | 2 | 2022-03-17 | 2022-05-11 | 2022-07-07 | -3 |  | 40 | 40 | 79 | 79 | [6 empty] | 2022-03-22 |  | 2022-07-07 | [5 empty] | 2022-04-07 | 2022-05-02 | 2022-05-02 | 18 | 18 | 2022-03-24 |  |  | 2022-03-28 | 3 | 3 | [7 empty] | 2022-07-30 | 90 | 90 |  |  | 2022-08-03 | 2022-08-26 | 18 | 18 | 2022-08-26 | 18 | 18 | 2022-08-26 |  |  |  | 232 | 232 |  |  | 2022
930 | CalTrans - 32-PED Calimesa | 32-PED Calimesa | Yucaipa | 92399 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 3179927 | 1945137 |  |  | 2 | NO |  | NO |  |  |  |  | 2021-09-27 | [15 empty] | 2021-09-28 | 2021-10-04 | 2021-11-02 | 2021-11-02 |  |  | 2021-11-02 | 2021-11-23 | 15 | 15 | 2023-11-02 | 2023-11-03 | 493 | 493 | 2023-11-06 | 2 | 2 | 2023-11-06 | 2023-11-21 | 2023-11-06 | 2023-11-06 | 2 | 2 | 494 | 494 | 1 | 1 | 2022-11-09 |  |  | -250 | [5 empty] | 2023-08-15 | -59 |  | 2023-09-20 | 26 | 26 | [6 empty] | -58 |  | 2023-11-08 | 2023-11-08 | 2023-12-11 | 22 | 22 | [12 empty] | 2023-12-05 | 2023-12-11 |  |  | 5 | 5 | 2024-01-08 | 2024-01-29 | 15 | 15 | 2024-01-31 | 17 | 17 | 2024-01-31 |  |  |  | 591 | 591 |  |  | 2024
931 | Whitewater Rest Area Eastbound | 57185 Whitewater Area | Whitewater | 92282 | Riverside County | 6. Requirements (permit, easment, etc.) | 79 - Palm Springs | Desert | SBRO |  |  | 3179987 | 1937959 |  |  | 2 | NO | Level 3 | NO |  |  |  |  | 2021-09-27 | [7 empty] | 2020-11-09 | [7 empty] | 2021-09-28 |  | 2021-11-02 | 2022-01-06 |  |  | 2022-01-06 | 2022-04-18 | 71 | 71 |  | 2022-04-27 | 8 | 8 | 2022-04-27 | 1 | 1 | 2023-09-15 | 2023-10-18 | 2023-09-15 | 2023-09-15 | 352 | 352 | 359 | 359 | 1 | 1 | [9 empty] | 2023-10-16 | 373 | 373 | 2023-10-29 | 10 | 10 | [6 empty] | 373 | 373 | 2023-11-06 | 2023-11-17 | 2023-12-04 | 19 | 19 | 2023-11-02 |  |  | 2023-11-15 | 10 | 10 | [6 empty] | 2023-12-04 | 2023-12-04 | 21 | 21 | 1 | 1 | 2024-01-09 | 2024-01-26 | 13 | 13 | 2024-01-26 | 13 | 13 | 2024-01-26 |  |  |  | 588 | 588 |  |  | 2024
932 | Whitewater Rest Area Westbound | 57182 Whitewater Area | Whitewater | 92282 | Riverside County | 7. Civil Construction | 79 - Palm Springs | Desert | SBRO |  |  | 3180232 | 1919268 |  | 2024-04-01 | 2 | NO | Level 3 | NO |  |  |  |  | 2021-09-27 | [7 empty] | 2020-11-09 | [7 empty] | 2021-09-28 | 2021-10-04 | 2021-10-04 | 2021-12-15 |  |  | 2021-12-15 | 2022-04-18 | 86 | 86 | 2023-10-04 | 2023-10-24 | 386 | 386 | 2023-10-24 | 1 | 1 | 2023-10-24 | 2023-11-06 | 2023-10-24 | 2023-10-25 | 1 | 1 | 387 | 387 | 2 | 2 | [9 empty] | 2023-10-16 | -7 | [10 empty] | -7 |  | 2023-11-02 | 2023-11-08 | 2023-11-21 | 14 | 14 | 2023-11-02 | 2023-11-08 | 2023-11-08 | 2023-11-15 | 10 | 10 | 2023-11-21 | 5 | 5 | 2023-11-21 | 10 | 10 | 2023-12-26 | 2024-01-01 | 39 | 39 | 4 | 4 | 2024-01-09
933 | Wiley Well Rest Area | 12254 Wileys Well Rd | Desert Center | 92239 | Riverside County | 11. Cancelled | 87 - Blythe | Rurals | SBRO |  |  | 3180260 | 1920935 |  | 2024-04-30 | 2 | NO | Level 3 | true |  |  |  |  | 2021-09-27 | [7 empty] | 2020-11-09 | [7 empty] | 2021-09-28 | 2021-10-04 | 2021-11-14 | 2022-01-10 |  |  | 2022-01-10 | 2022-01-14 | 5 | 5 | 2023-10-30 | 2023-10-19 | 447 | 447 | 2023-10-23 | 3 | 3 | 2023-10-23 | 2023-11-06 | 2023-10-23 | 2023-10-23 | 3 | 3 | 449 | 449 | 1 | 1 | [9 empty] | 2024-01-31 | 68 | 68 | [9 empty] | 70 | 70 | [5 empty] | 2024-03-08 |  |  | 2024-03-20 | 9 | 9
934 | Tustin, CA - 14042 Newport Ave | 14042 Newport Ave | Tustin | 92680 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES | 2021-09-28 | 2021-10-13 | 12 | 12 | 2021-09-28 | 2021-09-28 | 12 | 12 | 1 | 1 | 2021-09-29 |  | 2021-10-25
935 | Thousand Oaks - Hillcrest Dr | 350 W Hillcrest Dr | Thousand Oaks | 91360 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-10-04 | 2021-11-04 | 24 | 24 | 2021-09-28 | [6 empty] | 2022-12-14 | 2022-12-15 |  |  | 2 | 2
936 | Irvine, CA - 18952 MacArthur Blvd | 18952 MacArthur Blvd | Irvine | 92612 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3235600 | 1965276 |  |  | 12 |  |  | NO | 2021-09-29 | 2021-10-13 | 11 | 11 | 2021-09-29 | 2021-09-29 | 11 | 11 | 1 | 1 | 2021-09-29 |  | 2021-10-08 |  |  |  |  | 2022-01-10 | 70 | 70 | 2022-01-11 | 2022-01-12 | 2022-02-25 | 2022-03-24 | 52 | 52 | 2022-03-24
937 | Inglewood - Centinela Ave | 1201 Centinela Ave | Inglewood | 90302 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-08 | 2021-10-12 | 8 | 8 | 3 | 3
938 | Chino Hills - #33369 | 15450 Fairfield Ranch Rd | Chino Hills | 91709 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-01-20 | 4 | YES |  | NO |  |  |  |  | 2023-09-13 | 2023-09-13 |  |  | 1 | 1 | 2023-09-14 | 2023-09-18 | 2023-09-28 | 4 | 4 | 9 | 9
939 | Goleta - Hollister Ave | 7443 Hollister Ave | Goleta | 93117 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-07 | 2021-10-08 | 7 | 7 | 2 | 2
940 | Murrieta - Scott Road | 28015 Scott Road | Murrieta | 92563 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-11 | 2021-10-15 | 9 | 9 | 5 | 5
941 | Los Angeles - Normandie Ave | 11255 Normandie Ave | Los Angeles | 90047 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-08 | 2021-10-12 | 8 | 8 | 3 | 3
942 | Culvery City - Washington Blvd | 11001 Washington Blvd | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-08 | 2021-10-12 | 8 | 8 | 3 | 3
943 | Inglewood - Manchester Blvd | 345 W Manchester Blvd | Inglewood | 90301 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-08 | 2021-10-12 | 8 | 8 | 3 | 3
944 | Hacienda Heights - Tetley St | 15780 Tetley St | Hacienda Heights | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-10-01 | 2021-10-05 | 2021-10-13 | 5 | 5 | 7 | 7
945 | Santa Ana - Dyer Rd | 1700 E Dyer Rd | Santa Ana | 92705 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-01 | 2021-10-07 | 3 | 3 | 5 | 5
946 | Victorville, CA 92395 | 14595 Seventh St | Victorville | 92395 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 73 - Victorville | Rurals | SBRO | [9 empty] | YES |  |  |  |  | 2021-09-29 | 2021-09-29 |  |  | 1 | 1 | 2021-09-30 | 2021-10-12 | 2021-10-15 | 10 | 10 | 4 | 4
947 | Rancho Cucamonga, CA - 8443 Haven Ave | 8443 Haven Ave EV | Rancho Cucamonga | 91730 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  | Stig 12kV | 3425171 | 2209346 | 2209347 | 2024-06-20 | 16 | YES | Level 3 | NO | 2021-10-04 | 2021-10-28 | 19 | 19 | 2023-03-09 | 2023-03-09 | -342 |  | 1 | 1 | 2023-03-14 |  | 2023-03-17 |  |  |  |  | 2023-03-20 | 8 | 8 | 2023-07-14 | 2023-06-09 | 2023-08-11 | 2023-09-21 | 131 | 131 | 2023-09-22 | 2023-11-02 | 30 | 30 | 2023-12-18 | 2024-01-09 | 45 | 45 | 2024-01-10 | 2 | 2 | 2024-01-23 |  | 2024-01-23 | 2024-02-27 | 10 | 10 | 78 | 78 | 25 | 25 | 2024-02-14 | 2024-02-20 |  | 26 | 26 | [10 empty] | 2024-01-23
948 | Yucaipa Properties | 33439 Yucaipa Blvd | Yucaipa | 92399 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 31 - Redlands | Desert | SBRO |  |  | 3213210 | 1943799 | [5 empty] | NO |  |  |  |  | 2021-09-07 | 2021-09-30 |  |  | 18 | 18 | 2021-09-30 | 2021-10-05 | 2021-10-15 | 4 | 4 | 9 | 9 |  |  |  | 2021-11-23 | 2021-11-24 | 2022-01-13
949 | South Gate - Palm Gate (old 10800 Wright Rd) | 5205 Pendelton Ave | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3213880 | 1945773 | [5 empty] | NO |  |  |  |  | 2021-09-21 | 2021-09-30 |  |  | 8 | 8 | 2021-09-30 |  | 2021-10-12 | [7 empty] | 2021-11-24 | 2021-11-29 | 2022-01-12 | 2022-01-13 |  |  | 2022-01-13 |  |  |  |  | 2022-04-19 | [24 empty] | 2024-03-12 | [11 empty] | 479 | 479
950 | Huntington Beach PCH | 21058 Pacific Coast Highway | Huntington Beach | 92648 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2021-10-06 |  |  |  | 2021-10-06 | 2021-10-06 |  |  | 1 | 1 | 2021-10-07 |  | 2021-10-19
951 | Lake Forest, CA- 24251 Muirlands Blvd | 24251 Muirlands Blvd | Lake Forest | 92630 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback |  |  | 3240362 | 1956136 |  |  | 24 | NO |  | YES | 2021-10-06 | 2021-10-15 | 8 | 8 | 2021-10-05 | 2021-10-05 | 9 | 9 | 1 | 1 | 2021-10-13 | 2022-04-14 | 2021-10-26 | 132 | 132 | -117 |  | 2022-01-19 | 72 | 72 | 2022-01-20 | 2022-01-20 | 2022-03-04 | 2022-03-07 | 33 | 33 | 2022-03-07 |  |  |  |  | 2022-07-15 |  |  | 2022-07-15 | 1 | 1 | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-09-23 | 40 | 40 |  |  | 11 | 11 | 2022-07-26 | 2022-07-15 | 2022-07-26 | 8 | 8 | 8 | 8 | 1 | 1 | 2022-11-17 | 88 | 88 | 2022-11-30 | 8 | 8 | 2022-07-15 | 2022-07-15 | 2022-09-23 | 2022-11-30 | 95 | 95 | 88 | 88 | 2022-11-27 | 2022-12-07 | 2022-12-08 | 9 | 9 | [13 empty] | 2023-01-10 |  |  |  |  | 2023-01-13 |  |  |  | 2023-02-22 | 27 | 27 | 2023-02-22 |  |  |  | 348 | 348 | 277 | 277 | 2023
952 | Ventura, CA - S Ann St (Gasworks) | 1121 E Thompson Blvd #US | Ventura | 93001 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3250044 | 1965017 |  |  | 8 | NO |  | YES | 2021-10-07 | 2021-10-21 | 11 | 11 | 2021-10-07 | 2021-10-07 | 11 | 11 | 1 | 1 | 2021-10-08 |  | 2021-10-13 |  |  |  |  | 2022-02-07 | 83 | 83 | 2022-02-08 | 2022-02-09 | 2022-03-24 | 2022-05-03 | 61 | 61 | 2022-05-04 |  |  |  |  | 2022-05-03 |  |  | 2022-05-04 | 2 | 2 | 2023-03-07 | 2023-03-20 | 2023-03-07 | 2023-03-08 | 213 | 213 |  |  | 2 | 2 |  | 2023-03-10 | 2023-03-31 |  |  | 16 | 16 |  |  | 2023-08-10 | 322 | 322 | 2023-09-12 | 23 | 23 | 2023-03-07 | 2023-03-07 | 2023-03-31 | 2023-09-12 | 133 | 133 | 323 | 323 | [18 empty] | 2023-08-03 |  |  |  |  | 2023-08-17 |  |  |  | 2023-10-24 | 48 | 48 | 2023-10-24 |  |  |  | 517 | 517 | 435 | 435 | 2023
953 | Camarillo, CA - 2911 Petit St | 2911 Petit St | Camarillo | 93012 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | NO | 2021-10-08 | 2021-10-26 | 13 | 13 | 2021-10-07 | 2021-10-07 | 14 | 14 | 1 | 1 | 2021-10-13 | 2021-10-14 | 2021-10-18 | 6 | 6 | 3 | 3
954 | Westlake Village, CA - 30770 Russell | 30770 Russell Ranch Rd | Westlake Village | 91362 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2021-10-07 |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-13 |  | 2021-10-18
955 | Costa Mesa, CA - 150 Paularino Ave (Culture Yard) | 150 Paularino Ave Building B | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3249930 | [6 empty] | YES | 2021-10-11 | 2021-10-26 | 12 | 12 | 2021-10-08 | [7 empty] | 2022-01-10 |  |  |  |  | 2022-02-04 | 81 | 81 | 2022-02-08 | 2022-02-09 | 2022-03-24 | 2022-04-14 | 49 | 49 | 2022-04-14
956 | Santa Clarita, CA - 18800 Soledad Canyon Rd | 18800 Soledad Canyon Rd | Santa Clarita | 91351 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2021-09-23 | 2021-09-23 |  |  | 1 | 1 | 2021-09-24 |  | 2021-10-06
957 | Santa Barbara 7-Eleven #13900 | 1909 Cliff Drive | Santa Barbara | 93109 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-11 | 2021-10-18 | 3 | 3 | 6 | 6
958 | Long Beach, CA - 4250 Long Beac Blvd | 4250 Long Beach Blvd, Long Beach, CA 90807 | Long Beach | 90807 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO | 2021-10-13 |  |  |  | 2021-10-13 | 2021-10-13 |  |  | 1 | 1 | 2021-10-14 | 2021-10-25 | 2021-10-29 | 9 | 9 | 5 | 5
959 | Oxnard 7-Eleven #17957 | 2201 E Channel Islands Blvd | Oxnard | 93033 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-11 | 2021-10-13 | 3 | 3 | 3 | 3
960 | Diamond Bar 7-Eleven #13993 | 530 N Diamond Bar | Diamond Bar | 91765 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-15 | 2021-10-18 | 7 | 7 | 2 | 2
961 | Pomona 7-Eleven #13945 | 1550 Murchison Avenue | Pomona | 91768 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 |  | 2021-10-18
962 | Whittier 7-Eleven #16028 | 9727 Carmenita Rd | Whittier | 90605 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-08 | 2021-10-15 | 2 | 2 | 6 | 6
963 | Whittier 7-Eleven #33578 | 11807 Valley View Ave | Whittier | 90604 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-13 | 2021-10-15 | 5 | 5 | 3 | 3
964 | Cathedral City 7-Eleven #36028 | 68490 Dinah Shore | Cathedral City | 92234 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08
965 | Thousand Oaks - Promenade Way - Phase 2 | 100 Promenade Way | Thousand Oaks | 91362 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  | 2021-10-15 |  |  | 2021-10-13 | [7 empty] | 2021-10-25
966 | Palm Springs 7-Eleven #34637 | 150 W Vista Chino | Palm Springs | 92262 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08
967 | Tustin, CA - 14521 Red Hill Ave | 14537.5 Red Hill Avenue | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3228016 | 1944738 |  |  | 12 |  |  | NO | 2021-10-12 | 2021-10-26 | 11 | 11 | 2021-10-12 | 2021-10-12 | 11 | 11 | 1 | 1 | 2021-10-12 | 2021-10-18 | 2021-10-26 | 5 | 5 | 7 | 7 | 2021-12-17 | 46 | 46 | 2021-12-21 | 2021-12-22 | 2022-02-04 | 2022-02-17 | 43 | 43 | 2022-02-17 | 2022-02-23 | 4 | 4 | 2022-03-16 | 2022-03-08 | 10 | 10 | 2022-03-08 | 1 | 1 | 2022-05-09 | 2022-06-02 | 2022-05-09 |  | 45 | 45 |  |  |  |  | 2022-03-23 | 2022-04-27 | 2022-05-02 | 12 | 12 | 4 | 4 | 29 | 29 | 2022-07-08 | 87 | 87 | 2022-08-25 | 35 | 35 | 2022-04-27 | 2022-04-27 |  |  |  |  | 87 | 87 | 2022-08-08 | 2022-09-06 | 2022-09-06 | 21 | 21 | [13 empty] | 2022-09-16 |  |  |  |  | 2022-08-24 |  |  |  | 2022-09-16 | 17 | 17 | 2022-09-16 |  |  |  | 235 | 235 | 190 | 190 | 2022
968 | Mission Viejo 7-Eleven #35346 | 27271 Trabuco Road | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08
969 | Santa Ana 7-Eleven #17006 | 2910 S Main Street | Santa Ana | 92707 | Orange County | 4. Preliminary Design | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-19 | 2021-11-06 | 9 | 9 | 14 | 14
970 | Rancho Palos Verdes, CA - 28901 S Western Ave | 28901 S Western Avenue | Rancho Palos Verdes | 90275 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3653344 | 2211790 |  |  | 24 | YES | Level 2 | true | 2023-08-07 | 2023-08-15 | 7 | 7 | 2023-07-20 | 2023-07-20 | 19 | 19 | 1 | 1 | 2023-07-21 | 2023-07-24 | 2023-08-07 | 3 | 3 | 11 | 11 |  |  |  | 2024-01-11 | 2024-01-11 | 2024-03-08 | 2024-03-08 |  |  | 2024-03-08
971 | Inglewood, CA - 3150 W Imperial Hwy | 3150 W Imperial Hwy | Inglewood | 90303 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2021-10-13 | 2021-10-15 | 3 | 3 | 2021-10-13 | 2021-10-13 | 3 | 3 | 1 | 1 | 2021-10-13 | 2021-10-25 | 2021-10-29 | 9 | 9 | 5 | 5
972 | Arco Torrance | 1800 W Artesia | Torrance | 90504 | Los Angeles County | 10. Customer Hold | 44 - South Bay | Metro West | Alhambra |  |  | 3219270 | 1952283 |  |  | 2 | NO |  | NO |  |  |  |  | 2021-10-12 | 2021-10-12 |  |  | 1 | 1 | 2021-10-13 | 2021-10-21 | 2021-11-06 | 8 | 8 | 12 | 12 |  |  |  | 2021-12-06 | 2021-12-09 | 2022-02-18 | 2022-02-16 |  |  | 2022-02-16 | 2022-06-06 | 77 | 77 | 2022-06-30 | [6 empty] | 2022-07-14 | 2022-10-18 | 2022-07-14 | 2022-07-24 |  |  | 34 | 34 | 7 | 7 | 2022-07-21 | 2022-07-25 | 2022-08-19 |  |  | 20 | 20 | 22 | 22 | 2022-10-10 | [5 empty] | 2022-07-14 | 2022-07-14 | 2022-08-19 | [5 empty] | 2022-10-13 | 2022-10-29 | 2022-10-30 | 12 | 12 | 2022-08-29 | 2022-09-14 |  | 2022-09-05 | 5 | 5 | 2022-09-30 | 19 | 19 |  |  |  | 2022-11-14 | 2022-11-18 | 58 | 58 | 5 | 5 | 2022-11-21 | 2022-12-23 | 23 | 23 | 2022-12-23 | 23 | 23 | 2022-12-23 |  |  |  | 302 | 302 |  |  | 2022
973 | West Hollywood Gateway | 7100 Santa Monica Blvd | West Hollywood | 90046 | Los Angeles County | 9. Complete | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO | 2021-10-12 |  |  |  | 2021-10-12 | 2021-10-12 |  |  | 1 | 1 | 2021-10-13
974 | Manhattan Village-Sushi Roku | 3110 N Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3209470 | 1993782 |  |  | 2 | NO |  | YES |  |  |  |  | 2021-10-13 | 2021-10-13 |  |  | 1 | 1 | 2021-10-13 |  | 2021-11-07 | [7 empty] | 2021-11-17 | 2021-11-18 | 2022-01-07 | 2022-01-07 | [7 empty] | 2022-06-14 |  |  | 2022-06-16 | 3 | 3 | 2022-06-16 | 2022-07-08 | 2022-06-16 | 2022-06-16 | 3 | 3 |  |  | 1 | 1 | 2022-07-15 | 2022-10-13 | 2022-12-12 | 23 | 23 | 40 | 40 | 103 | 103 | [6 empty] | 2022-06-16 |  | 2022-12-12 | [5 empty] | 2022-09-09 | 2022-09-29 | 2022-09-29 | 15 | 15 | 2022-07-05 | 2022-07-05 |  | 2022-08-03 | 22 | 22 | 2022-08-04 | 2 | 2 |  |  |  | 2022-10-26 | 2022-11-17 | 96 | 96 | 16 | 16 | 2022-12-14 | 2023-01-06 | 18 | 18 | 2023-01-07 | 18 | 18 | 2023-01-07 |  |  |  | 311 | 311 |  |  | 2023
975 | Rialto - Farmer Boys | 1310 W Baseline Rd | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3237856 | 1955059 |  |  | 6 | NO |  | NO | 2021-10-13 | 2021-10-25 | 9 | 9 | 2021-10-13 | 2021-10-13 | 9 | 9 | 1 | 1 | 2021-10-14 |  | 2022-01-10 |  |  |  |  | 2022-01-12 | 62 | 62 | 2022-01-14 | 2022-01-21 | 2022-03-04 | 2022-11-04 | 208 | 208 | 2022-11-04 | 2022-11-09 | 4 | 4 | 2022-12-07 | 2022-12-21 | 28 | 28 | 2022-12-21 | 1 | 1 | 2023-01-26 | 2023-03-03 | 2023-01-26 | 2023-02-06 | 26 | 26 | 60 | 60 | 8 | 8 |  |  | 2023-02-28 | [14 empty] | 2023-02-28 | [5 empty] | 2023-01-31 | 2023-02-13 | 2023-02-13 | 10 | 10 | 2023-01-05 | [11 empty] | 2023-02-22 | 2023-02-28 | 37 | 37 | 5 | 5 | 2023-03-16 | 2023-04-13 | 21 | 21 | 2023-04-14 | 22 | 22 | 2023-04-14 |  |  |  | 379 | 379 | 318 | 318 | 2023
976 | Oxnard 7-Eleven #33159 | 1501 W 5th Street | Oxnard | 93030 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 | 2021-10-20 | 2021-10-21 | 5 | 5 | 2 | 2
977 | Crestline7-Eleven #23818 | 24156 Lake Drive | Crestline | 92325 | San Bernardino County | 11. Cancelled | 40 - Arrowhead | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 |  | 2021-10-30
978 | La Puente 7-Eleven #13997 | 16020 Main St | La Puente | 91744 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18
979 | Apple Valley 7-Eleven #23008 | 21718 Bear Valley Rd | Apple Valley | 92308 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 |  | 2021-10-30
980 | Westminster 7-Eleven #17782 | 9001 Bolsa Avenue | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [6 empty] | 4 |  |  | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 | 2021-10-26 | 2021-11-30 | 9 | 9 | 23 | 23
981 | Cathedral City 7-Eleven #37977 | 69123 Ramon Road | Cathedral City | 92234 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 |  | 2021-10-30
982 | Visalia 7-Eleven #22014 | 518 S Lovers Lane | Visalia | 93292 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18
983 | Bloomington 7-Eleven #16755 | 10492 Cedar Avenue | Bloomington | 92316 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 |  | 2021-10-30
984 | Santa Clarita 7-Eleven #33154 | 27602 Newhall Ranch Rd | Santa Clarita | 91355 | Los Angeles County | 4. Preliminary Design | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2021-10-14 | 2021-10-14 |  |  | 1 | 1 | 2021-10-18 | 2021-10-20 | 2021-10-22 | 5 | 5 | 3 | 3
985 | Orange 7-Eleven #26314 | 3197 N Glassell St | Orange | 92865 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3588795 |  |  |  | 4 | NO | Level 2 | true |  |  |  |  | 2023-08-15 | 2023-08-15 |  |  | 1 | 1 | 2023-08-16 | 2023-08-17 | 2023-08-17 | 3 | 3 | 1 | 1 | 2023-08-21 | 5 | 5 | 2023-08-22 | 2023-08-23 | 2023-11-22 | 2023-12-15 | 82 | 82 | 2023-12-18
986 | Simi Valley 7-Eleven #25132 | 2543 Royal Ave | Simi Valley | 93065 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2021-10-18 | 2021-10-18 |  |  | 1 | 1 | 2021-10-18 | 2021-10-21 | 2021-10-22 | 4 | 4 | 2 | 2
987 | Westminster 7-Eleven #33161 | 15991 Magnolia St | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2021-10-18 | 2021-10-18 |  |  | 1 | 1 | 2021-10-18 |  | 2021-12-06
988 | Long Beach, CA - 8123 E Wardlow Rd | 8123 E Wardlow Rd | Long Beach | 90808 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2021-10-15 | 2021-11-02 | 13 | 13 | 2021-10-18 | 2021-10-18 | 12 | 12 | 1 | 1 | 2021-10-18 |  | 2021-11-30
989 | Fillmore, CA - 736 Ventura St | 736 Ventura St. | Fillmore | 93015 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | true | 2021-10-18 | 2021-11-18 | 23 | 23 | 2021-10-18 | 2021-10-18 | 23 | 23 | 1 | 1 | 2021-10-18 | 2021-10-29 | 2021-11-04 | 10 | 10 | 5 | 5
990 | La Puente, CA - 1821 N Hacienda | 1821 N Hacienda | La Puente | 91744 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2021-10-19 | 2021-10-20 | 2 | 2 | 2021-10-15 | 2021-10-19 | 2 | 2 | 3 | 3 | 2021-10-19
991 | El Monte, CA - 11950 Garvey Ave | 11950 Garvey Ave | El Monte | 91732 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 22 - Montebello | Metro East | Pomona | [9 empty] | YES | 2021-10-19 | 2021-11-08 | 15 | 15 | 2021-10-15 | 2021-10-19 | 15 | 15 | 3 | 3 | 2021-10-19 |  | 2022-01-24
992 | Whittier, CA - 16258 Whittier Blvd | 16258 Whittier Blvd | Whittier | 90603 | Los Angeles County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  | Socrates 12kV | 3445814 | 2119043 |  | 2024-10-17 | 16 | YES | Level 2 | YES | 2021-10-15 | 2021-11-02 | 13 | 13 | 2023-03-22 | 2021-10-18 | 12 | 12 | -359 |  | 2021-10-19 |  | 2021-11-08 |  |  |  |  | 2023-03-22 | 1 | 1 | 2023-03-23 | 2023-03-23 | 2023-05-04 | 2023-04-14 | 18 | 18 | 2023-04-14 | 2023-08-28 | 95 | 95 | 2023-09-19 | 2023-09-14 | 13 | 13 | 2023-09-14 | 1 | 1
993 | Lakewood - Candlewood St | 500 Lakewood Center Mall | Lakewood | 90712 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  | 2021-11-03 |  |  | 2021-10-19
994 | Chino 7-Eleven #38097 | 7830 Pine Ave | Chino | 91708 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2021-10-07 | 2021-10-07 |  |  | 1 | 1 | 2021-10-08 | 2021-10-19 | 2021-11-06 | 9 | 9 | 14 | 14
995 | Target Foothill Ranch #T0913 | 26762 Portola Pkwy | Foothill Ranch | 92610 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2021-10-21 | 2021-10-28 | 6 | 6 | 2021-10-21 | 2021-10-21 | 6 | 6 | 1 | 1 | 2021-10-22 |  | 2021-11-30
996 | Visalia Bank of America | 212 E Main St | Visalia | 93291 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura |  |  | 3212660 | 1945604 | [5 empty] | NO | 2021-10-22 | 2021-10-25 | 2 | 2 | 2021-10-20 | 2021-10-20 | 4 | 4 | 1 | 1 | 2021-10-21 | 2021-10-25 | 2021-10-26 | 4 | 4 | 2 | 2 |  |  |  | 2021-11-22 | 2021-11-29 | 2022-01-12 | 2022-02-08 |  |  | 2022-02-10 | 2022-03-09 | 19 | 19 | 2022-03-30 | 2022-03-23 | 11 | 11 | 2022-03-25 | 3 | 3 | 2022-03-25 | 2022-05-02 | 2022-03-25 | 2022-04-04 | 3 | 3 | 19 | 19 | 7 | 7 | 2022-03-22 | 2022-04-20 |  | -2 | [11 empty] | 2022-03-25
997 | Artesia 7-Eleven #37052 | 12202 South St | Artesia | 90701 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-11-02 |  | 2021-12-09
998 | Long Beach - Long Beach Blvd 7-Eleven #18881 | 5000 Long Beach Blvd | Long Beach | 90805 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-28
999 | Hawthorne 7-Eleven #16848 | 4800 W 120th St | Hawthorne | 90250 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 | 2021-11-04 | 2021-12-05 | 10 | 10 | 19 | 19
1000 | Lakewood 7-Eleven #20314 | 5315 Paramount Blvd | Lakewood | 90712 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-11-02
1001 | Torrance 7-Eleven #18892 | 22601 Hawthorne Blvd | Torrance | 90505 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 | 2021-11-04 | 2021-12-04 | 10 | 10 | 19 | 19
1002 | Torrance 7-Eleven #21475 | 16520 Crenshaw Blvd | Torrance | 90504 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1003 | Artesia 7-Eleven #21843 | 3545 Artesia Blvd | Torrance | 90504 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1004 | Carson 7-Eleven #26294 | 22225 Avalon Blvd | Carson | 90745 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-28 |  | 2021-11-19
1005 | Tehachapi, CA -2000 E Tehachapi Blvd R1 | 580 Monolith St | Tehachapi | 93561 | Kern County | 11. Cancelled | 52 - Tehachapi | North Valley | Ventura |  |  | 3245495 | 1960811 |  | 2024-11-01 |  | YES | Level 3 | NO | 2023-05-16 | 2023-06-26 | 29 | 29 | 2023-03-23 | 2021-10-19 | 425 | 425 | -359 |  | 2021-10-27 |  | 2021-11-04 |  |  |  |  | 2023-08-08 | 97 | 97 | 2023-08-08 | 2023-03-27 | 2023-09-20 | 2023-09-27 | 36 | 36 | 2023-09-27
1006 | Torrance 7-Eleven #33699 | 2205 Sepulveda Blvd | Torrance | 90501 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1007 | Bellflower 7-Eleven #34004 | 14300 Bellflower Blvd | Bellflower | 90706 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1008 | Rancho Palos Verdes 7-Eleven #33601 | 31186 Hawthrone Blvd | Rancho Palos Verdes | 90275 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 | 2021-11-04 | 2021-12-04 | 10 | 10 | 19 | 19
1009 | Torrance 7-Eleven #37117 | 3401 Torrance Blvd | Torrance | 90503 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1010 | Gardena 7-Eleven #18690 | 16711 S Vermont Ave | Gardena | 90247 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 |  | 2021-12-06
1011 | Lawndale 7-Eleven #17243 | 15805 Prairie Ave | Lawndale | 90260 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 |  | 2021-12-06
1012 | Commerce 7-Eleven #33459 | 5536 E Washington Blvd | Commerce | 90040 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-28
1013 | Gardena 7-Eleven #23045 | 2200 Marine Ave | Gardena | 90249 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 |  | 2021-12-06
1014 | Alhambra 7-Eleven #17792 | 1200 S Garfield Ave | Alhambra | 91801 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 | 2021-10-27 | 2021-11-01 | 4 | 4 | 4 | 4
1015 | Paramount 7-Eleven #33319 | 8502 Alondra Blvd | Paramount | 90723 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-28 |  | 2021-11-19
1016 | Los Angeles - 7-Eleven #37191 | 4680 Olympic Blvd | Los Angeles | 90022 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-02
1017 | Los Angeles 7-Eleven #17165 | 5411 E Beverly Blvd | Los Angeles | 90022 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-02
1018 | Montrose 7-Eleven #17644 | 12759 Montrose Ave | Montrose | 91020 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 | 2021-10-28 | 2021-11-03 | 5 | 5 | 5 | 5
1019 | Moreno Valley 7-Eleven #17964 | 12531 Perris Blvd | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-26 | 2021-11-09 | 2021-11-13 | 13 | 13 | 3 | 3
1020 | Murrieta 7-Eleven #33552 | 40210 Murrieta Hot Springs Rd | Murrieta | 92563 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-26 |  | 2021-12-12
1021 | Moreno Valley 7-Eleven #33157 | 15020 Perris Blvd Unit A | Moreno Valley | 92551 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-26 | 2021-11-09 | 2021-11-13 | 13 | 13 | 3 | 3
1022 | Hemet 7-Eleven #38382 | 43271 E Florida Ave Hse | Hemet | 92545 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27 |  | 2021-11-12
1023 | Moreno Valley 7-Eleven #23520 | 23021 Sunnymead Blvd | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-26 |  | 2021-11-27
1024 | Los Angeles 7-Eleven #37274 | 12801 S Central Ave | Los Angeles | 90059 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-02
1025 | Lake Elsinore 7-Eleven #36788 | 515 N Main St | Lake Elsinore | 92530 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-25 | 2021-10-28 | 2021-11-01 | 5 | 5 | 3 | 3
1026 | Wildomar 7-Eleven #33595 | 32060 Clinton Keith Rd | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-26 | 2021-10-28 | 2021-11-01 | 5 | 5 | 3 | 3
1027 | Compton 7-Eleven #37301 | 307 W Compton Blvd | Compton | 90220 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-28 | 2021-11-10 | 2021-11-19 | 14 | 14 | 7 | 7
1028 | West Covina 7-Eleven #14004 | 1319 W Merced Ave | West Covina | 91790 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-01
1029 | Tustin 7-Eleven #20705 | 15202 Williams St | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-28 | 2021-11-10 | 2021-11-14 | 13 | 13 | 2 | 2
1030 | Sunset Ridge Parking Lot | 100 Superior Ave | Newport Beach | 92663 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3245610 | 1953106 |  |  |  | NO |  | NO | 2022-01-12 | 2022-01-28 | 12 | 12 | 2021-10-22 | 2021-10-22 | 66 | 66 | 1 | 1 | 2021-10-28 | 2021-11-09 | 2021-11-23 | 13 | 13 | 10 | 10 | 2022-01-12 | 55 | 55 | 2022-01-31 | 2022-01-31 | 2022-03-16 | 2022-03-31 | 55 | 55 | 2022-04-04 | 2022-07-21 | 77 | 77 | 2022-08-12 | 2022-10-19 | 64 | 64 | 2022-10-21 | 3 | 3 | 2022-10-21 |  | 2022-10-21 |  | 3 | 3 |  |  |  |  | 2022-10-03 |  |  | -13
1031 | Pomona 7-Eleven #17981 | 1707 Indian Hill Blvd | Pomona | 91767 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-01 | 2021-11-04 | 2021-11-07 | 9 | 9 | 2 | 2
1032 | San Dimas 7-Eleven #17210 | 660 E Foothill Blvd | San Dimas | 91773 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-01
1033 | La Habra 7-Eleven #18284 | 541 W Imperial Hwy | La Habra | 90631 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-01 | 2021-11-30 | 2021-12-04 | 24 | 24 | 4 | 4
1034 | Covina 7-Eleven #18840 | 1085 N Citrus Ave | Covina | 91722 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-25 |  | 2021-11-01
1035 | Baldwin Park 7-Eleven #19329 | 3705 Puente Ave | Baldwin Park | 91706 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-02
1036 | City Of Industry 7-Eleven #23961 | 16107 Gale Ave | City Of Industry | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-01 | 2021-11-16 | 2021-11-20 | 16 | 16 | 4 | 4
1037 | Redlands 7-Eleven #33292 | 1161 W Lugonia Ave | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-27 | 2021-11-08 | 2021-11-12 | 11 | 11 | 4 | 4
1038 | Garden Grove 7-Eleven #33168 | 13472 Euclid St | Garden Grove | 92843 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-01 | 2021-11-30 | 2021-12-04 | 24 | 24 | 4 | 4
1039 | Fontana 7-Eleven #33245 | 16096 Slover Ave | Fontana | 92337 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-26 |  | 2021-11-27
1040 | Rialto 7-Eleven #33442 | 1276 W Base Line Rd | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-27
1041 | Norco 7-Eleven #34032 | 445 Hidden Valley Pkwy | Norco | 92860 | Riverside County | 7. Civil Construction | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-11-01 | 2021-11-15 | 2021-11-20 | 15 | 15 | 5 | 5
1043 | Bristol Plaza - Santa Ana R29 (old 3321 3/4 Bristol St) | 3321 .75 S Bristol St Unit ELE01 | Santa Ana | 92704 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3229301 | 2098852 |  | 2024-06-26 | 4 | YES | Level 1 | false | 2021-12-27 | 2022-01-05 | 8 | 8 | 2023-01-30 | 2021-10-27 | 47 | 47 | -316 |  | 2021-10-28 | 2021-11-10 | 2021-11-14 | 11 | 11 | 2 | 2 | 2023-01-30 | 1 | 1 | 2023-01-30 | 2023-01-31 | 2023-03-15 | 2023-03-10 | 29 | 29 | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-04-04 | [6 empty] | 2022-05-03 | 2023-05-03 | 2022-05-03 | 2023-05-03 |  |  | 39 | 39 | 254 | 254 | 2023-04-08 | 2023-04-12 | 2024-01-05 |  |  | 186 | 186 | 188 | 188 | 2023-04-11 |  |  | 2024-03-14 | 234 | 234 | 2022-05-03 | 2022-05-03 | 2024-01-05 | 2024-03-14 | 471 | 471 |  |  | 2024-03-15 | [16 empty] | 2024-03-14
1044 | Westminster 7-Eleven #33611 | 13982 Bolsa Chica Rd | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-10-25 | 2021-10-25 |  |  | 1 | 1 | 2021-10-28 | 2021-11-09 | 2021-12-07 | 12 | 12 | 18 | 18
1045 | Fontana 7-Eleven #35309 | 10918 Sierra Ave | Fontana | 92336 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | true |  |  |  |  | 2021-11-01 | 2021-11-03 |  |  | 3 | 3 |  |  | 2021-12-22
1046 | Fontana 7-Eleven #38198 | 16060 Jurupa Ave | Fontana | 92337 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 |  | 2021-12-22
1047 | San Bernardino 7-Eleven #35303 | 1935 S Waterman Ave A | San Bernardino | 92408 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 |  | 2021-12-22
1048 | San Bernardino 7-Eleven #35060 | 501 S Waterman Ave A | San Bernardino | 92408 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | true |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 |  | 2021-12-22
1049 | Orange 7-Eleven #26764 | 4427 E Chapman Ave | Orange | 92869 | Orange County | 4. Preliminary Design | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1050 | Rancho Cucamonga 7-Eleven #34287 | 9638 Milliken Ave | Rancho Cucamonga | 91730 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3617984 | 2205567 | 2205569 | 2024-09-24 | 4 | YES | Level 1 | NO |  |  |  |  | 2023-08-17 | 2023-08-17 |  |  | 1 | 1 | 2023-08-21 | 2023-08-22 | 2023-10-11 | 4 | 4 | 36 | 36 | 2023-10-12 | 40 | 40 | 2023-10-13 |  | 2023-11-29 | 2023-12-12 | 42 | 42 | 2023-12-12
1051 | Downey 7-Eleven #16560 | 7400 Stewart And Gray Rd | Downey | 90241 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1052 | Rancho Cucamonga 7-Eleven #33308 | 10477 Alta Loma Dr | Rancho Cucamonga | 91737 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 | 2021-11-18 | 2021-12-03 | 13 | 13 | 10 | 10
1053 | Upland 7-Eleven #34701 | 775 N Central Ave | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 | 2021-11-15 | 2021-11-20 | 10 | 10 | 5 | 5
1054 | Baldwin Park 7-Eleven #38245 | 13853 Garvey Ave | Baldwin Park | 91706 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1055 | Pomona 7-Eleven #33092 | 2055 N Towne Ave | Pomona | 91767 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 | 2021-11-16 | 2021-11-21 | 11 | 11 | 4 | 4
1056 | Rosemead 7-Eleven #33242 | 3366 San Gabriel Blvd | Rosemead | 91770 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1057 | Rialto 7-Eleven #38168 | 1130 Renaissance Pkwy | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1058 | La Puente 7-Eleven #25185 | 14656 Francisquito Ave | La Puente | 91746 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1059 | South El Monte 7-Eleven #25922 | 1533 Peck Rd | South El Monte | 91733 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-02 |  | 2021-12-09
1060 | Garden Grove 7-Eleven #22414 | 12752 Brookhurst St | Garden Grove | 92840 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03
1061 | Ontario 7-Eleven #33035 | 3490 Jurupa St | Ontario | 91761 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2021-11-01 | 2021-11-01 |  |  | 1 | 1 | 2021-11-03 | 2021-11-18 | 2021-12-03 | 13 | 13 | 10 | 10
1062 | Santa Clarita, CA - 23502 Newhall Ave | 23502 Newhall Ave | Santa Clarita | 91321 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Coast | Ventura |  |  | 3261685 | 1967915 |  |  | 16 |  |  | NO | 2021-10-27 | 2022-02-02 | 66 | 66 | 2021-10-27 | 2021-10-27 | 66 | 66 | 1 | 1 | 2021-11-09 | 2021-11-12 | 2021-11-16 | 12 | 12 | 3 | 3 | 2022-02-24 | 81 | 81 | 2022-02-28 | 2022-03-01 | 2022-06-24 | 2022-04-27 | 45 | 45 | 2022-04-28 | 2022-07-07 | 49 | 49 | 2022-07-28 | 2022-07-27 | 15 | 15 | 2022-07-28 | 2 | 2 | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-10-12 | 3 | 3 | 69 | 69 | 53 | 53 | 2022-07-28 | 2022-08-02 | 2022-09-14 | 2 | 2 | 31 | 31 | 34 | 34 | 2022-12-01 | 87 | 87 | 2022-12-21 | 15 | 15 | 2022-07-29 | 2022-07-29 | 2022-10-12 | 2022-12-21 | 100 | 100 | 88 | 88 | [18 empty] | 2023-02-05 | [8 empty] | 2023-03-02 |  |  | 2023-03-02 |  |  |  | 338 | 338 | 258 | 258 | 2023
1063 | Rancho Palos Verdes 7-Eleven #33601 | 31186 Hawthrone Blvd | Rancho Palos Verdes | 90275 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2021-10-22 | 2021-10-22 |  |  | 1 | 1 | 2021-10-27
1064 | Inglewood - 3300 W Century Blvd R29 | 3380 W Century Blvd | Inglewood | 90303 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3359574 | 2052152 | 2052151 |  | 4 | YES | Level 3 | YES | 2021-11-02 | 2021-11-05 | 4 | 4 | 2022-04-14 | 2021-03-18 | 164 | 164 | -272 |  | 2021-03-18 | 2021-03-31 | 2021-04-01 | 10 | 10 | 2 | 2 | 2022-04-14 | 1 | 1 | 2022-04-19 |  | 2022-08-05 | 2022-08-11 | 84 | 84 | 2022-08-11 | 2022-09-23 | 31 | 31 | 2022-10-13 | 2022-11-04 | 31 | 31 | 2022-11-04 | 1 | 1 | 2022-12-08 | 2022-12-08 | 2022-12-08 | 2022-12-08 | 22 | 22 | 52 | 52 | 1 | 1 | 2022-11-08 | 2022-11-23 | 2023-03-27 | 3 | 3 | 85 | 85 | 95 | 95 | 2023-05-25 | 140 | 140 |  |  |  | 2022-11-23 | 2022-11-23 | 2023-03-27 |  |  |  | 140 | 140
1066 | Ontario 2440 S Vineyard Ave | 2442 S Vineyard-MP | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3206774 | 1942755 |  |  | 24 | NO |  | YES |  |  |  |  | 2021-11-01 | [12 empty] | 2021-11-01 | 1 | 1 |  |  | 2021-12-17 | 2022-12-31 | 293 | 293 | 2022-12-31 | 2022-10-11 | -56 |  | 2022-11-03 | 2022-11-20 | 28 | 28 | 2022-11-28 | 4 | 4 | 2023-01-26 | 2023-02-08 | 2023-01-26 | 2023-01-30 | 46 | 46 | 76 | 76 | 3 | 3 |  | 2023-02-13 | 2023-03-10 |  |  | 19 | 19 |  |  | 2023-08-25 | 191 | 191 | 2023-09-01 | 6 | 6 | 2023-01-26 | 2023-01-26 | 2023-03-10 | 2023-09-01 | 154 | 154 | 194 | 194 | 2023-06-23 | 2023-06-29 | 2023-06-29 | 5 | 5 | 2023-05-17 |  |  | 2023-05-23 | 5 | 5 | [6 empty] | 2023-05-18 | 2023-07-22 | 46 | 46 | 45 | 45 | 2023-07-25 | 2023-08-22 | 21 | 21
1067 | Victorville Seventh St. | 14598 Seventh St. | Victorville | 92395 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 73 - Victorville | Rurals | SBRO | [9 empty] | YES |  |  |  |  | 2021-11-01 | [17 empty] | 2022-01-13
1068 | Simi Valley, CA - 2757 Tapo Canyon Rd | 2751 1/4 Tapo Canyon Rd | Simi Valley | 93063 | Ventura County | 6. Requirements (permit, easment, etc.) | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3543873 | 2220721 | 2220722 | 2024-09-02 | 22 | YES | Level 3 | YES | 2021-11-04 | 2021-11-08 | 3 | 3 | 2021-11-04 | 2021-11-04 | 3 | 3 | 1 | 1 | 2021-11-05 | 2021-11-10 | 2021-11-15 | 5 | 5 | 3 | 3 |  |  |  | 2023-06-05 | 2023-06-05 | 2023-07-20 | 2023-11-26 |  |  | 2023-11-27 | 2023-11-28 | 2 | 2 | 2023-12-19 | 2024-01-18 | 35 | 35 | 2024-01-18 | 1 | 1 | 2024-03-05 |  | 2024-03-05 |  | 33 | 33 |  |  |  |  | 2024-01-31 |  |  | 10 | 10
1069 | Santa Monica Olympic HUB | 1003 Olympic Blvd EV | Santa Monica | 90404 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra |  |  | 3304513 | 2064779 | 1991566 | 2024-11-29 | 15 | YES | Level 3 | YES | 2022-04-27 | 2022-05-02 | 4 | 4 | 2022-10-11 | 2021-11-05 | 121 | 121 | -234 |  | 2021-11-05 | 2021-11-19 | 2021-12-10 | 10 | 10 | 14 | 14 | 2022-10-12 | 2 | 2 | 2022-05-06 | 2022-05-10 | 2022-11-08 | 2022-11-29 | 32 | 32 | 2022-11-29 | 2022-12-07 | 7 | 7 | 2023-01-03 | 2023-04-05 | 84 | 84 | 2023-04-05 | 1 | 1 | 2023-06-12 | 2023-06-12 | 2023-06-12 | 2023-06-16 | 48 | 48 | 135 | 135 | 5 | 5 | 2023-11-22 | 2023-12-01 | 2024-01-19 | 163 | 163 | 33 | 33 | 38 | 38 | [6 empty] | 2023-06-12 |  | 2024-01-19
1070 | Newbury Park, CA - 2321 Michael Dr | 2315 EV Michael Dr. | Newbury Park | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3404707 | 2199883 | 2199882 | 2024-07-03 | 16 | YES | Level 3 | YES | 2023-08-03 | 2023-08-08 | 4 | 4 | 2023-07-18 | 2023-07-18 | 16 | 16 | 1 | 1 | 2023-07-27 | 2023-07-31 | 2023-08-03 | 10 | 10 | 4 | 4 | 2022-06-08 | -281 |  | 2023-08-21 | 2023-08-21 | 2023-10-05 | 2023-10-09 | 339 | 339 | 2023-10-09 | 2023-10-16 | 6 | 6 | 2023-11-27 | 2023-11-30 | 32 | 32 | 2023-12-06 | 5 | 5 | 2024-02-27 |  | 2024-02-27 |  | 60 | 60 |  |  |  |  | 2024-01-29 | 2024-02-09 |  | 40 | 40 |  |  |  |  | 2024-02-27 | 56 | 56 |  |  |  | 2024-02-09 | 2024-02-09 |  |  |  |  | 60 | 60
1071 | Agoura Hills - 30125 Agoura Road | 30125 Agoura Road | Agoura Hills | 91301 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2021-11-04 | 2021-11-11 | 5 | 5 | 2021-11-04 | 2021-11-04 | 5 | 5 | 1 | 1 | 2021-11-05 |  | 2021-11-15
1072 | Long Beach, CA- 1601 Pacific Coast Highway | 1601 Pacific Coast Highway | Long Beach | 90806 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2021-12-08 | 2021-12-22 | 11 | 11 | 2021-11-05 | 2021-11-05 | 31 | 31 | 1 | 1 | 2021-12-03 | 2021-12-07 | 2021-12-07 | 20 | 20 | 1 | 1 | [20 empty] | 2021-11-05
1073 | Cudahy 7910 Atlantic Ave | 7910 Atlantic Ave | Cudahy | 90201 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2021-11-08 | 2021-11-30 | 14 | 14 | 2021-11-05 | 2021-11-05 | 15 | 15 | 1 | 1 | 2021-11-09 |  | 2021-12-09
1074 | South Coast Collection (SoCo) | 3303 Hyland Ave EV | Costa Mesa | 92626 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 3219169 | 1977915 |  | 2023-03-31 | 4 | NO |  | YES |  |  |  |  | 2021-11-08 | 2021-11-08 |  |  | 1 | 1 | 2021-11-09 |  | 2021-12-03 | [7 empty] | 2021-12-06 | 2021-12-08 | 2022-01-25 | 2022-01-22 |  |  | 2022-01-24 |  |  |  | 2022-05-20 | 2022-04-27 |  |  | 2022-04-28 | 2 | 2 | 2022-05-12 |  | 2022-05-12 | 2023-02-09 | 12 | 12 |  |  | 189 | 189 | 2022-04-28 | 2022-11-01 | 2023-02-01 | 2 | 2 | 63 | 63 | 193 | 193 | [6 empty] | 2022-05-12 |  | 2023-02-09 | [23 empty] | 2023-02-09 |  |  |  |  | 2023-03-03 | 2023-04-03 | 22 | 22 | 2023-04-03 | 22 | 22 | 2023-04-03 |  |  |  | 352 | 352 |  |  | 2023
1075 | Lake Elsinore, CA- 31500 Grape St | 31500 Grape St | Lake Elsinore | 92532 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3259271 | 1985958 |  |  | 16 |  |  | YES | 2021-11-09 | 2021-11-30 | 13 | 13 | 2021-11-09 | 2021-11-09 | 13 | 13 | 1 | 1 | 2021-11-15 |  | 2021-12-04 | [7 empty] | 2022-02-24 | 2022-03-02 | 2022-04-14 | 2022-04-08 |  |  | 2022-04-11 | 2022-04-22 | 10 | 10 | 2022-05-13 | 2022-04-29 | 6 | 6 | 2022-05-02 | 2 | 2 | 2022-05-31 |  | 2022-05-31 |  | 22 | 22 |  |  |  |  | 2022-05-02 | 2022-05-31 | 2022-06-06 | 2 | 2 | 5 | 5 | 25 | 25 | 2022-09-21 | 100 | 100 | 2022-09-22 | 2 | 2 | 2022-05-31 | 2022-05-31 |  |  |  |  | 101 | 101 |  |  | 2022-10-04 | [24 empty] | 2022-12-12 |  |  | 2022-12-12 |  |  |  | 273 | 273 |  |  | 2022
1076 | San Fernando S Workman St | 751 S Workman St | San Fernando | 91340 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2021-11-17 | 2021-11-18 | 2 | 2 | 2021-11-03 | 2021-11-03 | 11 | 11 | 1 | 1 | 2021-11-09 | 2021-11-12 | 2021-11-16 | 7 | 7 | 3 | 3 | [20 empty] | 2021-11-03
1077 | Huntington Beach 19051 Goldenwest St (Peninsula Marketplace) | 19051 Goldenwest St | Huntinton Beach | 92648 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2021-12-09 | 2021-12-22 | 10 | 10 | 2021-11-10 | 2021-11-10 | 28 | 28 | 1 | 1 | 2021-11-16 |  | 2021-12-07
1078 | Costa Mesa, CA - 1400 Bristol St | 1400 Bristol St, EM | Costa Mesa | 92626 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3349517 | 2017606 |  |  | 12 | NO |  | NO | 2021-12-09 | 2021-12-22 | 10 | 10 | 2021-11-12 | 2021-11-12 | 27 | 27 | 1 | 1 | 2021-11-16 | 2021-12-03 | 2021-12-07 | 14 | 14 | 3 | 3 | 2022-04-11 | 102 | 102 | 2022-04-12 | 2022-04-12 | 2022-05-27 | 2022-09-13 | 109 | 109 | 2022-09-13 | 2022-10-06 | 18 | 18 | 2022-10-27 | [6 empty] | 2022-11-17 | 2022-11-17 | 2022-11-17 | 2022-12-01 |  |  | 38 | 38 | 9 | 9 | 2022-10-26 | 2022-11-08 | 2023-03-02 |  |  | 78 | 78 | 87 | 87 | 2023-06-12 |  |  | 2023-07-14 | 24 | 24 | 2022-11-08 | 2022-11-08 | 2023-03-02 | 2023-07-14 | 172 | 172 |  |  | 2023-04-24 | 2023-04-27 | 2023-04-27 | 4 | 4 | [12 empty] | 2023-05-19 | 2023-06-03 |  |  | 10 | 10 | 2023-07-14 | 2023-08-19 | 26 | 26 | 2023-08-22 | 28 | 28 | 2023-08-22 |  |  |  | 448 | 448 | 347 | 347 | 2023
1079 | Perris - 7 Eleven #37338 | 4488 N Perris Blvd | Perris | 92562 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar |  |  | 3213090 | 1945468 |  |  | 2 | NO |  | NO |  |  |  |  | 2021-11-15 | 2021-11-15 |  |  | 1 | 1 | 2021-11-15 | 2021-11-17 | 2021-11-21 | 3 | 3 | 3 | 3 |  |  |  | 2021-11-29 | 2021-11-30 | 2022-03-10 | 2022-02-16 |  |  | 2022-02-16 | 2022-02-18 | 3 | 3 | 2022-03-15 | 2022-03-14 | 16 | 16 | 2022-03-14 | 1 | 1 | 2022-03-14 |  | 2022-03-14 |  | 1 | 1 |  |  |  |  | 2022-03-09 | 2022-04-05 | 2022-08-15 | -4 |  | 93 | 93 | 112 | 112 | [6 empty] | 2022-03-14
1080 | KPC South Coast Global medical Center | 2713 S Bristol St Unit# MTR01 | Santa Ana | 92704 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback |  |  | 3230486 | 1986129 |  |  | 4 | NO |  | NO |  |  |  |  | 2021-11-11 | 2021-11-18 |  |  | 5 | 5 | 2021-12-02 |  | 2021-12-09 |  |  |  |  | 2021-12-23 | 28 | 28 | 2021-12-29 | 2021-12-29 | 2022-02-14 | 2022-02-10 | 34 | 34 | 2022-02-11 | 2022-02-11 | 1 | 1 | 2022-03-09 | 2022-03-03 | 14 | 14 | 2022-04-11 | 28 | 28 | 2022-04-11 | 2022-06-22 | 2022-04-11 |  | 28 | 28 |  |  |  |  | 2022-05-02 | 2022-06-06 | 2023-01-16 | 43 | 43 | 155 | 155 | 179 | 179 | [6 empty] | 2022-04-11 | [12 empty] | 2023-03-15 |  |  | 2023-03-23 | 7 | 7 | [7 empty] | 2023-06-06 | 59 | 59 |  |  | 2023-08-08 | 2023-11-21 | 75 | 75 | 2023-11-21 | 75 | 75
1081 | LA Fitness Baldwin Park | 13822 Garvey Ave | Baldwin Park | 91706 | Los Angeles County | 3. Active | 27 - Monrovia | Metro East | Pomona |  |  | 3229035 | 1954848 |  | 2024-01-05 | 4 | NO |  | NO |  |  |  |  | 2021-11-11 | 2021-11-18 |  |  | 5 | 5 | 2021-12-03 |  | 2021-12-19 | [7 empty] | 2021-12-23 | 2022-01-12 | 2022-02-25 | 2022-02-25 |  |  | 2022-02-25 | 2022-03-17 | 15 | 15 | 2022-04-11 | 2022-04-20 | 25 | 25 | 2022-05-05 | 12 | 12 | 2022-05-05 | 2022-06-22 | 2022-05-05 | 2022-05-06 | 12 | 12 | 37 | 37 | 2 | 2 | 2022-04-01 | 2022-05-18 | 2023-10-05 | -14 |  | 351 | 351 | 384 | 384 | 2023-09-21 | 350 | 350 | 2023-11-29 | 48 | 48 | 2022-05-05 | 2022-05-05 | 2023-10-05 | 2023-11-29 | 397 | 397 | 361 | 361 |  |  | 2023-10-26 |  |  |  |  | 2022-08-17 | [9 empty] | 2022-08-17 | 2023-11-03 |  |  | 309 | 309 | 2023-11-30 | 2024-02-15 | 53 | 53 | 2024-02-15 | 53 | 53 | 2024-02-15 |  |  |  | 569 | 569 |  |  | 2024
1082 | Murrieta 7 Eleven #38687 | 26695 Jefferson Ave | Murrieta | 92562 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3273240 | 1985834 |  |  |  | NO |  | NO |  |  |  |  | 2021-11-16 | 2021-11-16 |  |  | 1 | 1 | 2021-11-16 | 2021-11-17 | 2021-11-21 | 2 | 2 | 3 | 3 |  |  |  | 2021-11-22 | 2021-11-23 | 2022-04-29 | 2022-04-28 |  |  | 2022-04-29 | 2022-05-05 | 5 | 5 | 2022-05-27 | 2022-06-14 | 28 | 28 | 2022-06-15 | 2 | 2 | 2022-06-15 |  | 2022-06-15 |  | 2 | 2
1083 | Eastvale 7 Eleven #38766 | 6291 Archibald Ave | Eastvale | 92880 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3212950 | 1946444 | [5 empty] | NO |  |  |  |  | 2021-11-16 | 2021-11-16 |  |  | 1 | 1 | 2021-11-16 | [9 empty] | 2021-11-22 | 2021-12-01 | 2021-12-29 | 2022-01-14 |  |  | 2022-01-14
1084 | Murrieta 7 Eleven #38453 | TBD - SE Corner of Murrieta Hot Springs Rd & Date | Murrieta | 92563 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-11-17
1085 | Menifee 7 Eleven #38490 | 27397 Menifee Rd | Menifee | 92585 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-11-17 | 2021-11-17 |  |  | 1 | 1 | 2021-12-02
1086 | Perris 7 Eleven #38970 | 2010 N Perris Blvd | Perris | 92570 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-11-17 | 2021-12-06 |  |  | 12 | 12 | 2021-12-06
1087 | San Bernardino 7 Eleven #13954 | 2384 Arden Ave | San Bernardino | 92404 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO |  |  | 3282940 | 1985793 | [5 empty] | NO |  |  |  |  | 2021-11-17 | 2021-11-17 |  |  | 1 | 1 | 2021-12-02 |  | 2021-12-22 | [7 empty] | 2022-04-04 | 2022-04-13 | 2022-05-18
1088 | Riverside 7 Eleven #41563 (March Airforce Base Reserve) | 14511 Meridian Parkway | Riverside | 92508 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar |  |  | 3274410 | 1994173 | [5 empty] | YES |  |  |  |  | 2021-11-17 | 2021-11-17 |  |  | 1 | 1 | 2021-12-02 |  | 2021-12-12 | [7 empty] | 2022-03-21 | 2022-03-24 | 2022-06-07 | 2022-06-03 |  |  | 2022-06-06
1089 | Yermo - Sunrise Canyon Rd | 40863 Sunrise Canyon Rd EV1 | Yermo | 92398 | San Bernardino County | 10. Customer Hold | 72 - Barstow | Rurals | SBRO |  |  | 3271843 | 1975544 |  |  | 40 | NO |  | NO | 2021-11-29 | 2021-12-15 | 13 | 13 | 2021-11-17 | 2021-11-17 | 19 | 19 | 1 | 1 | 2021-11-17 |  | 2021-11-23 |  |  |  |  | 2022-03-15 | 80 | 80 | 2022-03-16 | 2022-03-24 | 2022-04-29 | 2022-04-27 | 32 | 32 | 2022-04-28 | 2022-09-22 | 103 | 103 | 2022-10-14 | 2022-11-22 | 43 | 43 | 2022-11-28 | 3 | 3 | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-02-07 | 52 | 52 | 95 | 95 | 2 | 2 |  | 2022-12-15 | 2022-12-21 |  |  | 5 | 5 |  |  | 2023-01-05 | 29 | 29 |  |  |  | 2022-12-15 | 2022-12-15 | 2023-02-07 |  |  |  | 31 | 31 | [18 empty] | 2023-03-09 |  |  |  |  | 2023-03-30 |  |  |  | 2023-05-24 | 40 | 40 | 2023-05-24 |  |  |  | 383 | 383 | 304 | 304 | 2023
1090 | Gardena 7 Eleven #38647 | 15015 Crenshaw Blvd | Gardena | 90249 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3255200 | 1991486 | [5 empty] | YES |  |  |  |  | 2021-11-17 | 2021-11-17 |  |  | 1 | 1 | 2021-12-06 | 2021-12-12 | 2021-12-12 | 16 | 16 | 0 |  |  |  |  | 2022-02-16 | 2022-02-22 | 2022-05-17 | 2022-05-13 |  |  | 2022-05-16
1091 | Hawaiian Gardens, CA - 11871 E Carson St | 11871 Carson St Unit EV1 | Hawaiian Gardens | 90716 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  | Toblerone 12kv | 3438723 | 2116728 |  | 2023-08-31 | 32 | NO |  | NO | 2021-12-03 | 2021-12-17 | 11 | 11 | 2021-11-19 | 2021-11-19 | 19 | 19 | 1 | 1 | 2021-11-22 | 2021-11-29 | 2021-12-03 | 5 | 5 | 5 | 5 | 2022-11-18 | 252 | 252 | 2022-12-14 | 2022-12-15 | 2023-02-01 | 2023-02-01 | 51 | 51 | 2023-02-01 | 2023-02-08 | 6 | 6 | 2023-02-23 | 2023-04-09 | 42 | 42 | 2023-04-10 | 1 | 1 | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-09-21 | 17 | 17 | 158 | 158 | 100 | 100 | 2023-04-10 | 2023-04-27 | 2023-05-10 | 1 | 1 | 10 | 10 | 23 | 23 | 2023-10-03 | 124 | 124 | 2023-10-25 | 17 | 17 | 2023-04-27 | 2023-04-27 | 2023-09-21 | 2023-10-25 | 127 | 127 | 124 | 124 | 2023-07-18 | 2023-07-24 | 2023-09-08 | 38 | 38 | 2023-07-20 | 2023-08-30 |  | 2023-07-24 | 3 | 3 | [6 empty] | 2023-08-30 | 2023-09-08 | 36 | 36 | 7 | 7 | 2023-10-25 |  |  |  | 2023-12-12 | 33 | 33 | 2023-12-12 |  |  |  | 520 | 520 | 269 | 269 | 2023
1092 | Perris 7 Eleven #37728 | 3155 Case Rd | Perris | 92570 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2021-11-22 | 2021-12-06 |  |  | 9 | 9 | 2021-12-06
1093 | Laguna Hills, CA - Lake Forest Dr. (Carl's Jr.) | 23002 Lake Forest Dr. | Laguna Hills | 92653 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2021-12-09 | 2021-12-16 | 6 | 6 | 2021-11-22 | 2021-12-01 | 12 | 12 | 6 | 6 | 2021-12-02 | 2021-12-03 | 2021-12-07 | 3 | 3 | 3 | 3
1094 | Inglewood - 3530 W Century Blvd | 3530 W Century Blvd | Inglewood | 90303 | Los Angeles County | 7. Civil Construction | 44 - South Bay | Metro West | Alhambra |  |  | 3228390 | 1969186 |  |  | 4 | NO |  | NO | 2021-12-13 | 2021-12-20 | 6 | 6 | 2021-11-19 | [7 empty] | 2021-12-12 | [7 empty] | 2021-12-22 | 2021-12-28 | 2022-02-09 | 2022-02-09 |  |  |  | 2022-05-10 |  |  | 2022-06-07 | 2022-06-07 | 20 | 20 | 2022-06-08 | 2 | 2 | 2022-06-08 | 2022-06-21 | 2022-06-08 | 2022-06-09 | 2 | 2 | 22 | 22 | 2 | 2 | 2022-06-21 | 2022-07-22 | 2022-09-28 | 11 | 11 | 48 | 48 | 70 | 70 | 2022-11-28 | 119 | 119 |  |  |  | 2022-06-08 | 2022-06-08 | 2022-09-28 |  |  |  | 120 | 120 | 2022-11-22 | 2022-12-06 | 2022-12-14 | 15 | 15 | 2022-10-05 | 2022-10-11 | 2022-11-14 | 2022-10-12 | 6 | 6 | 2022-11-10 | 22 | 22 | 2022-11-21 | 6 | 6 | 2023-01-09 | 2023-01-09 | 66 | 66 | 1 | 1 | 2023-01-13 | 2023-02-02 | 14 | 14 | 2023-02-03 | 15 | 15 | 2023-02-03 |  |  |  | 304 | 304 |  |  | 2023
1095 | Temecula - Beyond Food Mart, Inc | 40135 Village Rd (mtr address: 40127) | Temecula | 92591 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3265247 | 2097873 |  | 2024-05-29 | 3 | YES | Level 3 | YES |  |  |  |  | 2021-11-30 | 2021-11-30 |  |  | 1 | 1 | 2021-12-06 | 2021-12-20 | 2022-01-07 | 15 | 15 | 14 | 14 |  |  |  | 2022-03-07 | 2022-03-14 | 2022-04-20 | 2022-04-28 |  |  | 2022-04-28 | 2022-04-29 | 2 | 2 |  | 2022-06-06 | 26 | 26 | 2022-06-06 | 1 | 1 | 2022-06-02 | 2024-03-15 | 2022-06-02 | 2024-03-15 | -3 |  | 474 | 474 | 451 | 451 | 2023-03-14 | 2023-03-24 | 2023-08-31 | 195 | 195 | 113 | 113 | 121 | 121 | [6 empty] | 2022-06-02 |  | 2024-03-15 | [5 empty] | 2024-03-25 |  |  |  |  | 2023-06-29 |  |  | 2023-07-07 | 6 | 6
1096 | Torrance Chase Bank R29 | 17200 S Hawthorne Blvd-EV | Torrance | 90504 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3240420 | 2051238 | 1959829 | 2024-01-26 | 4 | YES | Level 3 | YES | 2022-01-14 | 2022-01-18 | 2 | 2 | 2023-01-26 | 2021-12-01 | 33 | 33 | -292 |  | 2021-12-02 | 2021-12-06 | 2021-12-12 | 4 | 4 | 5 | 5 | 2023-01-26 | 1 | 1 | 2023-01-27 | 2023-01-30 | 2023-02-13 | 2023-05-15 | 77 | 77 | 2023-05-15 | 2023-05-17 | 3 | 3 | 2023-06-09 | 2023-06-13 | 19 | 19 | 2023-06-13 | 1 | 1 | 2023-06-16 |  | 2023-06-16 | 2023-06-20 | 4 | 4 | 24 | 24 | 3 | 3 | 2023-06-30 | 2023-07-11 | 2023-08-02 | 14 | 14 | 17 | 17 | 23 | 23 | [6 empty] | 2023-06-16 |  | 2023-08-02 | [5 empty] | 2023-09-20 | 2023-10-23 | 2023-10-27 | 28 | 28 |  | 2023-01-05 |  | 2023-08-09 | [8 empty] | 2023-10-23 | 2023-11-02 |  |  | 9 | 9 | 2023-11-03 | 2023-12-15 | 29 | 29 | 2023-12-16 | 29 | 29 | 2023-12-16 | 2024-01-12 | 18 | 18 | 226 | 226 | 226 | 226 | 2023
1097 | Barstow CK# 2705731 | 1501 E Main St | Barstow | 92311 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO | Tortilla | Peso 12kv | 3337205 |  |  | 2023-06-01 |  | YES | Level 3 | YES | 2022-06-27 | 2022-07-15 | 14 | 14 | 2021-12-02 | 2022-04-26 | 57 | 57 | 101 | 101 | 2022-04-27 | 2022-06-12 | 2022-06-12 | 33 | 33 | 0 |  | 2022-06-27 | 144 | 144 | 2022-08-15 | 2022-08-15 | 2022-09-28 | 2022-10-19 | 81 | 81 | 2022-10-20 | 2022-12-01 | 28 | 28 | 2022-12-27 | 2023-02-27 | 61 | 61 | [13 empty] | 2023-01-16 | 2023-02-13 | 2023-02-21 | -29 |  | 6 | 6 | 25 | 25
1098 | Corona Ck#2706064 | 8590 Cajalco Rd | Corona | 92881 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona | Corona | Owens 33kV | 3337280 | 2053865 |  | 2023-03-10 | 8 | YES | Level 2 | NO | 2022-06-28 | 2022-07-14 | 12 | 12 | 2022-07-29 | 2022-04-22 | 58 | 58 | -69 |  | 2022-05-22 | 2022-05-25 | 2022-06-10 | 24 | 24 | 12 | 12 | 2022-08-02 | 3 | 3 | 2022-08-02 |  | 2022-09-15 | 2022-09-20 | 35 | 35 | 2022-09-20 | 2022-09-21 | 2 | 2 | 2022-10-26 | 2022-11-04 | 33 | 33 | 2022-11-07 | 2 | 2 | 2022-12-21 | 2022-12-21 | 2022-12-21 | 2022-12-21 | 31 | 31 | 63 | 63 | 1 | 1 | 2022-11-10 | 2022-11-30 | 2022-12-14 | 5 | 5 | 11 | 11 | 22 | 22 | 2022-12-21 | 30 | 30 | 2023-03-02 | 50 | 50 | 2022-11-30 | 2022-11-30 | 2022-12-21 | 2023-03-02 | 65 | 65 | 31 | 31 | 2023-03-20 | 2023-04-06 | 2023-04-28 | 30 | 30 | 2022-11-21 |  |  | 2023-01-04 | 31 | 31 | [6 empty] | 2023-05-12 | 2023-05-21 | 126 | 126 | 6 | 6 | 2023-05-22 | 2023-06-22 | 23 | 23 | 2023-06-22 | 23 | 23 | 2023-06-22 | 2023-07-06 | 10 | 10 | 228 | 228 | 226 | 226 | 2023
1099 | Victorville CK# 2706066 | 15825 EV Mojave Dr | Victorville | 92394 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  |  | 3337365 | 2051742 |  | 2023-03-02 | 4 | YES | Level 2 | NO |  |  |  |  | 2021-12-02 | 2021-04-26 |  |  | -153 |  | 2022-04-27 | 2022-06-12 | 2022-06-12 | 285 | 285 | 0 |  | 2022-07-15 | 157 | 157 | 2022-08-15 |  | 2022-10-06 | 2022-11-02 | 78 | 78 | 2022-11-02 | 2022-11-03 | 2 | 2 | 2022-11-02 | 2022-11-04 | 2 | 2 | 2022-11-07 | 2 | 2 | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2 | 2 | 3 | 3 | 1 | 1 | 2022-10-26 | 2022-11-08 | 2022-12-14 | -8 |  | 24 | 24 | 33 | 33 | [6 empty] | 2022-11-07 |  | 2022-12-14 | [5 empty] | 2023-01-26 | 2023-02-10 | 2023-02-24 | 21 | 21 | 2022-11-17 |  |  | 2022-11-29 | 7 | 7 | [6 empty] | 2023-03-20 | 2023-03-24 | 88 | 88 | 5 | 5 | 2023-03-27 | 2023-04-24 | 21 | 21 | 2023-04-25 | 22 | 22 | 2023-04-28 | 2023-05-25 | 20 | 20 | 356 | 356 | 200 | 200 | 2023
1101 | San Bernardino 7 Eleven #38322 | 3154 W Kendall Drive | San Bernardino | 92407 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3273130 | 1986304 | [5 empty] | YES |  |  |  |  | 2021-11-17 | [7 empty] | 2022-03-07 | [7 empty] | 2022-03-17 | 2022-03-24 | 2022-05-05 | 2022-06-06 |  |  | 2022-06-06
1102 | Laguna Beach - Broadway | 239 Broadway | Laguna Beach | 92651 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO | 2021-12-08 | 2021-12-16 | 7 | 7 | 2021-12-03 | [7 empty] | 2021-12-04
1103 | Corona CK#2706063- Foothill | 1905 Foothill Pkwy | Corona | 92881 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3335516 | 2042277 | 2042275 | 2023-11-13 |  | YES | Level 3 | false |  |  |  |  | 2022-06-24 | [12 empty] | 2022-06-24 | 1 | 1 | 2023-02-17 |  | 2023-04-04 | 2023-04-10 | 200 | 200 | 2023-04-10 | 2023-04-13 | 4 | 4 | 2023-08-04 | 2023-08-04 | 80 | 80 | 2023-08-07 | 2 | 2 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  | 34 | 34 |  |  |  |  | 2023-08-30 |  |  | 19 | 19 |  |  |  |  | 2023-08-17 | 9 | 9 | 2023-09-21 | 25 | 25 | [6 empty] | 10 | 10 | [5 empty] | 2023-09-06 |  |  | 2023-09-08 | 3 | 3
1104 | Mission Viejo CK#2709425 | 26052 Marguerite Pkwy | Mission Viejo | 92691 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [7 empty] | NO |  | NO |  |  |  |  | 2021-12-03 | 2021-12-07 |  |  | 3 | 3 | 2021-12-09 | 2021-12-15 |  | 7 | 7
1105 | Victorville CK#2706059 Nisqualli | 15289 Nisqualli Rd | Victorville | 92395 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 73 - Victorville | Rurals | SBRO |  |  | 3336066 | 2040854 |  | 2023-03-13 | 4 | YES | Level 2 | NO |  |  |  |  | 2022-07-29 | 2022-04-26 |  |  | -67 |  | 2022-05-02 | 2022-05-16 | 2022-06-14 | 15 | 15 | 21 | 21 | 2022-08-02 | 3 | 3 | 2022-08-02 |  | 2022-10-10 | 2022-11-10 | 72 | 72 | 2022-11-10 | 2022-11-17 | 5 | 5 | 2022-12-08 | 2022-12-29 | 29 | 29 | 2023-01-17 | 13 | 13 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 13 | 13 | 41 | 41 | 1 | 1 | 2023-01-17 | 2023-01-26 | 2023-02-21 | 13 | 13 | 18 | 18 | 25 | 25 | [6 empty] | 2023-01-17 |  | 2023-02-21 | [5 empty] | 2023-03-17 | 2023-04-20 | 2023-04-21 | 26 | 26 | 2023-01-25 |  |  | 2023-02-01 | 6 | 6 | [6 empty] | 2023-05-12 | 2023-05-17 | 80 | 80 | 4 | 4 | 2023-05-18 | 2023-06-18 | 21 | 21 | 2023-06-19 | 22 | 22 | 2023-06-19 | 2023-07-06 | 13 | 13 | 225 | 225 | 223 | 223 | 2023
1106 | Simi Valley - D&Z Properties, LLC | 5820 1/2 Los Angeles Ave | Simi Valley | 93063 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3274478 | 1985391 | 2029472 | 2024-06-01 | 12 | YES | Level 3 | NO |  |  |  |  | 2021-12-06 | 2021-12-06 |  |  | 1 | 1 | 2021-12-06 | 2021-12-07 | 2022-01-21 | 2 | 2 | 32 | 32 |  |  |  | 2022-03-21 |  | 2022-05-04 | 2022-05-31 |  |  | 2022-06-06 | 2022-06-06 | 1 | 1 |  | 2022-08-25 | 58 | 58 | 2022-08-25 | 1 | 1 | 2022-09-22 | 2023-10-10 | 2022-09-22 | 2023-08-30 | 20 | 20 | 314 | 314 | 238 | 238 | 2022-08-25 | 2022-08-30 | 2022-09-08 | 1 | 1 | 7 | 7 | 10 | 10 | [6 empty] | 2022-08-30 |  | 2023-08-30
1107 | Indio CK# 2706067 | 82061 Avenue 42 | Indio CA 92203 | 92203 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | [7 empty] | NO |  | YES |  |  |  |  | 2021-12-07 | 2021-12-08 |  |  | 2 | 2 | 2021-12-09
1108 | Palm Desert CK#2709424 | 78005 Country Club Dr | Palm Desert | 92203 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO | Concho | Matador 12kV | 3313666 | 2016865 |  | 2023-03-02 | 4 | NO |  | NO | 2022-05-05 | 2022-05-18 | 10 | 10 | 2021-12-07 | 2021-12-07 | 114 | 114 | 1 | 1 | 2021-12-09 | 2022-05-02 | 2022-05-02 | 102 | 102 | 1 | 1 | 2022-05-20 | 116 | 116 | 2022-05-23 | 2022-06-01 | 2022-07-08 | 2022-08-10 | 57 | 57 | 2022-08-10 | 2022-09-23 | 32 | 32 | 2022-10-23 | 2022-10-22 | 21 | 21 | 2022-10-22 | 0 |  | 2022-11-01 | 2022-11-22 | 2022-11-01 |  | 7 | 7 |  |  |  |  | 2022-10-12 | 2022-10-27 | 2022-11-11 | -8 |  | 11 | 11 | 22 | 22 | 2022-12-08 | 31 | 31 | 2022-12-13 | 4 | 4 | 2022-10-27 | 2022-10-27 |  |  |  |  | 31 | 31 | 2023-03-02 | 2023-03-16 | 2023-03-16 | 11 | 11 | 2022-11-07 |  | 2022-12-05 | 2022-11-10 | 4 | 4 |  |  |  | 2022-12-07 | 3 | 3 | 2023-03-16 | 2023-03-22 | 93 | 93 | 5 | 5 | 2023-03-23 | 2023-04-18 | 19 | 19 | 2023-04-19 | 20 | 20 | 2023-04-20 |  |  |  | 347 | 347 | 232 | 232 | 2023
1109 | Perris CK# 2709455 | 1675 N Perris Blvd | Perris | 92571 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar | Bunker | Soldier 12kV | 3314090 | 2012748 |  | 2023-03-03 | 8 | NO |  | YES | 2022-05-11 | 2022-05-27 | 13 | 13 | 2021-12-07 | 2022-04-25 | 25 | 25 | 97 | 97 | 2022-04-25 | 2022-05-07 | 2022-05-07 | 10 | 10 | 0 |  | 2022-05-23 | 117 | 117 | 2022-05-24 | 2022-06-02 | 2022-07-15 | 2022-08-10 | 56 | 56 | 2022-08-10 | 2022-12-01 | 78 | 78 | 2022-12-27 | 2022-12-02 | 2 | 2 | 2022-12-02 | 1 | 1 | 2022-12-21 | 2023-02-15 | 2022-12-21 | 2023-01-16 | 14 | 14 | 32 | 32 | 18 | 18 | 2022-12-05 | 2022-12-19 | 2023-02-08 | 2 | 2 | 37 | 37 | 47 | 47 | 2023-01-12 | 30 | 30 | 2023-01-18 | 4 | 4 | 2022-12-19 | 2022-12-19 | 2023-02-08 | 2023-02-08 | 37 | 37 | 30 | 30 | 2023-03-23 | 2023-04-18 | 2023-05-02 | 29 | 29 | 2023-01-18 | 2023-03-06 |  | 2023-01-24 | 5 | 5 | 2023-03-13 | 34 | 34 |  |  |  | 2023-04-21 | 2023-05-17 | 85 | 85 | 19 | 19 | 2023-05-18 | 2023-07-16 | 40 | 40 | 2023-07-17 | 41 | 41 | 2023-07-17 |  |  |  | 407 | 407 | 291 | 291 | 2023
1110 | Irvine, CA - 5396 Walnut Ave (Expansion) | 5396 1/2 Walnut Ave | Irvine | 92604 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3290007 | 1992134 |  |  | 12 | NO |  | YES | 2021-12-21 | 2021-12-27 | 4 | 4 | 2021-12-07 | 2021-12-07 | 14 | 14 | 1 | 1 | 2021-12-13 |  | 2021-12-27 | [7 empty] | 2022-04-13 | 2022-04-14 | 2022-05-30 | 2022-07-19 |  |  | 2022-07-19 | 2022-09-08 | 37 | 37 | 2022-09-29 | 2022-10-07 | 22 | 22 | 2022-10-07 | 1 | 1 | 2022-10-21 | 2022-11-15 | 2022-10-21 | 2022-11-18 | 11 | 11 | 51 | 51 | 20 | 20 |  | 2022-10-20 | 2023-02-03 |  |  | 73 | 73 |  |  | 2023-05-02 | 143 | 143 | 2023-05-09 | 6 | 6 | 2022-10-20 | 2022-10-20 | 2023-02-03 | 2023-05-09 | 139 | 139 | 143 | 143 | [18 empty] | 2023-05-25 |  |  |  |  | 2023-05-31 |  |  |  | 2023-07-28 | 42 | 42 | 2023-07-28 |  |  |  | 416 | 416 |  |  | 2023
1111 | Redlands, CA - Alabama St | 9946 Alabama St | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-05-15 |  |  |  | NO |  |  |  |  | 2021-12-08 | 2021-12-08 |  |  | 1 | 1 | 2021-12-21 |  | 2022-03-02
1112 | Cabazon - Seminole Dr | 48400 Seminole Dr, Cabazon, CA 92230 | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2021-12-08 | [5 empty] | 2021-12-13 |  | 2022-01-12
1113 | La Mirada, CA - 14500 Firestone Blvd | 14500 Firestone Blvd | La Mirada | 90638 | Los Angeles County | 9. Complete | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO | 2021-12-20 | 2022-01-03 | 10 | 10 | 2021-12-09 | 2021-12-09 | 17 | 17 | 1 | 1 | 2021-12-13 |  | 2021-12-20
1114 | La Puente - Chase Bank Hacienda | 925 N Hacienda | La Puente | 91744 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3242405 | 1964281 |  |  | 8 | NO |  | YES | 2022-01-04 | 2022-01-11 | 6 | 6 | 2021-12-14 | 2021-12-15 | 19 | 19 | 2 | 2 | 2021-12-16 | 2021-12-21 | 2021-12-30 | 5 | 5 | 7 | 7 |  |  |  | 2022-01-25 | 2022-02-03 | 2022-03-18 | 2022-03-17 |  |  | 2022-03-21 | 2022-04-19 | 22 | 22 | 2022-05-16 | 2022-05-16 | 20 | 20 | 2022-05-17 | 2 | 2 | 2022-05-17 | 2022-09-23 | 2022-05-17 | 2022-06-01 | 2 | 2 | 31 | 31 | 11 | 11 | 2022-06-06 | 2022-08-05 | 2022-09-16 | 15 | 15 | 30 | 30 | 73 | 73 | 2022-11-22 | 132 | 132 | 2023-01-10 | 34 | 34 | 2022-05-17 | 2022-05-17 | 2022-09-16 | 2023-01-10 | 165 | 165 | 133 | 133 | 2023-01-10 | 2023-01-24 | 2023-01-26 | 12 | 12 | 2022-09-02 | 2022-12-28 | 2023-02-17 | 2022-09-08 | 4 | 4 | 2023-01-04 | 82 | 82 | 2023-02-28 | 7 | 7 | 2023-02-28 | 2023-03-06 | 126 | 126 | 5 | 5 | 2023-03-09 | [6 empty] | 2023-04-22 |  |  |  | 343 | 343 |  |  | 2023
1115 | South Pasadena - Bank of America | 929 S Fair Oaks Ave | South Pasadena | 91030 | Los Angeles County | 10. Customer Hold | 27 - Monrovia | Metro East | Pomona | Alhambra | Asteroid KV | 3239419 | 1967602 |  |  | 4 | NO |  | YES | 2022-01-04 | 2022-01-18 | 10 | 10 | 2021-12-17 | 2021-12-17 | 21 | 21 | 1 | 1 | 2021-12-21 |  | 2022-01-03 |  |  |  |  | 2022-01-14 | 20 | 20 | 2023-01-04 | 2023-01-10 | 2023-02-23 | 2023-02-23 | 280 | 280 | 2023-02-23 | 2023-03-30 | 26 | 26 |  | 2023-04-25 | 19 | 19 | 2023-04-27 | 3 | 3 | [10 empty] | 2022-06-10 |  |  | -221
1116 | Alhambra, CA - W Valley Blvd | 1420 W Valley Blvd, EV-1 | Alhambra | 91803 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  | Kay 16kV | 3415597 | 2081921 |  | 2024-08-21 |  |  |  | true | 2021-12-21 | 2022-01-05 | 11 | 11 | 2021-11-16 | 2021-11-16 | 34 | 34 | 1 | 1 | 2021-11-16 |  | 2021-12-20 | [7 empty] | 2022-11-02 | 2022-11-02 | 2022-12-19 | 2023-03-14 |  |  | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-04-05 | 2023-04-10 | 20 | 20 | 2023-04-10 | 1 | 1 | 2023-04-10 |  | 2023-04-10 |  | 1 | 1 | [6 empty] | 2023-04-04
1117 | Long Beach, CA - 709 E Anaheim St | 709 E Anaheim St | Long Beach | 90813 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2022-01-04 | 2022-01-19 | 11 | 11 | 2021-12-22 | 2021-12-27 | 17 | 17 | 3 | 3 | 2021-12-27 |  | 2022-01-03
1118 | Malibu, CA - La Paz Lane | 23465 Civic Center Way | Malibu | 90265 | Los Angeles County | 10. Customer Hold | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2021-12-23 | 2021-12-27 |  |  | 2 | 2 | 2021-12-27
1119 | Beverly Hills, CA - 9595 Wilshire Blvd | 9595 Wilshire Blvd | Beverly Hills | 90212 | Los Angeles County | 4. Preliminary Design | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES | 2022-01-10 | 2022-01-12 | 3 | 3 | 2021-12-23 | 2021-12-23 | 14 | 14 | 1 | 1 | 2021-12-27 |  | 2022-01-10
1120 | Carson, CA - Civic Center Dr | 2 Civic Plaza Dr | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3300184 | 1996710 |  | 2024-05-17 |  | NO |  | NO | 2022-01-04 | 2022-01-05 | 2 | 2 | 2021-12-23 | 2021-12-27 | 8 | 8 | 2 | 2 | 2021-12-27 |  | 2022-01-03 |  |  |  |  | 2023-08-07 | 410 | 410 | 2024-02-09 | 2024-02-09 | 2024-03-25 | 2024-03-15 | 153 | 153 | 2024-03-21 | [43 empty] | 2023-10-12
1121 | Tehachapi - Tehachapi Blvd | 422 W Tehachapi Blvd | Tehachapi | 93561 | Kern County | 6. Requirements (permit, easment, etc.) | 52 - Tehachapi | North Valley | Ventura |  |  | 3262261 | 1975346 |  |  |  | NO |  | YES |  |  |  |  | 2021-12-28 | 2021-12-29 |  |  | 2 | 2 | 2021-12-29 |  | 2022-01-07 |  |  |  |  | 2022-03-01 | 44 | 44 | 2022-03-02 | 2022-03-02 | 2022-04-15 | 2022-03-31 | 23 | 23 | 2022-03-31 | 2022-12-02 | 171 | 171 | 2023-01-25 | [6 empty] | 2023-03-13 |  | 2023-03-13 | 2023-03-14 |  |  | 71 | 71 | 2 | 2 | 2023-02-22 | 2023-03-10 | [13 empty] | 2023-03-10
1122 | Barstow - 1503 E Main St | 1504 E Main St | Barstow | 92311 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO |  |  | 3296306 | 2001148 |  | 2024-08-23 | 120 | NO |  | NO | 2021-12-29 | 2021-12-30 | 2 | 2 | 2021-12-16 | 2021-12-16 | 10 | 10 | 1 | 1 | 2021-12-21 |  | 2021-12-28 |  |  |  |  | 2022-04-20 | 87 | 87 | 2023-10-31 | 2023-10-31 | 2023-12-15 | [7 empty] | 2024-01-12 | 2024-01-24 |  |  | 2024-01-24 | 1 | 1 | 2024-01-24 |  | 2024-01-24 |  | 1 | 1
1123 | Pomona - S East End Ave | 200 S East End (New Address: 296) | Pomona | 91766 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona |  |  | 3235300 | 1959179 |  |  |  | NO |  | YES |  |  |  |  | 2021-11-23 | 2021-12-03 |  |  | 7 | 7 | 2021-12-03 |  | 2022-01-02 | [7 empty] | 2022-01-11 | 2022-01-20 | 2022-02-24 | 2022-02-25 |  |  | 2022-02-25 | 2022-04-07 | 30 | 30 | 2022-05-03 | 2022-05-06 | 22 | 22 | 2022-05-06 | 1 | 1 | 2022-05-16 | 2022-06-03 | 2022-05-16 | 2022-06-22 | 7 | 7 | 54 | 54 | 27 | 27 | [23 empty] | 2022-12-13 | 2022-12-15 | 2022-12-22 | 8 | 8 | 2022-10-26 | [11 empty] | 2022-04-07 | 2022-04-28 | -127 |  | 16 | 16 | 2023-02-17 | 2023-03-14 | 17 | 17 | 2023-03-15 | 18 | 18
1124 | El Monte, CA - 11629 Lower Azusa Rd | 4802 Peck Road EV1 | El Monte | 91732 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 3321389 | 2018024 |  | 2024-07-15 |  | NO |  | YES | 2022-01-04 | 2022-01-20 | 12 | 12 | 2021-12-15 | 2021-12-15 | 25 | 25 | 1 | 1 | 2021-12-15 |  | 2022-01-03 |  |  |  |  | 2022-06-02 | 118 | 118 | 2022-07-27 | 2022-08-01 | 2023-08-25 | 2023-07-27 | 292 | 292 | 2023-07-28 | 2023-08-02 | 4 | 4 | 2023-08-23 | 2023-08-23 | 16 | 16 | 2023-08-25 | 3 | 3 | 2023-08-23 | 2023-08-23 | 2023-08-23 |  | 1 | 1 | [5 empty] | 2023-03-10 | 2023-04-13 |  |  | 25 | 25 | [8 empty] | 2023-03-10
1125 | City of Industry | 13300 Crossroads Pkwy | City of Industry | 91746 | Los Angeles County | 4. Preliminary Design | 26 - Covina | Metro East | Pomona | [7 empty] | NO |  | NO | 2022-01-14 | 2022-01-18 | 2 | 2 | 2022-01-04 | 2022-01-04 | 10 | 10 | 1 | 1 | 2022-01-05 | 2022-01-10 | 2022-01-13 | 5 | 5 | 4 | 4
1126 | Wildomar - Clinton Keith Rd | 23805 Clinton Keith Rd | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3238099 | 1988746 | [5 empty] | YES |  |  |  |  | 2022-01-06 | 2022-01-06 |  |  | 1 | 1 | 2022-01-06 | 2022-01-11 | 2022-01-14 | 4 | 4 | 4 | 4 |  |  |  | 2022-01-14 | 2022-01-18 | 2022-05-25 | 2022-08-21 |  |  | 2022-08-22
1127 | Long Beach - East Marina Dr | 6480 E Marina Dr, Long Beach, CA 90803 | Long Beach | 90803 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2022-01-19 | 2022-01-20 | 2 | 2 | 2022-01-05 | 2022-01-05 | 11 | 11 | 1 | 1 | 2022-01-06 | 2022-01-11 | 2022-01-19 | 5 | 5 | 6 | 6
1128 | Seal Beach Chase Bank | 801 Pacific Coast Hwy- EV | Seal Beach | 90740 | Orange County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3240930 | 1973410 |  |  | 8 | NO |  | YES | 2022-01-19 | 2022-01-20 | 2 | 2 | 2022-01-07 | 2022-01-10 | 8 | 8 | 2 | 2 | 2022-01-11 | 2022-01-12 | 2022-01-19 | 3 | 3 | 5 | 5 | 2022-01-13 | 5 | 5 | 2022-01-21 | 2022-01-21 | 2022-04-12 | 2022-04-11 | 61 | 61 | 2022-04-12 | 2022-05-10 | 21 | 21 | 2022-06-07 | 2022-06-07 | 20 | 20 | 2022-06-08 | 2 | 2 | 2022-06-08 | 2022-07-20 | 2022-06-08 | 2022-06-14 | 2 | 2 | 25 | 25 | 5 | 5 | 2022-06-21 | 2022-08-05 | 2022-08-15 | 11 | 11 | 7 | 7 | 39 | 39 | 2022-12-29 | 142 | 142 | 2023-01-02 | 3 | 3 | 2022-06-08 | 2022-06-08 | 2022-08-15 | 2023-01-02 | 144 | 144 | 143 | 143 | 2023-02-09 | 2023-02-24 | 2023-03-01 | 14 | 14 | 2022-08-18 | [11 empty] | 2023-03-24 | 2023-03-27 | 152 | 152 | 2 | 2 | 2023-03-28 | 2023-04-28 | 24 | 24 | 2023-04-29 | 24 | 24 | 2023-04-28 |  |  |  | 331 | 331 | 327 | 327 | 2023
1129 | Upland, CA - 1200 E 20th St | 1200 E 20th St | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | false | 2022-01-28 | 2022-02-18 | 16 | 16 | 2022-01-06 | 2022-01-06 | 31 | 31 | 1 | 1 | 2022-01-19 | 2022-01-27 | 2022-01-28 | 15 | 15 | 2 | 2
1130 | San Bernardino - 7-Eleven 34175 | 2885 Del Rosa Avenue | San Bernardino | 92404 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | false |  |  |  |  | 2022-01-10 | 2022-01-10 |  |  | 1 | 1 | 2022-01-11 |  | 2022-01-14
1131 | Rialto - 7-Eleven 34175 | 668 W Baseline Rd | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-01-11 | 2022-01-12 |  |  | 2 | 2 | 2022-01-12 |  | 2022-01-14
1132 | Culver City Trader Joe's | 9290 Culver Blvd | Culver City | 90232 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2022-01-11 | 2022-01-13 |  |  | 3 | 3 | 2022-01-18 | 2022-01-25 | 2022-01-27 | 8 | 8 | 3 | 3
1133 | Los Angeles - W Pico Blvd | 10701 W Pico Blvd | Los Angeles | 90064 | Los Angeles County | 7. Civil Construction | 22 - Montebello | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-01-12
1134 | Santa Ana - 1008 17th St | 1008 17th St | Santa Ana | 92701 | Orange County | 10. Customer Hold | 29 - Santa Ana | Orange | Saddleback |  |  | 3302771 | 1999936 |  | 2024-03-29 | 51 | NO |  | YES |  |  |  |  | 2021-12-29 | 2021-12-29 |  |  | 1 | 1 | 2022-01-12 | 2022-01-05 | 2022-01-12 | 6 | 6 | 6 | 6 | 2022-05-04 | 89 | 89 | 2022-05-04 | 2022-05-04 | 2022-06-20 | 2023-08-24 | 332 | 332 |  |  |  |  | 2023-10-06 | 2023-09-25 |  |  | 2022-12-01 | -208 |  | 2023-11-06 | 2023-11-22 | 2023-11-06 |  | 31 | 31 |  |  |  |  | 2022-11-16 | 2022-11-29 | 2023-02-28 | -217 |  | 64 | 64 | 71 | 71 | [6 empty] | 2022-11-29 | [7 empty] | 2023-09-14 | 2023-09-14 | 2023-09-29 | 12 | 12
1135 | Yermo, CA - 36017 Calico Rd, Yermo Expansion Eddies World | 36017 Calico Rd | Yermo | 92398 | San Bernardino County | 4. Preliminary Design | 72 - Barstow | Rurals | SBRO |  |  | 3288827 | 1991231 | [5 empty] | YES | 2022-01-24 | 2022-02-03 | 9 | 9 | 2022-01-12 | 2022-01-12 | 16 | 16 | 1 | 1 | 2022-01-13 | 2022-01-19 | 2022-01-24 | 5 | 5 | 4 | 4 | 2022-04-11 | 62 | 62 | 2022-04-12 | 2022-04-15 | 2022-05-27 | 2022-06-24 | 54 | 54 | 2022-06-27
1136 | Long Beach - Wardlow Rd | 1620 Wardlow Rd | Long Beach | 90810 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra |  |  | 3296342 | 2153059 | 2153058 |  |  | YES | Level 3 | YES | 2022-01-13 | 2022-01-27 | 10 | 10 | 2021-12-29 | 2021-12-29 | 21 | 21 | 1 | 1 | 2022-01-03 | 2022-01-05 | 2022-01-13 | 6 | 6 | 7 | 7 | 2023-06-13 | 369 | 369 | 2023-06-13 | 2023-06-16 | 2023-07-31 | 2023-08-03 | 37 | 37 | 2023-08-03
1137 | Long Beach Los Altos Market | 2080 N Bellflower Blvd | Long Beach | 90815 | Los Angeles County | 9. Complete | 46 - Long Beach | Metro West | Alhambra | Hathaway | Atherton 12kv | 3425113 | 2070457 |  | 2023-07-05 | 4 | NO |  | NO | 2022-08-17 | 2022-11-10 | 61 | 61 | 2022-08-17 | 2022-08-17 | 61 | 61 | 1 | 1 | 2022-08-18 | 2022-08-22 | 2022-09-16 | 4 | 4 | 19 | 19 | 2022-10-25 | 49 | 49 | 2022-11-17 | 2022-11-21 | 2023-01-06 | 2022-12-30 | 46 | 46 | 2023-01-30 | 2023-02-03 | 5 | 5 | 2023-03-01 | 2023-03-06 | 21 | 21 | 2023-03-06 | 1 | 1 | 2023-03-07 | 2023-03-29 | 2023-03-07 | 2023-03-07 | 2 | 2 | 22 | 22 | 1 | 1 | 2023-02-15 | 2023-03-14 | 2023-05-09 | -13 |  | 41 | 41 | 59 | 59 | 2023-03-22 | 13 | 13 | 2023-04-03 | 9 | 9 | 2023-03-07 | 2023-03-07 | 2023-05-09 | 2023-05-09 | 46 | 46 | 13 | 13 | [5 empty] | 2023-03-21 | 2023-04-28 |  | 2023-03-29 | 7 | 7 | 2023-05-09 | 8 | 8 |  |  |  | 2023-05-03 | 2023-05-24 | 47 | 47 | 16 | 16 | 2023-05-31 | 2023-07-05 | 25 | 25 | 2023-07-06 | 26 | 26 | 2023-07-06 |  |  |  | 224 | 224 | 176 | 176 | 2023
1138 | Fountain Valley LA Fitness | 10115 Talbert Avenue | Fountain Valley | 92708 | Orange County | 7. Civil Construction | 33 - Huntington Beach | Orange | Saddleback |  |  | 3250291 | 1956810 |  | 2023-06-30 | 4 | NO |  | NO |  |  |  |  | 2022-01-14 | 2022-01-14 |  |  | 1 | 1 | 2022-01-18 | 2022-01-20 | 2022-02-02 | 4 | 4 | 10 | 10 | 2022-01-31 | 11 | 11 | 2022-02-08 | 2022-02-09 | 2022-03-24 | 2022-04-05 | 46 | 46 | 2022-04-05 | 2022-04-07 | 3 | 3 | 2022-04-29 | 2022-04-15 | 7 | 7 | 2022-04-20 | 4 | 4 | 2022-05-03 | 2022-07-05 | 2022-05-03 | 2022-05-03 | 13 | 13 | 19 | 19 | 1 | 1 | 2022-04-28 | 2022-10-10 | 2022-11-01 | 10 | 10 | 17 | 17 | 131 | 131 | 2023-06-22 | 298 | 298 | 2023-06-22 | 1 | 1 | 2022-05-03 | 2022-05-03 | 2022-11-01 | 2023-06-22 | 289 | 289 | 301 | 301 | [5 empty] | 2022-07-13 | [12 empty] | 2023-06-26 | 242 | 242 |  |  | 2023-08-01 | 2023-09-18 | 34 | 34 | 2023-09-19 | 35 | 35 | 2023-09-19 |  |  |  | 425 | 425 | 415 | 415 | 2023
1139 | LA Fitness Lake Elsinore | 18550 Dexter Ave | Lake Elsinore | 92532 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3251667 | 1971019 |  | 2024-05-01 | 4 | NO |  | YES |  |  |  |  | 2022-01-14 | 2022-01-14 |  |  | 1 | 1 | 2022-01-18 | 2022-01-19 | 2022-01-21 | 3 | 3 | 3 | 3 |  |  |  | 2022-02-10 | 2022-02-17 | 2022-04-01 | 2022-04-06 |  |  | 2022-04-07 | 2022-04-07 | 1 | 1 | 2022-04-29 | 2022-05-03 | 19 | 19 | 2022-05-06 | 4 | 4 | 2022-05-10 | 2022-06-15 | 2022-05-10 | 2022-05-11 | 6 | 6 | 25 | 25 | 2 | 2 | 2022-04-18 | 2022-05-31 | 2024-03-19 | -12 |  | 455 | 455 | 485 | 485 | [6 empty] | 2022-05-10 |  | 2024-03-19 | [5 empty] | 2022-08-22 |  | 2022-09-12 | 15 | 15 | 2022-07-08 |  |  | 2022-08-02 | 18 | 18
1140 | Newport Beach, CA - 4241 MacArthur Blvd | 4241 (EM) MacArthur Blvd | Newport Beach | 92660 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3329698 | 2010456 |  |  | 16 | NO |  | YES | 2022-01-31 | 2022-02-14 | 11 | 11 | 2022-01-18 | 2022-01-18 | 20 | 20 | 1 | 1 | 2022-01-19 | 2022-01-28 | 2022-02-07 | 9 | 9 | 7 | 7 |  |  |  | 2022-06-17 | 2022-06-17 | 2022-08-01 | 2022-07-13 |  |  | 2022-07-13 |  |  |  |  | 2023-01-09 |  |  | 2023-01-10 | 2 | 2 | 2023-02-06 | 2023-02-16 | 2023-02-06 | 2023-02-07 | 20 | 20 |  |  | 2 | 2 | 2023-01-18 | 2023-01-26 | 2023-03-03 | 7 | 7 | 26 | 26 | 32 | 32 | [6 empty] | 2023-01-26 |  | 2023-03-03 | [5 empty] | 2023-03-17 | 2023-04-11 | 2023-04-11 | 18 | 18 | [13 empty] | 2023-04-17 |  |  |  |  | 2023-04-27 |  |  |  | 2023-06-20 | 38 | 38 | 2023-06-20 |  |  |  | 361 | 361 |  |  | 2023
1141 | Baker, CA - 56383 Mojave Pointe Rd R2 eng calls it Wholesale fireworks need BAKER sub upgrades in 2024 Do NOT ENERGIZE UNTIL BAKER SUB UPGRADES COMPLETE CLEAR WITH RYAN | 56385 Mojave Pointe Rd | Baker | 92309 | San Bernardino County | 4. Preliminary Design | 72 - Barstow | Rurals | SBRO |  |  | 3332444 | 2026970 |  | 2024-09-06 | 40 | YES | Level 3 | YES | 2022-01-25 | 2022-02-03 | 8 | 8 | 2022-01-18 | 2022-01-18 | 13 | 13 | 1 | 1 |  |  | 2022-01-24 | [35 empty] | 2023-01-30 | 2023-02-14 |  |  | 12 | 12
1142 | El Segundo, CA - 150 S Sepulveda Blvd | 150 Pacific Coast Hwy EV1 | El Segundo | 90245 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3512918 |  |  | 2024-09-01 |  | NO |  | YES | 2022-01-27 | 2022-02-02 | 5 | 5 | 2022-01-19 | 2022-01-19 | 11 | 11 | 1 | 1 | 2022-01-20 | 2022-01-27 | 2022-02-01 | 7 | 7 | 4 | 4 |  |  |  | 2023-04-13 | 2023-04-17 | 2023-05-30 | 2023-05-23 |  |  | 2023-05-24
1143 | Irvine, CA - 4790 Irvine Blvd (Northwood Town Center) | 4790 Irvine Blvd #105-114 | Irvine | 92620 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3311858 | 2009068 | [5 empty] | YES | 2022-01-31 | 2022-02-02 | 3 | 3 | 2022-01-20 | 2022-01-20 | 10 | 10 | 1 | 1 | 2022-01-21 | 2022-01-28 | 2022-01-28 | 7 | 7 | 1 | 1 | 2022-05-18 | 84 | 84 | 2022-05-19 | 2022-05-19 | 2022-07-06 | 2022-08-22 | 67 | 67 | 2022-08-22
1144 | Fontana, CA - S Highland Ave | 16173 S Highland Ave | Fontana | 92336 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [9 empty] | YES | 2022-02-23 | 2022-03-09 | 11 | 11 | 2022-01-21 | 2022-01-21 | 33 | 33 | 1 | 1 | 2022-01-24 | 2022-01-26 | 2022-02-24 | 4 | 4 | 21 | 21
1145 | Westlake Village, CA - 1125 Lindero Canyon Rd | 1145 EV Lindero Canyon Rd | Westlake Village | 91362 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-09-01 |  | YES |  | YES | [12 empty] | 2023-10-14
1146 | Chino Hills, CA - 2959 Chino Ave | 2959 Chino Ave, Chino Hills, CA 91709 | Chino Hills | 91709 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2022-02-08 | 2022-02-11 | 4 | 4 | 2022-01-24 | 2022-01-24 | 15 | 15 | 1 | 1 | 2022-01-26 | 2022-02-07 | 2022-02-07 | 11 | 11 | 1 | 1
1147 | Hawthorne, CA - 14398 Ocean Gate Ave | 14398 Ocean Gate Ave | Hawthorne | 90250 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2022-02-09 | 2022-02-11 | 3 | 3 | 2022-01-25 | 2022-01-25 | 14 | 14 | 1 | 1 | 2022-01-26 | 2022-02-03 | 2022-02-18 | 8 | 8 | 12 | 12
1148 | South Gate, CA- 5820 Firestone Blvd | 5824 Firestone Blvd EVC | South Gate | 90280 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra |  | Donald 12kV | 3445669 | 2092628 |  | 2024-04-26 | 12 | NO |  | YES | 2022-04-19 | 2022-04-27 | 7 | 7 | 2022-01-25 | 2022-01-25 | 66 | 66 | 1 | 1 | 2022-01-26 | 2022-04-15 | 2022-04-15 | 58 | 58 | 1 | 1 | 2022-12-14 | 225 | 225 | 2022-12-28 | 2022-12-29 | 2023-02-15 | 2023-02-15 | 45 | 45 | 2023-02-15 |  |  |  | 2023-08-14 | 2023-08-29 |  |  | 2023-08-29 | 1 | 1 | 2023-09-06 | 2023-10-05 | 2023-09-06 |  | 6 | 6 |  |  |  |  | 2024-02-13 | 2023-09-19 |  | 115 | 115 |  |  |  |  | 2023-08-09 | -15 |  | 2024-02-20 | 133 | 133 | 2023-09-06 | 2023-08-09 |  |  |  |  | -15
1149 | Torrance, CA - 2965 Rolling Hills Rd. (Formerly 2095 Rolling Hills Rd) R1 | 2965 Rolling Hills Rd EV | Torrance | 90505 | Los Angeles County | 7. Civil Construction | 44 - South Bay | Metro West | Alhambra |  |  | 3507186 | 2115175 |  | 2024-09-22 |  | NO |  | YES | 2022-02-09 | 2022-02-11 | 3 | 3 | 2023-03-11 | 2022-01-25 | 14 | 14 | -285 |  | 2022-01-26 | 2022-02-04 | 2022-02-18 | 9 | 9 | 11 | 11 | 2023-12-20 | 198 | 198 | 2023-11-16 | 2023-12-21
1150 | Hawaiian Gardens, CA - 12090 E Carson St | 12090 E Carson St UNIT E | Hawaiian Gardens | 90716 | Los Angeles County | 4. Preliminary Design | 46 - Long Beach | Metro West | Alhambra |  |  | 3480397 | 2137147 | 2180013 | 2024-05-01 | 12 | YES | Level 3 | NO | 2022-02-09 | 2022-02-17 | 7 | 7 | 2023-03-15 | 2022-01-25 | 18 | 18 | -288 |  | 2022-01-26 | 2022-02-04 | 2022-02-18 | 9 | 9 | 11 | 11 | 2023-03-15 | 1 | 1 | 2023-03-16 | 2023-03-17 | 2023-04-28 | 2023-06-01 | 56 | 56 | 2023-06-14 | 2023-06-20 | 5 | 5 | 2023-07-21 | 2023-08-13 | 38 | 38 | 2023-08-13 | 0 |  | 2023-12-21 | 2024-01-23 | 2024-01-05 | 2024-01-08 | 100 | 100 | 139 | 139 | 2 | 2 | 2023-09-29 | 2023-10-16 | 2023-11-09 | 34 | 34 | 19 | 19 | 30 | 30 | 2023-12-21 | 91 | 91 |  |  |  | 2023-10-16 | 2023-10-16 | 2024-01-08 |  |  |  | 91 | 91 | [5 empty] | 2023-12-05 |  |  | 2024-01-11 | 26 | 26
1151 | Buena Park - 7-Eleven #42062 | 8650 Beach Blvd | Buena Park | 90620 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback |  |  | 3444132 |  |  |  | 4 | YES | Level 3 | NO |  |  |  |  | 2022-01-26 | 2022-01-26 |  |  | 1 | 1 | 2022-02-01 | 2022-02-02 | 2022-02-09 | 6 | 6 | 6 | 6 | 2022-02-16 | 16 | 16 | 2022-02-17 | 2022-10-19 | 2022-04-04 | 2022-12-22 | 215 | 215 | 2023-04-18
1152 | Lynwood - 7-Eleven #38355 | 2800 E Imperial Hwy | Lynwood | 90262 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 3255050 | 1977113 | [5 empty] | YES |  |  |  |  | 2022-01-26 | 2022-01-26 |  |  | 1 | 1 | 2022-02-01 | 2022-02-02 | 2022-02-04 | 6 | 6 | 3 | 3 |  |  |  | 2022-02-16 | 2022-02-22 | 2022-04-01 | 2022-04-06 |  |  | 2022-04-06
1153 | Barstow, CA-2796 Tanger Way - Phase 2 | 2796 Tanger Way | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO |  |  | 3245015 | 1962220 |  |  | 50 | NO |  | NO |  |  |  |  | 2022-01-28 | [15 empty] | 2022-01-28 | 2022-01-31 | 2022-05-05 | 2022-05-24 |  |  | 2022-05-24 | 2022-06-01 | 6 | 6 | 2022-06-22 | 2022-07-11 | 28 | 28 | 2022-07-11 | 1 | 1 | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-24 | 26 | 26 | 60 | 60 | 8 | 8 |  | 2022-07-26 | 2022-08-25 |  |  | 23 | 23 | [8 empty] | 2022-07-26 |  | 2022-08-25 | [5 empty] | 2023-09-26 |  | 2023-10-06 | 9 | 9 | [13 empty] | 2023-02-28 |  |  |  |  | 2023-10-10 | [6 empty] | 2023-11-20 | 2023-11-22 | 3 | 3 | 460 | 460 |  |  | 2023
1154 | Parking Garage | 8632 Garfield Ave | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3293090 | 1989944 |  | 2024-06-30 |  | NO |  | NO |  |  |  |  | 2022-01-28 | 2022-01-28 |  |  | 1 | 1 | 2022-01-28 | 2022-04-15 | 2022-04-15 | 55 | 55 | 1 | 1 | 2022-03-24 | 39 | 39 | 2022-04-19 | 2022-04-20 | 2022-06-03 | 2022-08-04 | 94 | 94 | 2022-08-04 |  |  |  |  | 2022-08-19 |  |  | 2022-08-24 | 4 | 4 | 2022-08-24 | 2022-11-16 | 2022-08-24 | 2022-09-14 | 4 | 4 |  |  | 15 | 15 | 2022-11-15 | 2022-12-05 | 2023-01-04 | 61 | 61 | 23 | 23 | 35 | 35 | [6 empty] | 2022-08-24 |  | 2023-01-04 | [10 empty] | 2022-09-22
1155 | Hooters Restaurant | 8730 Garfield Ave | South Gate | 90280 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3275910 | 1989152 |  | 2024-06-30 |  | NO |  | NO |  |  |  |  | 2022-01-28 | 2022-01-31 |  |  | 2 | 2 | 2022-02-03 | 2022-02-08 | 2022-02-28 | 7 | 7 | 14 | 14 | 2022-03-16 | 33 | 33 | 2022-03-23 |  | 2022-05-18 | 2022-05-18 | 46 | 46 | 2022-05-18 | 2022-05-19 | 2 | 2 | 2022-06-13 | [6 empty] | 2022-07-15 | 2022-07-28 | 2022-07-15 | 2022-11-13 |  |  | 123 | 123 | 84 | 84 | 2022-08-22 | 2022-11-29 | 2023-02-08 |  |  | 51 | 51 | 118 | 118 | [6 empty] | 2022-07-15 |  | 2023-02-08
1156 | City of Industry - Valley Blvd | 15930 Valley Blvd | City of Industry | 91744 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 1 | 1 | 2022-02-03 |  | 2022-02-07
1157 | Los Alamitos Chase Bank | 3502 Katella Ave | Los Alamitos | 90720 | Orange County | 11. Cancelled | 46 - Long Beach | Orange | Alhambra |  |  | 3268621 | 1982915 |  |  | 4 | NO |  | YES | 2022-02-09 | 2022-02-17 | 7 | 7 | 2022-01-31 | 2022-01-31 | 14 | 14 | 1 | 1 | 2022-02-03 | 2022-02-08 | 2022-02-09 | 7 | 7 | 2 | 2 | 2022-03-10 | 28 | 28 | 2022-03-11 |  | 2022-04-26 | 2022-04-26 | 34 | 34 | 2022-04-26 | 2022-05-23 | 20 | 20 | 2022-06-16 | 2022-06-02 | 8 | 8 | 2022-11-22 | 121 | 121 | 2022-11-22 | 2022-11-16 | 2022-11-22 | 2022-07-24 | 121 | 121 | 43 | 43 | -85 |  | 2022-11-28 | 2022-12-07 | 2023-01-05 | 123 | 123 | 22 | 22 | 29 | 29 | 2022-12-14 | 15 | 15 | 2023-01-23 | 28 | 28 | 2022-11-22 | 2022-11-22 | 2023-01-05 | 2023-01-23 | 42 | 42 | 135 | 135 | 2022-12-05 | 2022-12-12 | 2022-12-12 | 6 | 6 | 2022-08-18 |  |  | 2022-09-30 | 31 | 31 | [7 empty] | 2022-12-19 | 84 | 84 |  |  | 2022-12-27 | 2023-02-02 | 27 | 27 | 2023-02-03 | 28 | 28 | 2023-02-03 |  |  |  | 257 | 257 | 230 | 230 | 2023
1158 | Fontana Winco 33 | 14338 Foothill Blvd | Fontana | 92335 | San Bernardino County | 9. Complete | 30 - Foothill | Desert | SBRO |  |  | 3423658 |  |  |  |  | NO |  | NO | 2022-11-09 | 2022-11-14 | 3 | 3 | 2022-01-31 | 2022-02-01 | 200 | 200 | 2 | 2 | 2022-02-03 | 2022-02-17 | 2022-03-07 | 13 | 13 | 12 | 12 | 2022-07-29 | 127 | 127 | 2022-11-15 | 2022-11-17 | 2023-01-04 | 2023-01-31 | 128 | 128 | 2023-01-31 | 2023-02-03 | 4 | 4 | 2023-03-01 | 2023-03-06 | 21 | 21 | 2023-03-06 | 1 | 1
1159 | Murrieta LA Fitness | 40985 California Oaks Rd | Murrieta | 92562 | Riverside County | 9. Complete | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3344835 | 2023029 |  | 2023-09-01 | 5 | NO |  | NO |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 1 | 1 | 2022-08-26 | 2022-02-09 | 2022-02-09 | 8 | 8 | 1 | 1 | 2022-01-31 | 1 | 1 | 2022-07-13 | 2022-07-14 | 2022-08-24 | 2022-08-26 | 147 | 147 | 2022-08-29 | 2022-08-31 | 3 | 3 | 2022-09-23 | 2022-10-10 | 28 | 28 | 2022-10-12 | 3 | 3 | 2022-10-12 | 2023-09-18 | 2022-10-12 | 2022-11-13 | 3 | 3 | 51 | 51 | 22 | 22 |  | 2022-10-16 | 2022-12-21 |  |  | 45 | 45 | [8 empty] | 2022-10-12 |  | 2022-12-21 | [5 empty] | 2023-03-12 |  |  |  |  | 2023-01-31 |  |  | 2023-02-08 | 7 | 7 | [6 empty] | 2023-07-10 | 2023-07-21 | 121 | 121 | 10 | 10 | 2023-08-01 | 2023-09-21 | 37 | 37 | 2023-09-22 | 38 | 38 | 2023-09-22 |  |  |  | 418 | 418 | 418 | 418 | 2023
1160 | Irvine LA Fitness | 2880 Michelle Dr EV | Irvine | 92606 | Orange County | 6. Requirements (permit, easment, etc.) | 43 - Saddleback | Orange | Saddleback |  |  | 3296544 | 1996590 |  |  | 4 | NO |  | NO |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 1 | 1 | 2022-02-03 | 2022-02-08 | 2022-02-28 | 7 | 7 | 14 | 14 | 2022-01-31 | 1 | 1 | 2022-04-25 | 2022-04-26 | 2022-06-09 | [8 empty] | 2022-07-25 |  |  | 2022-08-02 | 7 | 7 | 2022-08-02 | 2023-03-09 | 2022-08-02 | 2022-08-31 | 7 | 7 |  |  | 22 | 22 | 2022-07-15 | 2022-07-29 | 2023-01-31 | -7 |  | 128 | 128 | 138 | 138 | [6 empty] | 2022-07-29 |  | 2023-01-31 | [5 empty] | 2023-09-05 | 2023-09-11 | 2023-09-18 | 10 | 10 | 2022-07-15 |  |  | 2022-07-27 | 9 | 9 | [7 empty] | 2023-10-04 | 310 | 310 |  |  | 2023-10-09 | 2023-10-24 | 12 | 12 | 2023-10-24 | 12 | 12 | 2023-10-24 |  |  |  | 440 | 440 | 440 | 440 | 2023
1161 | Diamond Bar LA Fitness | 20801 Golden Springs Dr | Diamond Bar | 91789 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona |  |  | 3302862 | 2013820 |  | 2024-06-28 |  | NO |  | NO |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 1 | 1 | 2022-02-03 | 2022-02-07 | 2022-02-07 | 6 | 6 | 1 | 1 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-08-16 | 2022-08-16 |  |  | 2022-08-17 | 2022-10-18 | 44 | 44 | 2022-11-14 | 2022-11-16 | 21 | 21 | 2022-11-21 | 4 | 4 | 2022-11-21 | 2022-11-21 | 2022-11-21 |  | 4 | 4 |  |  |  |  | 2022-11-09 | 2022-12-12 |  | -5 | [11 empty] | 2022-11-21
1162 | Santa Clarita LA Fitness | 26455 Golden Valley Rd | Santa Clarita | 91350 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 3302920 | 2013912 |  | 2024-09-30 |  | NO |  | YES |  |  |  |  | 2022-01-31 | 2022-01-31 |  |  | 1 | 1 | 2022-02-03 | 2022-02-04 | 2022-02-09 | 5 | 5 | 4 | 4 |  |  |  | 2022-05-04 | 2022-05-04 | 2022-06-20 | 2022-08-08 |  |  | 2022-08-08 | 2022-09-22 | 33 | 33 | 2022-10-14 | 2022-10-18 | 19 | 19 | 2022-10-21 | 4 | 4 | 2022-10-21 |  | 2022-10-21 | 2022-10-25 | 4 | 4 | 24 | 24 | 3 | 3 | 2022-10-17 | 2022-10-28 |  | -2 | [11 empty] | 2022-10-21
1163 | Long Beach, CA – 65 S Cedar Ave | 65 S Cedar Ave | Long Beach | 90802 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2022-03-01 | 2022-03-15 | 11 | 11 | 2022-01-31 | 2022-01-31 | 31 | 31 | 1 | 1 | 2022-02-03 | 2022-02-10 | 2022-03-03 | 9 | 9 | 15 | 15
1164 | Hanford, CA - 140 12th Ave | 140 12th Ave | Hanford | 93230 | Kings County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura | [9 empty] | YES | 2022-02-15 | 2022-02-18 | 4 | 4 | 2022-02-01 | 2022-02-01 | 14 | 14 | 1 | 1 | 2022-02-03 | 2022-02-08 | 2022-02-10 | 6 | 6 | 3 | 3
1165 | West Covina, CA - 2370 S Azusa Ave | 2370 S Azusa Ave | West Covina | 91792 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | YES | 2022-02-28 | 2022-03-09 | 8 | 8 | 2022-02-01 | 2022-02-01 | 26 | 26 | 1 | 1 | 2022-02-03 | 2022-02-10 | 2022-03-02 | 8 | 8 | 14 | 14
1166 | Redondo Beach, CA - Kingsdale Ave | 1815 Hawthorne Blvd | Redondo Beach | 90278 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-02-04 | 2022-02-04 |  |  | 1 | 1 | 2023-05-04 | 2023-05-04 | 2022-02-10 | 316 | 316 | -312
1167 | Tustin, CA - 14661 Franklin Ave | 14661.5 Franklin Ave (14659 Franklin) | Tustin | 92780 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback |  |  | 3312603 | 2017020 |  |  | 36 | NO |  | YES | 2022-03-11 | 2022-03-11 | 1 | 1 | 2022-02-08 | 2022-02-08 | 23 | 23 | 1 | 1 | 2022-02-11 | 2022-02-24 | 2022-03-31 | 12 | 12 | 26 | 26 | 2022-05-19 | 72 | 72 | 2022-05-20 | 2022-05-23 | 2022-07-07 | 2022-08-29 | 71 | 71 | 2022-08-29 | 2022-11-02 | 47 | 47 |  | 2022-12-08 | 24 | 24 | 2022-12-08 | 1 | 1 | 2022-12-08 | 2022-12-08 | 2022-12-08 | 2022-12-13 | 1 | 1 | 27 | 27 | 4 | 4 | 2022-11-17 | 2022-12-08 | 2022-12-27 | -14 |  | 14 | 14 | 27 | 27 | 2023-03-17 | 70 | 70 | 2023-04-18 | 23 | 23 | 2022-12-08 | 2022-12-08 | 2022-12-27 | 2023-04-18 | 92 | 92 | 70 | 70 | 2023-04-20 | 2023-05-10 | 2023-05-10 | 15 | 15 | [13 empty] | 2023-05-19 |  |  |  |  | 2023-04-18 |  |  |  | 2023-05-25 | 28 | 28 | 2023-05-25 |  |  |  | 329 | 329 | 258 | 258 | 2023
1168 | Redondo Beach, CA - Kingsdale Ave | 1824 Kingsdale Ave #EV1 | Redondo Beach | 90278 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [7 empty] | NO |  | NO | 2022-02-15 | 2022-02-28 | 9 | 9 | 2022-02-03 | 2022-02-03 | 17 | 17 | 1 | 1 |  |  | 2022-02-10
1169 | Santa Ana - 7 Eleven Store #38384 | 813 N Euclid St | Santa Ana | 92703 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback |  |  | 3263434 | 2056934 |  |  |  | NO |  | NO |  |  |  |  | 2022-02-10 | 2022-02-10 |  |  | 1 | 1 | 2022-02-11 | 2022-02-21 | 2022-02-25 | 7 | 7 | 4 | 4 |  |  |  | 2022-03-03 | 2022-03-04 | 2022-04-18 | 2022-06-20 |  |  | 2022-06-20 | 2022-06-22 | 3 | 3 | 2022-07-13 | 2022-08-04 | 31 | 31 | 2022-08-05 | 2 | 2
1170 | Tustin - 7 Eleven Store #13799 | 16791 McFadden Ave | Tustin | 92705 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback |  |  | 3263520 | 2014165 |  |  |  | NO |  | YES |  |  |  |  | 2022-02-10 | 2022-02-10 |  |  | 1 | 1 | 2022-02-11 | 2022-02-21 | 2022-02-25 | 7 | 7 | 4 | 4 | 2022-03-03 | 15 | 15 | 2022-03-03 | 2022-03-04 | 2022-04-18 | 2022-07-15 | 95 | 95 | 2022-07-18
1171 | Chino - 12423 Central Ave | 5394 Walnut Ave. | Chino | 91710 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3317885 | 2174026 | 2010554 | 2024-08-23 | 24 | YES | Level 3 | NO | 2022-03-11 | 2022-03-18 | 6 | 6 | 2022-02-14 | 2022-02-14 | 24 | 24 | 1 | 1 | 2022-02-15 | 2022-04-01 | 2022-04-01 | 34 | 34 | 1 | 1 | 2022-05-25 | 72 | 72 | 2023-07-12 | 2023-07-12 | 2023-08-23 | 2023-09-05 | 324 | 324 | 2023-09-06
1172 | Santa Barbara - Turnpike Rd | 191 S Turnpike Rd 191 S Turnpike Rd | Santa Barbara | 93111 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2022-02-15 | 2022-02-15 |  |  | 1 | 1 | 2022-02-15
1173 | Santa Clarita, CA - Golden Valley Rd | 19105 Golden Valley Rd | Santa Clarita | 91387 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2022-02-15 | 2022-03-01 | 10 | 10 | 2022-02-15 | 2022-02-15 | 10 | 10 | 1 | 1 |  |  | 2022-02-11
1174 | Carson CA - 20220 S Avalon Blvd | 20220 S Avalon Blvd | Carson | 90746 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | YES | 2022-03-09 | 2022-03-10 | 2 | 2 | 2022-02-15 | 2022-02-15 | 17 | 17 | 1 | 1 | 2022-02-18 |  | 2022-03-17
1175 | West Hollywood, CA - 9039 Beverly Blvd | 9039 Beverly Blvd | West Hollywood | 90048 | Los Angeles County | 7. Civil Construction | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2022-03-11 |  |  |  | 2022-02-15 | 2022-02-15 |  |  | 1 | 1 | 2022-02-18 | 2022-03-01 | 2022-04-01 | 10 | 10 | 24 | 24
1176 | Carson, CA - 801 E Carson St | 875U E Carson St | Carson | 90745 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 32 - Compton | Metro West | Alhambra |  |  | 3467945 | 2120398 |  | 2024-11-25 | 20 | YES | Level 2 | YES | 2023-01-20 | 2023-02-06 | 12 | 12 | 2023-03-21 | 2022-02-15 | 247 | 247 | -277 |  | 2022-02-18 | 2022-02-22 | 2022-03-17 | 5 | 5 | 18 | 18 | 2023-01-20 | -42 |  | 2023-03-23 | 2023-03-23 | 2023-05-08 | 2023-04-25 | 67 | 67 | 2023-04-25 | 2023-06-28 | 46 | 46 | 2023-07-20 | 2023-10-16 | 77 | 77 | 2023-10-16 | 1 | 1 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 1 | 1 | 77 | 77 | 1 | 1 | 2023-12-05 | 2023-12-19 | 2024-01-26 | 35 | 35 | 26 | 26 | 36 | 36 | 2023-10-19 | 4 | 4 | 2023-11-21 | 24 | 24 | 2023-10-16 | 2023-10-16 | 2024-01-26 | 2024-01-26 | 70 | 70 | 4 | 4 | 2024-03-19 |  |  |  |  | 2024-02-28
1177 | Camarillo, CA - 1775 E Daily Drive | 1881 E Daily Drive 1/2 | Camarillo | 93010 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  | redstone 16kv | 3445706 | 2214009 | 2214011 | 2024-06-21 | 24 | YES |  | YES | 2022-03-21 | 2022-04-07 | 14 | 14 | 2022-02-16 | 2022-02-16 | 36 | 36 | 1 | 1 | 2022-02-18 | 2022-03-03 | 2022-03-07 | 11 | 11 | 3 | 3 |  |  |  | 2022-12-28 | 2022-12-28 | 2023-05-17 | 2023-10-06 |  |  | 2023-10-06 | 2023-11-15 | 29 | 29 | 2023-12-08 | 2024-01-29 | 49 | 49 | 2024-03-11 | 30 | 30 | 2024-03-11 |  | 2024-03-11 |  | 30 | 30 |  |  |  |  | 2024-01-02 | 2024-01-11 |  | -19 | [5 empty] | 2024-02-01 | -27 |  | 2024-03-06 | 24 | 24 | 2024-01-11 | 2024-01-11 |  |  |  |  | 4 | 4
1178 | Moorpark, CA - Collins Dr | 6591 Collins Dr | Moorpark | 93021 | Ventura County | 4. Preliminary Design | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-05-01 |  | YES |  | YES | 2023-04-07 | 2023-07-12 | 67 | 67 | 2023-04-17 | 2023-04-17 | 61 | 61 | 1 | 1 | 2023-04-17 |  | 2023-06-05
1179 | Santa Paula, CA - W Main St | 542 W Main St | Santa Paula | 93060 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3538557 |  |  | 2024-08-07 |  | YES | Level 3 | YES | 2022-02-28 | 2023-05-23 | 314 | 314 | 2022-02-16 | 2022-02-16 | 321 | 321 | 1 | 1 | 2022-02-18 | 2022-02-25 | 2022-02-26 | 7 | 7 | 1 | 1 |  |  |  | 2023-05-24 | 2023-05-25 | 2023-07-12 | 2023-08-16 |  |  | 2023-08-16
1180 | Westlake Village, CA - 3845 E Thousand Oaks Blvd | 3835 E Thousand Oaks Blvd (EV1) | Thousand Oaks | 91362 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-08-23 | 5 | YES |  | YES | 2022-03-09 | 2022-03-10 | 2 | 2 | 2023-06-29 | 2023-08-21 | -368 |  | 37 | 37 | 2023-08-21 | 2023-08-22 |  | 2 | 2
1181 | Redondo Beach, CA - 2700 Marine Ave | 2700 Marine Avenue | Redondo Beach | 90278 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2022-03-09 | 2022-03-14 | 4 | 4 | 2022-02-16 | 2022-02-16 | 18 | 18 | 1 | 1 | 2022-02-18 | 2022-03-03 | 2022-03-04 | 11 | 11 | 2 | 2
1182 | Barstow, CA - 1308 E Main St | 1308 E Main St | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [9 empty] | NO | 2022-02-18 | 2022-03-01 | 7 | 7 | 2022-02-18 | 2022-02-07 | 16 | 16 | -10 |  | 2022-02-07 | 2022-02-15 | 2022-02-18 | 7 | 7 | 4 | 4
1183 | San Jacinto - 7-Eleven | Ramona Expressway and Main St | San Jacinto | 92583 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES |  |  |  |  | 2022-02-22 | 2022-02-22 |  |  | 1 | 1 | 2022-02-22
1184 | Tustin, CA - 518 E First St | 518 E 1st St | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES | 2022-03-11 | 2022-03-23 | 9 | 9 | 2022-02-22 | 2022-02-22 | 22 | 22 | 1 | 1 | 2022-02-24 | 2022-03-08 | 2022-03-11 | 11 | 11 | 4 | 4
1185 | Tustin, CA - 1098.5 Irvine Blvd | 1098.5 Irvine Blvd | Tustin | 92780 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3329651 | 2010501 |  |  |  | NO |  | YES | 2022-03-11 | 2022-03-11 | 1 | 1 | 2022-02-22 | 2022-02-22 | 14 | 14 | 1 | 1 | 2022-02-24 | 2022-03-08 | 2022-03-11 | 11 | 11 | 4 | 4 | [5 empty] | 2022-09-09 | 2022-12-20 |  |  | 2022-12-20 | 2023-04-11 | 79 | 79 | 2023-05-02 | 2023-04-24 | 10 | 10 | 2023-05-04 | 9 | 9 | 2023-05-10 |  | 2023-05-10 |  | 13 | 13 |  |  |  |  | 2023-04-21 | 2023-07-31 |  | -2 | [11 empty] | 2023-05-10
1186 | Gardena - Maple Ave | 14701 Maple Ave | Gardena | 90248 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2022-03-11 | 2022-03-18 | 6 | 6 | 2022-02-23 | 2022-02-25 | 16 | 16 | 3 | 3 | 2022-02-28 | 2022-04-11 | 2022-04-11 | 32 | 32 | 1 | 1
1187 | Bishop, CA - Rocking W Dr | 1390 N Barlow Lane | Bishop | 93514 | Inyo County | 9. Complete | 85 - Bishop/Mammoth | Rurals | Ventura |  |  | 3329861 | 2009901 |  |  | 24 | NO |  | YES | 2022-02-28 | 2022-03-15 | 12 | 12 | 2022-02-11 | 2022-02-11 | 22 | 22 | 1 | 1 |  |  | 2022-02-26 | [7 empty] | 2022-06-17 | 2022-06-20 |  | 2022-09-13 |  |  | 2022-09-13 | 2022-09-15 | 3 | 3 | 2022-10-06 | 2023-01-14 | 84 | 84 | 2023-03-01 | 31 | 31 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-07-11 | 117 | 117 | 207 | 207 | 7 | 7 | 2023-01-16 | 2023-01-26 | 2023-02-21 | 0 |  | 18 | 18 | 25 | 25 | 2022-11-07 | -78 |  | 2023-05-22 | 136 | 136 | 2023-01-26 | 2022-11-07 | 2023-07-11 | 2023-07-11 | 170 | 170 | -47 |  | 2023-03-29 | 2023-04-18 | 2023-06-22 | 61 | 61 | 2023-04-05 |  |  | 2023-04-05 | 1 | 1 |  |  |  | 2023-06-29 |  |  |  | 2023-05-25 | 37 | 37 |  |  | 2023-07-11 |  |  |  | 2023-09-08 | 43 | 43 | 2023-09-08 |  |  |  | 399 | 399 |  |  | 2023
1188 | Inglewood - Aviation Blvd. | 9150 S Aviation Blvd EV1 | Inglewood | 90301 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra |  |  | 3427478 | 2080988 | 2080986 | 2024-01-19 | 8 | YES | Level 2 | YES | 2022-10-10 | 2022-10-13 | 4 | 4 | 2022-10-10 | 2022-02-28 | 161 | 161 | -158 |  | 2022-03-01 | 2022-03-03 | 2022-04-05 | 4 | 4 | 24 | 24 | 2022-11-18 | 29 | 29 | 2022-11-22 |  | 2023-01-19 | 2023-01-26 | 47 | 47 | 2023-04-12 | 2023-06-05 | 38 | 38 | 2023-09-14 | 2023-09-26 | 80 | 80 | 2023-09-26 | 1 | 1 | 2023-09-26 | 2024-01-25 | 2023-09-26 | 2023-09-27 | 1 | 1 | 81 | 81 | 2 | 2 | 2023-06-27 | 2023-07-25 | 2023-08-29 | -64 |  | 26 | 26 | 45 | 45 | 2023-10-17 | 16 | 16 | 2023-10-30 | 10 | 10 | 2023-07-25 | 2023-07-25 | 2023-09-27 | 2023-10-30 | 69 | 69 | 16 | 16 | 2023-11-01 | 2023-12-26 | 2024-01-10 | 47 | 47 | 2023-12-12 |  |  | 2023-12-12 | 1 | 1 | [6 empty] | 2024-01-05 | 2024-01-10 | 20 | 20 | 4 | 4 | 2024-01-11 | 2024-02-16 | 26 | 26 | 2024-02-17 | 26 | 26 | 2024-02-17 | 2024-02-28 | 7 | 7 | 342 | 342 | 314 | 314 | 2024
1189 | Laguna Beach, CA - 600 N PCH | 600 N Pacific Coast Hwy | Laguna Beach | 92651 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-06-20 | 4 | YES | Level 3 | NO | 2023-05-01 | 2023-06-12 | 30 | 30 | 2022-03-01 | 2024-02-02 | -163 |  | 488 | 488 | 2024-02-02 | 2024-02-07 | 2024-02-12 | 4 | 4 | 4 | 4
1190 | Santa Barbara - Anacapa St | 621 Anacapa St | Santa Barbara | 93101 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3262588 | 1970454 |  |  |  | NO |  | YES |  |  |  |  | 2022-03-01 | 2022-03-01 |  |  | 1 | 1 | [10 empty] | 2022-03-02 | 2022-03-15 | 2022-04-15 | 2022-04-30 |  |  | 2022-05-03 | 2022-05-03 | 1 | 1 | 2022-05-24 | 2022-05-31 | 20 | 20 | 2022-05-31 | 1 | 1 | 2022-05-31 | 2022-07-13 | 2022-05-31 |  | 1 | 1 | [32 empty] | 2023-08-07 |  |  | 2023-08-21 | 11 | 11 | [6 empty] | 2022-10-05 | 2023-09-25 | 35 | 35 | 246 | 246 | 2023-10-03 | 2023-12-04 | 43 | 43 | 2023-12-04 | 43 | 43 | 2023-12-04 |  |  |  | 447 | 447 |  |  | 2023
1191 | Santa Barbara, CA- 630 Garden Street | 630 Garden Street | Santa Barbara, | 93101 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [6 empty] | 10 |  | Level 3 | YES | 2022-03-02 |  |  |  | 2022-01-21 | [7 empty] | 2022-02-23
1192 | Santa Barbara, CA- 600 Garden St | 600 Garden Street | Santa Barbara | 93101 | Ventura County | 9. Complete | 49 - Santa Barbara | North Coast | Ventura | [6 empty] | 12 |  | Level 3 | YES | 2022-03-02 |  |  |  | 2022-02-02 | [7 empty] | 2022-02-23
1193 | Menifee, 27701 Scott Rd #202 CA - Scott Rd | 33070 Zeiders Rd, Menifee | Menifee | 92584 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3377941 | 2067752 |  | 2023-12-31 | 16 | NO |  | YES | 2022-03-25 | 2022-04-13 | 14 | 14 | 2022-03-02 | 2022-03-02 | 31 | 31 | 1 | 1 | 2022-03-02 | 2022-03-24 | 2022-03-25 | 17 | 17 | 2 | 2 | 2022-08-31 | 129 | 129 | 2022-09-02 | 2022-10-07 |  | 2022-12-15 | 73 | 73 | 2022-12-15 | 2023-02-07 | 38 | 38 | 2023-03-01 | 2023-05-05 | 63 | 63 | 2023-05-05 | 1 | 1 | 2023-05-10 | 2023-05-10 | 2023-05-10 | 2023-06-26 | 4 | 4 | 98 | 98 | 33 | 33 | 2023-05-02 | 2023-05-12 | 2023-05-22 | -4 |  | 7 | 7 | 15 | 15 | 2023-10-10 | 110 | 110 | 2023-10-19 | 8 | 8 | 2023-05-10 | 2023-05-10 | 2023-06-26 | 2023-10-19 | 114 | 114 | 110 | 110 | 2023-10-02 | 2023-10-23 | 2023-11-01 | 23 | 23 | [12 empty] | 2023-10-26 | 2023-11-03 |  |  | 7 | 7 | 2023-11-08 | 2023-12-12 | 23 | 23 | 2023-12-12 | 23 | 23 | 2023-12-13 |  |  |  | 453 | 453 | 325 | 325 | 2023
1194 | Laguna Hills, CA - 23046 Avenida De La Carlota | 23046 Avenida De La Carlota | Laguna Hills | 92653 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2022-03-28 | 2022-04-01 | 5 | 5 | 2022-03-02 | 2022-03-02 | 23 | 23 | 1 | 1 | 2022-03-03 | 2022-03-24 | 2022-03-25 | 17 | 17 | 2 | 2
1195 | Long Beach, CA - 5253 Long Beach Blvd | 5253 Long Beach Blvd | Long Beach | 90805 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES | 2022-03-15 | 2022-03-17 | 3 | 3 | 2022-03-07 | 2022-03-07 | 9 | 9 | 1 | 1 | 2022-03-08 | 2022-04-11 | 2022-04-11 | 26 | 26 | 1 | 1
1196 | Inglewood, CA - 8307 S La Cienega Blvd | 8307 S La Cienega Blvd | Inglewood | 90301 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO | 2022-03-28 | 2022-03-29 | 2 | 2 | 2022-03-07 | 2022-03-07 | 17 | 17 | 1 | 1 |  |  | 2022-03-25
1197 | DLX7 Cypress previously 6450 Katella | 6460 Katella Ave | Cypress | 90630 | Orange County | 9. Complete | 48 - Fullerton | Orange | Saddleback |  |  | 3265812 | 1966405 |  | 2023-06-30 | 146 | NO |  | YES |  |  |  |  | 2022-03-07 | 2022-03-07 |  |  | 1 | 1 | 2022-03-07 |  | 2022-03-07 |  |  |  |  | 2022-03-08 | 2 | 2 | 2023-01-30 | 2023-01-31 |  | 2023-01-30 | 228 | 228 | 2023-01-30 | 2023-01-30 | 1 | 1 |  | 2023-02-14 | 12 | 12 | 2023-02-14 | 1 | 1 | 2023-03-15 | 2023-06-20 | 2023-03-15 | 2023-04-19 | 21 | 21 | 57 | 57 | 26 | 26 | 2022-09-14 | 2022-10-06 | 2023-02-22 | -106 |  | 95 | 95 | 111 | 111 | 2022-09-15 | -105 |  | 2022-10-17 | 23 | 23 | 2022-10-06 | 2022-09-15 | 2023-04-19 | 2023-04-19 | 150 | 150 | -105 |  | 2023-04-25 | 2023-05-18 | 2023-05-22 | 20 | 20 | [13 empty] | 2023-06-05 |  |  |  |  | 2023-06-20 | 2023-08-09 | 36 | 36 | 2023-08-10 | 37 | 37 | 2023-08-11 |  |  |  | 365 | 365 | 364 | 364 | 2023
1198 | Cypress, CA - 4959 Katella Ave | 4959 Katella Ave EV1 | Cypress | 90720 | Orange County | 6. Requirements (permit, easment, etc.) | 48 - Fullerton | Orange | Saddleback |  |  | 3329806 | 2011272 |  |  | 16 | NO |  | YES | 2022-03-25 | 2022-04-06 | 9 | 9 | 2022-03-08 | 2022-03-08 | 22 | 22 | 1 | 1 | 2022-03-10 |  | 2022-03-25 | [7 empty] | 2022-12-28 | 2022-12-28 |  | 2022-08-03 |  |  | 2022-08-04 | 2022-09-22 | 35 | 35 | 2022-10-14 | 2022-10-24 | 23 | 23 | 2022-10-24 | 1 | 1 | 2023-01-24 | 2022-11-03 | 2023-01-24 | 2023-01-26 | 63 | 63 | 87 | 87 | 3 | 3 |  | 2022-10-25 | 2023-01-25 |  |  | 63 | 63 |  |  | 2022-11-18 | 19 | 19 |  |  |  | 2022-10-25 | 2022-10-25 | 2023-01-26 |  |  |  | 19 | 19 | 2023-02-07 | 2023-03-03 | 2023-03-03 | 18 | 18 | [12 empty] | 2023-03-03 | 2023-02-24 |  |  | -6 |  | 2023-02-28 |  |  |  | 2023-04-01 | 24 | 24 | 2023-04-01 |  |  |  | 271 | 271 |  |  | 2023
1199 | Simi Valley, CA - 2550 Erringer Rd | 2550 1/8 Erringer Rd | Simi Valley | 93065 | Ventura County | 6. Requirements (permit, easment, etc.) | 39 - Ventura | North Coast | Ventura |  | Burleson 16kV | 3445772 | 2089882 |  | 2024-04-15 | 12 | NO |  | NO | 2022-03-25 | 2022-03-28 | 2 | 2 | 2022-03-09 | 2022-03-09 | 14 | 14 | 1 | 1 | 2022-03-11 | 2022-03-24 | 2022-03-25 | 12 | 12 | 2 | 2 | 2022-12-01 | 186 | 186 | 2022-12-28 | 2022-12-28 | 2023-02-14 | 2023-02-07 | 48 | 48 | 2023-02-07 | 2023-03-27 | 34 | 34 | 2023-04-20 | 2023-04-24 | 21 | 21 | 2023-04-24 | 1 | 1 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 136 | 136 | 157 | 157 | 2 | 2 | 2024-02-02 | 2024-02-12 | 2024-02-29 | 197 | 197 | 13 | 13 | 19 | 19 | [6 empty] | 2023-11-02 |  | 2024-02-29 | [5 empty] | 2024-03-21 |  |  |  |  | 2023-11-09 | 2024-03-06 | 2024-03-06 | 2023-11-20 | 8 | 8 | 2024-03-06 | 72 | 72
1200 | Thousand Oaks - Cho Cho San Inc | 400 EV E Thousand Oaks Blvd | Thousand Oaks | 92591 | Orange County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3309585 | 1995483 | 2051570 | 2024-06-01 |  | YES | Level 3 | YES |  |  |  |  | 2022-03-09 | 2022-03-09 |  |  | 1 | 1 | 2022-03-10 | [9 empty] | 2022-05-16 | 2022-05-16 | 2022-06-30 | 2022-06-29 |  |  | 2022-06-29 | 2022-10-26 | 84 | 84 |  | 2022-11-09 | 11 | 11 | 2022-11-10 | 2 | 2 | 2023-02-08 | 2023-09-12 | 2023-02-08 | 2023-09-07 | 62 | 62 | 219 | 219 | 148 | 148 | 2023-02-09 | 2023-02-22 | 2023-08-28 | 63 | 63 | 132 | 132 | 140 | 140 | [6 empty] | 2023-02-08 |  | 2023-09-07
1201 | Walnut, CA - 20701 Currier Rd | 20701 Currier Rd | Walnut | 91789 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO | 2022-03-21 | 2022-03-28 | 6 | 6 | 2022-03-09 | 2022-03-09 | 14 | 14 | 1 | 1 | 2022-03-10 | 2022-04-18 | 2022-04-18 | 29 | 29 | 1 | 1
1202 | Santa Barbara - Fredrick Lopez Rd | 140 Fredrick Lopez Rd | Santa Barbara | 93101 | Ventura County | 6. Requirements (permit, easment, etc.) | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2022-03-11 | 2022-03-11 |  |  | 1 | 1 | 2022-03-11 |  | 2022-03-19
1203 | Laguna Niguel - Alicia Pkwy | 29941 EV Alicia Pkwy | Laguna Niguel | 92677 | Orange County | 5. Final Design | 43 - Saddleback | Orange | Saddleback | Niguel | Piano 12 KV | 3297139 | 1998395 |  | 2024-03-27 | 4 | NO | Level 2 | YES | 2022-04-25 | 2022-04-27 | 3 | 3 | 2022-03-03 | 2022-03-10 | 35 | 35 | 6 | 6 | 2022-03-15 | 2022-03-22 | 2022-03-25 | 9 | 9 | 4 | 4 | 2022-04-25 | 38 | 38 | 2022-04-26 | 2022-04-26 | 2023-03-08 | 2023-02-07 | 200 | 200 | 2023-02-08 | 2023-02-27 | 13 | 13 | 2023-03-23 | 2023-03-16 | 14 | 14 | 2023-03-20 | 3 | 3 | 2023-03-20 |  | 2023-03-20 |  | 3 | 3 | [5 empty] | 2022-11-29 | [13 empty] | 2022-11-29
1204 | Old Address 500 Inland Center Drive. San Bernardino Inland Center | 512 S. Inland Center Drive | San Bernardino | 92408 | San Bernardino County | 7. Civil Construction | 31 - Redlands | Desert | SBRO |  |  | 3274561 | 1984640 |  | 2024-05-15 | 4 | NO | Level 2 | YES | 2021-02-08 | 2021-02-10 | 3 | 3 | 2022-03-15 | 2023-07-27 | -622 |  | 348 | 348 | 2022-08-01 | 2022-08-01 | 2022-03-15 | -251 |  | -98 |  |  |  |  | 2023-08-18 | 2023-08-18 | 2023-10-02 | 2023-10-02 |  |  | 2023-10-02 | 2023-10-03 | 2 | 2 | 2023-10-24 | 2023-10-19 | 13 | 13 | 2023-10-19 | 1 | 1 | [10 empty] | 2023-10-05 | 2023-10-17 | 2024-03-13 | -11 |  | 101 | 101 | 109 | 109
1205 | Buena Park, CA - 8888 Knott Ave R1 | 8902 1/2 Knott Ave | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  | Karen 12kV | 3409492 | 2111617 | 2097445 | 2024-09-06 | 28 | YES | Level 3 | NO | 2022-04-11 | 2022-04-21 | 9 | 9 | 2023-03-15 | 2022-03-22 | 23 | 23 | -249 |  | 2022-03-23 | 2022-04-08 | 2022-04-08 | 14 | 14 | 1 | 1 | 2023-03-15 | 1 | 1 | 2023-09-26 | 2023-09-27 | 2023-11-09 | [8 empty] | 2023-10-31 |  |  | 2023-10-31 | 1 | 1 | 2024-01-02 | 2024-01-30 | 2024-01-02 | 2024-03-13 | 42 | 42 |  |  | 50 | 50 | 2023-07-20 | 2023-08-01 | 2023-11-17 | -73 |  | 78 | 78 | 86 | 86 | 2024-01-03 | 43 | 43 | 2024-03-13 | 49 | 49 | 2023-08-01 | 2023-08-01 | 2024-03-13 | 2024-03-13 | 155 | 155 | 43 | 43 | 2024-03-14 |  |  |  |  | 2024-03-21 |  |  | 2024-04-09 | 14 | 14
1206 | City of Industry - Nelson Ave | 13400 Nelson Ave | City of Industry | 91746 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-03-22 | 2022-03-22 |  |  | 1 | 1 | 2022-03-23 | 2022-03-30 | 2022-04-03 | 7 | 7 | 3 | 3
1207 | Mojave, CA - 16862 CA-14 | 16862 CA-14 | Mojave | 93501 | Kern County | 11. Cancelled | 52 - Tehachapi | North Valley | Ventura |  | Boxcar 12kV | 3382646 | 2043236 |  |  | 12 | NO |  | NO | 2022-03-23 | 2022-04-04 | 9 | 9 | 2022-03-22 | 2022-03-22 | 10 | 10 | 1 | 1 | 2022-03-22 |  | 2022-03-22 |  |  |  |  | 2022-09-09 | 121 | 121 | 2022-09-12 | 2022-09-12 |  | 2022-10-26 | 34 | 34 | 2022-10-27 | 2023-01-25 | 61 | 61 | 2023-02-16 |  |  |  | 2023-03-07 |  |  | 2023-03-07 | 2023-04-26 | 2023-03-07 | 2023-04-26 |  |  | 65 | 65 | 37 | 37 | 2023-02-09 | 2023-02-24 | 2023-03-07 |  |  | 8 | 8 | 18 | 18 | [6 empty] | 2023-02-24 |  | 2023-04-26 | [5 empty] | 2023-05-31 | 2023-06-15 | 2023-06-15 | 12 | 12 | [13 empty] | 2023-07-05 |  |  |  |  | 2023-07-11 | 2023-08-18 | 29 | 29 | 2023-08-22 | 31 | 31 | 2023-08-22 |  |  |  | 361 | 361 | 241 | 241 | 2023
1208 | City of Industry - Chestnut St | 16900 Chestnut St | City of Industry | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-03-22 | 2022-03-22 |  |  | 1 | 1 | 2022-03-25 | 2022-03-30 |  | 7 | 7
1209 | Fontana - Look Rd | 13200 Look Rd | Fontana | 92337 | San Bernardino County | 5. Final Design | 30 - Foothill | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-03-22 | 2022-03-22 |  |  | 1 | 1 | 2022-03-25 | 2022-04-05 | 2022-04-15 | 11 | 11 | 9 | 9
1210 | Baldwin Park, CA - 13020 Francisquito Ave | 13020 Francisquito Ave | Baldwin Park | 91706 | Los Angeles County | 9. Complete | 27 - Monrovia | Metro East | Pomona |  | Pecos 12 kV | 3435431 | 2093722 |  | 2024-07-24 | 16 | YES | Level 3 | YES | 2022-04-20 |  |  |  | 2022-03-23 | 2022-03-23 |  |  | 1 | 1 | 2022-03-25 |  | 2022-04-19 |  |  |  |  | 2023-11-13 | 418 | 418 | 2023-11-13 |  | 2024-01-12 | 2024-01-16 | 42 | 42 | 2024-01-16 | 2024-01-19 | 4 | 4 | 2024-02-27 | 2024-02-14 | 19 | 19 | 2024-02-21 | 5 | 5 | [10 empty] | 2023-04-07 | 2024-03-20 |  | -216 | [5 empty] | 2024-03-25 | 24 | 24 | [9 empty] | 28 | 28
1211 | Pomona, CA - 58 Rio Rancho Rd | 62 1/2 Rio Rancho Road | Pomona | 91766 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  | Fernstrom 12kV | 3409853 | 2063124 |  | 2024-02-15 | 24 | NO |  | YES | 2022-04-22 | 2022-05-02 | 7 | 7 | 2022-03-23 | 2022-03-23 | 29 | 29 | 1 | 1 | 2022-03-25 | 2022-04-22 | 2022-04-22 | 23 | 23 | 1 | 1 |  |  |  | 2022-10-24 | 2022-10-28 | 2022-12-13 | 2022-12-14 |  |  | 2022-12-23 | 2023-07-11 | 139 | 139 | 2023-08-02 | 2023-07-14 | 4 | 4 |  |  |  | 2023-07-26 | 2023-10-25 | 2023-07-26 | 2023-07-31 | 9 | 9 | 15 | 15 | 4 | 4 | 2023-06-30 | 2023-07-17 | 2023-07-27 | -10 |  | 9 | 9 | 19 | 19 | 2024-01-04 |  |  | 2024-02-16 | 31 | 31 | 2023-07-17 | 2023-07-17 | 2023-07-31 | 2024-02-16 | 149 | 149 | 120 | 120 | 2023-11-01 | 2023-11-15 | 2023-12-21 | 35 | 35 | 2023-10-16 |  | 2023-12-12 | 2023-10-25 | 8 | 8 |  |  |  | 2023-12-21 | 8 | 8 |  | 2023-12-19 | 45 | 45 |  |  | 2024-01-16 | 2024-02-20 | 25 | 25 | 2024-03-20 | 46 | 46 | 2024-03-20 |  |  |  | 504 | 504 |  |  | 2024
1212 | Whittier, CA - 10033 Whittwood Drive | 10033 Whittwood Drive, EV-1 | Whittier | 90603 | Los Angeles County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  | Kappa 12kV | 3419368 | 2059842 |  |  | 12 | NO |  | YES | 2022-04-20 | 2022-04-21 | 2 | 2 | 2022-03-23 | 2022-03-23 | 22 | 22 | 1 | 1 | 2022-03-25 | 2022-04-19 | 2022-04-19 | 20 | 20 | 1 | 1 | 2022-10-19 | 148 | 148 | 2022-11-08 | 2023-08-23 | 2023-09-07 | 2023-01-09 | 56 | 56 | 2023-01-09 | 2023-01-18 | 7 | 7 | 2023-02-16 | 2023-02-13 | 19 | 19 | 2023-02-13 | 1 | 1 | 2023-03-10 | 2023-04-13 | 2023-03-10 | 2023-09-06 | 19 | 19 | 162 | 162 | 126 | 126 | 2023-02-08 | 2023-02-23 | 2023-03-16 | -4 |  | 16 | 16 | 26 | 26 | [6 empty] | 2023-02-23 |  | 2023-09-06 | [5 empty] | 2023-07-18 | 2023-07-26 | 2023-08-10 | 18 | 18 | [12 empty] | 2023-07-18 | 2023-08-17 |  |  | 23 | 23 | 2023-09-14 | 2023-10-18 | 25 | 25 | 2023-10-19 | 26 | 26 | 2023-10-19 |  |  |  | 401 | 401 | 254 | 254 | 2023
1213 | Bridgeport, CA | 226 Main St | Bridgeport | 93517 | Mono County | 11. Cancelled | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2024-10-15 |  |  |  | YES | 2022-03-24 | 2022-04-11 | 13 | 13 | 2022-03-08 | 2022-03-08 | 25 | 25 | 1 | 1 | 2022-03-08 |  | 2022-03-24
1214 | Rowland Heights, CA - 1015 S Nogales | 1015 S Nogales St | Rowland Heights | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  | Handcar 12kv | 3341478 | 2022954 | [5 empty] | YES | 2022-04-20 | 2022-04-21 | 2 | 2 | 2022-03-24 | 2022-03-24 | 21 | 21 | 1 | 1 | 2022-03-25 | 2022-04-19 | 2022-04-19 | 19 | 19 | 1 | 1 | [5 empty] | 2022-08-22 | 2022-08-16 |  |  | 2023-01-19
1215 | Fontana, CA - 10161 Citrus Ave | 10161 Citrus Ave | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | true | 2022-04-11 | 2022-04-21 | 9 | 9 | 2022-03-25 | 2022-03-25 | 20 | 20 | 1 | 1 | 2022-03-31
1216 | Los Angeles, CA - 199 S Barrington Pl | 199 S Barrington Pl | Los Angeles | 90049 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | true | 2022-06-15 |  |  |  | 2022-03-28 | 2022-03-28 |  |  | 1 | 1 | 2022-03-28 |  | 2022-06-15
1217 | Pico Rivera - Slauson Ave | 8830 Slauson Ave | Pico Rivera | 90660 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [9 empty] | YES | 2022-03-28 | 2022-03-30 | 3 | 3 | 2022-03-10 | 2022-03-10 | 15 | 15 | 1 | 1 | 2022-03-11 | 2022-04-18 | 2022-04-18 | 28 | 28 | 1 | 1
1218 | Paramount - Rosecrans Ave | 7201 Rosecrans Ave | Paramount | 90723 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [9 empty] | NO | 2022-05-03 |  |  |  | 2022-03-10 | 2022-03-10 |  |  | 1 | 1 | 2022-03-10 |  | 2022-05-02
1219 | Ontario - E Airport Dr Suite 100 | 3450 E Airport Dr Suite 100 | Ontario | 91761 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-03-30 | 2022-03-30 |  |  | 1 | 1 | 2022-03-31 | 2022-04-09 | 2022-04-09 | 8 | 8 | 0
1220 | Palm Springs - N Civic Dr | 2992 N Civic Dr | Palm Springs | 92262 | Riverside County | 9. Complete | 79 - Palm Springs | Desert | SBRO |  |  | 3406986 | 2090254 | 2090853 | 2024-06-07 | 4 | YES | Level 3 | NO |  |  |  |  | 2022-10-10 | 2022-03-30 |  |  | -136 |  | 2022-03-31 | 2022-04-07 | 2022-04-09 | 7 | 7 | 2 | 2 | 2022-11-22 | 31 | 31 | 2022-11-23 | 2022-11-23 | 2023-01-10 | 2023-02-06 | 52 | 52 | 2023-02-06 | 2023-05-09 | 66 | 66 | 2023-06-05 | 2023-07-27 | 56 | 56 | 2023-07-28 | 2 | 2 | 2023-07-31 | 2023-12-13 | 2023-07-31 | 2023-08-02 | 3 | 3 | 60 | 60 | 3 | 3 | 2023-08-10 | 2023-10-31 |  | 11 | 11 |  |  |  |  | 2023-10-31 | 67 | 67 | 2023-11-13 | 10 | 10 | 2023-07-31 | 2023-07-31 |  |  |  |  | 68 | 68 | [5 empty] | 2023-11-03
1221 | SNA/John Wayne Airport 4000 Campus | 4023 Birch St | Newport Beach | 92660 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3354709 | 2035332 |  | 2023-12-01 | 4 | YES | Level 1 | YES |  |  |  |  | 2022-07-27 | 2022-03-30 |  |  | -84 |  | 2022-03-31 | 2022-04-06 | 2022-04-18 | 6 | 6 | 9 | 9 | 2022-07-27 | 1 | 1 | 2022-07-28 | 2022-07-28 | 2022-09-09 | 2022-09-09 | 32 | 32 | 2022-09-12 | 2022-10-09 | 20 | 20 | 2022-11-02 | 2022-10-25 | 12 | 12 | 2022-11-21 | 19 | 19 | 2022-11-21 | 2022-11-21 | 2022-11-21 | 2022-11-21 | 19 | 19 | 30 | 30 | 1 | 1 | 2022-10-28 | 2022-11-08 | 2023-07-12 | 4 | 4 | 170 | 170 | 177 | 177 | [6 empty] | 2022-11-08 |  | 2023-07-12 | [5 empty] | 2023-08-30 | 2023-09-21 | 2023-09-21 | 16 | 16 | 2023-07-21 |  |  | 2023-08-15 | 18 | 18 | [6 empty] | 2023-09-06 | 2023-09-11 | 36 | 36 | 4 | 4 | 2023-10-17 | 2023-11-12 | 19 | 19 | 2023-11-13 | 20 | 20 | 2023-11-13 | 2024-01-17 | 43 | 43 | 330 | 330 | 330 | 330 | 2023
1222 | Huntington Park, CA - 5964 Pacific Blvd | 5964 Pacific Blvd | Huntington Park | 90255 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [9 empty] | YES | 2022-04-22 | 2022-05-02 | 7 | 7 | 2022-03-31 | 2022-03-31 | 23 | 23 | 1 | 1 | 2022-04-04 | 2022-04-22 | 2022-04-22 | 17 | 17 | 1 | 1
1223 | Yucca Valley Warren Vista Center | 57675 Twentynine Palms Hwy | Yucca Valley | 92284 | San Bernardino County | 11. Cancelled | 84 - Yucca Valley | Rurals | SBRO |  |  | 3471866 | 2103995 |  | 2023-12-13 | 6 | NO |  | NO | 2022-12-14 | 2023-01-05 | 17 | 17 | 2022-04-01 | 2022-04-01 | 194 | 194 | 1 | 1 |  | 2022-12-22 | 2023-01-05 | 184 | 184 | 11 | 11 | 2023-02-13 | 220 | 220 | 2023-02-13 | 2023-02-13 | 2023-03-29 | 2023-03-31 | 34 | 34 | 2023-03-31 | 2023-04-05 | 4 | 4 | 2023-04-28 | [6 empty] | 2023-06-29 | 2023-08-01 | 2023-07-31 | 2023-08-03 |  |  | 85 | 85 | 4 | 4 | 2023-04-14 | 2023-06-06 | 2023-06-16 |  |  | 9 | 9 | 45 | 45 | [6 empty] | 2023-06-06 |  | 2023-08-03 | [5 empty] | 2023-09-05 |  | 2023-10-03 | 21 | 21 | 2023-08-07 |  |  | 2023-08-15 | 7 | 7 | [6 empty] | 2023-10-02 | 2023-10-17 | 51 | 51 | 12 | 12 | 2023-10-18 | 2023-12-23 | 46 | 46 | 2023-12-24 | 46 | 46 | 2023-12-24 | 2024-01-12 | 13 | 13 | 438 | 438 | 219 | 219 | 2023
1224 | Santa Barbara - W Victoria St | 423 W Victoria St | Santa Barbara | 93101 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2022-03-25 | 2022-03-25 |  |  | 1 | 1 | 2022-03-25 |  | 2022-03-25
1225 | Ventura - US Fish & Wildlife Service | 2493 Portola Rd Suite B | Ventura | 93003 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3299270 | [6 empty] | YES |  |  |  |  | 2022-04-04 | 2022-04-04 |  |  | 1 | 1 | 2022-04-07 | 2022-04-19 | 2022-04-19 | 12 | 12 | 1 | 1 | 2022-04-26 | 17 | 17 | 2022-04-28 | 2022-04-29 | 2022-06-14 | 2022-05-31 | 25 | 25 | 2022-05-31 | 2022-05-31 | 1 | 1
1226 | Hesperia, CA - 11412 Fashion Court | 11412 Fashion Court | Hesperia | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [9 empty] | YES | 2022-04-22 |  |  |  | 2022-04-06 | 2022-04-06 |  |  | 1 | 1 | 2022-04-07 |  | 2022-04-22
1227 | Hesperia, CA - 11412 Fashion Ct Phase 2 | 11412 Fashion Court | Hesperia | 92345 | San Bernardino County | 7. Civil Construction | 73 - Victorville | Rurals | SBRO | [9 empty] | NO | 2022-04-22 | 2022-05-10 | 13 | 13 | 2022-04-06 | 2022-04-06 | 25 | 25 | 1 | 1 | 2022-04-07 | 2022-04-22 | 2022-04-22 | 13 | 13 | 1 | 1
1228 | Chino Hills - 3260 Chino Ave | 3260 Chino Ave | Chino Hills | 91709 | San Bernardino County | 1. FVR | 34 - Ontario | Metro East | Pomona |  |  | 3296602 | 2094567 |  | 2024-08-01 |  | NO |  | YES |  |  |  |  | 2022-04-07 | 2022-04-07 |  |  | 1 | 1 | 2022-04-11 | 2022-04-15 | 2022-04-15 | 7 | 7 | 1 | 1 |  |  |  | 2022-04-25 | 2022-05-04 | 2022-06-09 | 2022-06-20 |  |  | 2022-06-20 | 2022-10-20 | 87 | 87 | 2022-11-10 | 2022-11-22 | 23 | 23 | 2022-11-22 | 1 | 1 | 2023-02-21 | 2023-04-03 | 2023-02-21 | 2023-02-22 | 62 | 62 | 85 | 85 | 2 | 2 | 2023-02-14 | 2023-04-13 | 2024-03-12 | 58 | 58 | 230 | 230 | 271 | 271 | [6 empty] | 2023-02-21 |  | 2024-03-12
1229 | Costa Mesa, CA - 1731 Fullerton Ave | 1731 Fullerton Ave | Costa Mesa | 92627 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2022-04-22 | 2022-05-06 | 11 | 11 | 2022-04-08 | 2022-04-08 | 21 | 21 | 1 | 1 | 2022-04-12 | 2022-04-22 | 2022-04-22 | 11 | 11 | 1 | 1
1230 | Irvine, CA - 19100 Von Karman Ave | 19100 Von Karman Ave # 190 | Irvine | 92612 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3362711 | 2040974 |  |  |  | NO |  | NO | 2022-04-25 | 2022-05-06 | 10 | 10 | 2022-04-08 | 2022-04-08 | 21 | 21 | 1 | 1 | 2022-04-12 | 2022-04-25 | 2022-04-25 | 12 | 12 | 1 | 1 | 2022-08-09 | 86 | 86 | 2022-08-10 | 2022-08-10 | 2023-03-08 | 2023-02-28 | 140 | 140 | 2023-02-28
1231 | Palmdale - Palmdale Mall Phase 2 Expansion | 1233 W Rancho Vista Blvd | Palmdale | 93551 | San Bernardino County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | YES |  | 2022-05-05 |  |  | 2022-04-14 | 2022-04-14 | 16 | 16 | 1 | 1 | 2022-04-14
1232 | Palmdale, CA - 10th St W | 39341 10th St W | Palmdale | 93551 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | YES | 2022-04-19 | 2022-04-26 | 6 | 6 | 2022-04-01 | 2022-04-01 | 18 | 18 | 1 | 1 | 2022-04-04 | 2022-04-15 | 2022-04-15 | 11 | 11 | 1 | 1
1233 | Oxnard, CA - 180 W Esplanade Dr | 180 W Esplanade Dr | Oxnard | 93036 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [9 empty] | YES | 2022-05-02 | 2022-05-17 | 12 | 12 | 2022-04-15 | 2022-04-15 | 23 | 23 | 1 | 1 | 2022-04-18 | 2022-04-29 | 2022-04-29 | 11 | 11 | 1 | 1
1234 | Pomona Garey Park Plaza | 160 W Willow St | Pomona | 91768 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3343095 | 2029413 |  |  | 8 | YES |  | YES | 2022-05-20 | 2022-05-24 | 3 | 3 | 2022-04-15 | 2022-04-15 | 28 | 28 | 1 | 1 | 2022-05-07 | 2022-05-07 | 2022-05-07 | 16 | 16 | 0 |  | 2022-07-10 | 59 | 59 | 2022-07-11 | 2022-07-15 | 2022-08-26 | 2022-08-31 | 38 | 38 | 2022-09-01 | 2022-09-09 | 6 | 6 | 2022-10-07 | 2022-10-28 | 36 | 36 | 2022-10-31 | 2 | 2 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 17 | 17 | 52 | 52 | 1 | 1 | 2022-11-28 | 2022-11-29 |  | 19 | 19 | [10 empty] | 2022-11-22
1235 | Pomona - Winco | 90 Rio Rancho Rd | Pomona | 91766 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3332356 | 2011353 |  | 2023-07-12 | 8 | NO |  | NO | 2022-05-20 | 2022-05-23 | 2 | 2 | 2022-04-15 | 2022-04-15 | 27 | 27 | 1 | 1 | 2022-04-25 | 2022-05-06 | 2022-05-06 | 16 | 16 | 1 | 1 |  |  |  | 2022-06-22 | 2022-06-24 | 2022-08-08 | 2022-08-02 |  |  | 2022-08-02 | 2022-08-03 | 2 | 2 | 2022-08-26 |  |  |  | 2022-11-28 |  |  | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-11-30 |  |  | 82 | 82 | 3 | 3 | 2022-12-12 | 2023-06-08 | 2023-07-14 |  |  | 26 | 26 | 151 | 151 | 2023-03-13 | 74 | 74 | 2023-04-14 | 25 | 25 | 2022-11-28 | 2022-11-28 | 2023-07-14 | 2023-07-14 | 161 | 161 |  |  | 2023-07-03 | 2023-08-11 | 2023-08-11 | 29 | 29 | 2023-02-15 |  |  | 2023-03-01 | 10 | 10 | [7 empty] | 2023-06-15 | 85 | 85 |  |  | 2023-06-28 | 2023-08-10 | 31 | 31 | 2023-08-11 | 32 | 32 | 2023-08-11 |  |  |  | 336 | 336 |  |  | 2023
1236 | Fontana - Valley Blvd | 3550-A Valley Blvd | Fontana | 92335 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [9 empty] | YES | 2022-05-02 |  |  |  | 2022-04-18 | 2022-04-18 |  |  | 1 | 1 | 2022-04-26 | 2022-04-29 | 2022-04-29 | 10 | 10 | 1 | 1
1237 | Eastvale - Hamner Ave | 4250 Hamner Ave | Eastvale | 91752 | Los Angeles County | 7. Civil Construction | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-05-10 | 6 | YES | Level 1 | YES | 2023-06-28 | 2023-07-17 | 13 | 13 | 2022-04-18 | 2022-04-18 | 316 | 316 | 1 | 1 | 2022-04-18 | 2022-04-29 | 2022-04-29 | 10 | 10 | 1 | 1
1238 | Oxnard -125 W Pleasant valley Rd EV1 | 221 W. Pleasant Valley Rd EV1 | Oxnard | 93033 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura |  | Surfside 16kV | 3431220 | 2083710 |  | 2024-09-21 |  | NO |  | NO | 2022-05-02 | 2022-05-17 | 12 | 12 | 2022-04-19 | 2022-04-19 | 21 | 21 | 1 | 1 | 2022-04-20 | 2022-04-29 | 2022-04-29 | 9 | 9 | 1 | 1 | 2022-11-08 | 143 | 143 | 2022-11-30 | 2022-12-01 | 2023-05-08 | 2023-07-28 | 182 | 182 | 2023-07-28 | 2023-08-24 | 20 | 20 | 2023-11-27 | 2023-12-05 | 71 | 71 | 2023-12-05 | 1 | 1 | 2023-12-05 |  | 2023-12-05 | 2024-01-12 | 1 | 1 | 97 | 97 | 27 | 27 | 2023-12-08 | 2024-01-17 | 2024-01-26 | 4 | 4 | 8 | 8 | 33 | 33 | 2024-03-12 | 67 | 67 |  |  |  | 2023-12-05 | 2023-12-05 | 2024-01-26 |  |  |  | 67 | 67
1239 | HLA6-Visalia | 8817 W Kibler Ave | Visalia | 92391 | Tulare County | 7. Civil Construction | 51 - Tulare | San Joaquin | Ventura |  |  | 3324210 | 2023683 |  |  | 10 | NO |  | YES |  |  |  |  | 2022-04-19 | 2022-04-19 |  |  | 1 | 1 | 2022-04-19 | 2022-04-28 | 2022-04-28 | 8 | 8 | 1 | 1 |  |  |  | 2022-06-14 | 2022-06-14 | 2022-09-19 | 2022-09-19 |  |  | 2022-09-19 | 2023-01-23 | 87 | 87 | 2023-02-13 | 2023-01-27 | 5 | 5 | 2023-01-27 | 1 | 1 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2023-02-23 | 17 | 17 | 23 | 23 | 3 | 3 | 2023-01-27 | 2023-02-14 | 2023-03-03 | 1 | 1 | 13 | 13 | 25 | 25 | 2023-02-22 | 18 | 18 | 2023-02-23 | 2 | 2 | 2023-02-14 | 2023-02-14 | 2023-03-03 | 2023-03-03 | 13 | 13 | 18 | 18 | [5 empty] | 2023-02-07 |  |  | 2023-02-15 | 7 | 7 | [7 empty] | 2023-05-27 | 78 | 78 |  |  | 2023-07-17 |  |  |  | 2023-12-01 | 97 | 97
1241 | Huntington Beach - Brookhurst/ Adams | 20100 Brookhurst Ave | Huntington Beach | 92646 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3340769 | 2035304 |  | 2024-04-29 | 4 | YES | Level 1 | YES | 2022-05-10 | 2022-05-19 | 8 | 8 | 2022-04-20 | 2022-04-20 | 22 | 22 | 1 | 1 | 2022-04-25 | 2022-05-03 | 2022-05-09 | 10 | 10 | 5 | 5 | 2022-07-06 | 54 | 54 | 2022-07-06 |  | 2022-08-18 | 2022-09-09 | 47 | 47 | 2022-09-09 | 2022-09-20 | 8 | 8 | 2022-10-14 | 2022-09-21 | 2 | 2 | 2022-10-21 | 23 | 23 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 23 | 23 | 24 | 24 | 1 | 1 | 2022-09-29 | 2022-10-26 | 2023-03-06 | 7 | 7 | 89 | 89 | 108 | 108 | 2023-03-13 | 97 | 97 | 2023-05-09 | 42 | 42 | 2022-10-21 | 2022-10-21 | 2023-03-06 | 2023-05-09 | 138 | 138 | 119 | 119 | 2023-08-17 | 2023-09-11 |  |  |  | 2023-06-26
1242 | Huntington Park Margarita Plaza | 7000 Santa Fe Ave | Huntington Park | 90255 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3368960 | 2034919 |  | 2024-03-28 |  | NO |  | YES | 2022-05-20 | 2022-05-23 | 2 | 2 | 2022-04-20 | 2022-04-20 | 24 | 24 | 1 | 1 | 2022-04-25 | 2022-05-06 | 2022-05-06 | 13 | 13 | 1 | 1 | 2022-08-17 | 84 | 84 | 2022-08-19 | 2022-08-24 | 2022-10-07 | 2022-10-04 | 34 | 34 | 2022-10-05 | 2022-10-19 | 11 | 11 | 2022-11-10 | 2022-10-25 | 5 | 5 | 2022-10-27 | 3 | 3 | 2022-11-28 | 2022-12-08 | 2022-11-28 | 2022-11-29 | 22 | 22 | 27 | 27 | 2 | 2 | 2022-10-26 | 2022-11-23 | 2023-09-07 | 2 | 2 | 200 | 200 | 219 | 219 | [6 empty] | 2022-11-23 |  | 2023-09-07
1243 | Azalea Regional Shopping Center | 4841 Firestone Blvd EV | South Gate | 90280 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | Cudahy | Purex 16kV | 3385711 |  |  |  | 6 | NO |  | YES | 2022-09-14 | 2022-05-17 | -84 |  | 2022-04-21 | 2022-04-21 | 19 | 19 | 1 | 1 | 2022-04-25 | 2022-05-03 | 2022-05-10 | 9 | 9 | 6 | 6 | 2022-09-12 | 100 | 100 | 2022-09-15 | 2022-09-18 | 2022-10-31 | 2022-10-31 | 36 | 36 | 2022-10-31 | 2022-11-03 | 4 | 4 | 2023-03-07 | 2023-02-09 | 67 | 67 | 2023-02-10 | 2 | 2 | [10 empty] | 2023-02-09 | 2023-02-24 |  | 1 | 1
1244 | WinCo Foods - Moreno Valley Phase 2 | 12882 Day St | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3331860 | 2030795 |  |  | 4 | YES | Level 3 | YES | 2022-05-17 | 2022-06-01 | 11 | 11 | 2022-04-21 | 2022-04-21 | 29 | 29 | 1 | 1 | 2022-04-25 | 2022-05-07 | 2022-05-07 | 12 | 12 | 0 |  | 2022-06-16 | 40 | 40 | 2022-06-21 | 2022-06-23 | 2022-08-08 | 2022-08-31 | 54 | 54 | 2022-09-01 | 2022-09-09 | 6 | 6 | 2022-09-30 | 2022-09-14 | 4 | 4 | 2022-09-14 | 1 | 1 | 2022-10-06 | 2022-10-06 | 2022-10-06 | 2022-10-06 | 17 | 17 | 20 | 20 | 1 | 1 | 2022-09-13 | 2022-10-12 | 2023-02-03 | -2 |  | 79 | 79 | 100 | 100 | [6 empty] | 2022-10-06 |  | 2023-02-03 | [5 empty] | 2023-03-23 | 2023-04-19 | 2023-04-20 | 21 | 21 | 2023-02-14 |  |  | 2023-02-21 | 5 | 5 | [6 empty] | 2023-04-26 | 2023-05-16 | 65 | 65 | 15 | 15 | 2023-05-16 | 2023-06-20 | 25 | 25 | 2023-06-21 | 26 | 26 | 2023-06-21 | 2023-07-17 | 18 | 18 | 296 | 296 | 257 | 257 | 2023
1246 | Santa Ana - S Birch St | 2701 S Birch St | Santa Ana | 92707 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | johanna | poker 12kv | 3342040 | [6 empty] | NO | 2022-05-17 | 2022-06-01 | 11 | 11 | 2022-04-25 | 2022-04-25 | 27 | 27 | 1 | 1 | 2022-04-25 | 2022-05-09 | 2022-05-09 | 11 | 11 | 1 | 1 | 2022-07-15 | 58 | 58 | 2022-07-21 | 2022-07-22
1247 | Riverside - La Sierra Ave | 3765 La Sierra Ave | Riverside | 92505 | Riverside County | 1. FVR | 31 - Redlands | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-04-25 | 2022-04-25 |  |  | 1 | 1
1248 | Oxnard, CA- 858 S Oxnard Blvd | 858 S Oxnard Blvd | Oxnard | 93030 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [5 empty] | 2024-09-01 | 28 | YES |  | NO |  |  |  |  | 2023-12-22 | 2023-12-22 |  |  | 1 | 1 | 2023-12-26 | 2023-12-28 | 2023-12-30 | 4 | 4 | 2 | 2
1249 | Santa Ana, CA - 1430 E Edinger Ave | 1430 E Edinger Ave | Santa Ana | 92705 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-04-26 | 2022-04-26 |  |  | 1 | 1 | 2022-04-27
1250 | Redondo Beach, CA - 400 N Harbor Dr | 400 N Harbor Dr | Redondo Beach | 90277 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES | 2022-05-10 | 2022-05-17 | 6 | 6 | 2022-04-27 | 2022-04-27 | 15 | 15 | 1 | 1 | 2022-04-29 | 2022-05-10 | 2022-05-10 | 10 | 10 | 1 | 1
1252 | Moreno Valley - 12641 Moreno Beach Dr | 12641-12831 Moreno Beach Dr | Moreno Valley | 92555 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES |  |  |  |  | 2022-04-27 | 2022-04-27 |  |  | 1 | 1
1253 | Santa Fe Springs Marketplace R3 | 7860-EV Norwalk Blvd | Whittier | 90670 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | Passons | Alburtis 12kv | 3341712 | 2193749 |  | 2024-08-27 | 4 | YES | Level 2 | YES | 2022-06-23 | 2022-06-28 | 4 | 4 | 2023-03-15 | 2022-04-28 | 43 | 43 | -222 |  | 2022-04-29 | 2022-06-02 | 2022-06-23 | 25 | 25 | 16 | 16 | 2023-03-15 | 1 | 1 | 2023-09-12 | 2023-09-14 | 2023-10-24 | 2023-10-20 | 155 | 155 | 2023-10-24 | 2023-10-25 | 2 | 2 | 2023-11-17 | 2023-12-01 | 26 | 26 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 1 | 1 | 26 | 26 | 1 | 1 | 2023-11-01 | 2023-11-08 | 2024-01-18 | -21 |  | 47 | 47 | 52 | 52 | [6 empty] | 2023-11-08 |  | 2024-01-18
1254 | Long Beach Chase Bank | 4501 E Pacific Coast Hwy - EV | Long Beach | 90804 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | Hathaway | Alterton 12kv | 3375327 | 2037823 | 2056722 |  | 8 | NO |  | YES | 2022-06-08 | 2022-06-24 | 13 | 13 | 2022-04-28 | 2022-04-28 | 41 | 41 | 1 | 1 | 2022-04-29 | 2022-06-05 | 2022-06-05 | 26 | 26 | 0 |  | 2022-08-25 | 84 | 84 | 2022-08-30 | 2022-08-31 | 2022-10-14 | 2022-09-22 | 20 | 20 | 2022-09-22 | 2022-10-10 | 13 | 13 | 2022-11-07 | 2022-11-01 | 17 | 17 | 2022-11-02 | 2 | 2 | 2022-11-30 | 2023-02-01 | 2022-11-30 | 2022-12-08 | 19 | 19 | 41 | 41 | 7 | 7 | 2022-11-02 | 2022-11-11 | 2023-01-05 | 2 | 2 | 37 | 37 | 44 | 44 | [6 empty] | 2022-11-11 |  | 2023-01-05 | [5 empty] | 2023-02-07 | 2023-03-01 | 2023-03-01 | 16 | 16 | 2022-12-08 |  |  | 2022-12-16 | 7 | 7 | [7 empty] | 2023-03-13 | 66 | 66 |  |  | 2023-03-15 |  |  |  | 2023-04-21 | 28 | 28 | 2023-04-21 |  |  |  | 249 | 249 | 166 | 166 | 2023
1255 | Huntington Beach Meadowlark Plaza | 5141 Warner Ave | Huntington Beach | 92649 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2022-05-16 | 2022-05-20 | 5 | 5 | 2022-04-27 | 2022-04-27 | 18 | 18 | 1 | 1 | 2022-04-29 | 2022-05-10 | 2022-05-13 | 10 | 10 | 4 | 4
1256 | Pomona, CA - 90 Rio Rancho Rd | 90 1/2 Rio Rancho Rd | Pomona | 91766 | Los Angeles County | 9. Complete | 26 - Covina | Metro East | Pomona |  |  | 3374859 | 2042572 |  |  | 16 |  |  | YES | 2022-05-16 | 2022-05-24 | 7 | 7 | 2022-04-28 | 2022-04-28 | 19 | 19 | 1 | 1 | 2022-04-29 | 2022-05-14 | 2022-05-14 | 12 | 12 | 0 |  | 2022-08-29 | 86 | 86 |  |  |  | 2022-09-29 | 23 | 23 | 2022-10-03 | [10 empty] | 2022-12-08 | 2022-12-19 | [31 empty] | 2023-06-16 | 2023-07-31 | 2023-08-11 | 40 | 40 | [13 empty] | 2023-06-15 |  |  |  |  | 2023-07-03 | 2023-08-07 | 25 | 25 | 2023-08-11 | 29 | 29 | 2023-08-11 |  |  |  | 327 | 327 | 242 | 242 | 2023
1257 | El Monte Chase Bank - Santa Anita Ave | 4749 Santa Anita Ave | El Monte | 91731 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | Anita | Meridian 16kv | 3340891 | 2031270 | 2031269 | 2022-12-09 | 4 | YES | Level 3 | YES | 2022-06-22 | 2022-07-01 | 8 | 8 | 2022-04-28 | 2022-04-28 | 46 | 46 | 1 | 1 | 2022-04-29 | 2022-05-09 | 2022-06-21 | 8 | 8 | 31 | 31 | 2022-07-06 | 48 | 48 | 2022-07-06 | 2022-07-15 | 2022-08-26 | 2022-09-20 | 54 | 54 | 2022-11-08 | 2022-11-09 | 2 | 2 | 2022-12-09 | 2022-12-29 | 34 | 34 | 2022-12-08 | -16 |  | 2022-12-29 | 2023-04-25 | 2022-12-29 | 2023-01-03 | 1 | 1 | 37 | 37 | 4 | 4 | 2022-12-16 | 2023-01-31 | 2023-02-06 | -10 |  | 5 | 5 | 36 | 36 | [6 empty] | 2022-12-29 |  | 2023-02-06 | [5 empty] | 2023-03-02 |  | 2023-04-28 | 42 | 42 | 2023-03-21 |  |  | 2023-03-28 | 6 | 6 | [6 empty] | 2023-03-21 | 2023-05-11 | 38 | 38 | 38 | 38 | 2023-05-12 | 2023-06-21 | 28 | 28 | 2023-06-22 | 29 | 29 | 2023-06-22 | 2023-07-06 | 10 | 10 | 292 | 292 | 245 | 245 | 2023
1258 | Victorville, 15617 Roy Rogers Dr | 15617 Roy Rogers Dr | Victorville | 92394 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 73 - Victorville | Rurals | SBRO |  |  | 3379888 |  |  | 2023-08-15 |  | NO |  | YES | 2022-05-02 | 2022-05-19 | 14 | 14 | 2022-04-21 | 2022-04-21 | 21 | 21 | 1 | 1 | 2022-04-25 | 2022-04-29 | 2022-05-29 | 7 | 7 | 21 | 21 | 2022-09-06 | 96 | 96 | 2023-01-17 | 2023-01-17 | 2022-10-24
1259 | San Fernando, CA - 12920 Foothill Blvd | 12920 Foothill Blvd | Sylmar | 91342 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 59 - Valencia | North Valley | Ventura |  | Mission 16kV | 3374583 | 2032306 |  | 2024-10-24 | 24 | NO |  | YES | 2022-05-02 | 2022-05-03 | 2 | 2 | 2023-03-22 | 2022-04-20 | 10 | 10 | -233 |  | 2022-04-20 | 2022-04-20 | 2022-04-30 | 1 | 1 | 8 | 8 | 2022-08-19 | -148 |  | 2023-03-24 | 2023-03-27 | 2023-05-10 | 2023-05-26 | 195 | 195 | 2023-05-30 | 2023-08-25 | 63 | 63 |  | 2023-10-04 | 28 | 28 | 2023-10-04 | 1 | 1 | 2024-01-02 | 2024-01-23 | 2024-01-02 |  | 61 | 61 |  |  |  |  | 2023-12-04 | 2023-12-12 | 2023-12-21 | 42 | 42 | 8 | 8 | 14 | 14 | 2024-02-20 | 94 | 94 | 2024-03-05 | 11 | 11 | 2023-12-12 | 2023-12-12 |  |  |  |  | 94 | 94
1260 | R29 Westar - Rancho Mirage Marketplace - R3 | 36101 1/2 Bob Hope Dr | Rancho Mirage | 92270 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3482677 | 2165456 | 2101271 | 2024-07-31 | 4 | YES | Level 3 | YES | 2023-02-01 | 2023-02-14 | 10 | 10 | 2023-04-19 | 2022-11-22 | 58 | 58 | -103 |  | 2022-11-28 | 2022-11-29 | 2023-02-01 | 4 | 4 | 46 | 46 | 2023-06-22 | 46 | 46 | 2023-06-26 |  | 2023-08-11 | 2023-08-15 | 38 | 38 | 2023-08-16 | 2023-08-24 | 7 | 7 | 2023-09-15 | 2023-10-06 | 31 | 31 | 2023-11-02 | 20 | 20 | 2023-11-14 | 2024-01-10 | 2023-11-14 | 2023-11-20 | 28 | 28 | 62 | 62 | 5 | 5 | 2023-08-30 | 2023-10-11 | 2024-02-05 | -27 |  | 79 | 79 | 108 | 108 | [6 empty] | 2023-10-11 |  | 2024-02-05
1261 | Rancho Santa Margarita - Antonio Pkwy | 22461 Antonio Pkwy EV | Rancho Santa Margarita | 92688 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | Oneill | Empresa 12KV | 3413275 |  |  |  |  | NO |  | YES | 2022-05-23 | 2022-06-06 | 10 | 10 | 2022-05-02 | 2022-05-02 | 25 | 25 | 1 | 1 | 2022-05-02 | 2022-05-23 | 2022-05-23 | 16 | 16 | 1 | 1 | 2022-10-24 | 123 | 123 | 2022-10-28 | 2022-10-31 | 2022-12-15 | 2023-02-10 | 76 | 76 | 2023-02-13
1262 | Eastvale, CA -Ontario Ranch Rd and Hamner Ave | Eastvale, CA - 4910 Hamner Ave | Ontario | 91752 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2022-05-31 |  |  |  | 2022-05-02 | 2022-05-02 |  |  | 1 | 1 | 2022-05-03 | 2022-05-29 | 2022-05-29 | 20 | 20 | 0
1263 | Temecula, CA - 40486 Winchester Rd (Commons at Temecula) | 40490 Winchester Rd | Temecula | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  | Temeck 12kV | 3413791 | 2113416 |  | 2024-01-31 | 16 | YES | Level 2 | NO | 2022-06-03 | 2022-10-26 | 102 | 102 | 2022-05-04 | 2022-05-04 | 123 | 123 | 1 | 1 | 2022-05-09 | 2022-06-01 | 2022-06-01 | 20 | 20 | 1 | 1 | 2022-10-18 | 117 | 117 | 2023-03-30 | 2022-11-18 | 2023-05-11 | 2023-05-15 | 145 | 145 | 2023-05-15 | 2023-07-14 | 43 | 43 | 2023-08-07 | 2023-08-08 | 18 | 18 | 2023-08-15 | 6 | 6 | [10 empty] | 2023-07-18 | 2023-07-31 | 2023-09-22 | -16 |  | 39 | 39 | 48 | 48 | 2023-08-07 | -7 |  | 2023-08-17 | 9 | 9 | [6 empty] | -2 |  | 2023-10-11 | 2023-11-06 | 2023-11-21 | 30 | 30 | 2023-10-20 |  |  | 2023-10-20 | 1 | 1 | [6 empty] | 2023-11-22 | 2023-11-28 | 26 | 26 | 3 | 3 | 2023-11-29 | 2024-02-08 | 49 | 49 | 2024-02-09 | 50 | 50 | 2024-02-09 | 2024-02-15 | 5 | 5 | 447 | 447 | 331 | 331 | 2024
1264 | Nipton, CA - Cima Rd | 65053 Xeno Rd | Nipton | 92364 | San Bernardino County | 9. Complete | 72 - Barstow | Rurals | SBRO | [9 empty] | YES |  |  |  |  | 2022-05-04 | 2022-05-04 |  |  | 1 | 1 | 2022-05-23
1265 | Santa Monica Chase Bank | 2701 Wilshire Blvd | Santa Monica | 90403 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra |  |  | 3325603 | 2044722 | 2113847 | 2023-11-16 | 4 | YES | Level 1 | YES | 2022-05-24 | 2022-06-01 | 6 | 6 | 2023-02-14 | 2022-05-04 | 20 | 20 | -198 |  | 2022-05-05 | 2022-05-22 | 2022-05-22 | 13 | 13 | 0 |  | 2023-02-14 | 1 | 1 | 2023-02-14 | 2022-06-14 | 2022-07-28 | 2023-03-31 | 33 | 33 | 2023-04-07 | 2023-04-10 | 2 | 2 | 2023-04-14 | 2023-04-17 | 6 | 6 | 2023-04-25 | 7 | 7 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | 1 | 1 | 6 | 6 | 1 | 1 | 2023-03-17 | 2023-04-10 | 2023-05-31 | -22 |  | 37 | 37 | 53 | 53 | 2023-04-25 | 1 | 1 | 2023-05-02 | 6 | 6 | 2023-04-10 | 2023-04-10 | 2023-05-31 | 2023-05-31 | 37 | 37 | 7 | 7 | 2023-08-30 | 2023-09-25 | 2023-10-20 | 37 | 37 | 2023-06-28 |  |  | 2023-07-05 | 5 | 5 | [6 empty] | 2023-10-17 | 2023-10-25 | 84 | 84 | 7 | 7 | 2023-10-26 | 2023-12-15 | 35 | 35 | 2023-12-17 | 35 | 35 | 2023-12-17 | 2024-01-12 | 18 | 18 | 213 | 213 | 213 | 213 | 2023
1266 | Santa Clarita Fairfield Inn | 25340 The Old Rd | Santa Clarita | 91381 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | YES | 2022-05-17 | 2022-05-18 | 2 | 2 | 2022-05-03 | 2022-05-03 | 12 | 12 | 1 | 1 | 2022-05-06 | 2022-05-15 | 2022-05-15 | 9 | 9 | 0
1267 | Agoura Hills Homewood Suites by Hilton | 28901 Canwood St | Agoura Hills | 91301 | Los Angeles County | 7. Civil Construction | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | YES | 2022-05-17 | 2022-05-18 | 2 | 2 | 2022-05-04 | 2022-05-04 | 11 | 11 | 1 | 1 | 2022-05-04 | 2022-05-15 | 2022-05-15 | 8 | 8 | 0
1268 | Ridgecrest - S China Lake & French Ave | 154 N China Lake Blvd | Ridgecrest | 93555 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 3343388 | 2021880 |  | 2024-04-30 |  | NO |  | YES | 2022-05-18 | 2022-06-22 | 25 | 25 | 2022-05-04 | 2022-05-04 | 35 | 35 | 1 | 1 | 2022-05-04 | 2022-05-18 | 2022-05-18 | 11 | 11 | 1 | 1 | 2022-07-07 | 45 | 45 | 2022-08-11 | 2022-07-13 | 2022-08-25 | 2022-08-25 | 36 | 36 | 2022-08-25 | 2022-10-10 | 32 | 32 |  | 2022-10-13 | 4 | 4 | 2022-10-13 | 1 | 1 | 2023-01-12 | 2023-01-12 | 2023-01-12 | 2023-01-25 | 63 | 63 | 74 | 74 | 9 | 9 | 2022-10-18 | 2022-11-04 | 2022-11-21 | 4 | 4 | 11 | 11 | 24 | 24 | [6 empty] | 2022-11-04 |  | 2023-01-25 | [10 empty] | 2023-11-28 |  |  | 2023-11-28 | 1 | 1
1269 | Boron, CA- 40716 US-395 (Kramer Junction) | Boron, CA- 40716 US-395 | Boron | 93516 | Kern County | 6. Requirements (permit, easment, etc.) | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-12-01 |  |  |  | YES | 2022-05-05 | 2022-05-12 | 6 | 6 | 2022-05-04 | 2022-05-04 | 7 | 7 | 1 | 1 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 1 | 1 | 1 | 1
1270 | Santa Barbara Chase Bank R3 (old address 1302 E State) | 15 E Victoria St | Santa Barbara | 93101 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3372183 | 2211921 | 2211919 | 2024-07-02 | 6 | YES | Level 3 | YES | 2023-04-17 | 2023-04-19 | 3 | 3 | 2022-05-04 | 2022-05-04 | 243 | 243 | 1 | 1 | 2022-05-06 | 2022-05-19 | 2022-05-19 | 12 | 12 | 1 | 1 | 2023-05-01 | 251 | 251 | 2023-05-02 | 2023-05-02 | 2023-08-18 | 2023-10-16 | 118 | 118 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-11-08 | 2023-12-27 | 50 | 50 | 2023-12-27 | 1 | 1 | 2023-12-27 | 2024-02-01 | 2023-12-27 | 2024-01-04 | 1 | 1 | 55 | 55 | 6 | 6 | 2023-12-26 | 2024-01-11 | 2024-03-12 | -2 |  | 42 | 42 | 53 | 53 | 2024-03-21 | 59 | 59 |  |  |  | 2023-12-27 | 2023-12-27 | 2024-03-12 |  |  |  | 59 | 59
1271 | Loma Linda Chase Bank | 25701 Barton Rd | Loma Linda | 92354 | San Bernardino County | 9. Complete | 31 - Redlands | Desert | SBRO | Timoteo | Nurses 12kV | 3419431 | 2066261 |  |  |  | NO |  | YES | 2022-05-17 | 2022-06-01 | 11 | 11 | 2022-05-04 | 2022-05-04 | 20 | 20 | 1 | 1 | 2022-05-06 | 2022-05-14 | 2022-06-14 | 8 | 8 | 21 | 21 | 2022-11-04 | 130 | 130 | 2022-11-08 | 2022-11-09 | 2022-12-29 | 2023-01-10 | 45 | 45 | 2023-01-10
1272 | Cypress Chase Bank | 10011 Valley View St | Cypress | 90630 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | Marion | Claudia 12kV | 3331247 | 2032239 |  | 2023-03-31 | 4 | YES | Level 2 | NO | 2022-05-16 | 2022-05-23 | 6 | 6 | 2022-05-05 | 2022-05-05 | 13 | 13 | 1 | 1 | 2022-05-06 | 2022-05-13 | 2022-05-13 | 7 | 7 | 1 | 1 | 2022-06-13 | 27 | 27 | 2022-06-21 | 2022-06-21 | 2022-08-05 | 2022-08-04 | 38 | 38 | 2022-08-04 | 2022-08-04 | 1 | 1 | 2022-08-26 | 2022-09-01 | 21 | 21 | 2022-10-11 | 28 | 28 | 2022-10-11 | 2022-10-11 | 2022-10-11 | 2022-10-11 | 28 | 28 | 48 | 48 | 1 | 1 | 2022-09-23 | 2022-10-04 | 2022-10-10 | 16 | 16 | 5 | 5 | 12 | 12 | [6 empty] | 2022-10-04 |  | 2022-10-11 | [5 empty] | 2022-10-25 | 2022-11-16 | 2022-11-16 | 16 | 16 | 2022-09-19 | 2022-10-11 |  | 2022-09-27 | 7 | 7 | 2022-10-21 | 19 | 19 |  |  |  | 2022-11-18 | 2022-11-23 | 47 | 47 | 4 | 4 | 2022-12-05 | 2023-01-17 | 31 | 31 | 2023-01-31 | 41 | 41 | 2023-01-31 | 2023-02-14 | 11 | 11 | 187 | 187 | 161 | 161 | 2023
1273 | Costa Mesa - Placentia Ave | 2150 Placentia Ave | Costa Mesa | 92627 | Orange County | 9. Complete | 33 - Huntington Beach | Orange | Saddleback |  |  | 3321540 | 2039249 |  |  |  | NO |  | YES |  |  |  |  | 2022-05-05 | 2022-05-05 |  |  | 1 | 1 | 2022-05-06 | 2022-05-18 | 2022-05-18 | 10 | 10 | 1 | 1 |  |  |  | 2022-06-06 | 2022-06-06 | 2022-07-21 | 2022-10-05 |  |  | 2022-10-05
1274 | Bellflower -17308 Bellflower | 17308 Bellflower Blvd - EV | Bellflower | 90706 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | Somerset | Larry 12kv | 3375409 | 2056944 |  |  | 8 | NO |  | YES | 2022-06-07 | 2022-06-24 | 14 | 14 | 2022-05-06 | 2022-05-06 | 35 | 35 | 1 | 1 | 2022-05-06 | 2022-05-17 | 2022-06-06 | 8 | 8 | 14 | 14 | 2022-08-26 | 79 | 79 | 2022-11-01 | 2022-11-02 | 2022-12-20 | 2022-12-01 | 66 | 66 | 2022-12-01 | 2022-12-06 | 4 | 4 | 2023-01-03 | 2022-12-16 | 9 | 9 | 2022-12-19 | 2 | 2 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2023-01-10 | 9 | 9 | 26 | 26 | 10 | 10 | 2022-12-15 | 2022-12-28 | 2023-01-26 | -2 |  | 21 | 21 | 30 | 30 | 2023-02-06 | 35 | 35 | 2023-03-29 | 37 | 37 | 2022-12-28 | 2022-12-28 | 2023-01-26 | 2023-03-29 | 64 | 64 | 36 | 36 | [5 empty] | 2023-02-02 | 2023-03-28 |  | 2023-02-13 | 8 | 8 | 2023-04-04 | 36 | 36 |  |  |  | 2023-04-04 | 2023-04-21 | 56 | 56 | 14 | 14 | 2023-05-02 | 2023-05-25 | 18 | 18 | 2023-05-25 | 18 | 18 | 2023-05-26 |  |  |  | 268 | 268 | 190 | 190 | 2023
1275 | Chase Bellflower - Previously 16804 Bellflower Blvd | 9828 Flower St-EV | Bellflower | 90706 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3455079 | 2107432 |  | 2024-09-02 | 6 | YES | Level 2 | NO | 2022-12-22 | 2023-01-04 | 10 | 10 | 2022-05-06 | 2022-05-06 | 168 | 168 | 1 | 1 | 2022-05-06 | 2022-05-17 | 2022-06-06 | 8 | 8 | 14 | 14 | 2022-12-21 | 158 | 158 | 2023-01-18 | 2023-01-20 | 2023-03-17 | 2023-05-19 | 106 | 106 | 2023-06-02 | 2023-06-05 | 2 | 2 | 2023-06-26 | 2023-07-12 | 27 | 27 | 2023-07-13 | 2 | 2 | 2023-07-13 | 2023-07-13 | 2023-07-13 | 2023-07-13 | 2 | 2 | 28 | 28 | 1 | 1 | 2023-06-30 |  | 2023-07-14 | -8 |  |  |  | 10 | 10 | [8 empty] | 2023-07-14
1276 | Whittier - Mulberry Dr | 14212 Mulberry Dr | Whittier | 90606 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-05-06 | 2022-05-06 |  |  | 1 | 1 | 2022-05-10 | 2022-06-13 | 2022-06-13 | 26 | 26 | 1 | 1
1277 | Huntington Beach - Arco Gas Station 21422 | 21422 Brookhurst St | Huntington Beach | 92646 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | Hamilton | Feller 12kv |  |  |  | 2023-04-23 |  |  |  | YES | 2022-07-11 | 2022-08-09 | 22 | 22 | 2022-05-06 | 2022-05-06 | 66 | 66 | 1 | 1 | 2022-05-13 | 2022-05-19 | 2022-06-13 | 10 | 10 | 17 | 17
1278 | Thousand Oaks Janss Marketplace | 275 N Moorpark Rd | Thousand Oaks | 91360 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2026-04-15 | 4 | YES |  | YES | 2023-03-20 | 2023-05-04 | 34 | 34 | 2023-03-20 | 2023-03-08 | 42 | 42 | -9 |  | 2023-03-09 | 2023-03-13 | 2023-03-14 | 4 | 4 | 2 | 2
1279 | Rialto - Riverside Ave | 1276 Riverside Ave | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-09-26 |  | NO |  | NO | 2022-05-17 | 2022-06-03 | 13 | 13 | 2022-05-06 | 2022-05-06 | 20 | 20 | 1 | 1 | 2022-05-09 | 2022-05-14 | 2022-05-14 | 6 | 6 | 0
1281 | Inglewood - W Century Blvd | 5138 W Century Blvd | Inglewood | 90304 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-11-01 |  |  |  | YES |  |  |  |  | 2022-05-09 | 2022-05-09 |  |  | 1 | 1 | 2022-05-05
1282 | Chino, CA - Pine Ave | 7911 Pine Ave | Chino | 91708 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2022-05-31 | 2022-06-01 | 2 | 2 | 2022-05-10 | 2022-05-03 | 21 | 21 | -6 |  | 2022-05-12 | 2022-05-29 | 2022-05-29 | 19 | 19 | 0
1283 | Ontario, CA - Fourth St and N Haven Ave | 951 N Haven Ave | Ontario | 91764 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-05-10 | 2022-05-10 |  |  | 1 | 1 | 2022-05-12 | 2022-05-29 | 2022-05-29 | 14 | 14 | 0
1284 | Huntington Park LA Fitness | 3081 E Slauson Ave | Huntington Park | 90255 | Los Angeles County | 7. Civil Construction | 32 - Compton | Metro West | Alhambra |  |  | 3431971 | 2084287 |  | 2024-09-01 |  | NO |  | YES |  |  |  |  | 2022-05-11 | 2022-05-11 |  |  | 1 | 1 | 2022-05-13 | 2022-05-26 | 2022-06-10 | 12 | 12 | 11 | 11 | 2022-12-01 | 141 | 141 | 2022-12-01 | 2023-03-31 | 2023-01-17 | 2023-01-27 | 41 | 41 | 2023-01-30 | 2023-02-03 | 5 | 5 | 2023-03-07 | 2023-03-10 | 25 | 25 | 2023-03-10 | 1 | 1 | 2023-03-10 | 2023-03-31 | 2023-03-10 | 2023-03-10 | 1 | 1 | 25 | 25 | 1 | 1 | 2023-03-13 | 2023-03-22 | 2023-03-29 | 2 | 2 | 6 | 6 | 13 | 13 | [6 empty] | 2023-03-10 |  | 2023-03-29
1285 | Gardena, CA - 1425 Artesia Blvd | 1425 1/2 Artesia Blvd | Gardena | 90248 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3460770 | 2130078 | 2130077 | 2024-04-10 | 20 | YES | Level 3 | YES | 2023-01-24 | 2023-01-26 | 3 | 3 | 2023-03-13 | 2022-05-11 | 180 | 180 | -211 |  | 2022-05-16 |  | 2022-06-29 |  |  |  |  | 2023-03-13 | 1 | 1 | 2023-03-22 | 2023-03-22 | 2023-05-03 | 2023-06-21 | 72 | 72 | 2023-06-21 | 2023-07-12 | 15 | 15 | 2023-08-18 | 2023-09-28 | 56 | 56 | 2023-09-29 | 2 | 2 | 2023-10-10 |  | 2023-10-10 | 2023-10-12 | 9 | 9 | 66 | 66 | 3 | 3 | 2023-10-02 | 2023-10-16 | 2024-01-23 | 3 | 3 | 67 | 67 | 77 | 77 | 2023-10-03 | 3 | 3 | 2023-11-13 | 30 | 30 | 2023-10-10 | 2023-10-03 | 2024-01-23 | 2024-01-23 | 76 | 76 | 4 | 4 | 2024-01-31 | 2024-02-28 |  |  |  | 2023-11-16 |  |  | 2024-02-23 | 66 | 66
1286 | Cerritos - Los Cerritos Center Phase 2 | 239 Los Cerritos Center | Cerritos | 90703 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  |  | 3321239 | 2006437 |  |  | 8 |  |  | YES | 2022-05-12 | 2022-05-26 | 11 | 11 | 2022-05-09 | 2022-05-09 | 14 | 14 | 1 | 1 | 2022-05-12 | 2022-06-06 | 2022-06-06 | 20 | 20 | 1 | 1 |  |  |  | 2022-06-06 | 2022-06-07 | 2022-07-21 | [11 empty] | 2022-07-18 |  |  | 2022-12-22 | 2023-01-10 | 2022-12-22 | 2023-01-30 |  |  |  |  | 27 | 27 | [46 empty] | 2023-01-13 |  |  |  | 2023-02-24 | 29 | 29 | 2023-02-24 |  |  |  | 202 | 202 |  |  | 2023
1287 | Ontario - Concours & N Haven - EV | 850 N Center Ave | Ontario | 91764 | San Bernardino County | 4. Preliminary Design | 34 - Ontario | Metro East | Pomona |  |  | 3412653 | 2071484 | [5 empty] | NO | 2022-06-07 | 2022-07-05 | 20 | 20 | 2022-05-12 | 2022-05-12 | 37 | 37 | 1 | 1 | 2022-05-13 | 2022-05-29 | 2022-05-29 | 12 | 12 | 0 |  | 2022-10-24 | 115 | 115 | 2022-10-27 |  | 2022-12-14 | 2022-12-15 | 36 | 36 | 2022-12-15
1288 | Torrance - W 190th St | 1849 W 190th St | Torrance | 90504 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | La Fresa | Artisano 16kV | 3382552 |  |  |  |  | NO |  | YES | 2022-06-10 | 2022-06-13 | 2 | 2 | 2022-05-12 | 2022-05-12 | 22 | 22 | 1 | 1 | 2022-05-13 | 2022-06-10 | 2022-06-10 | 21 | 21 | 1 | 1 | 2022-10-31 | 120 | 120 | 2022-10-31 |  | 2023-09-15 | 2024-01-31 | 315 | 315 | 2024-01-31
1289 | Costa Mesa - Harbor Blvd | 2640 Harbor Blvd EV | Costa Mesa | 92626 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3379907 | 2043633 |  |  | 40 | NO |  | NO | 2022-06-07 | 2022-06-21 | 11 | 11 | 2022-05-12 | 2022-05-12 | 28 | 28 | 1 | 1 | 2022-05-13 | 2022-06-01 | 2022-06-01 | 14 | 14 | 1 | 1 | 2022-09-06 | 81 | 81 | 2024-01-18 | 2024-01-22 | 2024-03-06 | 2023-04-12 | 152 | 152 | 2023-04-12 |  |  |  |  | 2023-08-31 |  |  | 2023-08-31 | 1 | 1 | 2023-09-19 |  | 2023-09-19 |  | 13 | 13
1290 | Oxnard - Ventura Blvd | 1811 Ventura Blvd | Oxnard | 93036 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  |  | 3372436 | 2031067 | [5 empty] | YES |  |  |  |  | 2022-05-18 | 2022-05-18 |  |  | 1 | 1 | 2022-05-23 | [6 empty] | 2022-08-22 | 67 | 67 | 2022-08-24 |  | 2022-10-10
1291 | La Verne Gateway Pointe Shopping Center | 1275 Foothill Blvd | La Verne | 91750 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3468630 |  |  |  |  | NO |  | YES | 2023-02-07 |  |  |  | 2022-05-18 | 2022-05-18 |  |  | 1 | 1 | 2022-05-23 | [6 empty] | 2023-01-31 | 178 | 178 | 2023-02-07 |  | 2023-03-24
1292 | Calabasas Creekside Village Shopping Center | 26527 Agoura Rd | Calabasas | 91302 | Los Angeles County | 9. Complete | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO | 2022-06-02 |  |  |  | 2022-05-18 | 2022-05-18 |  |  | 1 | 1 | 2022-05-19 | 2022-05-28 | 2022-05-28 | 8 | 8 | 0
1293 | Corona Kohls- Phase 2 | 460 Hidden Valley Parkway | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3330083 | 2022679 |  |  | 1 | YES | Level 1 | NO |  |  |  |  | 2022-05-17 | 2022-05-17 |  |  | 1 | 1 | 2022-05-17 | 2022-05-31 | 2022-06-17 | 10 | 10 | 14 | 14 | 2022-06-17 | 23 | 23 | 2022-06-17 | 2022-06-27 | 2022-08-03 | 2022-08-07 | 35 | 35 | 2022-08-08 | 2022-08-11 | 4 | 4 | 2022-08-31 | 2022-08-31 | 15 | 15 | 2022-08-31 | 1 | 1 | [56 empty] | 2022-10-31 | 2022-12-09 | 27 | 27 | 2022-12-09 | 27 | 27 | 2022-12-09 |  |  |  | 143 | 143 | 121 | 121 | 2022
1294 | Long Beach - Barbara London Dr | 4235 Barbara London Dr | Long Beach | 90806 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-05-31 |  |  |  | YES |  |  |  |  | 2022-05-19 | 2022-05-19 |  |  | 1 | 1 | 2022-05-23
1295 | Foothill Ranch, CA - 26762 Portola Pkwy (Target) | 26762 Portola Pkwy | Foothill Ranch | 92610 | Orange County | 9. Complete | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-05-24 | 2022-05-24 |  |  | 1 | 1 | 2022-05-27
1296 | West Covina, CA- 1414 S Azusa Ave | 1414 S Azusa Ave, Unit EV | West Covina | 91791 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  | Amar 12kv | 3423962 | 2068981 |  | 2023-09-01 | 20 | YES | Level 3 | YES | 2022-05-16 | 2022-05-24 | 7 | 7 | 2022-05-05 | 2022-05-05 | 14 | 14 | 1 | 1 | 2022-05-06 | 2022-05-14 | 2022-05-14 | 7 | 7 | 0 |  | 2022-10-27 | 123 | 123 | 2022-11-16 | 2022-11-22 | 2023-01-09 | 2023-01-10 | 51 | 51 | 2023-01-12 | 2023-01-17 | 3 | 3 | 2023-02-07 | [17 empty] | 2023-03-07 | 2023-03-20 |  |  | 10 | 10 |  |  | 2023-01-17 |  |  | 2023-08-02 | 139 | 139 | [8 empty] | 2023-03-28 | 2023-05-01 | 2023-06-12 | 54 | 54 |  |  |  | 2023-04-18 | [9 empty] | 2023-06-06 |  |  |  |  | 2023-06-20 | 2023-08-25 | 48 | 48 | 2023-08-30 | 51 | 51 | 2023-08-30 |  |  |  | 335 | 335 | 213 | 213 | 2023
1297 | Lake Elsinore - Dexter Ave | 18550 Dexter Ave | Lake Elsinore | 92532 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | Elsinore | Collier 12kv | 3363557 |  |  | 2023-04-22 |  | NO |  | NO |  | 2022-08-01 |  |  | 2022-05-25 | 2022-05-25 | 47 | 47 | 1 | 1 | 2022-05-31 | [6 empty] | 2022-08-09 | 53 | 53 | 2022-08-11 | 2022-08-11 | 2022-11-18
1298 | Rancho Santa Margarita Ralphs | 31481 Santa Margarita Pkwy | Rancho Santa Margarita | 92688 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3411022 |  |  |  | 2 |  |  | NO |  |  |  |  | 2022-05-25 | 2022-05-25 |  |  | 1 | 1 | 2022-06-01 | [6 empty] | 2022-10-10 | 96 | 96 |  |  | 2022-12-12
1299 | Indio - Highway 111 | 80925 Highway 111 | Indio | 92201 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-05-25 | 2022-05-25 |  |  | 1 | 1 | 2022-06-02
1300 | Walgreens | 401 N Azusa Ave | Covina | 91722 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-08-19 | 2022-08-23 |  |  | 3 | 3 | 2022-08-25 | 2022-09-06 | 2022-10-10 | 10 | 10 | 25 | 25
1301 | Torrance, CA - 22217 Palos Verdes Blvd | 22217 Palos Verdes Blvd | Torrance | 90505 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | NO |  |  |  |  | 2022-05-31 | 2022-05-31 |  |  | 1 | 1 | 2022-06-01
1302 | Newport Beach - 1520 West Coast Highway | 1520 West Coast Highway | Newport Beach | 92663 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-05-24 | 2022-05-24 |  |  | 1 | 1 | 2022-06-01
1303 | R29 Montebello, CA - 855 N Wilcox Ave | 855UT1, 855UT2 N Wilcox Ave | Montebello | 90640 | Los Angeles County | 4. Preliminary Design | 22 - Montebello | Metro East | Pomona |  | Cerveza 16kV | 3445683 | 2209777 | 2209778 | 2024-06-07 | 76 | YES | Level 3 | YES |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-02 | [9 empty] | 2023-10-30 | 2023-11-06 | 2023-12-14 | 2023-12-14 |  |  | 2023-12-14 | 2023-12-18 | 3 | 3 | 2024-02-02 | 2024-02-08 | 36 | 36 | 2024-02-08 | 1 | 1 | 2024-02-16 |  | 2024-02-08 |  | 1 | 1 |  |  |  |  | 2024-02-21 | 2024-03-05 |  | 9 | 9 | [10 empty] | 2024-02-08
1304 | Ontario Discount Tire Shop | 4583 Mills Circle EV | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3663391 |  |  | 2024-12-27 | 4 | YES | Level 1 | YES | 2023-11-08 | 2024-01-11 | 43 | 43 | 2023-06-27 | 2023-06-27 | 137 | 137 | 1 | 1 | 2023-06-29 | 2023-07-06 | 2023-07-08 | 7 | 7 | 2 | 2 | 2023-11-08 | 95 | 95 | 2024-01-24 | 2024-01-23 | 2024-03-15 | 2024-03-15 | 87 | 87 | 2024-03-15
1305 | Upland, CA - 161 E Foothill Blvd | 161 E Foothill Blvd | Upland | 91786 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona |  | Guasti 12kV | [7 empty] | YES |  | 2022-07-19 |  |  | 2022-06-02 | 2022-06-02 | 33 | 33 | 1 | 1 | 2022-06-06 |  | 2022-09-14
1306 | Redlands, CA -10000 Alabama St | 27190 W Lugonia St | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3482591 | 2198140 | 2198141 | 2024-06-13 | 20 | YES | Level 3 | NO | 2023-02-06 | 2023-02-28 | 16 | 16 | 2022-06-02 | 2022-06-02 | 187 | 187 | 1 | 1 | 2022-06-06 |  | 2022-07-10 |  |  |  |  | 2023-03-15 | 198 | 198 | 2023-03-15 | 2023-03-15 | 2023-08-29 | 2023-09-15 | 130 | 130 | 2023-09-15 | 2023-09-26 | 8 | 8 | 2023-10-17 | 2023-11-21 | 41 | 41 | 2023-11-22 | 2 | 2 | 2024-03-26 |  | 2024-03-26 |  | 85 | 85 |  |  |  |  | 2023-12-15 | 2024-01-07 |  | 17 | 17 |  |  |  |  | 2023-12-19 | 18 | 18 | 2024-01-18 | 20 | 20 | 2024-01-07 | 2023-12-19 |  |  |  |  | 19 | 19
1307 | Orange - 490 N Tustin Street | 490 N Tustin St | Orange | 92867 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback |  |  | 3359411 | 2058533 |  |  |  | YES | Level 1 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | [6 empty] | 2022-08-02 | 44 | 44 | 2022-08-04 | 2022-08-04 | 2022-09-19 | 2022-11-16 | 75 | 75 | 2022-11-16 | 2022-11-22 | 5 | 5 | 2022-12-15 | 2022-12-28 | 25 | 25 | 2023-01-03 | 5 | 5 | [10 empty] | 2022-12-08 | 2022-12-19 |  | -15
1308 | Palmdale - 739 W Avenue P | 739 W Avenue P | Palmdale | 93551 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-20 | 2022-06-24 | 14 | 14 | 5 | 5
1309 | Corona - 1134 W 6th St | 1134 W 6th St | Corona | 92882 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-22 | 2022-07-24 | 16 | 16 | 22 | 22
1310 | Riverside - 1420 University Ave | 1420 University Ave | Riverside | 92507 | Riverside County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1
1311 | Ontario - 1885 E 4th St | 1885 E 4th St | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3360094 | 2036975 |  | 2022-08-05 |  | YES | Level 1 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-27 | 2022-07-26 | 19 | 19 | 21 | 21 | 2022-08-02 | 44 | 44 | 2022-08-05 | 2022-08-12 | 2022-09-26 | 2022-09-15 | 32 | 32 | 2022-09-15 | 2022-11-28 | 50 | 50 | 2022-12-19 | 2022-12-26 | 21 | 21 | 2022-12-27 | 2 | 2 | [10 empty] | 2023-01-05 | 2023-01-23 |  | 9 | 9
1312 | Ontario - 2201 S Mountain Ave | 2201 S Mountain Ave | Ontario | 91762 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3360147 | 2039089 |  |  |  | YES | Level 1 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-27 | 2022-08-03 | 19 | 19 | 27 | 27 | 2022-08-02 | 44 | 44 | 2022-08-05 | 2022-08-12 | 2022-09-28 | 2022-09-19 | 34 | 34 | 2022-09-19 | 2022-11-28 | 48 | 48 | 2022-12-19 | 2022-12-21 | 18 | 18 | 2022-12-22 | 2 | 2 | [10 empty] | 2023-01-05 | 2023-01-23 |  | 12 | 12
1313 | Ontario - 2544 S Archibald Ave | 2544 S Archibald Ave | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3360040 | 2038532 |  | 2023-08-05 |  | YES | Level 2 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-27 | 2022-07-27 | 19 | 19 | 22 | 22 | 2022-08-02 | 44 | 44 | 2022-08-05 | 2022-08-12 | 2022-09-20 | 2022-09-18 | 33 | 33 | 2022-09-19 | 2022-11-28 | 48 | 48 | 2022-12-19 | 2022-12-23 | 20 | 20 | 2022-12-27 | 3 | 3 | [10 empty] | 2023-01-05 | 2023-01-24 |  | 10 | 10
1314 | Riverside - 2560 N Perris Blvd | 2560 N Perris Blvd | Riverside | 92571 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1
1315 | Rancho Cucamonga- 9709 Baseline Rd | 9709 Baseline Rd. | Rancho Cucamonga | 91730 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3362592 | 2057206 | 2057203 |  |  | YES | Level 1 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-28 | 2022-08-09 | 20 | 20 | 30 | 30 | 2022-08-02 | 44 | 44 | 2022-08-10 | 2022-08-12 | 2022-09-29 | 2022-11-15 | 74 | 74 | 2022-11-15 | 2022-11-22 | 6 | 6 | 2022-12-15 | 2022-12-08 | 11 | 11 | 2022-12-08 | 1 | 1 | [10 empty] | 2022-11-10 | 2022-11-28 |  | -18
1316 | Riverside - 10995 Magnolia Ave | 10995 Magnolia Ave | Riverside | 92505 | Riverside County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1
1317 | Rancho Cucamonga - 12789 Foothill Blvd | 12789 Foothill Blvd | Rancho Cucamonga | 91739 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3361034 | 2047840 | 2048035 |  |  | YES | Level 2 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-28 | 2022-08-07 | 20 | 20 | 28 | 28 | 2022-08-02 | 44 | 44 | 2022-08-08 | 2022-08-12 | 2022-09-27 | 2022-10-13 | 52 | 52 | 2022-10-17 | 2022-11-28 | 28 | 28 | 2022-12-19
1318 | San Fernando - 14511 Chatsworth Dr | 14511 Chatsworth Dr | San Fernando | 91340 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1
1319 | Fontana - 16863 Valley Blvd | 16863 Valley Blvd | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3362783 | 2023864 | 2034869 |  |  | YES | Level 2 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-10 | 2022-06-28 | 2022-08-09 | 20 | 20 | 30 | 30 | 2022-08-09 | 49 | 49 | 2022-08-10 | [35 empty] | 2022-09-07 |  |  | 2022-11-03 | 42 | 42
1320 | Fontana - 17111 W Foothill Blvd | 17111 W Foothill Blvd | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3361086 | 2033551 | 2034821 |  |  | YES | Level 2 | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-28 | 2022-08-07 | 20 | 20 | 28 | 28 | 2022-08-02 | 44 | 44 | 2022-08-08 | 2022-08-12 | 2022-09-27 | 2022-09-27 | 40 | 40 | 2022-09-27
1321 | Lake Forest - 23651 Rockfield Blvd | 23651 Rockfield Blvd | Lake Forest | 92630 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09
1322 | Palmdale - 37910 47th St E | 37910 47th St E | Palmdale | 93552 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-20 | 2022-06-22 | 14 | 14 | 3 | 3
1323 | Ontario - 859 N Mountain Ave | 859 N Mountain Ave | Ontario | 91762 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3359651 | 2056159 |  |  |  | YES | Level 2 | YES |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-27 | 2022-07-26 | 19 | 19 | 21 | 21 | 2022-08-03 | 45 | 45 | 2022-08-04 | 2022-08-12 | 2022-09-28 | 2022-09-22 | 36 | 36 | 2022-09-22 | 2022-10-26 | 25 | 25 |  | 2022-11-30 | 23 | 23 | 2022-11-30 | 1 | 1 | [10 empty] | 2022-11-29 | 2022-12-06 |  | -2 | [5 empty] | 2023-01-09 | 29 | 29 | 2023-01-25 | 12 | 12 | [6 empty] | 29 | 29
1324 | La Canada Flintridge - 2151 Foothill Blvd | 2151 Foothill Blvd | La Canada Flintridge | 91011 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-14 | 2022-06-24 | 10 | 10 | 9 | 9
1325 | Orange - 468 S Main St | 468 S Main St | Orange | 92868 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [14 empty] | 2022-06-01 | 2022-06-01 |  |  | 1 | 1 | 2022-06-09 | 2022-06-22 | 2022-07-13 | 16 | 16 | 15 | 15
1326 | Corona - Temescal Canyon Rd | 4688 Temescal Canyon Rd | Corona | 92883 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-06-07 | 2022-06-07 |  |  | 1 | 1 | 2022-06-09 | 2022-06-22 |  | 12 | 12
1327 | Santa Monica - 1415 12th St | 1415 12th St | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Santa Monica | Beachcomber 16kV |  |  |  |  | 27 |  |  | YES | 2022-06-15 | 2022-07-01 | 13 | 13 | 2022-06-07 | 2022-06-07 | 19 | 19 | 1 | 1 | 2022-06-08 | 2022-06-14 | 2022-06-14 | 6 | 6 | 1 | 1
1328 | Santa Monica - 1230 Santa Monica Blvd | 1230 Santa Monica Blvd | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Santa Monica | Beachcomber 16kV |  |  |  |  | 27 |  |  | true | 2022-06-15 | 2022-07-01 | 13 | 13 | 2022-06-07 | 2022-06-07 | 19 | 19 | 1 | 1 | 2022-06-08 | 2022-06-15 | 2022-06-15 | 7 | 7 | 1 | 1
1329 | Arcadia, CA - 169 E Foothill Blvd | 169 E Foothill Blvd, Arcadia, CA 91006 | Arcadia | 91006 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-08 | 2022-06-08 |  |  | 1 | 1 | 2022-06-09
1330 | Pomona - 2090 S Garey Ave | 2090 S Garey Ave | Pomona | 91766 | Los Angeles County | 4. Preliminary Design | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2022-07-12 16:50 |  |  |  | 2022-06-08 | 2022-06-08 |  |  | 1 | 1 | 2022-06-16
1331 | Chino, CA - 12170 Central Ave | 12146 Central Ave | Chino | 91710 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  | Mosebrook 12kV | 3672540 | 2224717 |  | 2024-11-22 |  | YES |  | YES | 2022-07-20 | 2022-07-28 | 7 | 7 | 2023-04-21 | 2023-04-21 | -186 |  | 1 | 1 | 2023-05-08 |  | 2023-05-22 |  |  |  |  | 2024-02-02 | 198 | 198 | 2024-02-02 |  | 2024-03-25
1332 | Cathedral City, CA - 68575 Aliso Rd | 68575 Aliso Rd | Cathedral City | 92234 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-06-07 | 2022-06-07 |  |  | 1 | 1 | 2022-06-09
1333 | Torrance Crenshaw Blvd | 24329 Crenshaw Blvd | Torrance | 90505 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3348780 | [6 empty] | false |  |  |  |  | 2022-06-08 | 2022-06-08 |  |  | 1 | 1 | 2022-06-09 | [6 empty] | 2022-07-12 | 24 | 24 | 2022-07-19 | 2022-07-21 | 2022-08-31
1334 | Rolling Hills Estates - Peninsula Center | 50 Peninsula Center | Rolling Hills Estates | 90274 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-06-08 | 2022-06-08 |  |  | 1 | 1 | 2022-06-09
1335 | Moreno Valley, CA - 12880 Day St | 12884 Day St | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  | Brutte 12kV |  |  |  |  | 16 | YES | Level 3 | YES | 2023-05-26 | 2023-07-17 | 35 | 35 | 2023-05-26 | 2023-05-31 | 33 | 33 | 3 | 3 | 2023-05-31 | 2023-06-15 |  | 12 | 12
1336 | McKinley Crossroads | 284 Dupont St | Corona | 92879 | Riverside County | 8. Electrical Construction | 34 - Ontario | Metro East | Pomona | Chase | Weirick 12kV |  |  |  | 2023-05-09 |  |  |  | YES | 2022-07-28 | 2022-08-05 | 7 | 7 | 2022-06-10 | 2022-06-10 | 40 | 40 | 1 | 1 | 2022-06-13 | 2022-06-22 | 2022-07-24 | 9 | 9 | 22 | 22
1337 | El Monte, CA - 3828 Peck Rd | 3818 Peck Rd P | El Monte | 91732 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  | Gardea 16kV | 3438996 | 2128686 |  | 2024-02-20 | 20 | NO |  | YES |  |  |  |  | 2023-12-13 | 2023-12-13 |  |  | 1 | 1 | 2023-12-21 |  | 2023-12-14 |  |  |  |  | 2022-12-14 | -254 |  | 2022-12-14 | 2023-02-02 | 2023-06-09 | 2023-06-07 | 123 | 123 | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-07-05 | 2023-08-03 | 37 | 37 | 2023-08-03 | 1 | 1 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2024-01-09 | 93 | 93 | 145 | 145 | 17 | 17 |  | 2023-09-14 | 2023-10-02 |  |  | 13 | 13 |  |  | 2024-01-23 | 118 | 118 | 2024-02-27 | 25 | 25 | 2023-09-14 | 2023-09-14 | 2024-01-09 | 2024-02-27 | 113 | 113 | 118 | 118 |  | 2023-11-13 | 2024-01-10 |  |  | 2023-10-30 |  |  | 2023-11-06 | 6 | 6 | [6 empty] | 2023-12-21 | 2024-01-11 | 50 | 50 | 14 | 14 | 2024-01-30
1338 | El Monte, CA - 10683 Valley Blvd | 10683 Valley Blvd | El Monte | 91731 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  | Velma 16kV | [7 empty] | NO |  | 2022-08-01 |  |  | 2022-06-15 | 2022-06-15 | 33 | 33 | 1 | 1
1341 | Lancaster - Fern Avenue | 44933 1/2 Fern Avenue | Lancaster | 93534 | Los Angeles County | 3. Active | 36 - Antelope Valley | North Valley | Ventura |  |  | 3436773 | 2081428 |  |  |  | YES | Level 1 | NO |  |  |  |  | 2022-06-14 | 2022-06-14 |  |  | 1 | 1 | 2022-06-14 | 2022-06-25 | 2022-06-25 | 9 | 9 | 0 |  |  |  |  | 2022-12-12 | 2022-12-12 | 2023-01-30 | 2023-01-30 |  |  | 2023-01-30 | 2023-02-02 | 4 | 4 | 2023-02-23 | [17 empty] | 2023-03-09 | [7 empty] | 2023-02-02
1342 | Gardena Target Phase 3 | 2169 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra |  |  | 3392155 |  |  |  | 1 | NO |  | YES |  |  |  |  | 2022-06-15 | 2022-06-15 |  |  | 1 | 1 | 2022-08-29 |  | 2022-09-19 | [7 empty] | 2022-09-30 | 2022-10-03 | 2022-11-15
1343 | Los Angeles - Bank of America Expansion (4142 S. Centinela) | 12316 W Washington Blvd | Los Angeles | 90066 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Culver | Mar Vista | 3340446 | 2018082 |  |  | 1 | NO | Level 1 | NO |  | 2022-07-05 |  |  | 2022-06-16 | 2022-06-16 | 13 | 13 | 1 | 1 | 2022-06-16 |  | 2022-06-25 | [7 empty] | 2022-07-06 | 2022-07-07 | 2022-08-19 | [8 empty] | 2022-08-10 |  |  | 2022-08-10 | 1 | 1 | 2022-09-16 | 2022-10-13 | [36 empty] | 2023-02-02 | [17 empty] | 2023-06-13 | 2023-09-22 | 72 | 72 | 2023-09-22 | 72 | 72 | 2023-09-22 | 2023-10-10 | 13 | 13 | 322 | 322 |  |  | 2023
1344 | Moreno Valley - Sunnymead Blvd | 23010 Sunnymead Blvd | Moreno Valley | 92553 | Riverside County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES |  |  |  |  | 2022-06-21 | 2022-06-21 |  |  | 1 | 1 | 2022-06-22 | 2022-07-12 | 2022-08-07 | 15 | 15 | 19 | 19
1345 | Irvine Cypress Village Phase 2 | 14001 Jeffrey Rd | Irvine | 92620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3348124 | 2051633 |  | 2024-05-24 | 3 | NO | Level 1 | YES | 2022-08-12 | 2022-10-12 | 43 | 43 | 2022-06-15 | 2022-06-15 | 84 | 84 | 1 | 1 | 2022-06-16 |  | 2022-07-15 | [7 empty] | 2022-07-18 |  | 2022-08-31 | 2022-10-19 |  |  | 2022-10-19 | 2022-11-01 | 10 | 10 | 2022-11-30 |  |  |  | 2023-02-28 |  |  | 2023-02-28 | 2023-02-28 | 2023-02-28
1346 | Walmart Foothill Ranch Phase 2 | 26502 Towne Centre Dr | Foothill Ranch | 92610 | Orange County | 6. Requirements (permit, easment, etc.) | 43 - Saddleback | Orange | Saddleback | Futuro 12KV | Viejo | 3347896 | 203059 |  |  | 3 |  |  | YES | 2022-07-15 | 2022-08-12 | 21 | 21 | 2022-06-15 | 2022-06-15 | 42 | 42 | 1 | 1 | 2022-06-16 |  | 2022-07-15 | [7 empty] | 2022-07-18 |  | 2022-08-30 | 2022-09-19 |  |  | 2022-09-19 | [7 empty] | 2022-10-14
1347 | Diamond Bar Target Phase 3 | 747 Grand Ave | Diamond Bar | 91765 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3347403 | 2032750 |  | 2025-01-01 | 3 | NO | Level 1 | YES |  | 2022-07-15 |  |  | 2022-06-15 | 2022-06-15 | 22 | 22 | 1 | 1 | 2022-06-16 | 2022-06-21 | 2022-07-06 | 5 | 5 | 11 | 11 | [5 empty] | 2022-09-07 | 2022-09-07 |  |  | 2022-09-08 | 2023-01-03 | 81 | 81 | 2023-01-27 | 2023-02-02 | 22 | 22 | 2023-02-16 | 11 | 11 | 2023-02-16 | 2023-02-16 | 2023-02-16 |  | 11 | 11
1348 | Santa Clarita Riverview Plaza | 26861 Sierra Hwy | Santa Clarita | 91321 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  | 2022-07-06 |  |  | 2022-06-22 | 2022-06-22 | 10 | 10 | 1 | 1 | 2022-06-22 | 2022-07-01 | 2022-07-01 | 8 | 8 | 1 | 1
1349 | Stevenson Ranch - Pico Canyon Rd | 24712 Pico Canyon Rd | Stevenson Ranch | 91381 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 59 - Valencia | North Valley | Ventura |  |  | 3438157 |  |  |  |  | YES | Level 2 | YES |  |  |  |  | 2022-06-21 | 2022-06-21 |  |  | 1 | 1 | 2022-06-21 | 2022-06-30 | 2022-07-01 | 8 | 8 | 2 | 2 | 2022-12-13 | 121 | 121 | 2022-12-13 | 2022-12-14 | 2023-01-13
1350 | Upland, CA - W Arrow Ave | 2450 Arrow Route, Upland, CA 91786 | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3416003 | 2136042 | 2079795 | 2024-05-01 |  | YES | Level 3 | YES | 2023-03-10 |  |  |  | 2023-03-22 | 2022-06-20 |  |  | -191 |  | 2022-06-20 |  | 2022-07-15 |  |  |  |  | 2023-03-22 | 1 | 1 | 2023-03-23 |  | 2023-05-06 | 2023-05-26 | 48 | 48 | 2023-05-30 | 2023-06-26 | 20 | 20 | 2023-08-02 | 2023-08-16 | 37 | 37 | 2023-08-16 | 1 | 1 | 2023-10-18 | 2023-10-18 | 2023-10-18 | 2023-10-23 | 45 | 45 | 84 | 84 | 4 | 4 | 2023-08-24 | 2023-09-05 |  | 7 | 7 |  |  |  |  | 2023-10-25 | 50 | 50 | 2023-12-05 | 28 | 28 | 2023-09-05 | 2023-09-05 |  |  |  |  | 50 | 50 | 2023-12-06 |  |  |  |  | 2023-12-04
1351 | Westminster, CA - 13100 Goldenwest St | 13100 Goldenwest St | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  | Apache 12kV | [7 empty] | NO | 2022-07-15 16:00 | 2022-08-02 | 13 | 13 | 2022-06-23 | 2022-06-23 | 28 | 28 | 1 | 1 | 2022-06-27 |  | 2022-07-15
1352 | Chino - Central Ave | 12382 Central Ave | Chino | 91710 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22 | 2022-07-11 | 2022-08-02 | 13 | 13 | 17 | 17
1353 | Yorba Linda - Old Canal Rd | 22300 Old Canal Rd | Yorba Linda | 92887 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22 | 2022-07-11 | 2022-07-21 | 13 | 13 | 9 | 9
1354 | Long Beach - 525 E Seaside Way | 525 E Seaside Way | Long Beach | 90802 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22
1355 | Arcadia, CA - 16 Live Oak Ave | 16 Live Oak Ave, Arcadia, CA 91006 | Arcadia | 91006 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  | La Porte 16kV | [7 empty] | NO | 2022-08-01 | 2022-08-18 | 14 | 14 | 2022-06-23 | 2022-06-23 | 40 | 40 | 1 | 1 | 2022-06-23 | 2022-07-31 | 2022-07-31 | 26 | 26 | 0
1356 | Hemet - 43466 E Florida Ave | 43466 E Florida Ave | Hemet | 92544 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | YES |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22 | 2022-07-12 | 2022-08-24 | 14 | 14 | 32 | 32
1357 | Cabazon, CA - Expansion Phase 2 | 48400 Seminole Dr | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  | Stores 12kV | [5 empty] | NO |  | NO | 2022-08-29 | 2022-09-12 | 10 | 10 | 2022-06-15 | 2022-06-16 | 61 | 61 | 2 | 2 | 2022-06-21
1358 | San Jacinto - 785 N Ramona Blvd | 785 N Ramona Blvd | San Jacinto | 92583 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-21 | 2022-06-21 |  |  | 1 | 1 | 2022-06-22 | 2022-07-12 | 2022-08-14 | 15 | 15 | 24 | 24
1359 | Moreno Valley - 24936 Elder Ave | 24936 Elder Ave | Moreno Valley | 92557 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-21 | 2022-06-21 |  |  | 1 | 1 | 2022-06-22 | 2022-07-12 | 2022-08-07 | 15 | 15 | 19 | 19
1360 | Corona - 2193 Sampson Ave | 2193 Sampson Ave | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-21 | 2022-06-21 |  |  | 1 | 1 | 2022-06-22 | 2022-07-11 | 2022-08-07 | 14 | 14 | 20 | 20
1361 | Eastvale - 12486 Limonite Ave | 12486 Limonite Ave | Eastvale | 91752 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22 | 2022-07-11 | 2022-08-07 | 13 | 13 | 20 | 20
1362 | Riverside - 6970 Mission Blvd | 6970 Mission Blvd | Riverside | 92509 | Riverside County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-06-22 | 2022-06-22 |  |  | 1 | 1 | 2022-06-22 | 2022-07-11 | 2022-08-03 | 13 | 13 | 18 | 18
1363 | Tustin, 662 1/2 E 1st St | 662 1/2 E 1st St | Tustin | 92780 | Orange County | 6. Requirements (permit, easment, etc.) | 29 - Santa Ana | Orange | Saddleback |  |  | 3335650 | 2020684 |  |  | 16 | NO |  | YES |  | 2022-03-23 |  |  | 2022-06-23 | 2022-06-23 | -66 |  | 1 | 1 | [10 empty] | 2022-06-27 | 2022-06-27 | 2022-08-12 |  |  |  | 2023-02-08 | 2023-02-23 | 11 | 11 |  |  |  |  | 2023-03-08 |  |  | 2023-03-31 |  | 2023-03-31 | [8 empty] | 2023-04-04 | [13 empty] | 2023-03-31
1364 | Santa Monica - 1222 Broadway | 1222 Broadway | Santa Monica | 90404 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra | Marine | Marshall 16kV | 3395214 | 2051525 | 2045664 | 2024-05-13 | 32 | YES | Level 3 | YES | 2022-05-17 | 2022-05-19 | 3 | 3 | 2022-05-05 | 2022-05-05 | 11 | 11 | 1 | 1 |  |  | 2022-05-12 |  |  |  |  | 2022-05-15 | 7 | 7 | 2023-01-26 |  |  | 2023-02-06 | 184 | 184 | 2023-02-06 | 2023-07-17 | 113 | 113 | 2023-08-04 | 2023-08-04 | 15 | 15 | 2023-08-07 | 2 | 2 | 2023-09-01 | 2023-10-13 | 2023-09-01 | 2023-10-13 | 21 | 21 | 64 | 64 | 30 | 30 | 2023-07-25 | 2023-08-15 | 2023-08-24 | -9 |  | 8 | 8 | 23 | 23 | 2023-08-09 | 3 | 3 |  |  |  | 2023-08-15 | 2023-08-09 | 2023-10-13 |  |  |  | 4 | 4 | 2023-11-02 |  |  |  |  | 2023-10-09 |  |  | 2023-10-17 | 7 | 7
1365 | Santa Monica - 1310 Broadway | 1310 Broadway | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Marine | Marshall 16kV | 3395440 | 2051527 | 2046071 | 2024-06-01 | 32 | YES | Level 3 | NO | 2022-05-17 | 2022-05-19 | 3 | 3 | 2022-05-05 | 2022-05-05 | 11 | 11 | 1 | 1 |  |  | 2022-05-12 | [7 empty] | 2023-01-26 |  |  | 2023-02-10 |  |  | 2023-02-10 | 2023-07-17 | 109 | 109 | 2023-08-04 | 2023-08-04 | 15 | 15 | 2023-08-07 | 2 | 2 | 2023-09-01 | 2023-12-27 | 2023-09-01 | 2023-10-13 | 21 | 21 | 64 | 64 | 30 | 30 | 2023-08-02 | 2023-08-21 | 2023-08-24 | -3 |  | 4 | 4 | 17 | 17 | 2023-08-09 | 3 | 3 |  |  |  | 2023-08-21 | 2023-08-09 | 2023-10-13 |  |  |  | 4 | 4 | 2023-11-02 |  |  |  |  | 2023-10-09 |  |  | 2023-10-17 | 7 | 7
1366 | Chino Hills - 4200 Chino Hills Pkwy | 4200 Chino Hills Pkwy | Chino Hills | 91709 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-27 | 2022-06-27 |  |  | 1 | 1 | 2022-06-27 | 2022-07-07 | 2022-08-10 | 8 | 8 | 25 | 25
1367 | Montclair - 8720 Central Ave | 8720 Central Ave | Montclair | 91763 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-06-27 | 2022-06-27 |  |  | 1 | 1 | 2022-06-27 | 2022-07-07 | 2022-07-31 | 8 | 8 | 17 | 17
1368 | Bloomington - 18772 Valley Blvd | 18772 Valley Blvd | Bloomington, CA 92316 | 92316 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 30 - Foothill | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-06-27 | 2022-06-27 |  |  | 1 | 1 | 2022-06-27 | 2022-07-06 | 2022-07-27 | 7 | 7 | 16 | 16
1369 | Inglewood, CA - 3100 W Imperial Hwy R3 | 3172 W Imperial Hwy | Inglewood | 90303 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3470003 | 2108963 |  | 2024-08-29 | 40 | YES | Level 2 | NO |  | 2023-02-08 |  |  | 2022-06-28 | 2022-06-28 | 156 | 156 | 1 | 1 | 2022-06-29 |  | 2022-07-09 |  |  |  |  | 2023-01-25 | 146 | 146 | 2023-06-16 | 2023-06-20 | 2023-12-04 | 2023-08-17 | 144 | 144 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-12-12 | 2024-02-13 | 59 | 59 | 2024-02-13 | 1 | 1 | [10 empty] | 2024-01-23 | 2024-01-31 |  | -16 | [5 empty] | 2024-02-13 | 1 | 1 | [9 empty] | 1 | 1
1370 | Palmdale - 102 W Palmdale Blvd | 102 W Palmdale Blvd | Palmdale | 93550 | Los Angeles County | 3. Active | 36 - Antelope Valley | North Valley | Ventura | [9 empty] | YES |  |  |  |  | 2022-06-27 | 2022-06-27 |  |  | 1 | 1 | 2022-06-27 | 2022-06-29 | 2022-07-01 | 3 | 3 | 3 | 3
1371 | Pomona - 102 North Main St | 102 N Main St | Pomona | 91768 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-03-01 | 0 | YES | Level 3 | YES | 2022-09-27 | 2022-11-01 | 26 | 26 | 2023-06-07 | 2023-06-07 | -151 |  | 1 | 1 | 2023-06-08 | 2023-06-12 | 2023-07-21 | 4 | 4 | 29 | 29
1372 | Huntington Park Autozone | 2901 E Florence Ave | Huntington Park | 90255 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | Cudahy | Creamery 16kv | 3424929 |  |  | 2023-06-02 |  |  |  | NO | 2022-07-26 | 2022-12-12 | 96 | 96 | 2022-06-28 | 2022-06-28 | 115 | 115 | 1 | 1 | 2022-06-29 | 2022-07-07 | 2022-07-19 | 7 | 7 | 9 | 9 | 2022-11-10 | 96 | 96 | 2022-11-17
1373 | Santa Clarita - 18943 Soledad Canyon Rd | 18943 Soledad Canyon Rd | Santa Clarita | 91351 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [9 empty] | NO |  |  |  |  | 2022-06-27 | 2022-06-27 |  |  | 1 | 1 | 2022-06-27 | 2022-06-30 | 2022-07-02 | 4 | 4 | 2 | 2
1374 | Brea - Hines Brea, 135 S State College Blvd | 135 S State College Blvd | Brea | 92821 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-06-28 | 2022-06-28 |  |  | 1 | 1 | 2022-06-28 | 2022-07-14 | 2022-07-20 | 12 | 12 | 5 | 5
1375 | Redlands Chipotle | 635 Orange St | Redlands | 92374 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | Redlands | Dearborn 12kV | [7 empty] | NO | 2022-08-01 | 2022-08-02 | 2 | 2 | 2022-06-29 | 2022-06-29 | 24 | 24 | 1 | 1 | 2022-06-29
1376 | Moreno Valley - 27010 Fir Ave | 27010 Fir Ave | Moreno Valley | 92555 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-29 | 2022-06-29 |  |  | 1 | 1 | 2022-06-29 | 2022-07-18 | 2022-08-09 | 13 | 13 | 17 | 17
1377 | Hemet - 3317 W Florida Ave | 3317 W Florida Ave | Hemet | 92545 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-29 | 2022-06-29 |  |  | 1 | 1 | 2022-06-29
1378 | Riverside - 5587 Arlington Ave | 5587 Arlington Ave | Riverside | 92504 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-06-29 | 2022-06-29 |  |  | 1 | 1 | 2022-06-29
1379 | Simi Valley - 2360 Tapo St | 2360 Tapo St | Simi Valley | 93063 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2022-06-30 | 2022-06-30 |  |  | 1 | 1 | 2022-06-30 | 2022-07-11 | 2022-07-16 | 7 | 7 | 5 | 5
1380 | Simi Valley - 1438 E Los Angeles | 1438 E Los Angeles | Simi Valley | 93065 | Ventura County | 9. Complete | 39 - Ventura | North Coast | Ventura | [6 empty] | 6 |  |  | YES |  |  |  |  | 2022-06-30 | 2022-06-30 |  |  | 1 | 1 | 2022-06-30 | 2022-07-11 | 2022-07-16 | 7 | 7 | 5 | 5
1381 | Huntington Park, CA - 5731 Bickett St | 5731 Bickett St EV1 | Huntington Park | 90255 | Orange County | 11. Cancelled | 32 - Compton | Metro West | Alhambra |  |  | 3418454 | 2068481 |  | 2023-06-20 | 12 | NO |  | YES |  | 2022-07-05 |  |  | 2022-05-27 | 2022-05-27 | 26 | 26 | 1 | 1 | 2022-05-27 | 2022-06-07 | 2022-06-30 | 7 | 7 | 18 | 18 |  |  |  | 2022-11-07 | 2022-11-08 | 2022-12-23 | 2022-12-21 |  |  | 2022-12-22 | 2023-01-31 | 28 | 28 | 2023-02-22 | 2023-02-22 | 16 | 16 | 2023-02-24 | 3 | 3 | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-03-13 | 3 | 3 | 29 | 29 | 12 | 12 | 2023-02-02 | 2023-02-15 | 2023-03-20 | -14 |  | 23 | 23 | 32 | 32 | [6 empty] | 2023-02-15 |  | 2023-03-20 | [5 empty] | 2023-06-19 | 2023-07-18 | 2023-07-18 | 21 | 21 | [13 empty] | 2023-08-16 |  |  |  |  | 2023-08-23 | 2023-09-26 | 24 | 24 | 2023-09-28 | 26 | 26 | 2023-09-28 |  |  |  | 339 | 339 |  |  | 2023
1382 | Costa Mesa - 179 E 17th St | 179 E 17th St | Costa Mesa | 92627 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | Lafayette | Hogan 12kV | [7 empty] | YES | 2022-08-18 | 2022-09-19 | 22 | 22 | 2022-07-02 | 2022-07-01 | 55 | 55 | -1 |  | 2022-07-06 | 2022-08-02 | 2022-08-18 | 22 | 22 | 13 | 13
1383 | Goldenwest & Warner | 7101 Warner Ave-EV | Huntington Beach | 92647 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | Oceanview | Standard 12kV |  |  |  | 2023-03-18 |  |  |  | NO | 2022-08-18 | 2022-09-19 | 22 | 22 | 2022-07-01 | 2022-07-01 | 55 | 55 | 1 | 1 | 2022-08-02
1384 | Santa Ana - 1810 N Bristol | 1810 N Bristol | Santa Ana | 92706 | Orange County | 9. Complete | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-20 | 2022-07-24 | 13 | 13 | 3 | 3
1385 | Whittier, CA - 11300 Washington Blvd | 11300-EV Washington Blvd | Whittier | 90606 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  |  | 3384721 | 2070245 |  | 2024-01-19 | 16 | NO |  | YES |  | 2022-07-05 |  |  | 2022-06-09 | 2022-06-09 | 18 | 18 | 1 | 1 | 2022-06-09 | 2022-06-09 | 2022-07-01 | 1 | 1 | 17 | 17 | 2022-09-13 | 67 | 67 | 2022-09-14 | 2022-09-28 |  | 2022-12-19 | 67 | 67 | 2022-12-21 | 2023-01-30 | 28 | 28 | 2023-02-20 | 2023-02-22 | 17 | 17 | 2023-02-22 | 1 | 1 | 2023-02-24 | 2023-02-24 | 2023-02-24 | 2023-03-01 | 3 | 3 | 22 | 22 | 4 | 4 | 2023-02-07 |  | 2023-05-09 | -11 |  |  |  | 65 | 65 | [8 empty] | 2023-05-09 | [5 empty] | 2023-08-01 | 2024-02-13 | 2024-02-20 | 139 | 139 | 2023-08-03 |  |  | 2023-08-08 | 4 | 4 | [7 empty] | 2024-01-24 | 119 | 119 |  |  | 2024-01-16 | 2024-02-09 | 19 | 19 | 2024-02-14 | 22 | 22 | 2024-02-22 |  |  |  | 430 | 430 | 364 | 364 | 2024
1386 | Palm Springs, CA -1555 S Palm Canyon Dr | 1555 1/2 S Palm Canyon Dr | Palm Springs | 92264 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  | Stack 12kV | 3438783 | 2087257 |  | 2024-03-01 |  | NO |  | NO | 2022-08-09 | 2022-08-24 | 12 | 12 | 2022-07-05 | 2022-07-05 | 37 | 37 | 1 | 1 | 2022-07-05 | 2022-08-07 | 2022-08-07 | 24 | 24 | 0 |  | 2022-12-12 | 111 | 111 | 2022-12-14 | 2022-12-19 | 2023-02-02 | 2023-02-10 | 44 | 44 | 2023-02-10 | 2023-03-24 | 30 | 30 | 2023-07-17 | 2023-08-08 | 96 | 96 | 2023-08-08 | 1 | 1 | 2023-08-08 |  | 2023-08-08 |  | 1 | 1 |  |  |  |  | 2023-05-26 | 2023-07-07 |  | -51 | [5 empty] | 2023-11-01 | 61 | 61 | 2023-11-13 | 9 | 9 | 2023-07-07 | 2023-07-07 |  |  |  |  | 61 | 61
1387 | Goleta - 6864 Cortona Dr | 6864 Cortona Drive | Goleta | 93117 | Los Angeles County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-13 | 2022-07-17 | 8 | 8 | 3 | 3
1388 | Pomona - 690 Indian Hill Blvd | 690 Indian Hill Blvd | Pomona | 91767 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-20 | 2022-08-14 | 13 | 13 | 18 | 18
1389 | Fontana - 15140 Summit Ave | 15140 Summit Ave | Fontana | 92336 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-25 | 2022-08-21 | 16 | 16 | 20 | 20
1390 | Orange - 2233 N Tustin St | 2233 N Tustin St | Orange | 92865 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-22 | 2022-07-29 | 15 | 15 | 6 | 6
1391 | Norco - 1140 Hamner Ave | 1140 Hamner Ave | Norco | 92860 | Riverside County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06
1392 | Chino Hills - 3140 Chino Ave | 3140 Chino Ave | Chino Hills | 91709 | San Bernardino County | 9. Complete | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-11 | 2022-08-21 | 6 | 6 | 30 | 30
1393 | Barstow, 502 E Virginia Way | 502 E Virginia Way EV1 | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | Tortilla | Burrito 12kV | 3362106 | 2044179 |  |  | 10 | NO |  | NO | 2022-08-07 | 2022-08-08 | 1 | 1 | 2022-07-01 | 2022-07-01 | 26 | 26 | 1 | 1 | 2022-07-06 | 2022-08-07 | 2022-08-07 | 25 | 25 | 0 |  |  |  |  | 2022-08-09 | 2022-08-10 | 2022-09-26 | 2022-09-30 | [7 empty] | 2022-09-30 | [5 empty] | 2022-10-03 | 2022-10-03 | [58 empty] | 2022-11-16 |  |  | 2022-11-16 |  |  |  | 96 | 96 |  |  | 2022
1394 | Hacienda Heights - 2136 S Hacienda Blvd | 2136 S Hacienda Blvd | Hacienda Heights | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-27 | 2022-08-21 | 18 | 18 | 18 | 18
1395 | Fontana - 16045 Sierra Lakes Pkwy | 16045 Sierra Lakes Pkwy | Fontana | 92336 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-25 | 2022-08-16 | 16 | 16 | 17 | 17
1396 | Upland - 989 W Foothill Blvd | 989 W Foothill Blvd | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-08 | 2022-07-28 | 2022-08-17 | 19 | 19 | 15 | 15
1397 | Moreno Valley - 22585 Alessandro Blvd | 22585 Alessandro Blvd | Moreno Valley | 92553 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-07-01 | 2022-07-01 |  |  | 1 | 1 | 2022-07-06 | 2022-07-20 | 2022-08-09 | 13 | 13 | 15 | 15
1398 | Gonzales Park Compton Pool Building | 1101 W Cressey St | Compton | 90222 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra | [5 empty] | 2023-09-01 | 1 | NO |  | YES |  |  |  |  | 2022-07-06 | 2022-07-06 |  |  | 1 | 1 | 2022-07-06 | 2022-07-18 | 2022-07-26 | 9 | 9 | 7 | 7
1399 | Norwalk, CA - 11300 Firestone Blvd -R1 | 11300 Firestone Blvd EV1 | Norwalk | 90650 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra |  | Tiger 12kV | 3420041 | 2125119 | 2067896 | 2024-01-10 | 16 | YES | Level 3 | NO | 2022-08-17 | 2022-11-10 | 61 | 61 | 2023-03-15 | 2022-07-06 | 91 | 91 | -175 |  | 2022-07-08 |  | 2022-08-17 |  |  |  |  | 2022-11-08 | -87 |  | 2023-03-16 | 2023-05-01 | 2023-05-01 | 2023-05-01 | 120 | 120 | 2023-05-01 | 2023-05-16 | 12 | 12 | 2023-06-06 | 2023-07-13 | 41 | 41 | 2023-07-14 | 2 | 2 | 2023-08-08 | 2023-08-30 | 2023-08-08 | 2023-10-02 | 19 | 19 | 97 | 97 | 39 | 39 | 2023-08-08 | 2023-08-22 | 2023-08-29 | 19 | 19 | 6 | 6 | 16 | 16 | [6 empty] | 2023-08-08 |  | 2023-10-02 | [5 empty] | 2023-08-29 | 2023-11-06 | 2023-12-04 | 67 | 67 | 2023-08-22 |  |  | 2023-09-12 | 15 | 15 | [6 empty] | 2024-01-11 | 2024-01-11 | 98 | 98 | 1 | 1 | 2024-01-22 | 2024-02-27 | 26 | 26 | 2024-03-08 | 34 | 34 | 2024-03-08 |  |  |  | 249 | 249 | 335 | 335 | 2024
1400 | Rancho Cucamonga-Taco Bell | 6579 Milliken Ave | Rancho Cucamonga | 91701 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2022-07-07 | 2022-07-07 |  |  | 1 | 1 | 2022-07-28
1401 | Corona - Taco Bell | 4718 Green River Rd. | Corona | 92880 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | NO |  |  |  |  | 2022-07-07 | 2022-07-07 |  |  | 1 | 1 | 2022-07-28
1402 | Norco - 6th St Taco Bell | 1448 6th St | Norco | 92860 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-07-07 | 2022-07-07 |  |  | 1 | 1
1403 | Pomona - 2090 S Garey Ave Food4Less | 2090 S Garey Ave | Pomona | 91766 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | Francis | Atlas 12kv | [7 empty] | YES | 2022-07-12 | 2022-07-18 | 5 | 5 | 2022-06-09 | 2022-06-09 | 27 | 27 | 1 | 1 | 2022-06-09 | 2022-07-05 | 2022-07-05 | 18 | 18 | 1 | 1
1404 | Wildomar - Oak Creek Center | 23905 Clinton Keith Rd - EV | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | Tenaja | Corinth 12kV | 3377835 |  |  | 2023-03-31 |  | NO |  | NO | 2022-08-17 | 2022-08-26 | 8 | 8 | 2022-07-11 | 2022-07-11 | 35 | 35 | 1 | 1 | 2022-07-21 | 2022-08-02 | 2022-08-10 | 17 | 17 | 7 | 7 | 2022-09-01 | 39 | 39 | 2022-09-02 | 2022-09-19
1405 | WinCo Temecula | 40435 Winchester Rd. | Temecula | 92591 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [9 empty] | NO |  |  |  |  | 2022-07-12 | 2022-07-12 |  |  | 1 | 1 | 2022-07-19
1406 | Long Beach - Donald Douglas Dr | 4100 Donald Douglas Dr | Long Beach | 90806 | Los Angeles County | 10. Customer Hold | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-05-31 |  |  |  | YES |  |  |  |  | 2022-07-12 | 2022-07-12 |  |  | 1 | 1 | 2022-09-06 | 2022-09-14 | 2022-09-17 | 46 | 46 | 3 | 3
1407 | Northpark Plaza | 3981 Irvine Blvd | Irvine | 92602 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | Bryan | Barbados 12kV | 3420194 | 2116952 |  | 2024-11-18 |  | NO |  |  | 2022-08-30 | 2022-09-30 | 23 | 23 | 2022-07-13 | 2022-07-13 | 57 | 57 | 1 | 1 | 2022-07-21 | 2022-08-04 | 2022-08-28 | 17 | 17 | 17 | 17 | 2022-11-07 | 83 | 83 | 2022-11-09 | 2022-12-27 | 2023-02-21 | 2023-03-07 | 82 | 82 | 2023-03-07 | 2023-03-13 | 5 | 5 | 2023-04-05 | 2023-05-05 | 40 | 40 | 2023-05-05 | 1 | 1 | 2023-05-05 |  | 2023-05-05 |  | 1 | 1 |  |  |  |  | 2023-04-11 |  |  | -19
1409 | Newport Towne Square | 27774 Newport Rd | Menifee | 92586 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [6 empty] | 20 |  |  | YES |  |  |  |  | 2022-07-20 | 2022-07-20 |  |  | 1 | 1 | 2022-08-09 | 2022-08-09 | 2022-09-22 | 15 | 15 | 32 | 32
1410 | Santa Monica Blvd Property | 825 Santa Monica Blvd. | Santa Monica | 90401 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Santa Monica | Tradewind 16kv |  |  |  | 2023-07-01 |  | NO |  |  | 2022-07-28 | 2022-08-09 | 9 | 9 | 2022-07-07 | 2022-07-07 | 24 | 24 | 1 | 1 | 2022-07-20 | 2022-07-19 | 2022-07-23 | 9 | 9 | 4 | 4
1412 | Jurupa Valley, CA - Ben Nevis Blvd | Ben Nevis Blvd & Pedley Rd, Jurupa Valley CA 92509 | Jurupa Valley | 92509 | Riverside County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [7 empty] | NO |  | YES |  | 2022-09-21 |  |  | 2022-07-24 | 2022-07-24 | 42 | 42 | 0 |  | 2022-08-05 | 2022-08-18 | 2022-09-08 | 19 | 19 | 15 | 15 | [58 empty] | 2022-07-29
1413 | Death Valley, CA - Hwy 190 | California 190, Death Valley, CA 92328, Death Valley | Death Valley | 92328 | Inyo County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura | [7 empty] | NO |  | YES |  |  |  |  | 2022-07-24 | 2022-07-24 |  |  | 0 |  | 2022-08-02 | 2022-08-27 | 2022-08-27 | 25 | 25 | 0
1417 | La Verne, CA - 1207 Foothill Blvd | 1207 Foothill Blvd, La Verne | La Verne | 91750 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  | Brackett 12kV | [5 empty] | NO |  | YES | 2022-08-26 | 2022-08-30 | 3 | 3 | 2022-07-25 | 2022-07-25 | 27 | 27 | 1 | 1 | 2022-08-12 | 2022-08-21 | 2022-08-21 | 20 | 20 | 0
1418 | El Monte, CA - 9804 Flair Dr | 9804 Flair Dr El Monte | El Monte | 91731 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  | Gladys 16kV |  |  |  | 2024-10-01 |  | NO |  | YES | 2022-08-12 |  |  |  | 2022-07-25 | 2022-07-25 |  |  | 1 | 1 | 2022-08-02 | 2022-08-10 | 2022-08-10 | 13 | 13 | 1 | 1
1419 | Corona, CA - 1180 El Camino Ave | 1180 El Camino Ave. Corona | Corona | 92879 | Riverside County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-02-28 |  | NO |  | YES |  |  |  |  | 2022-10-26 | 2022-10-26 |  |  | 1 | 1 | 2022-10-27 | 2022-11-01 | 2022-11-06 | 5 | 5 | 4 | 4
1420 | Thousand Oaks, CA - Newbury Rd | 1516 Newbury Rd, Thousand Oaks, CA 91320 | Thousand Oaks | 91320 | Ventura County | 3. Active | 35 - Thousand Oaks | North Coast | Ventura |  | Borchard 16kV | [5 empty] | NO |  | YES | 2022-08-04 | 2022-08-17 | 10 | 10 | 2022-07-18 | 2022-07-18 | 23 | 23 | 1 | 1 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 13 | 13 | 1 | 1
1421 |  | 7810 Norwalk Blvd | Whittier | 90606 | Los Angeles County | 11. Cancelled | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2024-09-27 |  | NO | Level 3 |  | 2022-07-18 | 2022-07-19 | 2 | 2 | 2022-06-22 | 2022-06-22 | 19 | 19 | 1 | 1 | 2022-06-22 | 2023-01-05 | 2023-01-09 | 137 | 137 | 3 | 3
1422 | Fountain Valley - Palm Island Senior Apartments | 11300 Warner Ave. | Fountain Valley | 92708 | Orange County | 4. Preliminary Design | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-07-22 | 2022-07-25 |  |  | 2 | 2 | 2022-08-15 | 2022-08-15 | 2022-09-26 | 16 | 16 | 30 | 30
1423 | Jurupa Valley - Glen Avon Shopping Center | 9001 Mission Blvd | Jurupa Valley | 92509 | Riverside County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3437773 |  |  | 2024-06-01 | 9 | YES | Level 1 |  | 2023-10-23 | 2023-11-08 | 13 | 13 | 2022-07-26 | 2022-07-27 | 327 | 327 | 2 | 2 | 2022-08-10 | 2022-08-10 | 2022-09-06 | 11 | 11 | 19 | 19 | 2022-12-12 | 96 | 96 | 2023-12-26 | 2023-12-28 | 2024-02-08 | 2024-01-17 | 278 | 278 | 2024-01-17 | [20 empty] | 2024-03-26
1424 | Downey - Mas Chingon Downey Properties | 8218 Firestone Blvd. | Downey | 90241 | Los Angeles County | 10. Customer Hold | 47 - Whittier | Metro West | Alhambra | [14 empty] | 2022-07-26 | 2022-07-27 |  |  | 2 | 2 | 2022-08-16 | 2022-08-16 | 2022-12-07 | 15 | 15 | 78 | 78
1425 |  | 9320 Slauson Ave | Pico Rivera | 90660 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [7 empty] | NO |  | YES | 2022-07-27 |  |  |  | 2022-07-27 | 2022-07-27 |  |  | 1 | 1 |  | 2022-07-27 | 2022-07-27 | 1 | 1 | 1 | 1
1427 |  | 2000 E Anaheim St | Long Beach | 90804 | Los Angeles County | 10. Customer Hold | 46 - Long Beach | Metro West | Alhambra | Broadway | Capri 12 KV |  |  |  | 2023-03-06 | 3 | NO |  | YES | 2022-09-21 | 2022-10-03 | 9 | 9 | 2022-07-28 | [5 empty] | 2022-08-15 | 2022-09-20 | 2022-09-20 |  |  | 1 | 1
1428 |  | 8923 Washington Blvd | Pico Rivera | 90660 | Los Angeles County | 10. Customer Hold | 22 - Montebello | Metro East | Pomona | [7 empty] | NO |  | YES | 2022-07-28 |  |  |  | 2022-07-28
1429 |  | 8810 Whittier Blvd | Pico Rivera | 90660 | Los Angeles County | 3. Active | 47 - Whittier | Metro West | Alhambra | [9 empty] | NO | 2022-07-29 |  |  |  | 2022-07-28 | 2022-07-28 |  |  | 1 | 1 |  | 2022-07-28 | 2022-07-28 | 1 | 1 | 1 | 1
1430 | Alessandro Shopping Center | 22216 Alessandro Blvd | Moreno Valley | 92553 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar |  |  | 3621678 | 2190998 | 2194205 |  | 41 | YES | Level 3 | YES |  |  |  |  | 2022-07-29 | 2022-07-29 |  |  | 1 | 1 | 2022-08-09 | 2022-08-09 | 2022-09-06 | 8 | 8 | 20 | 20 | 2023-10-20 | 312 | 312 | 2023-10-20 | 2023-10-24 | 2023-11-27
1431 | 26529 Highland Ave | 26529 Highland Ave | Highland | 92346 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 31 - Redlands | Desert | SBRO |  |  | 3661876 | 2222854 | 2222856 | 2024-07-26 | 6 | YES | Level 2 |  | 2023-12-21 | 2023-01-11 | -240 |  | 2022-07-29 | 2022-07-29 | 115 | 115 | 1 | 1 |  | 2022-07-31 | 2022-07-31 | 1 | 1 | 0 |  | 2024-01-12 | 368 | 368 | 2024-01-12 | 2024-01-16 | 2024-02-14 | 2024-02-08 | 19 | 19 | 2024-02-09
1432 | Santa Barbara-David Love | 25 David Love Pl EV | Santa Barbara | 93117 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3389871 | 2051748 |  | 2024-04-30 | 3 | NO | [6 empty] | 2022-07-28 | 2022-07-28 |  |  | 1 | 1 | 2022-07-28 | 2022-08-01 | 2022-08-08 | 3 | 3 | 6 | 6 | 2022-09-21 | 39 | 39 | 2022-09-21 |  | 2022-11-09 | 2022-11-09 | 36 | 36 | 2022-11-09 | 2022-11-15 | 4 | 4 | 2023-09-14 | 2023-09-15 | 212 | 212 | 2023-09-18 | 2 | 2 | 2022-12-21 | 2023-03-17 | 2023-09-18 | 2023-09-20 | 2 | 2 | 215 | 215 | 3 | 3 | [9 empty] | 2023-06-27 | -58 |  | 2023-07-07 | 8 | 8 | [6 empty] | -57 | [6 empty] | 2023-10-03 |  |  | 2023-10-16 | 10 | 10
1433 | Kohl's Porterville | 1275 W Henderson Ave | Porterville | 93257 | Tulare County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura | [7 empty] | NO |  | YES |  |  |  |  | 2022-08-04 | 2022-08-04 |  |  | 1 | 1 | 2022-08-05 | 2022-08-22 | 2022-08-26 | 13 | 13 | 5 | 5
1434 |  | 71927 Baker Blvd | Baker | 92309 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-05-01 |  | NO |  |  |  | 2022-09-06 |  |  | 2022-05-03 | 2022-05-03 | 88 | 88 | 1 | 1 | 2022-07-13 | 2022-08-07 | 2022-08-07 | 67 | 67 | 0
1435 | 1600 Fairplex Dr | 1600 Fairplex Dr | Pomona | 91768 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona |  | Cal Poly 12kV |  |  |  | 2023-12-01 |  | NO |  | YES | 2022-09-02 | 2022-09-13 | 7 | 7 | 2022-08-05 | 2022-08-05 | 27 | 27 | 1 | 1 | 2022-08-08 | 2022-08-31 | 2022-08-31 | 19 | 19 | 1 | 1
1436 | Ontario, CA - Old address 3760 Inland Empire Blvd | 3570 Porsche Way-MP | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3534045 | 2157607 |  | 2024-04-15 | 24 | YES | Level 3 | NO | 2023-02-06 | 2023-03-20 | 30 | 30 | 2022-08-05 | 2022-08-05 | 156 | 156 | 1 | 1 | 2022-08-08 | 2022-08-31 | 2022-08-31 | 19 | 19 | 1 | 1 | 2023-02-06 | 127 | 127 | 2023-05-17 |  | 2023-08-11 | 2023-08-10 | 131 | 131 | 2023-08-15 | 2023-08-16 | 2 | 2 | 2023-09-06 | 2023-10-12 | 41 | 41 | 2023-10-25 | 10 | 10 | 2023-10-25 |  | 2023-10-25 |  | 10 | 10 |  |  |  |  | 2023-11-08 |  |  | 20 | 20
1437 | Bishop-Vons | 1190 N Main St. | Bishop | 93514 | Inyo County | 3. Active | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2023-08-04 |  | NO |  | YES |  |  |  |  | 2022-08-04 | 2022-08-04 |  |  | 1 | 1 | 2022-09-08 | 2022-08-24 | 2022-09-12 | 15 | 15 | 13 | 13
1438 |  | 25635 Crucero Rd | Ludlow | 92338 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-09-03 |  | NO | Level 3 |  | 2022-08-09 | 2022-08-19 | 9 | 9 | 2022-07-13 | 2022-07-13 | 28 | 28 | 1 | 1 | 2022-07-13 | 2022-08-07 | 2022-08-07 | 18 | 18 | 0
1439 |  | 2099 E Harbor Blvd | Ventura | 93001 | Ventura County | 6. Requirements (permit, easment, etc.) | 39 - Ventura | North Coast | Ventura |  |  | 3413250 | 2058097 |  | 2024-08-01 | 4 | YES | Level 1 | [5 empty] | 2022-08-08 | 2022-08-08 |  |  | 1 | 1 | 2022-08-15 | 2022-08-15 | 2022-09-03 | 6 | 6 | 15 | 15 | 2022-10-25 | 56 | 56 | 2022-10-28 |  | 2022-12-15 | 2023-02-10 | 75 | 75 | 2023-02-10 | 2023-03-06 | 16 | 16 | 2023-03-27 | 2023-04-06 | 24 | 24 | 2023-04-06 | 1 | 1 | [10 empty] | 2023-04-12 | 2023-06-01 |  | 5 | 5
1440 |  | 19161 Skyline Ranch Rd | Santa Clarita | 91350 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 3412803 | 2062216 | 2062212 | 2024-08-01 | 4 | YES | Level 3 | [5 empty] | 2022-08-08 | 2022-08-08 |  |  | 1 | 1 | 2022-08-15 | 2022-08-15 | 2022-08-21 | 6 | 6 | 5 | 5 | 2022-10-25 | 56 | 56 | 2022-10-27 |  | 2022-12-15 | 2022-12-13 | 33 | 33 | 2022-12-13 | 2023-01-11 | 22 | 22 | 2023-02-02 | 2023-02-21 | 28 | 28 |  |  |  | 2023-02-21 |  | 2023-02-21 | 2023-03-28 | 1 | 1 | 53 | 53 | 26 | 26 | 2023-02-22 | 2023-03-10 | 2023-04-06 | 2 | 2 | 20 | 20 | 32 | 32 | [6 empty] | 2023-02-21 |  | 2023-04-06
1441 |  | 2477 Lomita Blvd | Lomita | 90717 | Los Angeles County | 10. Customer Hold | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-08-08 | [8 empty] | 2022-08-08 | 2022-08-08 |  |  | 1 | 1 | 2022-08-17 | 2022-08-17 | 2022-09-02 | 8 | 8 | 13 | 13
1442 | West Hollywood Development | 8612 Santa Monica Blvd | West Hollywood | 90069 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2023-08-08 |  |  |  | YES |  |  |  |  | 2022-08-05 | 2022-08-08 |  |  | 2 | 2 | 2022-08-16
1444 | Jurupa Valley, 4134 Pyrite St | 8169 Mission Blvd | Jurupa Valley | 92509 | Riverside County | 3. Active | 30 - Foothill | Desert | SBRO |  | Texfi 12kV | 3637438 |  |  | 2024-12-20 | 35 | YES | Level 2 | NO | 2023-11-07 | 2023-11-13 | 5 | 5 | 2023-07-14 | 2023-07-14 | 86 | 86 | 1 | 1 | 2023-07-20 | 2023-08-01 | 2023-09-11 | 13 | 13 | 29 | 29 | 2023-11-20 | 91 | 91 | 2023-11-20 | 2023-11-21 | 2024-04-18
1445 |  | 500 James Fowler Road | Santa Barbara | 93117 | Ventura County | 7. Civil Construction | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2022-05-02 |  | NO | Level 1 | YES | 2022-08-09 |  |  |  | 2022-07-23 | 2022-07-23 |  |  | 0 |  | 2022-08-06 | 2022-08-06 | 2022-08-06 | 10 | 10 | 0
1446 | Costco Murrieta | 35875 EV Warm Springs Pkwy | Murrieta | 92563 | Riverside County | 2. Engineering | 88 - Wildomar | San Jacinto | Wildomar | Auld | Garboni 12kv | 3414617 | 2203999 |  | 2024-03-29 | 10 | YES | Level 2 | YES | 2022-08-09 | 2022-08-26 | 14 | 14 | 2022-06-28 | 2022-06-28 | 43 | 43 | 1 | 1 | 2023-10-05 | 2022-07-18 | 2022-08-08 | 14 | 14 | 16 | 16 | 2022-10-31 | 88 | 88 | 2023-11-14 | 2023-11-15 | 2024-01-02 | 2023-11-30 | 274 | 274 | 2023-12-04 | 2023-12-05 | 2 | 2 | 2024-01-02 | 2024-01-02 | 19 | 19 | 2024-01-03 | 2 | 2 | [10 empty] | 2023-12-13 | 2023-12-27 | 2024-01-11 | -13 |  | 11 | 11 | 20 | 20 | 2023-03-27 | -196 |  | 2024-02-13 | 224 | 224 | [6 empty] | -195 |  | 2024-02-14
1447 | Bridgeport, CA - Main St | 76773 Main St | Bridgeport | 93517 | Mono County | 6. Requirements (permit, easment, etc.) | 85 - Bishop/Mammoth | Rurals | Ventura |  | Strosnider 16kV |  |  |  | 2024-09-18 |  | NO |  | YES | 2024-03-12 |  |  |  | 2023-08-23 | [6 empty] | 2022-08-10 | 2022-08-10 |  |  | 1 | 1
1448 | Univeristy-2015 University Drive | 18861U Broadwick St EV | Compton | 90220 | Los Angeles County | 9. Complete | 32 - Compton | Metro West | Alhambra |  |  | 3482058 | 2194744 | 2194748 | 2024-06-28 | 30 | YES | Level 3 | YES | 2022-10-19 | 2022-10-25 | 5 | 5 | 2022-08-11 | 2022-08-11 | 53 | 53 | 1 | 1 | 2022-08-15 | 2022-08-18 | 2022-09-10 | 6 | 6 | 16 | 16 | 2023-01-25 | 115 | 115 | 2023-11-28 | 2023-11-30 | 2024-01-12 | 2024-01-12 | 245 | 245 | 2024-01-12 | 2024-01-22 | 6 | 6 | 2024-02-12 | 2024-03-04 | 30 | 30 | 2024-03-06 | 3 | 3 | 2024-03-06 | 2024-03-06 | 2024-03-06 |  | 3 | 3 |  |  |  |  | 2023-11-10 | 2024-03-13 |  | -76 | [11 empty] | 2024-03-06
1449 | 1232 W Ave K | 43500 1/4 13th St W | Lancaster | 93534 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura |  |  | 3447003 | 2084618 |  | 2024-04-01 | 20 | NO |  | YES | 2022-10-03 | 2022-10-18 | 12 | 12 | 2022-08-12 | 2022-08-12 | 47 | 47 | 1 | 1 |  |  | 2022-10-02 | [7 empty] | 2022-12-30 | 2023-01-03 |  | 2023-02-16 |  |  | 2023-02-16 | 2023-03-07 | 13 | 13 | 2023-04-10 | 2023-06-05 | 64 | 64 | 2023-04-12 | -38 |  | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 71 | 71 | 134 | 134 | 1 | 1 | 2023-03-21 | 2023-03-29 | 2023-04-07 | -54 |  | 8 | 8 | 14 | 14 | 2023-08-22 | 93 | 93 | 2023-09-07 | 12 | 12 | 2023-03-29 | 2023-03-29 | 2023-09-13 | 2023-09-13 | 118 | 118 | 56 | 56 | 2023-09-05 | 2023-07-10 | 2023-08-25 | -7 |  | 2023-06-01 |  |  | 2023-06-21 | 15 | 15 | [7 empty] | 2023-08-11 | 51 | 51 |  |  | 2023-09-19 | 2023-12-05 | 54 | 54 | 2024-01-09 | 77 | 77 | 2024-01-09 |  |  |  | 355 | 355 |  |  | 2024
1450 | Whittier Whitwood Town Center | 10445 Santa Gertrudes Ave. - EV | Whittier | 90603 | Los Angeles County | 7. Civil Construction | 48 - Fullerton | Orange | Saddleback | Telegraph | Mercado 12kV |  |  |  | 2023-12-14 |  |  |  | YES | 2022-09-13 | 2022-10-05 | 17 | 17 | 2022-08-12 | 2022-08-12 | 38 | 38 | 1 | 1 | 2022-08-15 | 2022-08-18 | 2022-09-09 | 5 | 5 | 16 | 16
1451 | 4031 1/2 Via Oro Avenue | 4031 1/2 Via Oro Avenue | Long Beach | 90810 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | Cameron | Kidd 12KV | 3388594 | 2057398 |  | 2024-05-31 | 16 | NO |  |  | 2022-09-09 | 2023-04-04 | 143 | 143 | 2022-08-12 | 2022-08-15 | 161 | 161 | 2 | 2 | 2022-08-22 | 2022-09-08 | 2022-09-08 | 18 | 18 | 1 | 1 |  |  |  | 2022-09-27 | 2022-09-29 | 2023-05-22 | 2023-04-25 |  |  | 2023-04-25 | 2023-05-04 | 8 | 8 | 2023-05-25 | 2023-06-12 | 27 | 27 | 2023-06-15 | 4 | 4 | 2023-06-15 | 2024-02-27 | 2023-06-15 | 2023-12-27 | 4 | 4 | 164 | 164 | 135 | 135 | 2023-06-19 | 2023-11-13 | 2023-12-08 | 6 | 6 | 18 | 18 | 121 | 121 | 2023-12-08 | 123 | 123 | 2023-12-13 | 4 | 4 | 2023-06-15 | 2023-06-15 | 2023-12-27 | 2023-12-27 | 135 | 135 | 126 | 126 | 2024-02-29 |  |  |  |  | 2024-01-11 |  |  | 2024-01-26 | 11 | 11
1452 | Waypoints - Yucaipa | 39611 Oak Glen Rd. | Yucaipa | 92300 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [14 empty] | 2022-07-14 | 2022-07-14 |  |  | 1 | 1 | 2022-07-15 | 2022-07-25 | 2022-08-15 | 8 | 8 | 16 | 16
1453 | Shell Neptune | 40808 Hwy 395 | Boron | 93516 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura |  |  | 3388515 | 2100758 | [5 empty] | YES |  |  |  |  | 2022-08-15 | 2022-08-15 |  |  | 1 | 1 | 2022-09-14 | 2022-09-14 | 2022-09-17 | 22 | 22 | 3 | 3 | 2022-09-20 | 26 | 26 | 2022-09-20 | 2023-01-04 | 2023-04-28 | 2023-05-02 | 156 | 156 | 2023-05-02
1455 | 4050 Chino Hills Pkwy | 4050 Chino Hills Pkwy | Chino Hills | 91709 | San Bernardino County | 12. System Upgrade | 34 - Ontario | Metro East | Pomona |  | Tupelo 12kV |  |  |  | 2023-06-30 |  |  |  | YES | 2022-10-12 | 2022-10-25 | 10 | 10 | 2022-08-17 | 2022-08-17 | 49 | 49 | 1 | 1 | 2022-08-26 |  | 2022-10-10
1456 | Montclair, CA - 4480 Holt Blvd | 4480 Holt Blvd, #EV-1 | Montclair | 91763 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  | Kadota 12kV |  |  |  | 2024-10-06 |  | YES |  | YES | 2022-09-21 | 2022-10-17 | 19 | 19 | 2023-08-09 | 2023-08-15 | -210 |  | 5 | 5 | 2023-08-17 |  | 2022-09-21
1457 | Rancho Cucamonga, CA - 11370 Fourth St | 11370 4th St | Rancho Cucamonga | 91730 | San Bernardino County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO |  | Yarborough 12kV |  |  |  | 2023-06-30 |  | NO |  | NO | 2022-09-23 | 2022-09-28 | 4 | 4 | 2022-08-17 | 2022-08-17 | 30 | 30 | 1 | 1 | 2022-08-26 |  | 2022-09-23
1458 | Skypark Santas Village | 29297 CA 18 | Skyforest | 92835 | San Bernardino County | 11. Cancelled | 40 - Arrowhead | Rurals | SBRO |  |  | 3625780 | 2209312 |  | 2024-11-11 | 60 | YES | Level 3 | [5 empty] | 2023-06-15 | 2023-06-28 |  |  | 10 | 10 | 2023-06-28 | 2023-07-05 | 2023-07-08 | 5 | 5 | 3 | 3 | 2023-10-27 | 95 | 95 | 2023-10-30 | 2023-10-30 | 2023-12-14 | 2023-12-12 | 31 | 31 | 2023-12-12 | 2023-12-13 | 2 | 2
1459 | Ojai Valley Inn & Spa | 905 Country Club Rd | Ojai | 93023 | Ventura County | 4. Preliminary Design | 39 - Ventura | North Coast | Ventura | [5 empty] | 2022-12-30 |  |  |  | YES |  |  |  |  | 2022-08-18 | 2022-08-18 |  |  | 1 | 1
1460 | 1802 Santa Monica Blvd | 1802 Santa Monica Blvd | Santa Monica | 90404 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | Colorado | Madison 16KV | 3641964 | 2237984 | 2237983 | 2024-09-30 | 28 | YES | Level 3 |  | 2022-09-06 | 2023-10-03 | 273 | 273 | 2022-08-18 | 2022-08-18 | 285 | 285 | 1 | 1 | 2022-08-31 | 2023-09-24 | 2023-09-24 | 278 | 278 | 0 |  | 2024-02-01 | 367 | 367 | 2024-02-01 | 2024-02-01 | 2024-03-15
1461 | Thousand Oaks Ralphs | 583 Ventu Park Rd | Thousand Oaks | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-09-01 | 2022-09-07 | 9 | 9 | 4 | 4
1462 | Agoura Hills - Ralphs | 5727 Kanan Rd | Agoura Hills | 91301 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-09-01 | 2022-09-06 | 9 | 9 | 3 | 3
1463 | Foothill Ranch- Ralphs | 26751 Portola Pkwy | Foothill Ranch | 92610 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-09-12 | 2022-10-10 | 15 | 15 | 21 | 21
1464 | Gardena Ralphs | 2201 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-08-22 | 2022-09-25 | 1 | 1 | 24 | 24
1465 | Arcadia Ralphs | 211 E Foothill Bld | Arcadia | 91006 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-08-26 | 2022-09-22 | 5 | 5 | 19 | 19
1466 | Apple Valley Food 4 Less | 20801 Bear Valley Rd. | Apple Valley | 92308 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-09-01 | 2022-09-01 | 2022-09-25 | 9 | 9 | 16 | 16
1467 | Lakewood Ralphs | 5951 Del Amo Blvd | Lakewood | 90713 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-22 | 2022-09-12 | 2022-10-14 | 15 | 15 | 25 | 25
1468 | Irvine Ralphs | 5345 Alton Pkwy | Irvine | 92604 | Orange County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-09-12 | 2022-08-30 | 2022-10-14 | 7 | 7 | 33 | 33
1469 | Colton Food 4 Less | 1150 N Pepper Ave | Colton | 92324 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-09-06 | 2022-09-06 | 2022-09-26 | 11 | 11 | 15 | 15
1470 | Stevenson Ranch Ralphs | 24975 Pico Canyon Rd | Stevenson Ranch | 91381 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | [14 empty] | 2022-08-22 | 2022-08-22 |  |  | 1 | 1 | 2022-08-25 | 2022-09-06 | 2022-09-25 | 11 | 11 | 14 | 14
1472 | Delano Chevy Dealership | 600 1st Ave. | Delano | 93215 | Kern County | 11. Cancelled | 51 - Tulare | San Joaquin | Ventura | [9 empty] | YES |  |  |  |  | 2022-08-23 | 2022-08-23 |  |  | 1 | 1 | 2022-08-25 | 2022-09-06 | 2022-09-09 | 10 | 10 | 4 | 4
1473 |  | 64200 20th Ave. | North Palm Springs | 92258 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3418926 | 2072578 |  |  |  | NO |  | YES | 2022-10-04 | 2022-10-18 | 11 | 11 | 2022-08-24 | 2022-08-24 | 39 | 39 | 1 | 1 | 2022-09-08 | 2022-09-08 | 2022-10-02 | 11 | 11 | 17 | 17 | 2022-11-07 | 53 | 53 | 2022-11-08 |  | 2022-12-27 | 2022-12-19 | 28 | 28 | 2022-12-20 | 2022-12-27 | 6 | 6 | 2023-01-18 | 2023-01-18 | 16 | 16 | 2023-01-18 | 1 | 1 | 2023-01-18 |  | 2023-01-18 |  | 1 | 1 |  |  |  |  | 2023-03-02 | 2023-05-03 |  | 31 | 31 | [10 empty] | 2023-01-18
1474 | Shell Neptune | 1559 E Baseline St. | San Bernardino | 92404 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | Cardiff | Harlem Springs 12kV | 3399469 | 2082300 |  |  |  | NO |  | YES | 2022-09-27 | 2022-09-30 | 4 | 4 | 2022-08-24 | 2022-08-24 | 27 | 27 | 1 | 1 | 2022-09-06 | 2022-09-06 | 2022-09-26 | 9 | 9 | 15 | 15 | 2022-10-05 | 30 | 30 | 2022-12-30 | 2022-12-01 | 2023-01-18 | 2023-03-03 | 103 | 103 | 2023-03-06
1475 | Shell Neptune | 835 E Nuevo Road | Perris | 92571 | Los Angeles County | 7. Civil Construction | 77 - Menifee | San Jacinto | Wildomar |  |  | 3422349 | 2090618 |  | 2023-06-10 |  | NO |  | YES | 2022-10-04 |  |  |  | 2022-08-24 | 2022-08-24 |  |  | 1 | 1 | 2022-09-06 | 2022-09-06 | 2022-10-03 | 9 | 9 | 20 | 20 | 2022-11-14 | 57 | 57 | 2022-11-14 | 2022-11-22 | 2022-12-30 | 2023-02-03 | 57 | 57 | 2023-02-03 |  |  |  |  | 2023-03-16 |  |  | 2023-03-16 | 1 | 1 | 2023-06-14 |  | 2023-06-14 |  | 64 | 64
1476 | Inglewood Century Blvd | 4600 W Century Blvd EV1 | Inglewood | 90304 | Los Angeles County | 7. Civil Construction | 44 - South Bay | Metro West | Alhambra |  |  | 3474545 | 2121240 | 2121239 | 2024-04-09 | 27 | YES | Level 3 | NO | 2022-10-17 | 2022-10-21 | 5 | 5 | 2022-08-24 | 2022-08-24 | 42 | 42 | 1 | 1 | 2022-08-31 | 2022-09-08 | 2022-10-01 | 11 | 11 | 17 | 17 | 2023-02-14 | 120 | 120 | 2023-02-15 | 2023-02-21 | 2023-05-19 | 2023-05-16 | 65 | 65 | 2023-05-16 | 2023-06-20 | 25 | 25 | 2023-07-13 | 2023-10-12 | 81 | 81 | 2023-10-12 | 1 | 1 | 2023-11-14 | 2023-11-30 | 2023-11-14 | 2023-11-17 | 24 | 24 | 107 | 107 | 4 | 4 | 2023-11-10 | 2023-12-04 | 2023-12-05 | 22 | 22 | 2 | 2 | 16 | 16 | 2023-12-04 | 36 | 36 | 2023-12-11 | 6 | 6 | 2023-11-14 | 2023-11-14 | 2023-12-05 | 2023-12-11 | 18 | 18 | 36 | 36 | 2023-12-12 | 2024-03-11 |  |  |  | 2023-11-28
1477 | Retail | 1008 E 17th St. Unit A | Santa Ana | 92701 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback |  |  | 3373144 | 2038246 |  | 2024-05-17 | 0 | NO |  | YES |  |  |  |  | 2022-04-12 | 2022-04-12 |  |  | 1 | 1 | 2022-04-27 | 2022-05-02 |  | 15 | 15 |  |  | 2022-08-24 | 95 | 95 | 2023-08-28 | 2023-08-29 | 2023-10-11 | [7 empty] | 2023-11-06 | 2023-09-25 | [5 empty] | 2023-10-17 | 2024-01-22 | 2023-10-17 |  | 17 | 17
1478 | Barstow PFJ 614 | 2611 Fisher Blvd | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-07-31 | 4 |  |  | YES | 2023-06-12 | 2023-07-24 | 30 | 30 | 2024-01-25 | 2024-01-25 | -128 |  | 1 | 1 | 2024-01-26 | 2024-01-30 | 2024-02-08 | 4 | 4 | 8 | 8
1479 | Corona Teller | 280 Teller St - EV | Corona | 92879 | Riverside County | 3. Active | 34 - Ontario | Metro East | Pomona | Chase | Weirick 12kV | [8 empty] | 2022-10-11 | 2022-10-24 | 10 | 10 | 2022-08-25 | 2022-08-25 | 42 | 42 | 1 | 1 | 2022-09-01 | 2022-09-08 | 2022-10-07 | 10 | 10 | 22 | 22
1480 | ACI Jet South 19711 Campus dr | 19361 Campus Dr #100 | Santa Ana | 92707 | Orange County | 10. Customer Hold | 33 - Huntington Beach | Orange | Saddleback | [7 empty] | YES |  | YES |  |  |  |  | 2022-08-23
1481 | Santa Clarita, CA -24235 Magic Mountain Pkwy | 24310 1/2 Creekside Rd., Santa Clarita | Santa Clarita | 91355 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 3373990 |  |  | 2022-06-30 |  |  |  | YES | 2021-04-19 | 2021-05-06 | 14 | 14 | 2021-04-10 | 2021-04-10 | 19 | 19 | 0 |  |  | 2022-08-27 | 2021-04-22 | 349 | 349 | -341 |  | 2022-08-30 | 351 | 351 | 2022-08-26 | 2022-08-30 |  | 2022-10-12 | 31 | 31 | 2022-10-13
1482 | Metrocenter | 1365 S Harbor Blvd- EV | Fullerton | 92832 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | Cudahy | Purex 16kV | [7 empty] | YES | 2022-08-29 | 2022-09-16 | 14 | 14 | 2022-07-13 | 2022-07-15 | 45 | 45 | 3 | 3 | 2022-07-21 |  | 2022-08-28
1483 | 48650 Seminole Drive, Cabazon, CA, United States | 48650 Seminole Dr | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  | Stores 12kV | [7 empty] | YES | 2022-08-29 | 2022-09-12 | 10 | 10 | 2022-08-29 | 2022-08-29 | 10 | 10 | 1 | 1 |  |  | 2022-08-24
1484 | Irvine The Square | 17951 MacArthur Blvd - EV | Irvine | 92614 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | Fairview | Flores or Redhill or Skypark 12kV |  |  |  | 2023-10-30 |  |  |  | YES | 2022-10-03 | 2022-10-12 | 8 | 8 | 2022-08-29 | 2022-08-29 | 32 | 32 | 1 | 1 | 2022-09-01 | 2022-09-07 | 2022-09-30 | 7 | 7 | 18 | 18
1485 | Hacienda Heights Gale Square Shopping Center | 15882 Gale Ave - EV | Hacienda Heights | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | Walnut | Shopper 12kV |  |  |  | 2023-06-30 |  |  |  | YES | 2022-09-13 | 2022-09-14 | 2 | 2 | 2022-08-30 | 2022-08-30 | 11 | 11 | 1 | 1 | 2022-09-06 | 2022-09-08 | 2022-09-09 | 7 | 7 | 2 | 2
1486 | Bel Bowl East Trim | 19700 Slover Avenue | Bloomington | 92324 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3376209 |  |  | 2024-04-01 |  |  |  | YES |  |  |  |  | 2022-08-30 | 2022-08-30 |  |  | 1 | 1 | [10 empty] | 2022-08-31 | 2022-09-09
1487 | Bel Bowl West Hump | 19700 Slover Avenue | Bloomington | 92324 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3378810 |  |  | 2024-04-01 |  |  |  | YES |  |  |  |  | 2022-08-30 | 2022-08-30 |  |  | 1 | 1 | [10 empty] | 2022-09-06 | 2022-09-09
1488 | Gorman, CA | 49771 Gorman Post Rd | Gorman | 93243 | Los Angeles County | 9. Complete | 36 - Antelope Valley | North Valley | Ventura |  | Ridge 12kV |  |  |  | 2024-12-30 |  | NO |  |  | 2022-09-02 |  |  |  | 2023-08-25 | 2023-08-25 |  |  | 1 | 1 | 2023-08-28 | 2023-09-05 | 2023-09-05 | 7 | 7 | 1 | 1
1489 | Calimesa, CA - 497 Sandalwood Dr (Burger King) | 501 Sandalwood Dr, Calimesa | Calimesa | 92320 | Riverside County | 9. Complete | 31 - Redlands | Desert | SBRO |  |  | 3454562 | 2085348 |  | 2024-03-30 | 12 | NO |  | YES | 2022-10-21 |  |  |  | 2022-09-07 | 2022-09-07 |  |  | 1 | 1 | 2022-09-15 | [6 empty] | 2023-01-17 | 91 | 91 | 2023-01-17 | 2023-01-19 |  | 2023-02-16 | 23 | 23 | 2023-02-16 | 2023-02-17 | 2 | 2 | 2023-03-14 | 2023-03-15 | 18 | 18 | 2023-03-15 | 1 | 1 | 2023-04-19 | 2023-04-19 | 2023-04-19 |  | 26 | 26 |  |  |  |  | 2023-02-27 | 2023-03-10 | 2023-03-30 | -13 |  | 15 | 15 | 24 | 24 | 2023-08-07 | 102 | 102 | 2023-08-09 | 3 | 3 | 2023-03-10 | 2023-03-10 |  |  |  |  | 102 | 102 | 2023-07-13 | 2023-06-27 | 2023-06-27 | -12 | [13 empty] | 2023-08-08 | 2023-08-08 |  |  | 1 | 1 | 2023-08-09 | 2023-08-23 | 11 | 11 | 2023-09-13 | 25 | 25 | 2023-09-13 |  |  |  | 258 | 258 | 168 | 168 | 2023
1490 | Cathedral City, CA - Date Palm Dr (Sonic) | 30775 Date Palm Dr, Cathedral City | Cathedral City | 92234 | Riverside County | 6. Requirements (permit, easment, etc.) | 79 - Palm Springs | Desert | SBRO |  | Date Palm 12kV | 3446839 | 2081308 |  | 2024-01-19 | 8 | NO |  | YES | 2021-10-21 |  |  |  | 2022-09-07 | 2022-09-07 |  |  | 1 | 1 | 2022-09-15 |  | 2022-10-18 |  |  |  |  | 2022-12-29 | 79 | 79 | 2022-12-29 |  |  | 2023-01-18 | 14 | 14 | 2023-01-18 | 2023-01-18 | 1 | 1 | 2023-02-10 | 2023-03-06 | 33 | 33 | 2023-03-08 | 3 | 3 | 2023-10-19 | 2023-10-23 | 2023-10-19 | 2023-12-26 | 161 | 161 | 238 | 238 | 46 | 46 | 2023-03-08 | 2023-03-16 | 2023-03-23 | 3 | 3 | 6 | 6 | 12 | 12 | [6 empty] | 2023-03-16 |  | 2023-12-26 | [5 empty] | 2023-09-27 | 2023-11-03 | 2023-11-15 | 36 | 36 | [12 empty] | 2023-12-05 | 2023-12-07 |  |  | 3 | 3 | 2023-12-26 | 2024-01-24 | 20 | 20 | 2024-01-25 | 21 | 21 | 2024-01-25 | 2024-02-07 | 10 | 10 | 349 | 349 | 271 | 271 | 2024
1491 | Hacienda Heights, CA - 15808 Gale Ave | 15870U Gale Ave, Hacienda Heights | Hacienda Heights | 91745 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3564580 | 2216224 | 2216225 | 2024-06-01 |  | YES | Level 3 |  | 2022-09-20 | 2022-10-12 | 17 | 17 | 2023-04-28 | 2023-05-09 | -145 |  | 8 | 8 | 2023-05-10 | 2023-05-17 |  | 7 | 7 |  |  | 2023-07-12 | 52 | 52 | 2023-07-12 | 2023-07-20 | 2023-08-31 | 2023-08-31 | 37 | 37 | 2023-09-19 | 2023-12-06 | 55 | 55 | 2024-01-29 | 2024-02-13 | 47 | 47 | 2024-02-14 | 2 | 2 | 2024-02-14 |  | 2024-02-14 |  | 2 | 2
1492 | Long Beach Westar-Bixby | 5745 E Pacific Coast Hwy - EV | Long Beach | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-09-08 | 2022-09-08 |  |  | 1 | 1 | 2022-09-08 | 2022-09-13 | 2022-10-17 | 4 | 4 | 25 | 25
1493 | Covina, CA - 420 Arrow Hwy | 1430 Hollenbeck Ave | Covina | 91722 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona |  |  | 3438300 |  |  | 2023-10-02 |  |  |  | YES |  |  |  |  | 2022-09-08 | 2022-09-08 |  |  | 1 | 1 | 2022-09-14 |  | 2022-09-19 |  |  |  |  | 2022-12-09 | 64 | 64 | 2022-12-14 |  | 2023-02-08 | 2023-03-16 | 68 | 68 | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-04-27 | 2023-05-16 | 44 | 44 | 2023-05-01 | -12
1494 | Taubman Gardens | 73545 El Paseo | Palm Desert | 92260 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | Palm Village | Gallon 12kv |  |  |  | 2024-09-02 | 6 | YES | Level 3 | NO | 2022-10-19 | 2022-10-26 | 6 | 6 | 2022-09-07 | 2022-09-07 | 36 | 36 | 1 | 1 | 2022-09-08 | 2022-10-15 | 2022-10-18 | 28 | 28 | 2 | 2
1495 | Martin Chevrolet Torrance | 23505 Hawthorne Blvd | Torrance | 90505 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-11-01 | 2 | YES | Level 3 | NO |  |  |  |  | 2022-09-09 | 2022-09-09 |  |  | 1 | 1 | 2022-09-20 | 2022-09-20 | 2022-10-31 | 8 | 8 | 30 | 30
1497 | 20151 S Main St Temp Service | 20151 S Main Street | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-12-30 |  |  |  | YES |  |  |  |  | 2022-09-13 | 2022-09-13 |  |  | 1 | 1 | 2022-09-13 | 2022-09-22 | 2022-10-23 | 8 | 8 | 22 | 22
1498 |  | 17080 Stoddard Wells Rd. | Victorville | 92394 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [9 empty] | NO | 2022-09-28 | 2022-10-11 | 10 | 10 | 2022-09-13 | 2022-09-13 | 21 | 21 | 1 | 1 | 2022-09-15 | 2022-09-15 | 2022-09-22 | 3 | 3 | 6 | 6
1499 | San Bernardino Highland | 694 E Highland Ave. | San Bernardino | 92404 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [14 empty] | 2022-09-15 | 2022-09-15 |  |  | 1 | 1 | 2022-09-16 | 2022-09-20 | 2022-09-25 | 4 | 4 | 4 | 4
1500 | Agoura Hills, CA - 29136 Roadside Dr | 29136 Roadside Dr, Agoura Hills, CA 91301 | Agoura Hills | 91301 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  | Chumash 16kV |  |  |  | 2023-12-30 |  |  |  |  | 2022-09-20 | 2022-10-14 | 19 | 19 | 2022-09-07 | [7 empty] | 2022-09-18
1501 | 1851 E Willow | 1851 E Willow | Signal Hill | 90755 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra |  | Montana 12kV | [7 empty] | YES | 2022-09-19 | 2022-09-28 | 8 | 8 | 2022-08-31 | 2022-08-31 | 20 | 20 | 1 | 1 | 2022-09-14 |  | 2022-09-17
1502 | Signal Hill, CA - 1851 E Willow Street | Signal Hill, CA - 1851 E Willow Street | Signal Hill | 90755 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-01-15 |  |  |  | YES | 2022-09-19 |  |  |  | 2022-08-31 | 2022-08-31 |  |  | 1 | 1 | 2022-09-06 |  | 2022-09-17
1503 | Camarillo, CA -660 Ventura Blvd | 656 1/2 Ventura Blvd, Camarillo | Camarillo | 93010 | Ventura County | 7. Civil Construction | 39 - Ventura | North Coast | Ventura |  | Mugu 16kV | 3467906 |  |  | 2024-08-23 |  | YES | Level 3 | YES | 2023-01-23 | 2023-02-06 | 11 | 11 | 2022-08-14 | 2022-08-14 | 121 | 121 | 0 |  | 2022-09-07 | 2023-09-02 | 2023-09-02 | 267 | 267 | 0 |  | 2023-11-16 | 320 | 320 | 2023-11-16 | 2023-11-17 | 2023-12-27 | 2023-12-29 | 29 | 29 | 2023-12-29
1504 | La Verne, CA-919 Foothill Blvd | 925 Foothill Blvd, La Verne | La Verne | 91750 | Los Angeles County | 8. Electrical Construction | 26 - Covina | Metro East | Pomona |  |  | 3414228 | 2108443 | 2061804 | 2024-05-15 | 16 | YES | Level 3 | YES | 2022-09-20 | 2022-09-28 | 7 | 7 | 2023-03-21 | 2024-01-02 | -318 |  | 199 | 199 | 2024-01-16 |  | 2022-09-16 |  |  |  |  | 2023-03-22 | 2 | 2 | 2023-03-22 |  | 2023-05-05 | 2023-04-25 | 25 | 25 | 2023-04-25 | 2023-05-17 | 17 | 17 | 2023-06-12 | 2023-06-12 | 18 | 18 | 2023-06-26 | 11 | 11 | 2023-06-26 | 2023-07-18 | 2023-06-26 | 2023-07-18 | 11 | 11 | 43 | 43 | 16 | 16 | 2023-05-31 | 2023-06-14 | 2023-09-06 | -9 |  | 59 | 59 | 69 | 69 | [6 empty] | 2023-06-14 |  | 2023-09-06 | [5 empty] | 2023-09-19 | 2023-10-03 | 2023-11-15 | 42 | 42 | 2024-01-02 |  |  | 2024-01-16 | 10 | 10
1505 | San Bernadino CA - 3235 W Little League Dr | 3237 W Little League Dr | San Bernardino | 92407 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO |  |  | 3479382 | 2115928 | 2126667 | 2024-04-01 | 12 | YES | Level 3 | YES | 2023-01-06 | 2023-02-06 | 21 | 21 | 2022-09-07 | 2022-09-07 | 105 | 105 | 1 | 1 | 2022-09-13 |  | 2022-09-16 |  |  |  |  | 2023-03-17 | 133 | 133 | 2023-07-07 | 2023-07-07 | 2023-08-31 | 2023-08-17 | 108 | 108 | 2023-08-17 | 2023-08-23 | 5 | 5 | 2023-09-08 | 2023-09-08 | 12 | 12 | 2023-09-11 | 2 | 2 | 2023-09-11 | 2023-09-11 | 2023-09-11 | 2023-09-25 | 2 | 2 | 23 | 23 | 11 | 11 | 2023-09-22 | 2023-10-18 | 2023-10-30 | 11 | 11 | 9 | 9 | 27 | 27 | 2023-12-22 | 73 | 73 | 2023-11-06 | -33 |  | 2023-09-11 | 2023-09-11 | 2023-10-30 | 2023-11-06 | 41 | 41 | 74 | 74 | 2023-11-20 | 2023-12-18 | 2024-02-21 | 62 | 62 | 2023-11-20 |  |  | 2023-12-01 | 8 | 8 | [6 empty] | 2024-01-31 | 2024-02-02 | 50 | 50 | 3 | 3 | 2024-02-22
1506 | Pepsi Buena Park, Bottling Group 6261 Caballero Blvd | 6261 1/2 Caballero Blvd Buena Park | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  | Cuba 12kV |  |  |  |  | 3 |  |  | YES | 2023-05-15 | 2022-10-11 | -150 |  | 2022-07-15 | 2023-10-03 | -248 |  | 309 | 309
1507 | Rialto, CA - 518 W Foothill Blvd | 520 W Foothill Blvd | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  | Mateus 12kV | 3472277 | 2153210 | 2153226 | 2023-06-30 | 12 | YES | Level 3 | YES | 2022-10-03 | 2022-10-18 | 12 | 12 | 2023-03-14 | 2022-09-20 | 21 | 21 | -121 |  | 2022-09-26 |  | 2022-09-30 |  |  |  |  | 2023-03-14 | 1 | 1 | 2023-03-14 | 2023-03-15 | 2023-07-28 | 2023-07-28 | 97 | 97 | 2023-07-28 | 2023-08-11 | 11 | 11 | 2023-09-01 | 2023-09-15 | 25 | 25 | 2023-09-18 | 2 | 2 | [10 empty] | 2023-09-15 | 2023-09-28 |  | 1 | 1 |  |  |  |  | 2023-09-21 | 4 | 4 | [9 empty] | 5 | 5
1508 | Corona, CA - 800 Serfas Club Dr | 800 Serfas Club Dr Corona | Corona | 92882 | Riverside County | 10. Customer Hold | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-06-30 |  |  |  |  | 2022-11-03 |  |  |  | 2022-09-21 | 2022-09-21 |  |  | 1 | 1 | 2022-09-28 |  | 2022-11-03
1509 |  | 132 North D St. | Exeter | 93221 | Tulare County | 4. Preliminary Design | 51 - Tulare | San Joaquin | Ventura | [9 empty] | YES |  |  |  |  | 2022-09-21 | 2022-09-21 |  |  | 1 | 1 | 2022-09-26 | 2022-09-26 | 2022-09-30 | 4 | 4 | 5 | 5
1510 | Ventura, CA - 5950 Telegraph Rd | 5950 Telegraph Rd | Ventura | 93003 | Ventura County | 6. Requirements (permit, easment, etc.) | 39 - Ventura | North Coast | Ventura |  | Vineyard or Maloy 16kV | 3680234 | 2229780 |  | 2024-12-30 | 8 | YES | Level 1 | YES | 2023-02-08 | 2024-02-12 | 255 | 255 | 2022-09-07 | 2022-09-07 | 361 | 361 | 1 | 1 | 2022-09-20 | 2023-09-05 | 2023-09-05 | 252 | 252 | 1 | 1 | 2024-02-15 | 364 | 364 | 2024-02-20 | 2024-02-20 | 2024-04-04
1511 | Ventura. CA -old address 4714 Telephone Rd | 4720 Telephone Rd EV-1 | Ventura | 93003 | Ventura County | 12. System Upgrade | 39 - Ventura | North Coast | Ventura |  | Alfredo 16kV | 3470915 | 2142886 |  | 2024-09-15 |  | YES | Level 2 | YES | 2023-01-09 | 2023-02-09 | 23 | 23 | 2022-09-07 | 2022-09-07 | 108 | 108 | 1 | 1 | 2022-09-07 | 2022-09-12 | 2022-09-23 | 4 | 4 | 10 | 10 |  |  |  | 2023-05-25 | 2023-05-25 | 2023-07-12 | 2023-07-07 |  |  | 2023-07-07 | 2023-07-18 | 8 | 8 |  | 2023-08-09 | 17 | 17 | 2023-08-09 | 1 | 1 | 2023-08-22 | 2023-08-22 | 2023-08-22 |  | 10 | 10 |  |  |  |  | 2023-08-16 | 2023-10-16 |  | 6 | 6 | [10 empty] | 2023-08-22
1512 | 5722 Telephone Rd, Ventura | 5722 Telephone Rd | Ventura | 93003 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  | Gringo 16kV |  |  |  | 2024-08-30 | 12 | YES |  | YES | 2022-09-23 | 2023-07-17 | 205 | 205 | 2022-09-07 | 2022-09-07 | 217 | 217 | 1 | 1 | 2023-06-22 |  | 2022-09-22
1513 | Oxnard, CA - 369 W Esplanade Dr | 369 W Esplanade Dr, Oxnard | Oxnard | 93036 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  | Alvarado 16kV |  |  |  | 2024-12-15 |  |  |  | YES | 2022-09-26 |  |  |  | 2022-09-07 | [7 empty] | 2022-09-26
1514 | Alhambra Costco Plaza | 2115 W Commonwealth Ave - EV | Alhambra | 91803 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona | [5 empty] | 2023-12-15 |  |  |  | YES | 2023-03-10 |  |  |  | 2023-02-07 | 2023-02-07 |  |  | 1 | 1 | 2023-02-08 | 2023-02-09 | 2023-02-22 | 3 | 3 | 9 | 9
1515 | Winco Foods | 40435 Winchester Rd | Temecula | 92591 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | Moraga | Temeck 12kV |  |  |  | 2023-11-01 |  |  |  | YES | 2022-11-15 | 2022-11-28 | 8 | 8 | 2022-09-23 | 2022-09-23 | 44 | 44 | 1 | 1 | 2022-09-27 | 2022-10-04 | 2022-11-09 | 8 | 8 | 27 | 27
1516 | City of Industry, CA - 1600 Stoner Creek Rd | 1600 Stoner Creek Rd | City of Industry | 91748 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-03-01 |  | NO |  |  | 2022-10-27 | 2023-01-17 | 55 | 55 | 2022-09-27 | 2022-09-27 | 77 | 77 | 1 | 1 | 2022-09-28 | 2022-10-06 | 2022-10-26 | 8 | 8 | 15 | 15 | 2023-01-03 | 68 | 68
1517 | 375 Bristol Street | 375 Bristol Street | Costa Mesa | 92626 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2023-02-28 | [8 empty] | 2022-09-27 | 2022-09-27 |  |  | 1 | 1 | 2022-09-29 |  | 2022-09-30
1518 | Camarillo, CA - 181 Arneill Rd | 181 Arneill Rd, Camarillo | Camarillo | 93010 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura |  | Crosson 16kV |  |  |  | 2024-09-02 |  |  |  | YES | 2022-10-21 | 2022-10-24 | 2 | 2 | 2022-09-28 | 2022-09-28 | 19 | 19 | 1 | 1 | 2022-09-28 | 2022-10-11 | 2022-10-14 | 10 | 10 | 4 | 4
1519 | 3116 W 135th St, Hawthorne | 3116 W 135th St | Hawthorne | 90250 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-03-17 |  |  |  | YES |  |  |  |  | 2022-09-28 | 2022-09-28 |  |  | 1 | 1 | 2022-10-11
1520 | 18 EV W Thousand Oaks Blvd | 18 EV W Thousand Oaks Blvd | Thousand Oaks | 91360 | Ventura County | 6. Requirements (permit, easment, etc.) | 35 - Thousand Oaks | North Coast | Ventura | Thousand Oaks | Byer 16 KV | 3440151 | 2195451 | 2195445 | 2024-06-05 | 6 | YES | Level 3 | YES | 2022-10-11 | 2022-10-17 | 5 | 5 | 2022-09-27 | 2022-09-27 | 15 | 15 | 1 | 1 | 2022-09-28 | 2022-10-04 | 2022-11-08 | 6 | 6 | 26 | 26 | 2022-12-15 | 55 | 55 | 2023-06-13 | 2022-12-20 | 2023-07-27 | 2023-08-25 | 178 | 178 | 2023-08-28 | 2023-09-28 | 23 | 23 | 2023-11-15 | 2023-11-14 | 34 | 34 | 2023-11-15 | 2 | 2 | 2024-03-18 |  | 2024-03-18 |  | 84 | 84 |  |  |  |  | 2023-11-14 | 2023-12-04 |  | 1 | 1 | [10 empty] | 2023-12-04
1521 | 6026 Telephone Road | 1175 Lark Ave, Unit US | Ventura | 93003 | Ventura County | 6. Requirements (permit, easment, etc.) | 39 - Ventura | North Coast | Ventura | San Miguel | Gringo 16KV | 3471643 | 2095167 |  | 2024-05-24 | 6 | YES | Level 3 | YES | 2022-10-11 | 2022-10-28 | 14 | 14 | 2022-09-28 | 2022-09-28 | 23 | 23 | 1 | 1 | 2022-09-28 | 2022-10-04 | 2022-10-08 | 5 | 5 | 4 | 4 | 2023-02-08 | 92 | 92 | 2023-02-12 | 2023-02-13 | 2023-07-07 | 2023-07-19 | 113 | 113 | 2023-07-19 | 2023-08-17 | 22 | 22 | 2023-09-15 | 2023-09-18 | 22 | 22 | 2023-09-18 | 1 | 1 | 2023-09-19 |  | 2023-09-19 |  | 2 | 2 |  |  |  |  | 2023-08-22 | 2023-10-13 | 2023-10-27 | -19 |  | 11 | 11 | 48 | 48 | 2023-10-11 | 18 | 18 |  |  |  | 2023-09-19 | 2023-09-19 |  |  |  |  | 18 | 18
1522 | Agoura Hills, CA - 28863 Agoura Rd, | 28752 1/2 ROADSIDE DR. | Agoura Hills | 91301 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  | Triunfo 16kV | 3564264 | 2194690 | 2194487 | 2024-07-29 |  | YES | Level 3 | YES | 2022-10-21 | 2022-10-27 | 5 | 5 | 2022-10-03 | 2022-10-03 | 19 | 19 | 1 | 1 | 2022-11-10 | 2022-10-10 | 2022-10-14 | 6 | 6 | 5 | 5 |  |  |  | 2023-07-12 | 2023-07-13 | 2023-11-10 | 2023-11-07 |  |  | 2023-11-13 | 2023-11-16 | 4 | 4 | 2023-12-14 | 2024-01-16 | 39 | 39 | 2024-01-18 | 3 | 3 | 2024-03-05 |  | 2024-03-05 | 2024-03-11 | 35 | 35 | 77 | 77 | 5 | 5 | 2023-12-06 | 2024-01-08 | 2024-03-07 | -27 |  | 42 | 42 | 63 | 63 | [6 empty] | 2024-01-08 |  | 2024-03-11
1523 | Corona, CA - 419 N McKinley St | 419 N McKinley St. Corona | Corona | 92879 | Riverside County | 9. Complete | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-06-30 |  |  |  | YES |  |  |  |  | 2022-10-04 | 2022-10-04 |  |  | 1 | 1 | 2022-10-10 |  | 2022-11-07
1524 | Highland, CA - 4150 E Highland Ave | 4154 E Highland Ave, Highland | Highland | 92346 | San Bernardino County | 5. Final Design | 31 - Redlands | Desert | SBRO |  | Goldbuckle 12kV | 3446788 | 2081307 |  | 2024-06-30 | 8 | NO |  | YES | 2022-10-21 |  |  |  | 2022-10-04 | 2023-08-16 |  |  | 220 | 220 | 2023-08-16 | 2023-08-22 | 2022-10-14 | 5 | 5 | -216 |  | 2022-12-29 | 60 | 60 | 2022-12-29 | 2023-08-16 | 2023-09-28 | 2023-01-12 | 11 | 11 | 2023-01-12 | 2023-01-17 | 3 | 3 | 2023-03-03 | 2023-08-16 | 149 | 149 | 2023-09-20 | 25 | 25 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-10-20 | 25 | 25 | 195 | 195 | 23 | 23 | 2023-02-15 | 2023-08-21 | 2023-10-18 | -128 |  | 42 | 42 | 172 | 172 | [6 empty] | 2023-08-21 |  | 2023-10-20 | [5 empty] | 2023-09-22 | 2023-09-27 | 2023-10-13 | 16 | 16 | 2023-07-06 | 2023-09-11 |  | 2023-07-19 | 10 | 10 | [6 empty] | 2023-10-11 | 2023-10-20 | 76 | 76 | 8 | 8 | 2023-10-24 | 2023-12-04 | 28 | 28 | 2023-12-05 | 29 | 29 | 2023-12-05 | 2023-12-05 | 1 | 1 | 296 | 296 | 237 | 237 | 2023
1525 | RACER LAX-Aviation | 9150 EV3 Aviation Blvd | Inglewood | 90301 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3483188 | 2199498 |  | 2024-12-31 |  | YES | Level 3 | YES | 2022-10-20 | 2022-10-25 | 4 | 4 | 2022-10-05 | 2022-10-06 | 14 | 14 | 2 | 2 | 2022-10-06 | 2022-10-11 | 2022-10-20 | 4 | 4 | 8 | 8 | 2023-02-27 | 99 | 99 | 2023-03-03 | 2023-03-03 | 2023-05-05 | 2023-06-30 | 89 | 89 | 2023-06-30 | 2024-02-28 | 166 | 166 | 2024-04-12
1526 | 12353 Mariposa Rd, Victorville | 12353 Mariposa Rd, Victorville | Victorville | 92395 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO |  | Mauna Loa 12kV |  |  |  | 2024-07-01 |  |  |  | YES | 2022-10-06 | 2022-10-18 | 9 | 9 | 2022-09-15 | 2022-09-15 | 24 | 24 | 1 | 1 | 2022-09-19 | 2023-09-29 | 2022-10-07 | 264 | 264 | -248
1527 | Norwalk, CA - 10968 Rosecrans Ave | 10968 Rosecrans Ave., Norwalk | Norwalk | 90650 | Los Angeles County | 3. Active | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2024-02-17 |  |  |  | YES |  |  |  |  | 2022-10-07 | 2022-10-07 |  |  | 1 | 1 | 2022-10-19 | 2022-11-16 | 2022-11-16 | 28 | 28 | 1 | 1
1528 | Montebello, CA - 1445 N Montebello Blvd | 1445 N Montebello Blvd, Montebello | Montebello | 90640 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 3488344 |  |  | 2024-12-31 | 16 | YES |  | YES | 2023-02-21 | 2023-03-07 | 11 | 11 | 2023-07-05 | 2023-07-05 | -85 |  | 1 | 1 | 2023-07-06 | 2023-07-10 | 2023-07-21 | 4 | 4 | 10 | 10 | 2023-10-18 | 75 | 75 | 2023-10-18
1529 | Redondo Beach, CA - 300 N Harbor Dr | 300 N Harbor Dr, Redondo Beach | Redondo Beach | 90277 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-02-13 |  |  |  | YES |  |  |  |  | 2022-10-10 | 2022-10-10 |  |  | 1 | 1 | 2022-10-18 |  | 2022-11-08
1531 | Town Center | 16328 Main St. | Chino | 91708 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona |  |  | 3454671 | 2207594 |  | 2024-05-15 |  | YES | Level 2 | YES | 2022-11-18 | 2023-01-06 | 34 | 34 | 2022-10-11 | 2022-10-11 | 61 | 61 | 1 | 1 | 2022-10-17 | 2022-12-06 | 2022-12-06 | 38 | 38 | 1 | 1 | 2023-09-20 | 239 | 239 | 2023-11-13 | 2023-11-13 | 2023-10-20 | 2023-10-16 | 19 | 19 | 2023-10-17 | 2023-11-06 | 15 | 15 | 2023-12-08 | 2023-12-08 | 23 | 23 | 2023-12-08 | 1 | 1 | [10 empty] | 2023-12-13 |  |  | 4 | 4
1532 | Lancaster 2706784 | 108 EV E Avenue K | Lancaster | 93535 | Los Angeles County | 10. Customer Hold | 36 - Antelope Valley | North Valley | Ventura |  | Assembly 12kV | 3484201 | 2228363 | 2228366 | 2024-01-31 | 4 | YES | Level 3 | YES | 2023-05-23 |  |  |  | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-17 | 2022-10-23 | 4 | 4 | 5 | 5 | 2023-06-06 | 164 | 164 | 2023-10-05 | 2023-10-05 | 2023-11-20 | 2023-12-06 | 128 | 128 | 2023-12-06 | 2024-01-12 | 26 | 26 | 2024-02-05 | 2024-02-15 | 24 | 24 | 2024-02-15 | 1 | 1 | 2024-03-13 | 2024-03-18 | 2024-03-13 |  | 19 | 19 |  |  |  |  | 2024-01-31 | 2024-02-15 |  | -12 | [5 empty] | 2024-02-16 | 2 | 2 | 2024-03-11 | 16 | 16 | 2024-02-15 | 2024-02-15 |  |  |  |  | 2 | 2
1533 | Covina 2709512 | 731 N Grand Ave. | Covina | 91723 | Los Angeles County | 10. Customer Hold | 26 - Covina | Metro East | Pomona |  |  | 3482159 |  |  | 2025-01-03 | 4 | YES |  | NO | 2023-06-06 | 2023-11-08 | 110 | 110 | 2022-10-12 | 2022-10-12 | 273 | 273 | 1 | 1 | 2022-10-13 | 2022-10-24 | 2022-11-22 | 9 | 9 | 21 | 21 | 2023-06-06 | 164 | 164 | 2023-02-28
1534 | Oxnard | 2200 N Rose Ave. | Oxnard | 93036 | Ventura County | 10. Customer Hold | 39 - Ventura | North Coast | Ventura |  |  | 3467645 |  |  |  |  | YES | [6 empty] | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-17 | 2022-10-25 | 4 | 4 | 7 | 7 | 2023-01-23 | 70 | 70 | 2023-03-21 | 2023-03-22 | 2023-05-04 | 2023-05-05 | 74 | 74
1535 | Yucca Valley | 6940 Old Woman Springs Rd. | Yucca Valley | 92284 | San Bernardino County | 10. Customer Hold | 84 - Yucca Valley | Rurals | SBRO | [7 empty] | YES | [6 empty] | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-17 | 2023-01-03 | 4 | 4 | 54 | 54
1536 | Lake Elsinore | 29300 Central Ave | Lake Elsinore | 92532 | Riverside County | 10. Customer Hold | 77 - Menifee | San Jacinto | Wildomar |  |  | 3483080 |  |  |  |  | YES | Level 2 | YES |  |  |  |  | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-18 | 2022-11-13 | 5 | 5 | 18 | 18 | 2023-01-23 | 70 | 70 | 2023-03-01 | 2023-03-02 | 2023-04-14 | 2023-04-05 | 52 | 52 | 2023-04-05
1537 | Sun City | 29955 Haun Rd. | Sun City | 92586 | Riverside County | 10. Customer Hold | 77 - Menifee | San Jacinto | Wildomar |  |  | 3485840 |  |  |  |  | YES |  | YES | 2023-05-23 | 2023-07-06 | 31 | 31 | 2022-10-12 | 2022-10-12 | 185 | 185 | 1 | 1 | 2022-10-13 | 2022-10-18 | 2022-11-30 | 5 | 5 | 29 | 29 | 2023-06-06 | 164 | 164 | 2023-07-12 | 2023-07-12
1538 | Palm Desert Gerald Ford 2709481 | 75000 Gerald Ford Dr | Palm Desert | 92211 | Riverside County | 5. Final Design | 79 - Palm Springs | Desert | SBRO |  |  | 3484851 |  |  |  | 6 | YES |  | YES | 2023-06-20 |  |  |  | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-17 | 2022-11-13 | 4 | 4 | 19 | 19 | 2023-03-02 | 97 | 97 | 2023-10-05 | 2023-10-05 | 2023-10-31 | 2023-10-18 | 162 | 162 | 2023-10-18
1539 | Hemet 2706062 R1 | 4852 W. Florida Ave. | Hemet | 92545 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3465598 | 2211695 | 2202275 | 2024-03-29 | 4 | YES |  | YES | 2023-06-20 | 2023-08-14 | 39 | 39 | 2022-10-12 | 2022-10-12 | 212 | 212 | 1 | 1 | 2022-10-13 | 2022-10-18 | 2022-12-07 | 5 | 5 | 34 | 34 | 2023-06-20 | 174 | 174 | 2023-10-23 |  | 2023-12-08 | 2024-01-18 | 146 | 146 | 2024-01-18 | 2024-02-08 | 16 | 16 | 2024-03-04
1540 | Fontana, CA - 16757 Slover Ave | 16757 Slover Ave Fontana | Fontana | 92337 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-06-30 |  |  |  | YES | 2022-10-31 |  |  |  | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 | 2022-10-13 | 2022-10-19 | 2022-10-31 | 6 | 6 | 9 | 9
1541 | La Puente, CA - 825 N Hacienda | 825 N Hacienda Blvd, La Puente | La Puente | 91744 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona |  |  | 3565677 |  |  | 2024-04-27 | 20 | YES | Level 2 | YES |  |  |  |  | 2022-10-12 | 2022-10-12 |  |  | 1 | 1 |  | 2022-10-24 | 2023-06-16 | 9 | 9 | 164 | 164 |  |  |  | 2023-07-14 | 2023-08-23 | 2023-09-05
1542 | Ontario, CA - 1521 E 4th St | 1521 E 4th St, Ontario, CA 91764 | Ontario | 91764 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-04-01 |  |  |  | YES | 2022-10-31 |  |  |  | 2022-10-13 | 2022-10-13 |  |  | 1 | 1 |  | 2022-10-24 | 2022-10-31 | 8 | 8 | 6 | 6
1543 | R29 West Covina, CA - 2400 S Azusa Ave | 2400 S Azusa Ave, West Covina | West Covina | 91792 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-11-29 |  | YES |  |  | 2024-02-14 |  |  |  | 2022-10-12 | 2023-08-01 |  |  | 203 | 203 | 2023-08-08 | 2023-08-15 | 2023-08-25 | 11 | 11 | 9 | 9
1544 | Shell Neptune | 1189 E 6th St. | Beaumont | 92223 | Riverside County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3422103 | 2079921 | [10 empty] | 2022-10-14 | 2022-10-17 |  |  | 2 | 2 | 2022-10-17 | 2022-10-19 | 2022-11-13 | 3 | 3 | 17 | 17 | 2022-11-14 | 21 | 21 | 2022-11-14 | 2022-11-17 | 2023-01-04 | 2023-01-12 | 42 | 42 | 2023-01-12 | 2023-01-16 | 2 | 2 | 2023-02-07 | [16 empty] | 2023-03-02 | 2023-03-06
1545 | Inglewood Burin | 11332 S Burin Ave | Inglewood | 90304 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2030-07-18 |  |  |  | NO |  |  |  |  | 2022-10-17 | 2022-10-17 |  |  | 1 | 1 | 2022-10-18 | 2022-10-26 | 2022-11-29 | 8 | 8 | 22 | 22
1546 | Housing Authority of the City of Los Angeles (HACLA) | 2212 E Imperial Hwy | Los Angeles | 90059 | Los Angeles County | 4. Preliminary Design | 32 - Compton | Metro West | Alhambra |  |  | 3555215 | 2226364 |  |  | 5 | YES |  | YES |  |  |  |  | 2022-10-17 | 2022-10-17 |  |  | 1 | 1 | 2022-10-18 | 2022-10-26 | 2022-11-01 | 8 | 8 | 5 | 5 | 2023-09-27 | 240 | 240 | 2024-01-17 | 2024-01-18 | 2024-02-15 | 2024-02-13 | 95 | 95 | 2024-02-13
1548 | Goldenwest Plaza | 7222 Edinger Ave | Huntington Beach | 92647 | Orange County | 1. FVR | 33 - Huntington Beach | Orange | Saddleback |  |  | 3516058 |  |  | 2024-12-15 | 32 | YES | Level 3 | YES | 2023-03-03 | 2023-04-12 | 29 | 29 | 2022-10-17 | 2022-10-17 | 123 | 123 | 1 | 1 | 2022-10-18 | 2022-10-27 | 2022-12-06 | 9 | 9 | 26 | 26 | 2023-03-09 | 99 | 99 | 2023-04-19 | 2023-04-19 | 2023-06-29 | 2023-06-29 | 80 | 80 | 2023-06-29
1549 | 6322 Mission Blvd | 6322 Mission Blvd | Riverside | 92509 | Riverside County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO | [6 empty] | 20 | YES |  | YES |  |  |  |  | 2023-11-08 | 2023-11-14 |  |  | 5 | 5 | 2023-11-16 | 2023-11-27 | 2023-11-27 | 8 | 8 | 1 | 1
1550 | DIB6 Redlands | 1895 Marigold Ave | Redlands | 92374 | San Bernardino County | 4. Preliminary Design | 31 - Redlands | Desert | SBRO |  |  | 3622668 | 2225608 |  | 2025-04-30 | 325 | NO |  | YES | 2023-08-25 | 2023-10-03 | 27 | 27 | 2022-10-20 | 2022-10-20 | 241 | 241 | 1 | 1 | 2022-10-24 | 2022-10-25 | 2022-10-31 | 4 | 4 | 5 | 5 | 2023-10-18 | 252 | 252 | 2023-10-23 | 2023-10-24 | 2024-02-20 | 2024-02-13 | 80 | 80 | 2024-02-13
1551 | DAX5 City of Industry | 15930 Valley Blvd | La Puente | 91744 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona |  |  | 3691454 |  |  | 2024-12-12 | 331 | NO |  | YES | 2023-08-11 |  |  |  | 2022-10-20 | 2022-10-20 |  |  | 1 | 1 | 2022-10-24 | 2022-10-31 | 2022-12-06 | 8 | 8 | 24 | 24 | 2024-03-06 | 346 | 346 | 2024-03-11 |  | 2024-04-22
1552 | DCX2 Mission Viejo | 25725 Jeronimo Rd. | Mission Viejo | 92691 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback |  |  | 3691695 |  |  | 2023-05-01 | 283 | NO |  | YES | 2024-01-24 | 2024-03-07 | 31 | 31 | 2022-10-20 | 2023-10-31 | 87 | 87 | 261 | 261 | 2023-11-01 | 2023-11-03 | 2023-11-08 | 4 | 4 | 4 | 4 | 2024-03-07 | 347 | 347
1553 | Temecula, CA - 30534 Rancho California Rd (burger king) | 30534 Rancho California Rd. | Temecula | 92591 | Riverside County | 9. Complete | 77 - Menifee | San Jacinto | Wildomar |  | Cariso 12kV | 3574555 |  |  | 2024-09-15 | 8 | YES | Level 1 | YES | 2023-05-23 | 2023-07-06 | 31 | 31 | 2022-09-16 | 2023-05-31 | 26 | 26 | 178 | 178 | 2023-05-31 | 2023-06-15 | 2023-06-21 | 12 | 12 | 5 | 5 | 2023-07-27 | 218 | 218 | 2023-07-28 | 2023-07-31
1554 | 6200 Edinger Ave | 6210 Edinger Ave | Huntington Beach | 92648 | Orange County | 1. FVR | 33 - Huntington Beach | Orange | Saddleback |  |  | 3431955 | 2078942 | 2111101 |  | 192 | YES | Level 3 | YES | 2022-10-24 | 2022-10-25 | 2 | 2 | 2022-10-10 | 2022-10-10 | 12 | 12 | 1 | 1 | 2022-10-11 | 2022-10-19 | 2022-10-24 | 8 | 8 | 4 | 4 | 2023-02-22 | 93 | 93 | 2023-07-06 | 2023-07-10 | 2023-08-17 | 2023-04-07 | 33 | 33 | 2023-04-07 | 2023-04-10 | 2 | 2 | 2023-05-01 | 2023-07-20 | 72 | 72 | 2023-07-21 | 2 | 2 | 2023-07-21 | 2023-08-07 | 2023-07-21 | 2023-08-07 | 2 | 2 | 84 | 84 | 12 | 12 | 2023-10-09 | 2023-10-18 | 2023-11-01 | 57 | 57 | 11 | 11 | 18 | 18 | [6 empty] | 2023-07-21 |  | 2023-11-01 | [5 empty] | 2023-09-01 | 2023-10-03 | 2023-11-14 | 52 | 52 | 2023-08-24 |  |  | 2023-08-24 | 1 | 1 | [6 empty] | 2024-01-30 | 2024-02-07 | 114 | 114 | 7 | 7 | 2023-09-14 | 2024-03-15 | 126 | 126 | 2024-03-15 | 126 | 126 | 2024-03-15 |  |  |  | 361 | 361 | 269 | 269 | 2024
1555 | Orange - City Blvd. | 20 City Boulevard West | Orange | 92868 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2025-02-10 | 12 | YES | [6 empty] | 2022-10-24 | 2024-03-11 |  |  | 347 | 347 | 2024-03-12 | 2024-03-25 |  | 11 | 11
1556 | Winco | 14338 Foothill Blvd | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-06-30 |  |  |  | YES |  |  |  |  | 2022-10-25 | 2022-10-25 |  |  | 1 | 1 | 2023-02-01 | 2022-10-31 | 2023-02-07 | 5 | 5 | 68 | 68
1557 | Murrieta, CA - 40931 California Oaks Rd | 40931 California Oaks Rd. | Murrieta | 92562 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  | Gridiron 12kV | 3601659 |  |  | 2024-01-15 | 16 | YES | Level 3 | YES | 2023-05-31 | 2023-07-14 | 32 | 32 | 2022-09-16 | 2023-06-28 | 12 | 12 | 198 | 198 | 2022-09-19 | 2023-07-10 | 2023-07-18 | 8 | 8 | 7 | 7 | 2023-08-31 | 243 | 243 | 2023-09-12 | 2023-09-13 | 2023-10-26
1558 | 1420 W Valley Blvd EV1 | 1420 W Valley Blvd EV1 | Alhambra | 91803 | Los Angeles County | 10. Customer Hold | 22 - Montebello | Metro East | Pomona | [9 empty] | NO | 2022-10-27 |  |  |  | 2022-10-27
1559 | CIRCLE K-CALIMESA | 109 W County Line RD | Calimesa | 92320 | Riverside County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-12-30 | 4 |  |  | YES |  |  |  |  | 2022-10-26 | 2022-10-26 |  |  | 1 | 1 | 2022-10-27 | 2022-11-01 | 2022-12-01 | 5 | 5 | 20 | 20
1560 | Whole Foods Plaza Laguna Niguel | 23932 Aliso Creek Rd. - EV | Laguna Niguel | 92677 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2023-06-22 |  |  |  |  | 2022-12-21 | 2023-01-23 | 23 | 23 | 2022-10-27 | 2022-10-27 | 59 | 59 | 1 | 1 | 2022-10-31 | 2022-11-01 | 2022-11-18 | 4 | 4 | 13 | 13
1561 | Intersection of Riverpark Blvd & Colorado River Pl, Oxnard, CA | Riverpark Blvd | Oxnard | 93036 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [5 empty] | 2023-12-29 | [16 empty] | 2022-11-05
1562 | Long Beach, CA- 2955 Bellflower Blvd | 2955 N Bellflower Blvd, Long Beach, CA, 90815 | Long Beach | 90815 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-04-27 |  |  |  | YES |  |  |  |  | 2022-10-27 | 2022-10-27 |  |  | 1 | 1 | 2022-11-03 | 2022-11-22 | 2022-11-22 | 18 | 18 | 1 | 1
1563 | Lancaster | 43144 10th St W | Lancaster | 93534 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | Shuttle | Han Solo 12kV | 3456432 |  |  | 2023-08-13 |  | NO |  | YES | 2023-01-18 | 2023-02-03 | 13 | 13 | 2022-10-26 | 2022-10-26 | 69 | 69 | 1 | 1 | 2022-11-01 | 2022-11-07 | 2022-11-14 | 9 | 9 | 5 | 5 | 2023-01-06 | 50 | 50 | 2023-01-19 | 2023-01-20 | 2023-03-07 | 2023-02-24 | 34 | 34 | 2023-02-24
1564 | Eastvale | 4950 Goodman Rd. | Eastvale | 91752 | Riverside County | 5. Final Design | 34 - Ontario | Metro East | Pomona | Mira Loma | Olympus 12kV |  |  |  | 2023-06-30 |  |  |  | YES | 2022-12-02 | 2022-12-15 | 10 | 10 | 2022-11-01 | 2022-11-01 | 30 | 30 | 1 | 1 | 2022-11-02 | 2022-11-07 |  | 5 | 5
1565 | John Wayne Airport | 1512 Main Street | Irvine | 92614 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | FAIRVIEW | REDHILL 12KV | 3618940 |  |  | 2023-12-30 | 10 | YES | Level 3 |  | 2023-08-28 | 2023-10-11 | 32 | 32 | 2022-10-25 | 2022-10-25 | 244 | 244 | 1 | 1 | 2022-11-08 | 2022-11-28 | 2022-11-28 | 22 | 22 | 1 | 1 | 2023-10-17 | 248 | 248 | 2023-10-17 | 2023-10-18 | 2023-12-04 | 2023-12-13 | 40 | 40 | 2023-12-13
1566 | Victorville | 12818 Mariposa Rd. | Victorville | 92395 | San Bernardino County | 7. Civil Construction | 73 - Victorville | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2022-11-02 | 2022-11-02 |  |  | 1 | 1 | 2022-11-02 | 2022-11-07 | 2022-11-14 | 4 | 4 | 5 | 5
1567 | Arcadia | 11800 Clark St EV | Arcadia | 91006 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 27 - Monrovia | Metro East | Pomona |  |  | 3544448 | 2211496 |  | 2024-07-05 | 4 | YES | Level 1 | YES |  |  |  |  | 2022-11-02 | 2022-11-02 |  |  | 1 | 1 | 2022-11-03 | 2022-11-09 | 2022-12-06 | 6 | 6 | 17 | 17 | 2023-06-05 | 148 | 148 | 2023-11-15 | 2023-11-30 | 2024-01-08 | 2023-12-21 | 140 | 140 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2024-01-12 | 2024-01-11 | 14 | 14 | 2024-01-09 | -3 |  | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 1 | 1 | 14 | 14 | 1 | 1 | 2023-08-22 | 2023-09-01 | 2024-03-19 | -98 |  | 136 | 136 | 144 | 144 | 2024-02-22 | 31 | 31 | 2024-03-15 | 17 | 17 | 2023-09-01 | 2023-09-01 | 2024-03-19 | 2024-03-19 | 136 | 136 | 29 | 29
1568 | Lebec PFJ 616- 42810 | 42706U Frazier Mountain Park Road | Lebec | 93243 | Kern County | 3. Active | 36 - Antelope Valley | North Valley | Ventura |  |  | 3600724 | 2192666 |  | 2024-06-28 | 4 | NO |  | YES | 2023-07-24 | 2023-09-07 | 33 | 33 | 2022-11-02 | 2022-11-02 | 214 | 214 | 1 | 1 | 2022-11-03 | 2022-11-15 | 2022-12-01 | 9 | 9 | 11 | 11 | 2023-09-12 | 217 | 217 | 2023-09-12 | 2023-09-13 | 2023-10-25 | 2023-11-01 | 37 | 37 | 2023-11-01 | 2023-11-15 | 11 | 11 | 2023-12-08 | 2024-01-11 | 38 | 38 | 2024-01-11 | 1 | 1 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 7 | 7 | 44 | 44 | 1 | 1 | 2024-01-24 | 2024-01-24 |  | 9 | 9 | [10 empty] | 2024-01-22
1569 | 27450 Ynez Rd, Temecula, CA, United States | 27450 Ynez Rd | Temecula | 92592 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-11-01 |  |  |  |  | 2022-10-31 |  |  |  | 2022-09-27 | 2022-09-27 |  |  | 1 | 1 | 2022-10-30 | 2022-10-30 | 2022-10-30 | 24 | 24 | 0
1570 | 625 N San Vincente Blvd, West Hollywood | 625 N San Vicente Blvd | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 |  | 2022-11-13 | 2022-11-13 | 10 | 10 | 0
1571 | Kings Road Parking Garage | 8383 Santa Monica Blvd | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 |  | 2022-11-13 | 2022-11-13 | 10 | 10 | 0
1572 | La Jolla Lot | 1044 N La Jolla Ave | Los Angeles | 90046 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-08 | 2022-11-15 | 2022-11-15 | 12 | 12 | 1 | 1
1573 | Plummer Park North | 1248 N Vista St | Los Angeles | 90068 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2024-06-30 |  |  |  | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-09 | 2022-11-17 | 2022-11-17 | 14 | 14 | 1 | 1
1574 | West Hollywood, CA- 7377 Santa Monica Blvd (Plummer Park South) | 7377 Santa Monica Blvd | West Hollywood | 90046 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2024-06-30 |  |  |  | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-09 | 2022-11-17 | 2022-11-17 | 14 | 14 | 1 | 1
1575 | Robertson Lot | 617 N Robertson Blvd | West Hollywood | 90069 | Los Angeles County | 11. Cancelled | 42 - Santa Monica | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-08 | 2022-11-13 | 2022-11-13 | 10 | 10 | 0
1576 | Spaulding Lot | 7718 Santa Monica | Los Angeles | 90046 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-04-01 |  |  |  | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-10
1577 | Spaulding Lot | 7718 Santa Monica Blvd | West Hollywood | 90046 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-10-28 | 2022-10-28 |  |  | 1 | 1 | 2022-11-09 | 2022-11-15 | 2022-11-15 | 12 | 12 | 1 | 1
1578 | Mira Loma PFJ 1009 | 11053 Riverside Drive | Mira Loma | 91752 | Riverside County | 3. Active | 30 - Foothill | Desert | SBRO |  |  | 3589226 |  |  |  | 6 | NO |  | YES | 2023-06-12 | 2023-07-14 | 24 | 24 | 2022-11-04 | 2022-11-04 | 174 | 174 | 1 | 1 | 2022-11-07 | 2022-11-08 | 2022-12-20 | 3 | 3 | 28 | 28 | 2023-06-05 | 146 | 146 | 2023-08-22 | 2023-08-28
1580 | Palmdale | 5231 Pearblossom Hwy | Palmdale | 93552 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura |  |  | 3630088 | 2207432 |  |  |  | NO |  | YES | 2023-10-10 | 2023-10-31 | 16 | 16 | 2023-08-08 | 2023-08-08 | 60 | 60 | 1 | 1 | 2023-08-08 | 2023-08-09 | 2023-10-06 | 2 | 2 | 42 | 42 | 2023-11-03 | 63 | 63 | 2023-11-06 |  | 2024-02-02
1581 | Mission Viejo Santa Margarita | 27888 Santa Margarita Pkwy - EV | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | Chiquita | Stinger 12 kV | 3450533 |  |  | 2023-09-01 |  | NO |  |  | 2022-12-15 | 2022-12-29 | 11 | 11 | 2022-11-04 | 2022-11-04 | 37 | 37 | 1 | 1 | 2022-11-07 | 2022-11-10 | 2022-12-02 | 5 | 5 | 14 | 14 | 2022-12-12 | 24 | 24 | 2023-01-09 | 2023-01-10 | 2023-02-24 | 2023-02-24 | 53 | 53 | 2023-02-24
1582 | San Gabriel, CA- 140 W Valley Blvd Phase 2 Expansion | 140 W Valley Blvd | San Gabriel | 91776 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  | Telstar 16kV | [7 empty] | YES |  | 2022-10-27 |  |  | 2022-10-10 | 2022-10-10 | 14 | 14 | 1 | 1 | 2022-10-20 | 2022-11-23 | 2022-11-23 | 32 | 32 | 1 | 1
1583 | WinCo Foods 40435 Winchester "Rd | 40435 Winchester Rd | Temecula | 92591 | Riverside County | 1. FVR | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3654565 | 2218249 | 2218250 | 2024-09-15 | 20 | YES | Level 3 | YES | 2023-05-23 |  |  |  | 2023-05-23 | 2023-05-26 |  |  | 4 | 4 | 2023-05-30 | 2023-06-12 | 2023-07-21 | 11 | 11 | 29 | 29 | 2023-12-26 | 150 | 150 | 2023-12-26 | 2023-12-26 | 2024-01-23 | 2024-01-29 | 23 | 23 | 2024-01-29
1584 | 39281 Harvard Rd | 39281 Harvard Rd | Newberry Springs | 92365 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-06-25 | 40 | YES |  |  | 2023-12-28 |  |  |  | 2023-12-13 | 2023-12-13 |  |  | 1 | 1 | 2022-12-14 | 2023-12-18 |  | 4 | 4
1585 | 20 Gill Station Coso Rd Olancha Ca 93549 | 20 Gill Station Coso Rd | Olancha | 93549 | Kern County | 3. Active | 86 - Ridgecrest | Rurals | SBRO | [9 empty] | YES |  |  |  |  | 2022-11-08 | 2022-11-08 |  |  | 1 | 1 | 2022-11-08 | 2022-11-08 | 2022-11-08 | 1 | 1 | 1 | 1
1586 |  | 1631 E Highland Ave | San Bernardino | 92404 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3467880 | 2094119 |  | 2023-11-01 |  | NO |  |  | 2023-02-06 | 2023-02-08 | 3 | 3 | 2022-10-21 | 2022-10-21 | 75 | 75 | 1 | 1 | 2022-11-06 | 2022-11-06 | 2022-11-08 | 11 | 11 | 2 | 2 | 2023-02-06 | 73 | 73 | 2023-02-07 | 2023-02-13 | 2023-03-29 | 2023-02-27 | 15 | 15 | 2023-02-27 | 2023-02-28 | 2 | 2 | 2023-03-21 | 2023-03-01 | 2 | 2 | 2023-03-01 | 1 | 1 | 2023-03-09 |  | 2023-03-09 |  | 7 | 7
1587 | Anderson Lot | 16470 E Pacific Coast Hwy | Huntington Beach | 90045 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-02-15 | [8 empty] | 2022-10-03 | 2022-10-03 |  |  | 1 | 1 | 2022-10-13 | 2022-11-07 | 2023-03-27 | 26 | 26 | 96 | 96
1588 | Sports Basement | 10800 Kalama River Ave | Fountain Valley | 92708 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-02-15 |  |  |  | YES |  |  |  |  | 2022-10-03 | 2022-10-03 |  |  | 1 | 1 | 2022-10-13 | 2022-11-07 | 2022-11-07 | 26 | 26 | 1 | 1
1590 | Hesperia Cardenas Market R2 | 15555 1/2 Main St. | Hesperia | 92345 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | Aqueduct | Turbine 12kV | 3499988 | 2197861 | 2200851 | 2024-08-29 | 6 | YES | Level 3 | YES | 2023-02-22 | 2023-03-22 | 21 | 21 | 2023-05-30 | 2022-11-09 | 91 | 91 | -139 |  | 2022-11-14 | 2022-11-17 | 2022-11-18 | 6 | 6 | 2 | 2 | 2023-05-30 | 1 | 1 | 2023-08-10 | 2023-08-10 | 2023-09-22 | 2023-09-22 | 82 | 82 | 2023-09-25 | 2023-10-17 | 17 | 17 | 2023-11-07 | 2023-11-16 | 23 | 23 | 2023-11-21 | 4 | 4 | 2024-01-24 | 2024-01-24 | 2024-01-24 | 2024-01-24 | 45 | 45 | 67 | 67 | 1 | 1 | 2023-11-17 | 2023-12-01 | 2023-12-19 | 2 | 2 | 13 | 13 | 21 | 21 | 2024-03-21 | 82 | 82 |  |  |  | 2023-12-01 | 2023-12-01 | 2024-01-24 |  |  |  | 85 | 85
1591 | Cabazon | 48400 Seminole Dr. | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3557187 | 2227962 |  | 2024-10-01 |  | YES | Level 3 | YES | 2023-04-20 | 2023-06-01 | 30 | 30 | 2022-11-10 | 2022-11-10 | 140 | 140 | 1 | 1 | 2022-11-14 | 2022-11-17 | 2022-12-20 | 5 | 5 | 22 | 22 | 2023-06-27 | 158 | 158 | 2023-09-05
1592 | Goleta Magnolia Shopping Center | 5170 Hollister Ave. | Goleta | 93111 | Santa Barbara County | 3. Active | 49 - Santa Barbara | North Coast | Ventura | Vegas | Storke 16kV |  |  |  | 2023-08-08 |  |  |  | YES | 2022-12-06 | 2022-12-15 | 8 | 8 | 2022-11-15 | 2022-11-15 | 21 | 21 | 1 | 1 | 2022-11-15 | 2022-11-21 | 2022-11-27 | 5 | 5 | 3 | 3
1593 | Tehachapi PFJ 1094 | 1668 E Tehachapi Blvd - A | Tehachapi | 93561 | Kern County | 6. Requirements (permit, easment, etc.) | 52 - Tehachapi | North Valley | Ventura |  |  | 3653647 |  |  |  | 4 | NO |  | YES | 2023-11-06 | 2023-12-20 | 31 | 31 | 2024-01-25 | 2024-01-25 | -24 |  | 1 | 1 | 2024-01-26 | 2024-02-01 | 2024-02-18 | 6 | 6 | 12 | 12 | 2023-11-06 | -54 |  | 2023-12-21 | 2024-01-02
1594 | Murrieta Target R1 | 27818 Clinton Keith Rd - EV | Murrieta | 92562 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3524161 | 2138110 |  | 2024-08-13 | 8 | YES | Level 1 | YES | 2023-05-01 |  |  |  | 2022-11-11 | 2022-11-15 |  |  | 2 | 2 | 2022-11-16 | 2022-11-23 | 2023-01-03 | 7 | 7 | 28 | 28 | 2023-05-01 | 117 | 117 | 2023-05-02 | 2023-05-04 | 2023-06-19 | 2023-06-19 | 35 | 35 | 2023-06-20 | 2023-07-28 | 28 | 28 | 2023-08-24 | 2023-09-12 | 32 | 32 | 2023-09-13 | 2 | 2 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2 | 2 | 33 | 33 | 1 | 1 | 2023-08-18 | 2023-08-30 | 2024-02-20 | -17 |  | 118 | 118 | 126 | 126 | [6 empty] | 2023-08-30 |  | 2024-02-20
1595 | Fullerton Orange Fair | 246 E Orangethorpe Ave - EV | Fullerton | 92832 | Orange County | 6. Requirements (permit, easment, etc.) | 48 - Fullerton | Orange | Saddleback | Fullerton | Raybestos 12kV |  |  |  | 2023-07-21 |  |  |  | YES | 2022-12-14 | 2022-12-16 | 3 | 3 | 2022-11-11 | 2022-11-15 | 22 | 22 | 2 | 2 | 2022-11-16 | 2022-11-17 | 2022-12-07 | 3 | 3 | 13 | 13
1596 | Hawthorne Lowes | 2800 W 120th St - EV | Hawthorne | 90250 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra |  |  | 3481417 | 2200370 | 2200369 | 2024-12-24 | 5 | YES | Level 3 | NO | 2023-02-24 | 2023-03-29 | 24 | 24 | 2022-11-15 | 2022-11-15 | 93 | 93 | 1 | 1 | 2022-11-16 | 2022-11-21 | 2022-12-12 | 5 | 5 | 14 | 14 | 2023-07-10 | 164 | 164 | 2023-07-12 | 2023-07-14 | 2023-08-28 | 2023-08-31 | 39 | 39 | 2023-08-31 | 2023-11-22 | 59 | 59 | 2023-12-18 | 2023-12-21 | 20 | 20 | 2023-12-21 | 1 | 1 | 2023-12-21 | 2023-12-21 | 2023-12-21 | 2024-01-02 | 1 | 1 | 26 | 26 | 7 | 7 | 2023-12-13 | 2024-01-24 |  | -7 | [11 empty] | 2023-12-21
1597 | Santa Barbara Amtrak Station | 209 State St | Santa Barbara | 93101 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2023-05-01 |  | YES | Level 2 | [12 empty] | 2022-11-18 | 2022-11-18 |  |  | 1 | 1
1598 |  | 1102 Montecito St | Santa Barbara | 93103 | Ventura County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2023-05-01 |  |  |  | YES |  |  |  |  | 2022-11-18 | 2022-11-18 |  |  | 1 | 1 | 2022-11-18 | 2022-11-18 | 2022-11-18 | 1 | 1 | 1 | 1
1599 | Town Center at the Preserve | 8391 Pine Ave | Chino | 91710 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-08-11 |  | YES | Level 2 |  | 2022-11-18
1600 |  | 1000 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-03-31 |  | YES |  | YES |  |  |  |  | 2022-11-17 | 2022-11-17 |  |  | 1 | 1 | 2022-11-28 | 2022-12-19 | 2022-12-19 | 21 | 21 | 1 | 1
1601 | 2750 South Towne Ave | 2720 S Towne Ave | Pomona | 91766 | Los Angeles County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3450699 | 2210534 | 2210535 | 2024-06-28 | 8 | YES | Level 3 | YES | 2023-01-09 | 2023-01-18 | 7 | 7 | 2022-11-17 | 2022-11-17 | 42 | 42 | 1 | 1 | 2023-04-10 | 2022-12-04 | 2022-12-04 | 10 | 10 | 0 |  | 2023-01-10 | 37 | 37 | 2023-08-11 | 2023-08-11 | 2023-11-08 | 2023-11-08 | 212 | 212 | 2023-11-08 | 2023-11-27 | 12 | 12 | 2024-01-02 | 2024-02-02 | 47 | 47 | 2024-02-06 | 3 | 3 | 2024-03-05 |  | 2024-03-05 | 2024-03-07 | 22 | 22 | 70 | 70 | 3 | 3 | 2024-02-02 | 2024-02-12 | 2024-03-04 | 1 | 1 | 15 | 15 | 21 | 21 | 2024-02-13 | 6 | 6 |  |  |  | 2024-02-12 | 2024-02-12 | 2024-03-07 |  |  |  | 8 | 8
1602 | WINCO | 740 W AVE K4 | LANCASTER | 93534 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2023-06-30 | [8 empty] | 2022-11-18 | 2022-11-21 |  |  | 2 | 2 | 2022-11-22 | 2022-11-29 |  | 5 | 5
1603 | 23885 Clinton Keith Rd | 23885 Clinton Keith Rd | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-01-15 |  |  |  | YES |  |  |  |  | 2022-09-27 | 2022-09-27 |  |  | 1 | 1 | 2022-10-05 | 2022-11-21 | 2022-11-21 | 39 | 39 | 1 | 1
1604 | Plaza Mexico | 3100 EAST IMPERIAL HIGHWAY - EV | LYNWOOD | 90262 | Los Angeles County | 10. Customer Hold | 32 - Compton | Metro West | Alhambra | [5 empty] | 2023-04-11 |  |  |  | YES |  |  |  |  | 2022-11-18 | 2022-11-21 |  |  | 2 | 2 | 2022-11-22
1605 | Irvine Home Depot | 6200 Irvine Blvd - EV | Irvine | 92620 | Orange County | 11. Cancelled | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2023-06-08 | [8 empty] | 2022-11-18 | 2022-11-22 |  |  | 3 | 3 | 2022-11-22 | 2022-12-01 | 2022-12-15 | 6 | 6 | 11 | 11
1606 | 22681 Lake Forest Dr, Lake Forest, CA, United States | 22681 Lake Forest Dr | Lake Forest | 92630 | Orange County | 1. FVR | 43 - Saddleback | Orange | Wildomar | [5 empty] | 2024-03-01 |  |  |  | NO |  |  |  |  | 2022-10-25 | 2022-10-25 |  |  | 1 | 1 | 2022-11-04 | 2022-11-22 | 2022-11-22 | 20 | 20 | 1 | 1
1607 | 105 Harbor Way | 105 Harbor Way | Santa Barbara | 93109 | Ventura County | 4. Preliminary Design | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2023-05-01 |  | YES |  | NO |  |  |  |  | 2023-04-05 | 2023-04-05 |  |  | 1 | 1 | 2023-04-06 | 2023-04-17 | 2023-04-23 | 9 | 9 | 5 | 5
1608 | Fullerton #33257 | 1000 W Orangethrope Ave | Fullerton | 92833 | Orange County | 4. Preliminary Design | 48 - Fullerton | Orange | Saddleback |  |  | 3602189 |  |  | 2024-01-10 | 4 | YES | Level 1 | YES |  |  |  |  | 2023-08-17 | 2023-08-17 |  |  | 1 | 1 | 2023-08-21 | 2023-08-22 | 2023-08-25 | 4 | 4 | 4 | 4 | 2023-08-28 | 8 | 8 | 2023-09-14 | 2023-09-14 | 2023-10-26 | 2023-10-23 | 40 | 40 | 2024-01-11
1609 | Upland #35875 | 2410 W Arrow Route | Upland | 91786 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3601968 |  |  | 2024-12-22 | 4 | YES | Level 1 |  | 2023-08-25 | 2023-09-04 | 6 | 6 | 2023-08-18 | 2023-08-18 | 11 | 11 | 1 | 1 | 2023-08-21 | 2023-08-22 | 2023-08-25 | 3 | 3 | 4 | 4 | 2023-09-11 | 16 | 16 | 2023-09-14 |  | 2024-01-29 | 2024-01-12 | 86 | 86 | 2024-01-12
1610 |  | 1384 S Riverside Ave. | Rialto | 92376 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [6 empty] | 4 |  |  | YES |  |  |  |  | 2022-11-22 | 2022-11-22 |  |  | 1 | 1 | 2022-11-28 | 2022-11-30 |  | 5 | 5
1611 |  | 14500 Firestone Blvd | La Mirada | 90638 | Los Angeles County | 9. Complete | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES | 2022-12-06 | 2023-01-18 | 31 | 31 | 2022-11-28 | 2022-11-28 | 37 | 37 | 1 | 1 | 2022-11-28 | 2022-11-30 | 2022-11-30 | 3 | 3 | 1 | 1
1612 | Harbor Town and Country Shopping Center | 12891 1/2 Harbor Blvd | Garden Grove | 92840 | Orange County | 6. Requirements (permit, easment, etc.) | 29 - Santa Ana | Orange | Saddleback |  |  | 3526249 | 2133241 |  | 2024-02-16 | 32 | YES | Level 2 | NO | 2023-03-16 | 2023-04-27 | 31 | 31 | 2022-10-25 | 2022-10-25 | 128 | 128 | 1 | 1 | 2022-11-04 | 2022-11-28 | 2022-11-28 | 22 | 22 | 1 | 1 |  |  |  | 2023-05-05 | 2023-05-05 | 2023-06-12 | 2023-06-13 |  |  | 2023-06-14 | 2023-06-15 | 2 | 2 | 2023-07-06 | 2023-07-18 | 23 | 23 | 2023-06-28 | -14 | [11 empty] | 2023-06-22 | 2023-07-03 | 2023-08-04 | -18 |  | 24 | 24 | 31 | 31 | 2023-08-03 | 26 | 26 | 2023-10-16 | 52 | 52 | [6 empty] | 13 | 13 | 2023-10-16 | 2023-10-30 | 2024-01-08 | 57 | 57 | [13 empty] | 2023-11-26 |  |  |  |  | 2024-01-16 | 2024-02-24 | 28 | 28 | 2024-03-01 | 33 | 33 | 2024-03-01 | 2024-03-05 | 3 | 3 | 340 | 340 |  |  | 2024
1613 | Chevron Hydrogen Moreno Valley | 12431 Heacock St Unit 2 Moreno Valley | Moreno Valley | 92553 | Riverside County | 10. Customer Hold | 77 - Menifee | San Jacinto | Wildomar |  |  | 3463945 | 2101749 |  | 2024-06-01 |  | NO | [6 empty] | 2022-10-31 | 2022-10-31 |  |  | 1 | 1 | 2022-11-02 | 2022-12-28 | 2022-12-28 | 40 | 40 | 1 | 1 | 2023-01-31 | 63 | 63 | 2023-02-01 | 2023-02-02 | 2023-03-17 | 2023-03-17 | 33 | 33 | 2023-03-20 | 2023-09-05 | 119 | 119 | 2023-10-23 | 2023-10-24 | 36 | 36 | 2023-10-25 | 2 | 2 | 2023-10-25 | 2023-12-11 | 2023-10-25 | 2023-11-01 | 2 | 2 | 42 | 42 | 6 | 6 | [28 empty] | 2024-01-11
1614 | Downtown Parking Structure | 74 S California St | Ventura | 93001 | Ventura County | 10. Customer Hold | 39 - Ventura | North Coast | Ventura | [14 empty] | 2022-11-04 | [7 empty] | 2022-11-27
1615 | 2. Hartman Parking | 2661 E Thompson Blvd | Ventura | 93003 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [14 empty] | 2022-11-04 | 2022-11-04 |  |  | 1 | 1 |  | 2022-11-27 | 2022-11-27 | 13 | 13 | 0
1616 | Foothill Ranch, CA - One Icon | One Icon, Lake Forest | Lake Forest | 92610 | Orange County | 12. System Upgrade | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-02-15 |  |  |  | YES |  |  |  |  | 2022-10-31 | [6 empty] | 2022-12-21 | 2022-12-21 |  |  | 1 | 1
1617 | 4700 Cherry Avenue | 4700 Cherry Ave | Long Beach | 90807 | Los Angeles County | 10. Customer Hold | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-09-30 | 8 | YES |  | YES |  |  |  |  | 2022-11-02 | 2022-11-02 |  |  | 1 | 1 | 2023-06-16 | 2022-12-02 | 2022-12-02 | 20 | 20 | 1 | 1
1618 | 32610 Oak Glen Rd, Yucaipa, CA, United States | 32610 Oak Glen Rd | Yucaipa | 92399 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-10-15 | 20 | YES |  |  | 2023-05-10 | 2023-05-31 | 15 | 15 | 2022-11-22 | 2023-05-17 | 10 | 10 | 123 | 123 | 2023-05-17 | 2023-05-23 |  | 5 | 5
1619 | Monrovia HD II | 1625 S Mountain Rd EV | Monrovia | 91016 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [9 empty] | YES | 2023-03-15 |  |  |  | 2022-12-02 | 2022-12-02 |  |  | 1 | 1 | 2022-12-05 | 2022-12-06 | 2023-01-10 | 3 | 3 | 26 | 26
1620 | Ralph El Toro | 23716 El Toro Rd | Lake Forest | 92630 | Orange County | 10. Customer Hold | 43 - Saddleback | Orange | Saddleback | [9 empty] | YES | 2022-12-02 |  |  |  | 2022-12-02 | 2022-12-02 |  |  | 1 | 1 | 2022-12-05 | 2022-12-07 | 2022-12-19 | 4 | 4 | 9 | 9
1621 | Magnolia & Adams | 9062 Adams Ave | Huntington Beach | 92646 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2022-12-02 | 2022-12-02 |  |  | 1 | 1 | 2022-12-05 | 2022-12-07 | 2022-12-19 | 4 | 4 | 9 | 9
1622 |  | 6050 Artesia Blvd | Buena Park | 90620 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2022-09-26 | [8 empty] | 2022-10-31 | 2022-10-31 |  |  | 1 | 1 | 2022-11-08 | 2022-11-15 | 2022-12-05 | 11 | 11 | 13 | 13
1623 | Lake Elsinore Albertsons | 30901 Riverside Dr - EV | Lake Elsinore | 92530 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [7 empty] | NO | [6 empty] | 2022-12-05 | 2022-12-05 |  |  | 1 | 1 | 2022-12-06 | 2022-12-07 | 2023-01-18 | 3 | 3 | 30 | 30
1624 | Sun City Albertsons | 27220 Sun City Blvd - EV | Sun City | 92586 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [10 empty] | 2023-03-15 |  |  |  | 2022-12-05 | 2022-12-05 |  |  | 1 | 1 | 2022-12-06 | 2022-12-07 | 2023-01-06 | 3 | 3 | 23 | 23
1625 | Fountain Valley, CA-18430 Brookhurst St | 18430 Brookhurst St | Fountain Valley | 92708 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-06-30 | [8 empty] | 2022-11-10 | 2022-11-10 |  |  | 1 | 1 |  | 2022-11-16 | 2022-12-05 | 4 | 4 | 12 | 12
1626 | Magnolia & Warner | 17070 Magnolia St. - EV | Fountain Valley | 92708 | Orange County | 5. Final Design | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES | 2023-03-15 |  |  |  | 2022-12-06 | 2022-12-06 |  |  | 1 | 1 | 2022-12-07 | 2022-12-08 | 2022-12-22 | 3 | 3 | 11 | 11
1627 | 19006 Brookhurst St -Huntington Beach | 10020 Garfield Ave | Huntington Beach | 92646 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3518829 | 2232109 |  | 2024-09-13 | 20 | YES | Level 2 | YES | 2023-03-10 | 2023-04-21 | 31 | 31 | 2022-11-14 | 2022-11-15 | 110 | 110 | 2 | 2 | 2022-11-16 | 2022-12-06 | 2022-12-06 | 14 | 14 | 1 | 1 | 2023-03-10 | 81 | 81 | 2023-04-24 | 2023-04-25 | 2024-03-01 | 2024-02-29 | 246 | 246 | 2024-03-01 | 2024-03-04 | 2 | 2 | 2024-03-26 | [16 empty] | 2024-03-15
1628 | 223 Frazier Mountain Park Rd | 223 Frazier Mountain Park Rd | Lebec | 93243 | Kern County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura |  |  | 3697385 |  |  | 2024-06-30 | 40 | YES | Level 2 | YES | 2023-04-28 | 2023-06-05 | 26 | 26 | 2024-01-12 | 2024-01-12 | -154 |  | 1 | 1 | 2024-01-17 | 2024-01-17 | 2024-01-20 | 3 | 3 | 3 | 3 |  |  |  | 2024-03-20 | 2024-03-20 | 2024-04-22
1629 | 31963 Rancho California Rd | 31963 Rancho California Rd | Temecula | 92592 | Riverside County | 10. Customer Hold | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-12-24 | 12 | YES | Level 2 |  | 2024-02-13 |  |  |  | 2023-11-30 | 2023-12-14 |  |  | 11 | 11 | 2023-12-14 | 2024-01-10 | 2024-01-10 | 18 | 18 | 1 | 1
1630 | Torrance Church | 700 Maple Ave | Torrance | 90503 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2022-12-08 | 2022-12-08 |  |  | 1 | 1 | 2022-12-13 | 2022-12-15 | 2023-01-06 | 6 | 6 | 17 | 17
1632 | Costco | 13463 Washington Blvd | Culver City | 90291 | Los Angeles County | 4. Preliminary Design | 42 - Santa Monica | Metro West | Alhambra |  |  | 3636954 | 2233000 |  | 2024-05-01 | 30 | YES | Level 3 | NO | 2023-06-27 | 2023-04-21 | -47 |  | 2022-12-12 | 2022-12-12 | 93 | 93 | 1 | 1 | 2022-12-13 | 2022-12-19 | 2023-01-16 | 6 | 6 | 20 | 20 | 2023-11-19 | 240 | 240 | 2024-01-31 | 2024-01-31 | 2024-03-14 | 2024-03-13 | 77 | 77 | 2024-03-13
1633 | Comfort Inn Huntington Beach | 16301 Beach Blvd | Huntington Beach | 92647 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3653100 | 2216275 |  |  | 4 | YES | Level 3 | YES |  |  |  |  | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-20 | 2022-12-28 | 2022-12-28 | 11 | 11 | 1 | 1 | 2023-12-20 | 259 | 259 | 2023-12-29 | 2024-01-05 | 2024-02-15 | 2024-01-30 | 27 | 27 | 2024-01-30 | 2024-02-02 | 4 | 4
1634 | Western Holiday Lodge | 40105 Sierra Dr | Three River | 93271 | Tulare County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [6 empty] | 4 | YES | Level 3 | [5 empty] | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-22 | 2022-12-22 | 2022-12-24 | 7 | 7 | 2 | 2
1635 | Hampton Inn Visalia | 4747 W NOBLE AVE | VISALIA | 93277 | Tulare County | 4. Preliminary Design | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2023-02-15 |  | YES |  | NO |  |  |  |  | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-22 | 2022-12-28 | 2022-12-28 | 11 | 11 | 1 | 1
1636 | Buena Park Hampton Inn | 7307 1/2 Artesia Blvd | Buena Park | 90621 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3655480 |  |  | 2023-01-15 | 8 | YES | Level 3 | YES |  |  |  |  | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-20 | 2022-12-29 | 2022-12-29 | 12 | 12 | 1 | 1 | 2024-02-23 | 302 | 302 | 2024-02-23 | 2024-02-27 | 2024-04-09
1637 | Corner of HWY 395 and Three Flags Rd. Hesperia, CA 92344 | Corner of HWY 395 and Three Flags Rd | Hesperia | 92344 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2023-12-15 |  |  |  | YES | 2023-01-12 | 2023-02-24 | 30 | 30 | 2022-12-15 | 2022-12-15 | 50 | 50 | 1 | 1 | 2022-12-15 | 2022-12-27 | 2023-01-04 | 9 | 9 | 7 | 7
1638 | E of Flying J and N of High Point Pkwy | 2611 Fisher Blvd | Barstow | 92311 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [5 empty] | 2025-08-01 | 44 | YES | Level 3 | YES | 2023-01-12 | 2023-02-22 | 28 | 28 | 2022-12-15 | 2023-10-25 | -173 |  | 220 | 220 | 2023-10-25 | 2023-11-01 | 2023-11-01 | 6 | 6 | 1 | 1
1639 | Intersection of Kelbakor Rd and Brannigan Mind Rd. Baker, CA 92364 | Intersection of Kelbakor Rd and Brannigan Mind Rd. | Baker | 92364 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2023-12-15 |  | YES | Level 3 | YES | 2023-01-12 | 2023-02-23 | 29 | 29 | 2022-12-15 | 2022-12-15 | 49 | 49 | 1 | 1 | 2022-12-15 | 2022-12-27 | 2023-01-04 | 9 | 9 | 7 | 7
1640 | Caruthhers EZ Stop Plaza | 1040 S 12th Ave | Hanford | 93609 | Fresno County | 10. Customer Hold | 51 - Tulare | San Joaquin | Ventura |  |  | 3468505 |  | 2113913 | 2023-12-15 |  | NO | Level 3 | YES | 2023-02-21 | 2023-03-10 | 14 | 14 | 2022-12-15 | 2022-12-15 | 60 | 60 | 1 | 1 | 2022-12-15 | 2022-12-22 | 2022-12-24 | 6 | 6 | 2 | 2 | 2023-03-07 | 57 | 57 | 2023-03-07 | 2023-03-09 | 2023-04-20 | 2023-05-17 | 52 | 52 | 2023-05-17 | 2023-05-19 | 3 | 3 | 2023-06-15 | 2023-06-05 | 11 | 11 | 2023-06-05 | 1 | 1 | 2023-06-15 | 2023-06-15 | 2023-06-15 |  | 9 | 9 |  |  |  |  | 2023-06-16 | 2023-06-22 | 2023-06-28 | 10 | 10 | 5 | 5 | 9 | 9 | [6 empty] | 2023-06-15
1641 | Chevron | 2568 Sycamore Dr | Simi Valley | 93065 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2023-08-01 |  | NO |  | YES |  |  |  |  | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-29 | 2023-12-29 | 2023-01-06 | 265 | 265 | -248
1642 | Chevron | 27549 The Old Road | Valencia | 93065 | Orange County | 11. Cancelled | 59 - Valencia | North Valley | Ventura | SAUGUS | TIPS 16KV |  |  |  | 2023-08-01 |  | NO |  | YES |  |  |  |  | 2022-12-14 | 2022-12-14 |  |  | 1 | 1 | 2022-12-20 | 2022-12-27 | 2022-12-27 | 10 | 10 | 1 | 1
1643 | Ontario, CA - The Collection | Fourth St & Haven Ave | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-12-31 |  | NO |  | NO |  |  |  |  | 2022-12-01 | 2022-12-01 |  |  | 1 | 1 | 2022-12-15 | 2022-12-16 | 2022-12-16 | 12 | 12 | 1 | 1
1644 | Ontario - Concours & N Haven - RETAIL | 850 N Center Ave | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2022-05-12 | 2022-05-12 |  |  | 1 | 1 | 2022-05-13 | 2022-05-29 | 2022-05-29 | 12 | 12 | 0 |  | 2022-10-24 | 115 | 115 | 2022-10-27 |  | 2022-12-14 | 2022-12-15 | 36 | 36 | 2022-12-15
1645 |  | 1481 Edinger Ave | Tustin | 92780 | Orange County | 4. Preliminary Design | 29 - Santa Ana | Orange | Saddleback | [9 empty] | NO | 2022-12-27 | 2023-01-18 | 16 | 16 | 2022-12-19 | 2022-12-19 | 22 | 22 | 1 | 1 | 2022-12-20 | 2022-12-21 | 2022-12-23 | 3 | 3 | 3 | 3
1646 | KPC Hemet Hospital | 1117 E Devonshire Ave | Hemet | 92543 | Riverside County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar |  |  | 3574818 |  |  | 2024-12-30 | 7 | YES |  | YES |  |  |  |  | 2022-12-19 | 2022-12-19 |  |  | 1 | 1 | 2022-12-20 | 2022-12-21 | 2023-01-18 | 3 | 3 | 20 | 20 | 2023-01-23 | 25 | 25 | 2023-07-31 | 2023-08-08 | 2023-09-21
1647 | Baldwin Park Maine Ave Marketplace | 4299 Maine Ave | Baldwin Park | 91706 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3479710 | 2124764 | 2124768 | 2024-12-26 | 4 | YES | Level 3 | YES | 2023-02-06 | 2023-02-22 | 12 | 12 | 2022-12-20 | 2022-12-20 | 45 | 45 | 1 | 1 | 2022-12-20 | 2022-12-22 | 2023-01-13 | 3 | 3 | 17 | 17 | 2023-02-17 | 43 | 43 | 2023-02-23 | 2023-04-17 | 2023-04-10 | 2023-05-01 | 51 | 51 | 2023-05-01 | 2023-05-02 | 2 | 2 | 2023-05-24 | 2023-06-07 | 26 | 26 | 2023-06-12 | 4 | 4 | 2023-06-12 | 2023-07-11 | 2023-06-12 | 2023-06-26 | 4 | 4 | 39 | 39 | 11 | 11 | 2023-05-26 | 2023-05-31 | 2023-06-19 | -8 |  | 14 | 14 | 16 | 16 | [6 empty] | 2023-05-31 |  | 2023-06-26
1648 | Oxnard Ventura Blvd | 802 N Ventura Rd | Oxnard | 93030 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [5 empty] | 2023-06-30 |  |  |  | YES | 2023-02-06 | 2023-02-09 | 4 | 4 | 2022-12-21 | 2022-12-21 | 36 | 36 | 1 | 1 | 2022-12-22 | 2023-01-03 | 2023-01-08 | 10 | 10 | 4 | 4
1649 | Lancaster | 4033 W Avenue L | Lancaster | 93536 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [14 empty] | 2022-12-21 | 2022-12-21 |  |  | 1 | 1 | 2022-12-22 | 2023-01-04 | 2023-01-07 | 11 | 11 | 3 | 3
1650 | 740 W Ave K 4 | 740 W Ave K 4 | Lancaster | 93534 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-04-01 | [8 empty] | 2022-12-23 | 2022-12-23 |  |  | 1 | 1 | 2022-12-23 | 2022-12-23 | 2022-12-23 | 1 | 1 | 1 | 1
1651 | 843 E Arrow Hwy | 843 E Arrow Hwy | Azusa | 91702 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-04-01 |  |  |  | YES |  |  |  |  | 2022-12-08 | 2022-12-08 |  |  | 1 | 1 | 2022-12-19 | 2022-12-26 | 2022-12-26 | 13 | 13 | 1 | 1
1652 | 4400 Ontario Mills Pkwy | 4410 Ontario Mills Pkwy-MP | Ontario | 91764 | San Bernardino County | 5. Final Design | 34 - Ontario | Metro East | Pomona |  |  | 3512340 | 2137923 |  | 2024-08-15 |  | YES | Level 2 | YES | 2023-04-06 | 2023-04-07 | 2 | 2 | 2022-12-08 | 2022-12-08 | 85 | 85 | 1 | 1 |  | 2022-12-26 | 2022-12-26 | 13 | 13 | 1 | 1 |  |  |  | 2023-04-13 |  | 2023-06-05 | 2023-06-06 |  |  | 2023-06-06 | 2023-06-07 | 2 | 2 | 2023-06-28 | 2023-08-30 | 60 | 60 | 2023-09-06 | 5 | 5 | [10 empty] | 2023-09-15 |  | 2023-11-09 | 12 | 12 |  |  | 40 | 40 | 2023-10-25 | 36 | 36 | [9 empty] | 40 | 40
1653 | Duarte | 2107 Huntington Drive | Duarte | 91010 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona |  |  | 3622263 | 2198488 | 2198487 | 2024-07-31 | 20 | YES | Level 3 |  | 2023-06-02 |  |  |  |  | 2022-12-09 |  |  |  |  | 2022-12-20 | 2022-12-20 | 2022-12-26 | 8 | 8 | 5 | 5 | 2023-02-15 |  |  | 2023-04-07 | 2023-06-30 | 2023-06-30 | 2023-11-10 | 189 | 189 | 2024-01-19 |  |  |  | 2024-02-16 | 2024-03-05 |  |  | 2024-03-06 | 2 | 2
1654 | 5953 Atlantic Blvd EV1 | 5953 Atlantic Blvd EV1 | Maywood | 90270 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-06-01 |  |  |  | YES |  |  |  |  | 2022-12-19 | [7 empty] | 2023-01-13
1655 | Pomona, CA - 2233 N Garey Ave | 2233 N Garey Ave | Pomona | 91767 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-04-01 |  | YES |  | YES | 2023-05-01 |  |  |  | 2022-12-08 | 2022-12-08 |  |  | 1 | 1 | 2022-12-19 | 2022-12-26 | 2022-12-26 | 13 | 13 | 1 | 1
1656 | Hacienda Heights, CA - 17100 Colima Rd | 17100 Colima Rd | Hacienda Heights | 91745 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-03-15 |  |  |  | YES |  |  |  |  | 2022-11-29 | 2022-11-29 |  |  | 1 | 1 | 2022-12-07 | 2022-12-28 | 2022-12-28 | 22 | 22 | 1 | 1
1657 | 4242 Campus Drive | 4242 Campus Drive (EM2) | Newport Beach | 92660 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback |  |  | 3561311 | 2154885 | 2150719 | 2024-08-14 | 4 | YES | Level 1 | YES | 2023-05-16 | 2023-06-29 | 32 | 32 | 2021-12-28 | 2022-12-28 | 129 | 129 | 254 | 254 | 2023-01-03 | 2023-01-03 | 2023-03-17 | 5 | 5 | 52 | 52 | 2023-07-06 | 386 | 386 | 2023-08-11 | 2023-08-14 | 2023-09-26 | 2023-08-16 | 30 | 30 | 2023-08-23 | 2023-10-10 | 34 | 34 | 2023-10-31 | 2023-10-26 | 13 | 13 | 2023-11-08 | 10 | 10 | [10 empty] | 2023-10-12 | 2023-10-19 |  | -11
1658 | 1550 W Redondo Beach Blvd | 1550 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 12. System Upgrade | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-05-01 |  |  |  |  | 2022-12-29 | 2023-01-10 | 9 | 9 | 2022-12-02 | 2022-12-02 | 28 | 28 | 1 | 1 | 2022-12-08 | 2022-12-28 | 2022-12-28 | 19 | 19 | 1 | 1
1659 | 107 N McKinley St | 107 N McKinley St | Corona | 92879 | Riverside County | 10. Customer Hold | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-04-01 | 20 | YES | [6 empty] | 2023-07-18 | 2023-07-26 |  |  | 7 | 7 |  | 2023-07-31 | 2023-08-07 | 4 | 4 | 6 | 6
1660 | Murrieta Hancock | 25100 Hancock Ave | Murrieta | 92562 | Riverside County | 4. Preliminary Design | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2023-06-30 |  | NO |  | NO | 2023-02-06 |  |  |  | 2022-12-29 | 2022-12-29 |  |  | 1 | 1 | 2022-12-29 | 2023-01-04 | 2023-02-09 | 5 | 5 | 26 | 26
1661 | 1202 EV East Carson St | 1202 EV East Carson St | Carson | 90745 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 32 - Compton | Metro West | Alhambra |  |  | 3508792 | 2130038 |  | 2024-08-22 |  | YES | Level 2 | YES |  |  |  |  | 2022-12-29 | 2022-12-29 |  |  | 1 | 1 | 2022-12-29 | 2023-01-03 | 2023-01-05 | 4 | 4 | 3 | 3 |  |  |  | 2023-04-06 | 2023-04-11 | 2024-03-14 | 2024-03-12 |  |  | 2024-03-12
1662 | Murrieta, CA - 29910 Hot Springs Rd | 29904 Murrieta Hot Springs Rd | Murrieta | 92563 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar |  |  | 3558819 | 2209820 | 2199188 | 2024-06-07 | 20 | YES | Level 3 | YES | 2023-05-01 | 2023-06-12 | 30 | 30 | 2023-01-02 | 2023-06-28 | -13 |  | 125 | 125 | 2023-06-29 | 2023-07-10 | 2023-07-18 | 8 | 8 | 7 | 7 | 2023-06-28 | 125 | 125 | 2023-06-29 | 2023-06-30 | 2023-12-11 | 2023-12-20 | 122 | 122 | 2023-12-21 | 2024-01-02 | 7 | 7 | 2024-02-01 | 2024-03-05 | 44 | 44 | 2024-03-07 | 3 | 3 | 2024-03-18 |  | 2024-03-18 | 2024-03-27 | 10 | 10 | 60 | 60 | 8 | 8 | 2024-02-05 | 2024-02-15 | 2024-02-26 | -21 |  | 7 | 7 | 15 | 15 | 2024-03-19 | 9 | 9 |  |  |  | 2024-02-15 | 2024-02-15 | 2024-03-27 |  |  |  | 11 | 11
1663 | 3150 Case Rd Building G-2, Perris, CA 92570 | 3150 Case Rd | Perris | 92570 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-06-30 |  |  |  | YES |  |  |  |  | 2022-11-28 | 2022-11-28 |  |  | 1 | 1 | 2023-05-04 | 2023-01-03 | 2023-05-29 | 27 | 27 | 102 | 102
1664 | 32120 Highway 79 South, Temecula, CA 92592 | 32120 Highway 79 South | Temecula | 92592 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-06-30 | 16 |  |  | YES | 2023-02-09 | 2023-03-30 | 35 | 35 | 2023-12-19 | 2023-12-19 | -184 |  | 1 | 1 | 2023-12-20 | 2023-12-27 | 2024-01-10 | 6 | 6 | 10 | 10
1665 | 1670 Devore Rd. San Bernardino, CA 92407 | 1670 Devore Rd. San Bernardino, CA 92407 | San Bernardino | 92407 | San Bernardino County | 7. Civil Construction | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-06-30 | 92 |  |  | YES | 2023-02-09 | 2023-05-22 | 72 | 72 | 2023-01-04 | 2023-01-04 | 97 | 97 | 1 | 1 | 2023-04-04 | 2023-04-13 | 2023-04-14 | 70 | 70 | 2 | 2
1669 | 6211 Beach Blvd | 6211 1/2 Beach Blvd | Buena Park | 90621 | Orange County | 11. Cancelled | 48 - Fullerton | Orange | Saddleback |  |  | 3510674 | 2121550 |  | 2024-04-30 | 34 | YES | Level 2 |  | 2023-01-12 | 2023-01-20 | 6 | 6 | 2022-12-29 | 2022-12-29 | 16 | 16 | 1 | 1 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 5 | 5 | 2 | 2 |  |  |  | 2023-04-11 | 2023-04-11 | 2023-05-23 | 2023-05-23 |  |  | 2023-05-23 | 2023-08-01 | 49 | 49 | 2023-08-28 | 2023-08-28 | 20 | 20 | 2023-08-28 | 1 | 1 | [10 empty] | 2023-08-07 | 2023-08-07 | 2023-09-05 | -16 |  | 21 | 21 | 21 | 21 | 2023-08-08 | -15 |  | 2023-10-31 | 60 | 60 | [6 empty] | -15 |  | 2023-11-01 | 2023-12-29 | 2024-01-17 | 51 | 51 | 2023-09-06 |  |  | 2023-09-06 | 1 | 1
1670 |  | 320 S Vermont Ave | Glendora | 91741 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2023-04-01 |  | NO |  | YES |  |  |  |  | 2022-12-29 | 2022-12-29 |  |  | 1 | 1 | 2023-01-09
1671 | Vons Manhattan Beach | 410 Manhattan Beach Blvd | Manhattan Beach | 90266 | Los Angeles County | 9. Complete | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-09-16 |  |  |  | YES | 2023-02-06 | 2023-02-21 | 11 | 11 | 2023-01-05 | 2023-01-05 | 32 | 32 | 1 | 1 | 2023-01-09 | 2023-01-10 | 2023-01-26 | 4 | 4 | 12 | 12
1672 | DJT6 Riverside | 21298 Krameria Ave. | Riverside | 92518 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3483814 | 2112961 |  | 2023-12-29 | 422 | NO |  |  | 2023-02-06 | 2023-02-22 | 12 | 12 | 2023-01-12 | 2023-01-12 | 28 | 28 | 1 | 1 | 2023-01-12 | 2023-01-17 | 2023-02-05 | 3 | 3 | 14 | 14 | 2023-02-28 | 32 | 32 | 2023-03-02 |  | 2023-03-14 | 2023-04-03 | 25 | 25 | 2023-04-03 | 2023-04-04 | 2 | 2 | 2023-04-25 | 2023-05-23 | 36 | 36 | 2023-05-23 | 1 | 1 | 2023-05-31 | 2023-06-07 | 2023-05-31 |  | 6 | 6 |  |  |  |  | 2023-05-04 | 2023-05-25 |  | -14 | [5 empty] | 2023-05-24 | 2 | 2 | 2023-06-07 | 10 | 10 | 2023-05-25 | 2023-05-24 |  |  |  |  | 2 | 2 | 2023-06-12 |  | 2023-06-27 | 12 | 12 | [13 empty] | 2023-10-11 |  |  |  |  | 2023-10-12 | 2023-12-07 | 39 | 39 | 2023-12-07 | 39 | 39 | 2023-12-07 |  |  |  | 229 | 229 | 198 | 198 | 2023
1673 | 5070 E 4th St, Ontario | 5070 E 4th St | Ontario | 91764 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-07-01 |  |  |  | YES |  |  |  |  | 2022-12-16 | 2023-01-09 |  |  | 17 | 17 | 2023-01-09 | 2023-01-14 | 2023-01-14 | 5 | 5 | 0
1674 | 33949 Orange St, Wildomar | 33949 Orange St | Wildomar | 92595 | Riverside County | 11. Cancelled | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-03-31 |  |  |  |  | 2023-02-09 | 2023-03-23 | 30 | 30 | 2022-12-06 | 2022-12-06 | 76 | 76 | 1 | 1 | 2022-12-08 | 2023-01-17 | 2023-01-17 | 30 | 30 | 1 | 1
1675 | 15350 Roy Rogers Dr, Victorville | 15350 Roy Rogers Dr | Victorville | 92393 | San Bernardino County | 5. Final Design | 73 - Victorville | Rurals | SBRO | [5 empty] | 2024-07-01 |  |  |  | NO |  |  |  |  | 2022-12-16 | 2022-12-16 |  |  | 1 | 1 | 2023-01-14 | 2023-01-14 | 2023-01-17 | 21 | 21 | 1 | 1
1676 | Idyllwild Inn Pine Cove | 54300 Village Center | Idyllwild | 94549 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar |  |  | 3553440 | 2210745 |  | 2024-06-24 | 10 | YES |  | YES |  |  |  |  | 2023-01-17 | 2023-01-17 |  |  | 1 | 1 | 2023-01-17 | 2023-01-23 | 2023-02-27 | 5 | 5 | 25 | 25 | 2023-06-16 | 107 | 107 | 2023-11-16 | 2023-11-17 | 2024-01-03 | 2024-01-11 | 144 | 144 | 2024-01-24 | 2024-01-29 | 4 | 4
1677 | Idyllwild - Tahquitz Pines Retreat | 55251 S Circle Dr | Idyllwild | 92549 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar |  |  | 3597156 |  |  |  | 8 | YES | Level 3 | NO | 2023-07-28 |  |  |  | 2023-06-08 | 2023-06-08 |  |  | 1 | 1 | 2023-06-12 | 2023-06-19 | 2023-07-12 | 8 | 8 | 17 | 17 | 2023-07-28 | 36 | 36 | 2023-11-16 | 2023-11-17 | 2024-01-04 | 2023-10-20 | 60 | 60 | 2023-10-23 | 2023-10-26 | 4 | 4
1678 | Idyllwild North Circle Dr. | 54385 N Circle Dr | Idyllwild | 92549 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3561047 | 2210957 |  |  | 8 | YES | Level 3 | [5 empty] | 2023-01-17 | 2023-01-17 |  |  | 1 | 1 | 2023-01-17 | 2023-01-23 | 2023-02-27 | 5 | 5 | 25 | 25 | 2023-07-05 | 119 | 119 | 2024-01-17 | 2024-01-18 | 2024-02-15 | 2024-01-04 | 127 | 127 | 2024-01-04
1679 | Long Beach, CA - 5802 Downey Ave | 5802 Downey Ave | Long Beach | 90805 | Los Angeles County | 2. Engineering | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-06-01 |  |  |  | YES |  |  |  |  | 2022-12-20 | 2022-12-20 |  |  | 1 | 1 | 2022-12-21 | 2023-01-13 | 2023-01-17 | 19 | 19 | 2 | 2
1680 | 1129 Fair Oaks Ave, South Pasadena, CA 91030 | 1129 Fair Oaks Ave | South Pasadena | 91030 | Los Angeles County | 4. Preliminary Design | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2024-07-01 | 11 |  |  |  | 2024-02-04 |  |  |  | 2022-12-16 | 2023-08-11 |  |  | 167 | 167 | 2023-08-14 | 2023-08-17 | 2023-09-01 | 5 | 5 | 12 | 12
1681 | Lincoln Station - 11900 South St EV1, Cerritos, CA | 11900 South Street | Cerritos | 90703 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra |  |  | 3579698 | 2184529 | 2184528 | 2024-08-01 |  | YES | Level 3 | YES |  |  |  |  | 2023-01-18 | 2023-07-26 |  |  | 133 | 133 |  | 2023-07-31 | 2023-08-07 | 4 | 4 | 6 | 6 | 2023-08-08 | 142 | 142 | 2023-08-08 | 2023-08-09 | 2023-09-22 | 2023-10-05 | 42 | 42 | 2023-10-05
1682 | 5900 Bixby Village Drive, Long Beach, CA, 90803 | 5900 Bixby Village Dr | Long Beach | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [10 empty] | 2023-02-16 | 2023-03-30 | 30 | 30 | 2023-01-19 | 2024-03-13 | -241 |  | 290 | 290 | 2023-02-26 | 2024-03-14 | 2024-03-14 | 2 | 2 | 1 | 1
1683 | 24911 S Western Ave, Lomita | 24911 S Western Ave | Lomita | 90717 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [14 empty] | 2023-01-19 | 2023-01-19 |  |  | 1 | 1
1684 | 6607 Atlantic Ave, Bell, CA 90201 | 6607 Atlantic Ave | Bell | 90201 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [7 empty] | YES | [6 empty] | 2023-01-19 | 2023-01-19 |  |  | 1 | 1 | 2023-01-24 | 2023-02-08 | 2023-02-08 | 15 | 15 | 1 | 1
1685 | Garden Lot | 11 Garden St | Santa Barbara | 93101 | Ventura County | 3. Active | 49 - Santa Barbara | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2023-01-20 | 2023-01-20 |  |  | 1 | 1 | 2023-01-24 | 2023-01-31 | 2023-01-31 | 8 | 8 | 1 | 1
1686 | Hemet, CA - 4602 W Florida Ave | 4602 W Florida Ave | Hemet | 92545 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-09-15 | 20 | YES | Level 3 | YES | 2023-04-30 | 2023-06-16 | 34 | 34 | 2022-11-28 | 2022-11-28 | 142 | 142 | 1 | 1 | 2022-11-29 | 2023-01-26 | 2023-01-26 | 43 | 43 | 1 | 1
1687 | Gosser Blythe 2 West | 16870 W Hobsonway | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Rurals | SBRO | [9 empty] | NO |  |  |  |  | 2023-01-30 | 2023-01-30 |  |  | 1 | 1 | 2023-01-30 | 2023-02-01 | 2023-02-17 | 3 | 3 | 13 | 13
1688 | Oasis Inn and Suites | 831 N China Lake Blvd | Ridgecrest | 93555 | Kern County | 11. Cancelled | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2023-09-23 | 14 | YES | Level 2 | [5 empty] | 2023-01-31 | 2023-01-31 |  |  | 1 | 1 | 2023-11-07 | 2023-02-02 | 2023-11-17 | 3 | 3 | 203 | 203
1689 | 5990 Green Valley Cir EV1 | 5990 Green Valley Cir EV1 | Culver City | 90230 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra |  |  | 3543774 | 2145067 |  | 2023-07-31 | 12 | YES | Level 2 | YES |  |  |  |  | 2023-02-01 | 2023-02-01 |  |  | 1 | 1 | 2023-02-02 | 2023-02-06 | 2023-02-20 | 4 | 4 | 10 | 10 |  |  |  | 2023-06-05 | 2023-06-07 | 2023-07-21 | 2023-07-18 |  |  | 2023-07-18
1690 | JVCA INVESTMENTS | 17401 ADELANTO RD | ADELANTO | 92301 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2023-04-28 | 6 | YES |  |  | 2023-02-17 | 2023-04-03 | 31 | 31 | 2023-02-13 | 2023-02-03 | 41 | 41 | -7 |  | 2023-02-06 | 2023-02-08 | 2023-02-13 | 4 | 4 | 4 | 4
1691 | Holiday Inn Express | 74675 Highway 111 | PALM DESERT | 92260 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2023-04-28 |  | NO | [6 empty] | 2023-02-02 | 2023-02-02 |  |  | 1 | 1 | 2023-02-06 | 2023-02-13 | 2023-04-04 | 8 | 8 | 36 | 36
1692 | 1007 S Prairie Ave. | 1007 S Prairie Ave | Inglewood | 90301 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-06-03 |  |  |  | YES |  |  |  |  | 2023-02-02 | 2023-02-02 |  |  | 1 | 1 |  |  | 2023-02-21
1693 | RAMADA BY WYANDHAM | 1511 E MAIN ST | BARSTOW | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2023-04-28 | 6 | YES |  |  | 2023-02-21 | 2023-03-10 | 14 | 14 | 2023-02-13 | 2023-02-02 | 26 | 26 | -8 |  | 2023-02-06 | 2023-02-08 | 2023-02-13 | 5 | 5 | 4 | 4
1694 | Morongo Gas | 49020 Seminole Dr | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-03-31 | [8 empty] | 2023-02-02 | 2023-02-02 |  |  | 1 | 1
1695 |  | 483 Shoreline Drive | Santa Barbara | 93109 | Ventura County | 3. Active | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2023-05-01 | [15 empty] | 2023-02-04 | 2023-02-04 |  |  | 0
1696 | DAYS INN | 1909 BUSINESS CENTER DR | SAN BERNARDINO | 92408 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2023-04-28 |  | YES | [6 empty] | 2023-02-03 | 2023-02-03 |  |  | 1 | 1 | 2023-02-06 | 2023-02-07 |  | 3 | 3
1697 | 9750 KEYPOINTE AVE | 9750 KEYPOINTE AVE | HESPERIA | 92345 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [5 empty] | 2023-09-15 |  | YES | Level 3 | YES |  |  |  |  | 2023-02-03 | 2023-02-03 |  |  | 1 | 1 | 2023-02-06 | 2023-02-08 | 2023-02-13 | 4 | 4 | 4 | 4
1698 | Ontario Target | 4200 E 4th St. | Ontario | 91764 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-02-06 |  |  |  | YES |  |  |  |  | 2023-02-06 | 2023-02-06 |  |  | 1 | 1 | 2023-02-07 | 2023-02-09 | 2023-02-13 | 4 | 4 | 3 | 3
1699 | Huntington Beach, CA - 6913 Warner Ave | 6943 Warner Ave | Huntington Beach | 92649 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-06-30 | 13 | YES |  |  | 2024-01-29 |  |  |  | 2023-02-07 | 2023-02-07 |  |  | 1 | 1 | 2023-02-08 | 2023-02-09 | 2023-08-09 | 3 | 3 | 127 | 127
1700 | Running Springs, CA | 32088 CA-18, Running Springs, CA 92382 | Running Springs | 92382 | San Bernardino County | 2. Engineering | 40 - Arrowhead | Rurals | SBRO | [5 empty] | 2024-12-31 |  |  |  | YES |  |  |  |  | 2023-02-07 | 2023-02-07 |  |  | 1 | 1 |  |  | 2023-02-21
1701 | 3351 N Centre Lake Dr | 3351 N Centre Lake Dr | Ontario | 91764 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-12-23 | 78 | YES | Level 3 | YES | 2024-01-29 | 2023-11-02 | -58 |  | 2023-05-22 | 2023-05-23 | 115 | 115 | 2 | 2 | 2023-05-23 | 2023-05-30 | 2023-06-06 | 5 | 5 | 6 | 6
1702 | Fullerton Ford | 700 W Commonwealth Ave | Fullerton | 92832 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [6 empty] | 21 | YES | Level 3 |  | 2024-02-28 |  |  |  | 2023-01-31 | 2024-02-12 |  |  | 261 | 261 | 2024-02-13 | 2024-02-14 | 2024-02-16 | 3 | 3 | 3 | 3
1703 | Palm Plaza | 7750 Palm Ave | Highland | 92346 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-07-01 |  |  |  | YES |  |  |  |  | 2023-02-09 | 2023-02-09 |  |  | 1 | 1 |  |  | 2023-02-21
1704 | 200 N Avenue H | 200 N Ave H | Barstow | 92311 | San Bernardino County | 10. Customer Hold | 72 - Barstow | Rurals | SBRO | [5 empty] | 2023-10-10 |  | YES |  | YES |  |  |  |  | 2023-05-30 | 2023-05-30 |  |  | 1 | 1 | 2023-05-31 | 2023-06-06 | 2023-06-11 | 6 | 6 | 4 | 4
1705 |  | 11900 Riverside Dr. | Jurupa Valley | 91752 | Riverside County | 2. Engineering | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-03-02 | 4 | YES | Level 1 | NO | 2023-06-15 | 2023-07-17 | 22 | 22 | 2023-02-10 | 2023-02-10 | 109 | 109 | 1 | 1 | 2023-02-13 | 2023-02-21 | 2023-02-27 | 7 | 7 | 5 | 5
1706 | 11188 Citrus Ave | 11188 Citrus Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-03-02 | 4 | YES | Level 3 | [5 empty] | 2023-02-10 | 2023-02-10 |  |  | 1 | 1 | 2023-02-13 | 2023-02-21 | 2023-02-27 | 7 | 7 | 5 | 5
1707 | Kaiser | 8811 Calabash Ave | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-10-10 |  | YES | [6 empty] | 2023-02-13 | 2023-02-13 |  |  | 1 | 1 | 2023-02-13 | 2023-02-22 | 2023-02-23 | 7 | 7 | 2 | 2
1708 | South Gate Chase | 4240 Tweedy Blvd | South Gate | 90280 | Los Angeles County | 10. Customer Hold | 32 - Compton | Metro West | Alhambra |  |  | 3517488 | 2121767 |  |  |  | YES | [6 empty] | 2023-02-13 | 2023-02-13 |  |  | 1 | 1 | 2023-02-13 | 2023-02-14 | 2023-03-06 | 2 | 2 | 14 | 14
1709 |  | 1850 W 4th St | San Bernardino | 92411 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2023-10-10 |  |  |  | YES
1710 | BMW/Mini of Ontario | 1251 Auto Center Drive | Ontario | 91761 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-06-05 |  | YES | Level 3 | YES | 2023-03-09 | 2023-03-27 | 13 | 13 | 2023-01-25 | 2023-01-25 | 43 | 43 | 1 | 1 | 2023-02-09 | 2023-02-14 | 2023-02-21 | 15 | 15 | 5 | 5
1711 |  | 6750 Kimball Ave | Chino | 91708 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-02-07 | 4 | YES | Level 2 | YES | 2023-06-15 | 2023-07-26 | 29 | 29 | 2023-02-13 | 2023-02-13 | 115 | 115 | 1 | 1 | 2023-02-14 | 2023-02-21 | 2023-02-27 | 6 | 6 | 5 | 5
1712 | 13550 - A Valley Blvd | 13550 - A Valley Blvd | Fontana | 92337 | San Bernardino County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-08-10 | 6 | YES | Level 1 | YES | 2023-07-21 | 2023-08-10 | 15 | 15 | 2023-02-10 | 2023-02-14 | 125 | 125 | 3 | 3 | 2023-02-15 | 2023-02-22 | 2023-02-24 | 6 | 6 | 3 | 3
1713 | 110 Coolwater Ln | 110 Coolwater Ln | Barstow | 92311 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO |  |  | 3534383 | 2137661 | 2137713 | 2023-08-25 | 4 | YES | Level 3 | YES | 2023-02-28 | 2023-04-12 | 32 | 32 | 2023-02-15 | 2023-02-15 | 40 | 40 | 1 | 1 | 2023-02-16 | 2023-02-20 | 2023-02-27 | 3 | 3 | 5 | 5 | 2023-05-17 | 65 | 65 | 2023-05-17 | 2023-05-18 | 2023-06-30 | 2023-07-10 | 37 | 37 | 2023-07-10
1714 |  | 1377 Foothill Blvd. | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-06-30 |  | YES | Level 3 |  | 2023-02-28 | 2023-04-13 | 33 | 33 | 2023-02-15 | 2023-02-15 | 41 | 41 | 1 | 1 | 2023-02-16 | 2023-02-22 | 2023-02-27 | 5 | 5 | 4 | 4
1715 | 924 N Sepulveda Blvd | 924 N Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-10-24 |  |  |  | YES |  |  |  |  | 2023-02-15 | 2023-02-15 |  |  | 1 | 1 |  |  | 2023-03-10
1716 | Desert Rd. & Salt Springs Ave | 34°51'23.9"N 117°05'48.2"W | Barstow | 92364 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-01-01 | 16 |  |  | YES | 2023-03-06 | 2023-04-21 | 35 | 35 | 2023-02-15 | 2023-02-16 | 46 | 46 | 2 | 2 | 2023-02-16 | 2023-02-20 | 2023-02-27 | 2 | 2 | 5 | 5
1717 |  | 14244 Valley Center Dr | Victorville | 92395 | San Bernardino County | 12. System Upgrade | 73 - Victorville | Rurals | SBRO | [5 empty] | 2023-08-25 | 4 | YES | Level 1 | YES | 2023-03-20 | 2023-04-18 | 22 | 22 | 2023-02-17 | 2023-02-17 | 42 | 42 | 1 | 1 | 2023-02-21 | 2023-02-23 | 2023-03-18 | 4 | 4 | 17 | 17
1718 | Greenlane | Baker Blvd at Lakeview Rd | Baker | 92309 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-06-01 | 18 | YES | Level 3 |  | 2023-03-24 | 2023-05-08 | 32 | 32 | 2023-02-21 | 2023-02-21 | 55 | 55 | 1 | 1 | 2023-02-21 | 2023-02-23 | 2023-03-10 | 3 | 3 | 12 | 12
1719 | Covina Town Square | 1460 N Azusa Ave | Covina | 91722 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2025-03-28 | 8 |  |  | YES | 2023-03-15 |  |  |  | 2023-02-21 | 2023-02-21 |  |  | 1 | 1 | 2023-02-23 | 2023-02-28 | 2023-03-14 | 6 | 6 | 11 | 11
1720 | Target | 25601 Jeronimo Rd | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-06-30 | 20 | [7 empty] | 2023-02-19 | 2023-02-19 |  |  | 0 |  | 2023-12-20 | 2023-12-21 | 2023-12-26 | 213 | 213 | 3 | 3
1721 |  | 445 Maple Ave | Torrance | 90503 | Los Angeles County | 8. Electrical Construction | 44 - South Bay | Metro West | Alhambra | [8 empty] | Level 3 | YES |  |  |  |  | 2023-02-22 | 2023-02-22 |  |  | 1 | 1 | 2023-02-23 | 2023-02-27 | 2023-03-14 | 4 | 4 | 12 | 12
1722 | Rialto Marketplace Phase II R29 | 1530 S Riverside Ave | Rialto | 92376 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 30 - Foothill | Desert | SBRO |  |  | 3501341 | 2119034 |  | 2024-04-29 | 4 | YES | Level 1 | YES | 2023-02-23 | 2023-03-10 | 12 | 12 | 2023-02-22 | [12 empty] | 2023-02-22 | 1 | 1 | 2023-03-27 | 2023-03-28 | 2023-05-09 | 2023-06-20 | 84 | 84 | 2023-06-26 | 2023-07-13 | 13 | 13 | 2023-08-04 | 2023-08-30 | 35 | 35 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2023-08-30 | 2023-08-30 | 2023-08-30 | 1 | 1 | 35 | 35 | 1 | 1 | 2024-02-28 | 2024-03-01 | 2023-11-16 | 124 | 124 | -71 |  | -69 | [7 empty] | 2023-08-30 |  | 2023-11-16 | [5 empty] | 2023-12-29 | 2024-02-16 | 2024-03-01 | 43 | 43 | 2023-12-26 |  |  | 2024-01-02 | 5 | 5 | [6 empty] | 2024-02-26 | 2024-02-28 | 44 | 44 | 3 | 3 | 2024-03-05 | 2024-03-28 | 18 | 18 | 2024-03-28 | 18 | 18
1724 | Hanford EZ Stop R29 | 1024 S 12th Ave EV | HANFORD | 93230 | Kings County | 7. Civil Construction | 51 - Tulare | San Joaquin | Ventura |  |  | 3468505 | 2109052 | 2113913 | 2024-12-19 | 3 | YES | Level 3 | YES | 2023-02-24 | 2023-03-06 | 7 | 7 | 2023-03-07 | [12 empty] | 2023-03-07 | 1 | 1 | 2023-03-07 |  | 2023-04-20 | 2023-04-14 | 29 | 29 | 2023-04-17 | 2023-05-19 | 25 | 25 | 2023-06-15 | 2023-06-05 | 11 | 11 | 2023-06-05 | 1 | 1 | 2023-06-07 | 2023-06-07 | 2023-06-07 |  | 3 | 3 |  |  |  |  | 2023-06-08 | 2023-06-21 |  | 4 | 4 | [10 empty] | 2023-06-07
1725 | Westar- Plaza Antonio R29 | 22461.5 Antonio Parkway | Rancho Santa Margarita | 92688 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3413275 | 2125972 |  | 2024-06-20 | 4 | YES | Level 2 | YES | 2023-02-24 | 2023-03-15 | 14 | 14 | 2023-02-22 | [12 empty] | 2023-02-22 | 1 | 1 | 2023-03-20 | 2023-03-20 | 2023-05-02 | 2023-07-27 | 110 | 110 | 2023-07-28 | 2023-08-02 | 4 | 4 | 2023-09-13 | 2023-09-05 | 24 | 24 | 2023-09-05 | 1 | 1 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 10 | 10 | 33 | 33 | 1 | 1 | 2023-08-25 | 2023-12-04 | 2024-02-05 | -7 |  | 43 | 43 | 111 | 111 | 2024-03-07 | 127 | 127 |  |  |  | 2023-09-18 | 2023-09-18 | 2024-02-05 |  |  |  | 127 | 127 | 2024-03-19
1726 | Chase Bank R29 Mission Viejo | 27888 Santa Margarita Pkwy - EV | Mission Viejo | 92691 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3450533 | 2118268 | 2118267 |  |  | YES | Level 3 | YES |  | 2022-12-29 | [15 empty] | 2023-02-24 |  |  | 2023-02-27 | 2023-02-28 | 2023-04-18 | 2023-04-27 | 45 | 45 | 2023-04-27
1727 | R29 | 620 Tehachapi Blvd | Tehachapi | 93280 | Kern County | 11. Cancelled | 52 - Tehachapi | North Valley | Ventura | [6 empty] | 4 | YES | Level 3 | YES | 2023-03-06 | 2023-04-10 | 26 | 26 | 2023-02-24 | 2023-02-24 | 32 | 32 | 1 | 1 | 2023-02-27 | 2023-02-28 | 2023-03-06 | 3 | 3 | 5 | 5
1728 | 45300 Club Drive | 45300 Club Drive | Indian Wells | 92210 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-12-31 | 24 | YES | Level 3 | [5 empty] | 2023-02-27 | 2023-02-27 |  |  | 1 | 1 | 2023-03-01 | 2023-03-06 | 2023-04-16 | 6 | 6 | 30 | 30
1729 | Turnpike Shopping Center SB R29 | 199 S Turnpike Rd | Santa Barbara | 93111 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura |  |  | 3280786 | 2206448 |  | 2024-03-26 | 4 | YES | Level 3 | YES |  |  |  |  | 2023-02-24 | [12 empty] | 2023-02-24 | 1 | 1 | 2023-09-12 |  | 2023-10-24 | 2023-10-23 | 169 | 169 | 2023-10-24 | 2023-12-15 | 37 | 37 | 2024-01-12
1730 |  | 14451 Myford Rd | Tustin | 92780 | Orange County | 5. Final Design | 29 - Santa Ana | Orange | Saddleback | [14 empty] | 2023-02-28 | 2023-02-28 |  |  | 1 | 1 | 2023-03-01 | 2023-03-03 | 2023-03-09 | 4 | 4 | 5 | 5
1731 | Baker Expansion Phase 3, EV-3 | Baker, CA- 71808 Baker Blvd (Ultra Gas & Mart - Phase 3) | Baker | 92309 | San Bernardino County | 10. Customer Hold | 72 - Barstow | Rurals | SBRO |  |  | 3482303 | 2113530 |  | 2023-07-20 |  | NO | [6 empty] | 2023-02-28 | 2023-02-28 |  |  | 1 | 1 | [10 empty] | 2023-02-28 | 2023-03-01 | 2023-03-29 | 2023-06-20 |  |  | 2023-07-13 | 2023-08-30 | 35 | 35 | 2023-11-06 | 2024-03-07 | 130 | 130 | 2024-03-20 | 10 | 10 | 2024-03-20 |  | 2024-03-20 |  | 10 | 10 | [45 empty] | 2023-10-02
1732 |  | 242 Hartford | Newport Beach | 92660 | Orange County | 5. Final Design | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2023-07-01 |  |  |  | YES
1733 | 75 EV W Thousand Oaks Blvd | 75 EV W Thousand Oak Blvd | Thousand Oaks | 91360 | Ventura County | 10. Customer Hold | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3656469 |  |  | 2024-12-01 | 8 | YES | Level 3 |  | 2023-04-07 | 2023-05-31 | 38 | 38 | 2023-02-28 | 2023-02-28 | 66 | 66 | 1 | 1 | 2023-03-01 | 2023-03-02 | 2023-03-09 | 3 | 3 | 6 | 6 | 2024-02-05 | 237 | 237 | 2024-01-02 | 2024-02-05 | 2024-03-21 | 2024-03-20 | 32 | 32 | 2024-03-20 | 2024-03-25 | 4 | 4 | 2024-04-10
1734 |  | 89 Seaborough | NewPort Beach | 92660 | Orange County | 10. Customer Hold | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2023-07-01
1735 |  | 101 Hartford | Newport Beach | 92660 | Orange County | 10. Customer Hold | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2023-07-01
1736 |  | 144 Woodburne | Newport Beach | 92660 | Orange County | 5. Final Design | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | YES
1737 | 1300 E Mineral King Ave Visalia Ford | 1300 E Mineral King Ave | Visalia | 93292 | Tulare County | 10. Customer Hold | 51 - Tulare | San Joaquin | Ventura |  |  | 3566315 |  |  | 2023-11-01 | 19 | YES | Level 3 | YES | 2023-05-04 | 2023-06-16 | 31 | 31 | 2023-03-28 | 2023-03-28 | 58 | 58 | 1 | 1 | 2023-03-01 | 2023-03-06 | 2023-04-20 | -17 |  | 34 | 34 | 2023-07-18 | 79 | 79 | 2023-07-18 | 2023-07-21 | 2023-10-09 | 2023-10-09 | 59 | 59 | 2023-10-09 | 2023-10-10 | 2 | 2
1738 |  | 700 W Rice St | Blythe | 92225 | Riverside County | 5. Final Design | 87 - Blythe | Rurals | SBRO | [5 empty] | 2023-06-23 | 4 | YES | Level 2 | YES |  |  |  |  | 2023-02-28 | 2023-02-28 |  |  | 1 | 1 | 2023-03-01 | 2023-03-20 | 2023-04-10 | 15 | 15 | 16 | 16
1739 | RACER LAX-Isis | 9150 EV2 Aviation Blvd | Inglewood | 90301 | Los Angeles County | 10. Customer Hold | 44 - South Bay | Metro West | Alhambra |  |  | 3483200 | 2198112 |  | 2024-10-31 |  | YES |  | YES | 2022-10-20 | 2022-10-25 | 4 | 4 | 2022-11-03 | 2022-11-03 | -8 |  | 1 | 1 | 2022-11-03 | 2022-11-10 | 2022-12-12 | 6 | 6 | 20 | 20 | 2023-02-27 | 78 | 78 | 2023-10-05 |  | 2023-11-17 | 2023-12-08 | 200 | 200 | 2023-12-11 | 2023-07-17 | -103 |  | 2024-04-15 | [16 empty] | 2024-02-01 | 2024-02-09
1740 | Lake Elsinore Target | 18287 Collier Ave - EV | Lake Elsinore | 92530 | Riverside County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2023-12-05 |  | YES |  | YES |  |  |  |  | 2023-03-01 | 2023-03-01 |  |  | 1 | 1 | 2023-03-02 | 2023-03-13 | 2023-03-27 | 9 | 9 | 11 | 11
1741 | R29 Barton Rd Chase Bank (old 25701 Barton Rd) | 11345 Mountain View Ave EV | Loma Linda | 92354 | San Bernardino County | 11. Cancelled | 31 - Redlands | Desert | SBRO |  |  | 3419431 | 2124978 |  | 2024-08-05 | 6 | YES | Level 1 | YES | 2022-05-17 | 2022-06-01 | 11 | 11 | 2023-03-01 | [12 empty] | 2023-03-01 | 1 | 1 | 2023-03-02 | 2023-03-02 | 2023-04-14 | 2023-05-01 | 44 | 44 | 2023-05-01 | 2023-06-26 | 40 | 40 | 2023-08-07 | 2023-09-11 | 54 | 54 | 2023-09-13 | 3 | 3 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 3 | 3 | 56 | 56 | 1 | 1 | 2023-09-26 | 2023-10-02 | 2023-11-13 | 12 | 12 | 31 | 31 | 35 | 35 | 2024-03-21 | 131 | 131 |  |  |  | 2023-09-13 | 2023-09-13 | 2023-11-13 |  |  |  | 133 | 133
1742 | 1209 Plaza Dr | 1209 Plaza Dr | West Covina | 91790 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-05-01 |  |  |  |  | 2023-05-11 | 2023-06-22 | 30 | 30 | 2023-03-03 | 2023-03-03 | 79 | 79 | 1 | 1 | 2023-04-09 |  | 2023-04-13
1743 |  | 6903 Schaefer | Chino | 91710 | San Bernardino County | 6. Requirements (permit, easment, etc.) | 34 - Ontario | Metro East | Pomona | [9 empty] | YES
1744 | 15617 Roy Rogers Dr #EV-1 | 15617 Roy Rogers Dr #EV-1 | Victorville | 92394 | Riverside County | 12. System Upgrade | 73 - Victorville | Rurals | SBRO |  |  | 3486501 | 2202285 | 2202286 | 2024-07-05 | 20 | YES | Level 3 | YES | 2022-05-02 | 2022-05-19 | 14 | 14 | 2023-03-06 | 2022-04-21 | 21 | 21 | -220 |  | 2022-04-25 | 2022-04-29 | 2022-05-29 | 7 | 7 | 21 | 21 |  |  |  | 2023-03-07 | 2023-03-08 | 2023-09-29 | 2023-11-27 |  |  | 2023-11-27 | 2023-11-28 | 2 | 2 | 2023-12-19 | 2023-12-20 | 17 | 17 |  |  |  | 2024-01-23 | 2024-01-23 | 2024-01-23 |  | 22 | 22 |  |  |  |  | 2023-12-14 | 2024-01-10 | 2024-02-05 | -5 |  | 18 | 18 | 35 | 35 | 2024-01-31 | [5 empty] | 2024-01-10 | 2024-01-10 |  |  |  |  | 28 | 28
1745 | Chino Hills | 4480 Chino Hills Pkwy | Chino Hills | 91710 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Alhambra | [5 empty] | 2023-08-01 | 7 | YES | Level 3 | NO | 2023-05-02 | 2023-06-15 | 32 | 32 | 2023-03-03 | 2023-03-03 | 74 | 74 | 1 | 1 | 2023-03-06 | 2023-03-09 | 2023-04-16 | 5 | 5 | 27 | 27
1746 | Desert Princess | 28-211 Desert Princess Drive | Cathedral City | 92234 | Riverside County | 4. Preliminary Design | 79 - Palm Springs | Desert | SBRO |  |  | 3641773 |  |  |  | 14 | YES | Level 2 | YES |  |  |  |  | 2023-03-03 | 2023-03-03 |  |  | 1 | 1 | 2023-03-06 | 2023-03-14 | 2023-04-10 | 8 | 8 | 20 | 20 | 2023-11-29 | 189 | 189 | 2023-11-29 | 2023-11-30
1747 | El Monte, CA - 9150 Flair Dr | 9200 Flair Dr | El Monte | 91731 | Los Angeles County | 11. Cancelled | 22 - Montebello | Metro East | Pomona |  |  | 3693841 |  |  | 2024-05-01 | 32 | YES | Level 3 |  |  | 2023-08-17 |  |  | 2023-03-03 | 2023-03-03 | 118 | 118 | 1 | 1 |  | 2023-03-09 | 2023-03-24 | 5 | 5 | 12 | 12 |  |  |  | 2024-03-14 | 2024-03-14 | 2024-04-25
1748 | Covina, CA - 1411 N Grand Ave | 1411 N Grand Ave | Covina | 91724 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 26 - Covina | Metro East | Pomona | [5 empty] | 2023-03-03 |  |  |  | YES |  |  |  |  | 2023-03-03 | 2023-03-03 |  |  | 1 | 1
1749 | K-8 & 10th St West Dvlpmt R29 Lancaster | 43144 10th St W | Lancaster | 93534 | Los Angeles County | 11. Cancelled | 36 - Antelope Valley | North Valley | Ventura |  |  | 3456432 | 2116473 | 2088407 | 2024-10-15 | 6 | YES | Level 3 |  | 2023-01-18 | 2023-02-03 | 13 | 13 | 2023-03-07 | [12 empty] | 2023-03-07 | 1 | 1 | 2023-03-07 | 2023-03-08 | 2023-04-20 | 2023-04-20 | 33 | 33 | 2023-04-21 | 2023-05-16 | 18 | 18 | 2023-07-05 | 2023-07-28 | 52 | 52 | 2023-07-18 | -9 |  | 2023-07-28 | 2023-09-11 | 2023-07-28 | 2023-08-24 | 1 | 1 | 71 | 71 | 20 | 20 | 2023-07-21 | 2023-08-15 |  | -6 | [11 empty] | 2023-07-28
1750 | West Covina Plaza | 112 Plaza Dr | West Covina | 91790 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [14 empty] | 2023-03-07 | 2023-03-07 |  |  | 1 | 1 | 2023-03-08 | 2023-03-10 | 2023-04-13 | 4 | 4 | 25 | 25
1751 | 73515 El Paseo | 73515 El Paseo | Palm Desert | 92260 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-09-30 |  |  |  | YES |  |  |  |  | 2023-03-07 | 2023-03-07 |  |  | 1 | 1 | 2023-03-08 | 2023-03-15 | 2023-04-11 | 7 | 7 | 20 | 20
1752 |  | 9757 Cataba Rd | Hesperia | 92345 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2023-06-28 | 6 | YES | Level 3 | YES | 2023-03-20 | 2023-03-29 | 8 | 8 | 2023-03-07 | 2023-03-07 | 17 | 17 | 1 | 1 | 2023-03-08 | 2023-03-10 | 2023-03-10 | 4 | 4 | 1 | 1
1753 |  | 3800 S Sepulveda Blvd -EV | Culver City | 90230 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-04-11 | 8 | YES |  |  | 2023-04-05 |  |  |  | 2023-03-08 | 2023-03-08 |  |  | 1 | 1 | 2023-03-09 | 2023-03-16 | 2023-04-04 | 7 | 7 | 14 | 14
1755 | R29 WinCo Foods Ventura R3 | 4750 Telephone Rd -EV | Ventura | 93003 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3196661 | 2122467 | 1923592 | 2024-08-19 | 3 | YES | Level 3 | YES |  |  |  |  | 2023-03-08 | [12 empty] | 2023-03-08 | 1 | 1 | 2023-03-09 | 2023-03-20 | 2023-05-04 | 2023-04-25 | 35 | 35 | 2023-05-18 | 2023-05-24 | 5 | 5 |  | 2023-07-06 | 30 | 30 | 2023-06-16 | -14 |  | 2023-08-09 | 2023-10-11 | 2023-08-09 | 2023-08-18 | 25 | 25 | 61 | 61 | 8 | 8
1756 |  | 56383 Mojave Point Rd | Baker | 92309 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [7 empty] | YES | Level 3 | YES | 2023-03-20 | 2023-04-25 | 27 | 27 | 2023-03-09 | 2023-03-09 | 34 | 34 | 1 | 1 | 2023-03-09 | 2023-03-13 | 2023-03-18 | 3 | 3 | 5 | 5
1758 | El Monte, CA - 3600 Peck Rd | 3600 Peck Rd | El Monte | 91730 | Los Angeles County | 2. Engineering | 22 - Montebello | Metro East | Pomona |  |  | 3684098 |  |  | 2024-09-01 |  | YES |  | YES | 2024-01-18 | 2024-02-12 | 18 | 18 | 2023-03-09 | 2023-03-09 | 235 | 235 | 1 | 1 | 2023-03-13 | 2023-03-21 | 2023-04-04 | 9 | 9 | 11 | 11 |  |  |  | 2024-02-27 | 2024-02-27 | 2024-04-09
1759 | 5665 Rosemead Blvd | 5665 Rosemead Blvd | Temple City | 91780 | Los Angeles County | 11. Cancelled | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2024-11-15 | 40 |  |  |  | 2024-02-08 |  |  |  | 2023-03-10 | 2023-03-10 |  |  | 1 | 1 | 2023-03-16 | 2023-03-21 | 2023-04-06 | 8 | 8 | 13 | 13
1760 | JD logistics | 13400 E Nelson Ave | City of Industry | 91746 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2023-03-10 | 2023-03-10 |  |  | 1 | 1 | 2023-03-13 | 2023-03-14 | 2023-03-16 | 3 | 3 | 3 | 3
1761 | Santa Monica/La Brea | 7080 Santa Monica Blvd - EV | West Hollywood | 90038 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-09-24 | 11 | YES |  | NO | 2023-03-21 |  |  |  | 2023-03-13 | 2023-03-13 |  |  | 1 | 1 | 2023-03-14 | 2023-03-15 | 2023-03-18 | 3 | 3 | 3 | 3
1762 | San Bernardino Shell | 5983 Palm Ave | San Bernardino | 92407 | San Bernardino County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO |  |  | 2911671 | 1773506 |  | 2024-08-01 | 2 | NO |  | YES |  |  |  |  | 2020-06-23 | 2020-06-23 |  |  | 1 | 1 | 2020-06-24 | 2020-07-02 | 2020-07-07 | 8 | 8 | 3 | 3 | 2020-07-08 | 11 | 11 | 2020-10-19 | 2020-10-23 | 2020-08-11 |  |  |  |  | 2020-12-17 |  |  |  | 2021-01-05 | 12 | 12 | 2021-01-05 | 1 | 1 | 2021-01-12 | 2021-04-21 | 2021-01-12 |  | 6 | 6 |  |  |  |  | 2021-01-13 | 2021-02-12 | 2021-03-30 | 7 | 7 | 32 | 32 | 53 | 53 | [6 empty] | 2021-01-12 | [8 empty] | 2022-02-03 | 2022-02-03 |  |  |  | 2022-01-07
1763 |  | 2350 Hall Ave | Jurupa Valley | 92509 | Riverside County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO |  |  | 3567506 | 2170302 | 2170304 | 2024-06-03 | 14 | YES | Level 3 | YES | 2023-04-11 | 2023-07-14 | 67 | 67 | 2023-03-14 | 2023-03-14 | 87 | 87 | 1 | 1 | 2023-03-15 | 2023-03-23 | 2023-04-03 | 8 | 8 | 8 | 8 | 2023-07-17 | 88 | 88 | 2023-08-10 | 2023-08-10 | 2023-09-25 | 2023-10-30 | 75 | 75 | 2023-10-31 | 2023-12-08 | 27 | 27
1764 | PSPC Blythe East - Phase 1 | 2088 E Hobsonway | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Rurals | SBRO |  |  | 3649595 |  |  | 2025-03-15 | 24 | NO |  | YES | 2023-08-31 | 2023-12-12 | 71 | 71 | 2023-03-23 | 2023-03-23 | 184 | 184 | 1 | 1 | 2023-03-27 | 2023-04-06 | 2023-05-09 | 11 | 11 | 24 | 24 | 2023-08-21 | 106 | 106 | 2024-01-18 | 2024-01-22 | 2024-02-20
1765 | W. Inyokern Rd & Brown Rd | W. Inyokern Rd & Brown Rd | Inyokern | 93527 | Kern County | 2. Engineering | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-10-01 | 30 | YES | Level 3 | YES | 2023-06-27 | 2023-07-28 | 23 | 23 | 2023-03-15 | 2023-03-15 | 96 | 96 | 1 | 1 | 2023-03-15 | 2023-03-21 | 2023-03-24 | 5 | 5 | 4 | 4
1766 | 4015 E Guasti Rd, Phase 2 | 4015 Guasti Rd | Ontario | 91761 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-03-30 | 12 | YES | Level 3 | YES | 2023-04-25 |  |  |  | 2023-03-15 | 2023-03-15 |  |  | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2 | 2 | 2 | 2
1767 | Harbor Blvd - Costa Mesa | 3589 Harbor Blvd | Costa Mesa | 92626 | Orange County | 4. Preliminary Design | 33 - Huntington Beach | Orange | Saddleback | [6 empty] | 10 | YES | Level 3 | YES | 2023-04-10 | 2023-05-25 | 34 | 34 | 2023-03-15 | 2023-03-15 | 52 | 52 | 1 | 1 | 2023-03-17 | 2023-03-23 | 2023-04-09 | 7 | 7 | 12 | 12
1768 | 1905 California St. (Originally 1901 California St) | 1905 California St. | Redlands | 92374 | San Bernardino County | 5. Final Design | 31 - Redlands | Desert | SBRO |  |  | 3629647 |  |  | 2023-09-30 | 12 | YES |  | YES | 2023-09-20 | 2023-11-03 | 33 | 33 | 2023-03-16 | 2023-03-16 | 164 | 164 | 1 | 1 | 2023-03-17 | 2023-03-21 | 2023-07-03 | 4 | 4 | 74 | 74 | 2023-11-03 | 164 | 164 | 2023-11-06 | 2023-11-07 | 2023-12-22 | 2024-01-26 | 56 | 56 | 2024-01-29 | 2024-01-30 | 2 | 2
1769 | 1990 S Cucamonga Ave | 1990 S Cucamonga Av-EV | Ontario | 91761 | San Bernardino County | 11. Cancelled | 34 - Ontario | Metro East | Pomona |  |  | 3632453 |  |  | 2023-09-30 | 12 | YES | Level 3 |  | 2023-09-21 |  |  |  | 2023-03-16 | 2023-03-16 |  |  | 1 | 1 | 2023-05-17 | 2023-03-21 | 2023-03-31 | 4 | 4 | 9 | 9 | 2023-11-09 | 168 | 168 | 2023-11-09 | 2023-11-14 | 2023-12-14 | 2024-01-23 | 49 | 49 | 2024-01-23 | 2024-01-26 | 4 | 4 | 2024-03-26
1770 | One Icon, Foothill Ranch, CA 92610 (EV1) | One Icon | Foothill Ranch | 92610 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-03-17 |  |  |  | YES |  |  |  |  | 2023-03-17 | 2023-03-17 |  |  | 1 | 1 | 2023-03-21 | 2023-04-06 | 2023-04-17 | 15 | 15 | 8 | 8
1771 |  | 1079 W Foothill Blvd | Upland | 91786 | San Bernardino County | 4. Preliminary Design | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-08-31 | 6 | YES | Level 3 | YES | 2023-04-21 | 2023-05-19 | 21 | 21 | 2023-03-23 | 2023-03-23 | 42 | 42 | 1 | 1 | 2023-03-23 | 2023-03-24 | 2023-04-07 | 2 | 2 | 11 | 11
1772 | Rialto-PSPC 2570 Riverside Ave Phase 1 | 10940 S. RIVERSIDE AVE.-EV | Rialto | 92501 | San Bernardino County | 2. Engineering | 30 - Foothill | Desert | SBRO |  |  | 3621517 |  |  |  | 10 |  |  | YES | 2023-08-31 |  |  |  | 2023-03-14 | 2023-03-14 |  |  | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 3 | 3 | 2 | 2 | 2023-10-19 | 155 | 155 | 2023-10-19 | 2023-10-23 | 2023-12-07 | 2024-01-29 | 68 | 68 | 2024-03-05
1773 | Inglewood, CA - 3550 W Century Blvd | 3550 W Century Blvd | Inglewood | 90303 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-11-22 | 8 | YES | Level 3 | YES | 2024-03-25 |  |  |  | 2023-03-23 | 2024-02-07 |  |  | 222 | 222 | 2024-02-08 | 2024-02-27 | 2024-02-28 | 14 | 14 | 2 | 2
1774 |  | 2510 Pico Blvd | Santa Monica | 90405 | Los Angeles County | 1. FVR | 42 - Santa Monica | Metro West | Alhambra | [7 empty] | YES | Level 3 |  | 2023-04-03 | 2023-04-21 | 15 | 15 | 2023-03-23 | 2023-03-23 | 22 | 22 | 1 | 1 | 2023-03-27 | 2023-03-28 | 2023-03-31 | 4 | 4 | 4 | 4
1775 | Torrance, CA - 5054 190th St | 5054 W 190th St | Torrance | 90503 | San Bernardino County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2025-03-02 | 16 | YES |  | YES |  |  |  |  | 2023-03-22 | 2024-03-18 |  |  | 250 | 250
1776 | South Gate Atlantic | 8990 Atlantic Ave | South Gate | 90280 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-04-15 |  |  |  | YES | 2023-04-20 | 2023-06-01 | 30 | 30 | 2023-03-23 | 2023-03-23 | 50 | 50 | 1 | 1 | 2023-03-27 | 2023-04-03 | 2023-04-20 | 8 | 8 | 14 | 14
1778 | 27923 Sloan Canyon Rd. Castaic, CA 91384 | 27923 Sloan Canyon Rd | Castaic | 91384 | Ventura County | 3. Active | 59 - Valencia | North Valley | Ventura | [5 empty] | 2024-12-31 | 16 | YES | Level 3 | [5 empty] | 2024-02-20 | 2024-02-20 |  |  | 1 | 1 | 2024-02-27 | 2024-03-01 | 2024-03-04 | 9 | 9 | 2 | 2
1779 | 8847 Avenue 280, Visalia, CA 93277 | 8847 Avenue 280 | Visalia | 93277 | Tulare County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-12-17 |  |  |  | YES |  |  |  |  | 2023-03-30 | 2023-03-30 |  |  | 1 | 1 | 2023-03-30 | 2023-04-11 | 2023-04-16 | 9 | 9 | 4 | 4
1780 | 3251 De Forest Circle | 3251 De Forest Circle | Mira Loma | 91752 | Riverside County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-10-06 | 100 | YES | Level 3 | YES | 2023-08-26 | 2023-09-12 | 11 | 11 | 2023-03-31 | 2023-03-31 | 115 | 115 | 1 | 1 | 2023-04-03 | 2023-04-11 | 2023-04-24 | 8 | 8 | 10 | 10
1782 | 4500 MacArthur Blvd, EV1, Newport Beach, CA - 92660 | 4500 MacArthur Blvd | Newport Beach | 92660 | Orange County | 1. FVR | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-09-30 | 16 | YES | Level 3 | YES | 2023-05-17 | 2023-07-29 | 51 | 51 | 2023-03-30 | 2023-03-30 | 85 | 85 | 1 | 1 | 2023-04-03 | 2023-04-05 | 2023-04-17 | 5 | 5 | 9 | 9
1783 | 2401 Atlantic Blvd | 2401 Atlantic Blvd | Monterey Park | 91754 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona | [5 empty] | 2023-11-30 | 2 | YES | Level 3 | YES | 2023-05-10 | 2023-06-20 | 29 | 29 | 2023-04-04 | 2023-04-04 | 55 | 55 | 1 | 1 | 2024-03-26 | 2023-04-17 | 2023-05-09 | 10 | 10 | 17 | 17
1784 | 2501 East Ave P, Bldg 584 | 2501 East Ave P, Bldg 584 | Palmdale | 93535 | Los Angeles County | 4. Preliminary Design | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-02-01 | 4 |  |  | YES |  |  |  |  | 2023-09-19 | 2023-09-19 |  |  | 1 | 1 | 2023-09-20 | 2023-10-01 | 2023-10-01 | 9 | 9 | 0
1785 | EV - PSPC North Palm Springs Indian Canyon | 6550 N Indian Canyon Dr. | Palm Springs | 92262 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO |  |  | 3665568 |  |  | 2024-05-15 | 17 | NO |  |  | 2024-01-22 |  |  |  | 2023-06-28 | 2023-06-28 |  |  | 1 | 1 | 2023-06-29 | 2023-07-13 | 2023-08-21 | 11 | 11 | 28 | 28 | 2024-01-19 | 141 | 141 | 2024-03-07 |  | 2024-04-04
1786 | Portifino- 5400 East The Toledo, Long Beach, CA 90803 | 5400 East The Toledo | Long Beach | 90803 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [7 empty] | YES |  | YES |  |  |  |  | 2023-04-04
1787 | La Habra Shopping Center | 2101 W Imperial Hwy - EV | La Habra | 90631 | Orange County | 1. FVR | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-01-10 |  | YES |  |  | 2023-04-25 |  |  |  | 2023-04-05 | 2023-04-05 |  |  | 1 | 1 | 2023-04-06 | 2023-04-18 | 2023-05-29 | 10 | 10 | 29 | 29
1789 | Rancho Santa Margarita Ford | 30031 Santa Margarita Pwky | Rancho Santa Margarita | 92688 | Orange County | 6. Requirements (permit, easment, etc.) | 43 - Saddleback | Orange | Saddleback | [7 empty] | YES | Level 3 | YES |  |  |  |  | 2023-04-02 | 2024-03-11 |  |  | 237 | 237 | 2024-03-11 | 2024-03-25 |  | 11 | 11
1790 | 102 Gill Station Coso Rd, Phase 1- (First EV Charging Station), Coso Junction | 30 Gill Station Coso Road | Olancha | 93549 | Inyo County | 10. Customer Hold | 86 - Ridgecrest | Rurals | Ventura |  |  | 3526531 | 2158776 |  | 2024-05-16 | 16 | NO |  |  | 2023-04-06 |  |  |  | 2023-04-10 | 2023-04-10 |  |  | 1 | 1 | [10 empty] | 2023-05-05 | 2023-05-08 | 2023-11-17 | 2023-11-13 |  |  | 2023-11-13 | 2023-11-21 | 7 | 7 | 2023-12-29 | 2023-12-29 | 26 | 26 | 2024-01-03 | 3 | 3 | 2024-01-03 | 2024-01-05 | 2024-01-03 | 2024-01-05 | 3 | 3 | 30 | 30 | 3 | 3 | 2023-12-27 | 2024-01-09 | 2024-01-18 | -3 |  | 7 | 7 | 15 | 15 | [6 empty] | 2024-01-03 |  | 2024-01-18
1791 | Motel 6 Westminster | 6266 Westminster Blvd | Westminster | 92683 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3573899 |  |  |  |  | YES | Level 3 | NO |  |  |  |  | 2023-04-07 | 2023-04-07 |  |  | 1 | 1 | 2023-04-10 | 2023-04-13 | 2023-04-24 | 5 | 5 | 8 | 8 | 2023-07-27 | 78 | 78 | 2023-07-27 | 2023-07-27 | 2023-09-12
1792 |  | 102 Baker St. East | Costa Mesa | 92626 | Orange County | 4. Preliminary Design | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2023-11-06 | 2 | YES | Level 2 | YES |  |  |  |  | 2023-04-13 | 2023-04-13 |  |  | 1 | 1 | 2023-04-17 | 2023-04-20 | 2023-05-09 | 6 | 6 | 14 | 14
1793 | Phase 1 - Commerce - Tanager | 2810 Tanager Ave | Commerce | 90040 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra |  |  | 3666473 |  |  | 2025-04-15 | 20 | NO |  | YES | 2023-09-25 | 2023-12-04 | 49 | 49 | 2023-04-13 | 2023-04-13 | 163 | 163 | 1 | 1 | 2023-04-17 | 2023-04-26 | 2023-04-28 | 10 | 10 | 3 | 3 | 2024-01-19 | 194 | 194 | 2024-01-22 | 2024-01-26 | 2024-03-08
1794 | High Desert Rd & Salt Springs | 2974 Lenwood Rd | Barstow | 92311 | San Bernardino County | 11. Cancelled | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-01-01 |  |  | Level 3 | [5 empty] | 2023-04-13 | 2023-04-13 |  |  | 1 | 1 | 2023-04-17 | 2023-04-25 | 2023-04-28 | 9 | 9 | 4 | 4
1795 | Death Valley, CA - Oasis at Death Valley | 6312 Zabriskie Ln | Death Valley | 92328 | Inyo County | 11. Cancelled | 86 - Ridgecrest | Rurals | SBRO | [5 empty] | 2025-05-30 |  | YES | [6 empty] | 2023-04-13 | 2023-04-13 |  |  | 1 | 1 | 2023-04-17 | 2023-04-26 | 2023-04-27 | 10 | 10 | 2 | 2
1796 | Long Beach, CA - 3321 E South St | 3321 E South St, EV-1 | Long Beach | 90805 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-11-30 |  | YES | [6 empty] | 2023-04-13 | 2023-04-13 |  |  | 1 | 1
1797 | Rialto, CA - 1355 W Renaissance Pkwy | 1355 W Renaissance Pkwy | Rialto | 92376 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-31 | [8 empty] | 2023-04-13 | 2023-04-13 |  |  | 1 | 1 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2 | 2 | 1 | 1
1798 | 1160 E Mariposa Ave, El Segundo, CA 90245 | 1160 E Mariposa Ave | El Segundo | 90245 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-11-22 | [8 empty] | 2023-04-19 | 2023-04-19 |  |  | 1 | 1 |  |  | 2023-05-16
1799 | 495 N Ventu Park Rd, Thousand Oaks, CA 91320 | 495 N Ventu Park Rd | Thousand Oaks | 91320 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-11-13 |  | NO | [6 empty] | 2023-04-18 | 2023-04-19 |  |  | 2 | 2 | 2023-04-19 | 2023-04-26 | 2023-04-30 | 6 | 6 | 3 | 3
1800 | 2 Dole Drive, Westlake Village, CA 91362 | 2 Dole Drive | Westlake Village | 91362 | Ventura County | 4. Preliminary Design | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-11-10 |  |  |  | YES |  |  |  |  | 2023-04-18 | 2023-04-18 |  |  | 1 | 1 | 2023-04-19 | 2023-04-25 | 2023-04-29 | 6 | 6 | 4 | 4
1801 | 21050 Golden Springs Dr | 21050 Golden Springs Dr | Diamond Bar | 91789 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona |  |  | 3668400 | 2228688 | 2241399 | 2024-12-10 | 16 | YES | Level 3 | YES | 2023-11-20 | 2024-01-05 | 31 | 31 | 2023-04-19 | 2023-04-19 | 181 | 181 | 1 | 1 | 2023-04-20 | 2023-04-27 | 2023-05-16 | 7 | 7 | 14 | 14 | 2024-01-25 | 194 | 194 | 2024-01-25 | 2024-01-26 | 2024-03-08 | 2024-03-22 | 41 | 41 | 2024-03-26
1802 | 1540 E Main St., EV1 | 1540 E Main St | Barstow | 92311 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [5 empty] | 2024-07-30 | 24 | YES | Level 3 | YES | 2024-02-13 |  |  |  | 2023-04-19 | 2023-04-19 |  |  | 1 | 1 | 2023-10-23 | 2024-10-24 | 2023-10-30 | 385 | 385 | -250
1803 | 8856 Valley Blvd | 8856 Valley Blvd | Rosemead | 91770 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona | [5 empty] | 2024-04-08 | 4 | YES | Level 3 | YES | 2023-05-06 | 2023-06-19 | 30 | 30 | 2023-04-20 | 2023-04-20 | 42 | 42 | 1 | 1 | 2023-04-24 | 2023-05-02 | 2023-05-05 | 9 | 9 | 4 | 4
1804 |  | 19646 S Figueroa St. | Carson | 90745 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2023-11-01 | 6 | YES | Level 3 | YES | 2023-06-26 | 2023-08-08 | 31 | 31 | 2023-04-20 | 2023-04-20 | 77 | 77 | 1 | 1 | 2023-04-24 | 2023-05-09 | 2023-05-23 | 14 | 14 | 11 | 11
1805 |  | 14228 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-11-01 | 14 | YES | Level 3 | YES | 2023-06-26 | 2023-08-09 | 32 | 32 | 2023-04-20 | 2023-04-20 | 78 | 78 | 1 | 1 | 2023-04-24 | 2023-05-08 | 2023-05-13 | 13 | 13 | 5 | 5
1806 | 1500 S Greenwood Ave | 1500 S Greenwood Ave | Montebello | 90640 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-01-01 | 16 | YES | Level 3 | YES | 2023-06-26 | 2023-07-26 | 22 | 22 | 2023-04-20 | 2023-04-20 | 68 | 68 | 1 | 1 | 2023-04-24 | 2023-05-03 | 2023-05-13 | 10 | 10 | 8 | 8
1807 |  | 100 Radio Rd | Corona | 92879 | Riverside County | 1. FVR | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-01-01 | 14 | YES | Level 3 |  | 2023-06-26 | 2023-08-02 | 27 | 27 | 2023-04-20 | 2023-04-20 | 73 | 73 | 1 | 1 | 2023-04-24 | 2023-05-08 | 2023-05-24 | 13 | 13 | 13 | 13
1808 | 5105 E Los Angeles Ave | 5105 E Los Angeles Ave | Simi Valley | 93063 | Ventura County | 10. Customer Hold | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2025-04-07 |  | YES |  | YES |  |  |  |  | 2023-04-18 | 2023-04-18 |  |  | 1 | 1 | 2023-12-20 | 2023-12-21 | 2023-12-28 | 173 | 173 | 5 | 5
1809 |  | 1465 S Greenwood Ave | Montebello | 90640 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-01-01 | 10 | YES | Level 3 |  | 2023-06-26 | 2023-07-26 | 22 | 22 | 2023-04-24 | 2023-04-24 | 66 | 66 | 1 | 1 | 2023-04-25 | 2023-05-04 | 2023-05-13 | 9 | 9 | 7 | 7
1810 |  | 2640 Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [7 empty] | YES |  | NO |  |  |  |  | 2023-04-24 | 2023-04-24 |  |  | 1 | 1 | 2023-04-25 | 2023-04-26 |  | 3 | 3
1811 | Yale & Green St | Yale & Green St | Santa Paula | 93060 | Ventura County | 4. Preliminary Design | 39 - Ventura | North Coast | Ventura | [5 empty] | 2023-11-01 | 6 |  |  | NO |  |  |  |  | 2023-04-25 | 2023-04-25 |  |  | 1 | 1 | 2023-04-26 | 2023-05-09 | 2023-05-13 | 11 | 11 | 4 | 4
1812 | Main St. Santa Paula | 801 E Main St | Santa Paula | 93060 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3687320 |  |  | 2024-08-31 | 6 | YES |  | YES |  |  |  |  | 2023-04-25 | 2023-04-25 |  |  | 1 | 1 | 2023-04-26 | 2023-05-09 | 2023-05-13 | 11 | 11 | 4 | 4 |  |  |  | 2024-03-04 | 2024-03-05 | 2024-04-17
1813 | 2640 N Sepulveda Blvd EV | 2640 N Sepulveda Blvd | Manhattan Beach | 90266 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2023-12-01 | 6 | NO |  | YES |  |  |  |  | 2023-04-25 | 2023-04-25 |  |  | 1 | 1 | 2023-04-25 | 2023-04-26 | 2023-05-12 | 2 | 2 | 13 | 13
1814 | 2450 Kella Ave | 2450 Kella Ave | Whittier | 90601 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona |  |  | 3689144 | 5575680 | 2242678 | 2025-06-01 | 12 | YES | Level 3 | YES | 2023-05-15 | 2023-06-26 | 30 | 30 | 2023-04-25 | 2023-04-25 | 44 | 44 | 1 | 1 | 2023-04-26 | 2023-05-02 | 2023-05-15 | 6 | 6 | 10 | 10 | 2024-03-06 | 218 | 218 | 2024-03-06 | 2024-03-07 | 2024-04-19
1815 | 919 N Mountain Ave EV1 | 919 N Mountain Ave | Upland | 91786 | San Bernardino County | 1. FVR | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-01-07 | 24 | YES | Level 3 |  | 2024-03-26 |  |  |  | 2024-02-15 | 2024-02-15 |  |  | 1 | 1 | 2024-02-20 | 2024-03-07 | 2024-02-07 | 15 | 15 | -21
1816 | MUSD | 5297 Maureen Lane | Moorpark | 93021 | Ventura County | 7. Civil Construction | 35 - Thousand Oaks | North Coast | Ventura | [9 empty] | NO |  |  |  |  | 2023-04-26 | 2023-04-26 |  |  | 1 | 1 | 2023-04-27 | 2023-05-09 | 2023-05-13 | 10 | 10 | 4 | 4
1817 | R29 Downey Crossroads | 9501 Lakewood Blvd #EV | Downey | 90242 | Los Angeles County | 3. Active | 47 - Whittier | Metro West | Alhambra |  |  | 3207804 | 2128835 |  | 2024-04-29 | 8 | YES | Level 2 | YES | 2021-11-12 | 2021-11-15 | 2 | 2 | 2023-04-21 | 2021-03-25 | 164 | 164 | -525 |  | 2021-03-29 | 2021-04-01 | 2021-04-08 | 6 | 6 | 6 | 6 | 2023-04-27 | 5 | 5 | 2023-04-28 | 2023-05-03 | 2023-06-15 | 2023-06-27 | 43 | 43 | 2023-06-27 | 2023-09-18 | 58 | 58 | 2023-09-27 | 2023-10-03 | 12 | 12 | 2023-10-11 | 7 | 7 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-11 | 7 | 7 | 18 | 18 | 1 | 1 | 2023-09-19 | 2023-10-11 | 2023-12-08 | -11 |  | 41 | 41 | 57 | 57 | [6 empty] | 2023-10-11 |  | 2023-12-08 | [5 empty] | 2024-01-08 | 2024-03-08 | 2024-03-15 | 48 | 48 | 2024-01-22 |  |  | 2024-01-29 | 6 | 6
1818 | 20140 Hawthorne Blvd EV1, Torrance CA 90503 | 20140 Hawthorne Blvd | Torrance | 90503 | Los Angeles County | 7. Civil Construction | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-09-06 | 32 |  |  |  | 2023-06-13 |  |  |  | 2023-04-28 | 2023-04-28 |  |  | 1 | 1 | 2023-05-01 |  | 2023-06-11
1819 | Simi Valley, CA - 5255 Cochran St | 5255 1/2 Cochran St | Simi Valley | 93063 | Ventura County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura |  |  | 3571677 | 2217489 | 2217488 | 2024-06-28 | 24 | YES | Level 3 | YES |  | 2023-07-13 |  |  | 2023-04-28 | 2023-04-28 | 53 | 53 | 1 | 1 | 2023-05-25 | 2023-06-21 | 2023-06-21 | 38 | 38 | 1 | 1 | 2023-07-25 | 61 | 61 | 2023-07-25 | 2023-07-25 | 2023-09-08 | 2023-09-22 | 43 | 43 | 2023-09-22 | 2023-10-11 | 14 | 14 | 2023-11-01 | 2024-01-11 | 63 | 63 | 2024-01-12 | 2 | 2 | 2024-02-05 | 2024-02-21 | 2024-02-05 | 2024-02-07 | 17 | 17 | 81 | 81 | 3 | 3 | 2024-01-31 | 2024-02-07 | 2024-02-23 | 14 | 14 | 12 | 12 | 17 | 17 | [6 empty] | 2024-02-05 |  | 2024-02-23
1820 | 625 S Placentia Ave (EV1) | 625 S Placentia Ave | Fullerton | 92831 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-12-01 |  |  |  | YES | 2023-06-07 | 2023-07-18 | 29 | 29 | 2023-05-04 | 2023-05-04 | 52 | 52 | 1 | 1 | 2023-05-04 |  | 2023-05-29
1821 | 30 S Baldwin Ave | 30 S Baldwin Ave | Sierra Madre | 91024 | Los Angeles County | 4. Preliminary Design | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2025-03-30 | 16 | YES |  | YES | 2024-02-14 |  |  |  | 2024-01-18 | 2024-01-18 |  |  | 1 | 1 | 2024-01-22 | 2024-01-29 | 2024-01-29 | 8 | 8 | 1 | 1
1822 | Forum Mobility | 2934 E Las Hermanas St | Compton | 90221 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra |  |  | 3620063 | 2208625 |  | 2025-01-31 | 60 | YES | Level 3 | YES | 2023-06-23 | 2023-08-25 | 45 | 45 | 2023-05-04 | 2023-05-04 | 80 | 80 | 1 | 1 | 2023-05-08 | 2023-05-18 | 2023-05-27 | 11 | 11 | 7 | 7 | 2023-10-17 | 116 | 116 | 2023-10-18 | 2023-10-20 | 2024-01-29 | 2023-12-06 | 35 | 35 | 2023-12-14 | 2024-01-25 | 28 | 28
1823 | 9640 Mariposa Rd | 9640 Mariposa Rd | Hesperia | 92344 | San Bernardino County | 2. Engineering | 73 - Victorville | Rurals | SBRO | [5 empty] | 2024-07-22 | 12 | YES | Level 2 | YES | 2023-06-27 | 2023-07-28 | 23 | 23 | 2023-05-04 | 2023-05-04 | 60 | 60 | 1 | 1 | 2023-05-08 | 2023-05-16 |  | 9 | 9
1824 | 401 Woollomes Ave | 401 Woollomes Ave | Delano | 93215 | Kern County | 10. Customer Hold | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2025-01-01 |  |  |  | YES |  |  |  |  | 2023-05-08 | 2023-05-08 |  |  | 1 | 1 | 2023-05-08 | 2023-05-16 | 2023-05-26 | 7 | 7 | 9 | 9
1825 | Oxnard Harbor District - N Terminal, Phase I | North Terminal Warf West SP, Phase I | Port Hueneme | 93041 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3550288 | 2145644 | 2145645 | 2024-09-01 | 2 | YES | Level 3 |  | 2023-05-17 | 2023-06-12 | 18 | 18 | 2023-05-08 | 2023-05-08 | 25 | 25 | 1 | 1 | 2023-05-09 | 2023-05-11 | 2023-05-16 | 4 | 4 | 4 | 4 | 2023-06-13 | 26 | 26 | 2023-09-28 | 2023-09-29 | 2023-11-14 | 2023-11-17 | 112 | 112 | 2023-11-20 | 2023-12-11 | 14 | 14 | 2024-01-02
1826 | Frontage - Corona | 2222 Frontage Rd | Corona | 92882 | Riverside County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2026-01-01 |  |  |  | YES |  |  |  |  | 2023-05-08 | 2023-05-08 |  |  | 1 | 1 | 2023-05-09 | 2023-05-15 | 2023-05-19 | 6 | 6 | 5 | 5
1827 | Morongo Commercial Center | 47993 Morongo Trail | Cabazon | 92330 | Riverside County | 1. FVR | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-03-01 | 4 |  | Level 2 | [5 empty] | 2023-05-09 | 2023-05-09 |  |  | 1 | 1 | 2023-05-10 | 2023-05-23 | 2023-06-19 | 11 | 11 | 19 | 19
1828 | Morongo Casion | 49500 Seminole Dr | Cabazon | 92230 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES |  |  |  |  | 2023-05-09 | 2023-05-09 |  |  | 1 | 1 | 2023-05-10 | 2023-05-23 |  | 11 | 11
1829 | Morongo Travel Center | 48540 Morongo Trail | Cabazon | 92230 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-03-01 | 4 |  | Level 3 | [5 empty] | 2023-05-09 | 2023-05-09 |  |  | 1 | 1 | 2023-05-10 | 2023-05-23 | 2023-06-20 | 11 | 11 | 20 | 20
1830 | Fontana | 16721 Valley Blvd | Fontana | 92335 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-01-01 | [8 empty] | 2023-05-09 | 2023-05-09 |  |  | 1 | 1 | 2023-05-10 | 2023-05-17 | 2023-05-22 | 7 | 7 | 4 | 4
1831 | Morongo Casion WC North | 49500 Seminole Dr - EV1 | Cabazon | 92230 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-06-01 |  | YES |  | YES |  |  |  |  | 2023-05-12 | 2023-05-12 |  |  | 1 | 1 | 2023-05-15 | 2023-05-23 | 2023-06-22 | 8 | 8 | 22 | 22
1832 | 102 Gill Station Coso Rd EV1, Phase 2 | 102 Gill Station Coso Rd | Olancha | 93549 | Inyo County | 11. Cancelled | 86 - Ridgecrest | Rurals | SBRO |  |  | 3531543 |  |  | 2024-10-01 | 48 | YES | Level 3 | YES | 2023-04-06 | 2023-04-10 | 3 | 3 | 2023-05-15 | 2023-05-15 | -26 |  | 1 | 1 | [10 empty] | 2023-05-15 | 2023-05-15
1833 | 23041 Savi Ranch Parkway | 23041 Savi Ranch Pkwy | Yorba Linda | 92887 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-02-28 | 20 | YES | Level 3 | YES | 2023-06-07 | 2023-07-20 | 31 | 31 | 2023-05-13 | 2023-05-13 | 47 | 47 | 0 |  | 2023-05-15 | 2023-05-23 | 2023-05-31 | 7 | 7 | 6 | 6
1834 | Watson Center Rd & Wilmington Ave | 22707 S Wilmington Ave | Carson | 90745 | Los Angeles County | 11. Cancelled | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-09-30 | 4 | YES | Level 3 |  | 2023-06-12 | 2023-06-16 | 5 | 5 | 2023-05-16 | 2023-05-16 | 23 | 23 | 1 | 1 | 2023-05-17 | 2023-05-23 | 2023-05-28 | 6 | 6 | 4 | 4
1835 | 1870 Harbor Blvd, EV-1 | 1870 Harbor Blvd | Costa Mesa | 92627 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-04-30 | 20 | YES |  | YES |  |  |  |  | 2023-05-22 | 2023-05-22 |  |  | 1 | 1 | 2023-05-22 | 2023-05-25 | 2023-05-31 | 4 | 4 | 4 | 4
1836 | 24372 Rockfield Blvd EV-1 | 24372 Rockfield Blvd | Lake Forest | 92630 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-04-30 | 20 | YES | Level 3 |  | 2023-08-29 | 2023-10-11 | 31 | 31 | 2023-05-19 | 2024-02-14 | -86 |  | 186 | 186 | 2024-02-16 | 2024-02-21 | 2024-02-20 | 5 | 5 | -2
1837 | 18920 Brookhurst St | 18920 Brookhurst St | Fountain Valley | 92708 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-09-30 | 16 |  |  | NO |  |  |  |  | 2023-05-19 | 2023-05-19 |  |  | 1 | 1 | 2023-05-22 | 2023-05-26 | 2023-06-05 | 6 | 6 | 6 | 6
1838 | 111 Pacifica | 111 Pacifica | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [6 empty] | 8 | YES | Level 3 | [5 empty] | 2023-05-22 | [5 empty] | 2023-04-28 | 2023-05-04 | 2023-05-22 |  |  | 13 | 13
1839 | 18261 Brookhurst St | 18261 Brookhurst St | Fountain Valley | 92708 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-09-30 | 24 |  |  | YES |  |  |  |  | 2023-05-22 | 2023-05-22 |  |  | 1 | 1 | 2023-05-23 | 2023-05-26 | 2023-06-05 | 5 | 5 | 6 | 6
1840 | 4100 N Webster Ave | 4102 N Webster Ave | Perris | 92571 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar |  |  | 3630506 | 2208921 |  | 2024-06-21 | 9 | YES | Level 2 | YES | 2023-10-06 | 2023-11-03 | 21 | 21 | 2023-05-23 | 2023-05-23 | 116 | 116 | 1 | 1 | 2023-05-25 | 2023-05-30 | 2023-06-21 | 5 | 5 | 17 | 17 | 2023-11-06 | 117 | 117 | 2023-11-07 |  | 2023-12-27 | 2023-12-22 | 33 | 33 | 2023-12-22 | 2024-01-08 | 10 | 10 | 2024-01-30 | 2024-02-06 | 21 | 21 | 2024-03-12 | 25 | 25 | [10 empty] | 2024-02-23 | 2024-03-05 |  | 13 | 13 |  |  |  |  | 2024-03-12 | 1 | 1 | 2024-03-22 | 9 | 9 | [6 empty] | 25 | 25
1841 | PSPC Slover Ave - Jurupa Valley | 12069 Riverside Dr | Jurupa Valley | 91752 | Riverside County | 6. Requirements (permit, easment, etc.) | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-11-30 |  |  |  | YES | 2023-06-14 |  |  |  | 2023-05-24 | 2023-05-24 |  |  | 1 | 1 | 2023-05-25 | 2023-05-31 | 2023-06-06 | 5 | 5 | 5 | 5
1842 | Castaic PFJ 372 | 31642 Castaic Rd | Castaic | 92377 | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura |  |  | 3574275 | 2161767 |  | 2024-06-28 | 10 | NO |  | YES | 2023-07-24 | 2023-07-26 | 3 | 3 | 2023-05-24 | 2023-05-24 | 44 | 44 | 1 | 1 | 2023-05-25 | 2023-05-30 | 2023-06-02 | 4 | 4 | 4 | 4 |  |  |  | 2023-08-01 | 2023-08-02 | 2023-09-14 | 2023-09-14 |  |  | 2023-09-14 | 2023-10-11 | 20 | 20 | 2023-11-09 | 2024-01-19 | 68 | 68 | 2024-01-22 | 2 | 2 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-25 | 2 | 2 | 72 | 72 | 4 | 4 | 2024-01-19 | 2024-01-31 |  | 1 | 1 | [10 empty] | 2024-01-22
1843 | Rialto | 2325 Sierra Lakes Pkwy | Rialto | 92377 | San Bernardino County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-12-02 | 8 | NO |  | YES | 2023-11-08 | 2023-12-18 | 27 | 27 | 2023-05-24 | 2023-05-24 | 144 | 144 | 1 | 1 | 2023-05-25 | 2023-06-05 | 2023-06-11 | 8 | 8 | 5 | 5 | 2023-11-27 | 129 | 129
1844 | Boron PFJ 200 | 5725 Hwy 58 | Boron | 93516 | Kern County | 7. Civil Construction | 86 - Ridgecrest | Rurals | Ventura |  |  | 3601534 |  |  | 2023-11-15 | 4 | NO |  | YES | 2023-07-25 | 2023-08-22 | 21 | 21 | 2023-05-24 | 2023-05-24 | 63 | 63 | 1 | 1 | 2023-05-25 | 2023-05-31 | 2023-06-03 | 5 | 5 | 3 | 3 | 2023-09-13 | 78 | 78 | 2024-03-15 | 2024-03-15 | 2024-04-26
1845 | R29 Azalea Shopping Center R2 | 4843 Firestone Blvd EV | South Gate | 90280 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra |  |  | 3385711 | 2137255 | 2077985 | 2024-05-28 | 8 | YES | Level 3 | YES | 2022-09-14 | 2022-09-16 | 3 | 3 | 2022-04-21 | 2022-04-21 | 104 | 104 | 1 | 1 | 2022-04-25 | 2022-05-03 | 2022-05-10 | 9 | 9 | 6 | 6 | 2023-05-25 | 278 | 278 | 2023-05-25 | 2023-05-30 | 2023-07-13 | 2023-07-06 | 29 | 29 | 2023-08-29 | 2023-09-06 | 6 | 6 | 2023-09-29 | 2023-10-20 | 33 | 33 | 2023-10-20 | 1 | 1 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2023-10-23 | 1 | 1 | 34 | 34 | 2 | 2 | 2023-11-01 | 2024-01-01 | 2024-03-01 | 9 | 9 | 42 | 42 | 82 | 82 | [6 empty] | 2023-10-20 |  | 2024-03-01 | [5 empty] | 2024-03-11 |  |  |  |  | 2024-03-06
1846 | Ventura | 1264 Callens Rd | Ventura | 93003 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura | [5 empty] | 2024-01-01 | 6 | YES | Level 3 | YES | 2023-06-27 | 2023-08-01 | 25 | 25 | 2023-05-26 | 2023-05-26 | 46 | 46 | 1 | 1 | 2023-05-30 | 2023-06-01 | 2023-06-03 | 4 | 4 | 2 | 2
1847 | La Mirada | 15050 Northam St | La Mirada | 90638 | Los Angeles County | 4. Preliminary Design | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2024-01-01 | 8 | YES | Level 3 | YES | 2023-07-05 | 2023-08-18 | 33 | 33 | 2023-05-26 | 2023-05-26 | 59 | 59 | 1 | 1 | 2023-05-30 | 2023-06-02 | 2023-06-06 | 5 | 5 | 3 | 3
1848 | Phase 1 - Slover Almond | 14311 Slover Ave | Fontana | 92337 | San Bernardino County | 2. Engineering | 30 - Foothill | Desert | SBRO |  |  | 3667788 |  |  | 2024-03-15 | 16 | NO |  | YES | 2023-09-25 | 2023-11-30 | 47 | 47 | 2023-05-26 | 2023-05-26 | 130 | 130 | 1 | 1 | 2023-05-30 | 2023-06-01 | 2023-06-06 | 4 | 4 | 4 | 4 | 2024-01-18 | 162 | 162 | 2024-01-24 | 2024-01-29 | 2024-02-21
1849 | 17114 Slover Ave | 17114 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-10-01 | 12 | YES | Level 3 | YES | 2023-09-25 | 2023-11-01 | 28 | 28 | 2023-05-31 | 2023-05-31 | 109 | 109 | 1 | 1 | 2023-06-02 | 2023-06-12 | 2023-07-17 | 9 | 9 | 25 | 25
1850 | 24801 Alicia Parkway | 24801 Alicia Parkway | Laguna Hills | 92563 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback |  |  | 3634511 | 2203377 |  | 2024-04-01 | 8 | YES | Level 3 | YES | 2023-09-20 | 2023-11-07 | 35 | 35 | 2023-05-31 | 2023-05-31 | 113 | 113 | 1 | 1 | 2023-06-02 | 2023-06-13 | 2023-06-16 | 10 | 10 | 4 | 4 | 2023-11-14 | 118 | 118 | 2023-11-14 | 2023-11-20
1851 | 701 S Parker St | 701 S Parker St | Orange | 92868 | Orange County | 5. Final Design | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-06-01 | 20 |  | Level 3 | YES |  |  |  |  | 2023-05-31 | 2023-05-31 |  |  | 1 | 1 | 2023-06-02 | 2023-06-13 | 2023-06-19 | 10 | 10 | 5 | 5
1852 | 135 E Victoria Street | 135 E Victoria St | Carson | 90746 | Los Angeles County | 1. FVR | 32 - Compton | Metro West | Alhambra |  |  | 3635369 | 2220673 |  | 2023-12-31 |  | NO |  |  | 2023-10-04 | 2023-11-14 | 30 | 30 | 2023-05-30 | 2023-05-30 | 119 | 119 | 1 | 1 | 2023-05-31 | 2023-06-05 | 2023-06-23 | 5 | 5 | 15 | 15 | 2023-11-15 | 120 | 120 | 2023-11-15 | 2023-11-21 | 2024-01-08 | 2024-02-06 | 55 | 55 | 2024-02-06 | 2024-03-07 | 22 | 22 | 2024-04-18
1853 | 18461 Brookhurst St | 18461 Brookhurst St | Fountain Valley | 92708 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-11-01 | 24 | [7 empty] | 2023-05-30 | 2023-06-02 |  |  | 4 | 4 | 2023-06-14
1854 | Morongo Casion WC South | 49500 Seminola Dr, EV-2 | Cabazon | 92230 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-06-01 |  | YES |  | NO |  |  |  |  | 2023-06-06 | 2023-06-06 |  |  | 1 | 1 | 2023-06-07 | 2023-06-19 | 2023-06-22 | 10 | 10 | 4 | 4
1855 | 12970 Day Street | 12970 Day St | Moreno Valley | 92553 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar |  |  | 3576309 |  |  |  | 2 | YES | Level 3 | NO |  |  |  |  | 2023-03-27 | 2023-06-07 |  |  | 52 | 52 | 2023-06-08 | 2023-06-14 | 2023-06-28 | 6 | 6 | 11 | 11 | 2023-09-26 | 129 | 129 | 2023-10-02 | 2023-10-02
1856 | KPC Menifee | 28400 McCall Blvd | Menifee | 92585 | Riverside County | 12. System Upgrade | 77 - Menifee | San Jacinto | Wildomar |  |  | 3582385 | 2195030 |  | 2025-03-28 |  | YES |  | YES |  |  |  |  | 2023-06-07 | 2023-06-07 |  |  | 1 | 1 | 2023-06-08 | 2023-06-14 | 2023-07-10 | 6 | 6 | 18 | 18 | 2023-08-04 | 42 | 42 | 2023-10-10 | 2023-10-10 | 2024-04-18
1857 | Irvine | 18912 MacArthur Blvd | Irvine | 92612 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-12-02 |  |  |  | YES | 2023-07-11 | 2023-08-25 | 34 | 34 | 2023-06-12 | 2023-06-12 | 54 | 54 | 1 | 1 | 2023-06-13 | 2023-06-19 | 2023-06-25 | 6 | 6 | 5 | 5
1858 | Rancho Cucamonga | 11560 E Fourth St | Rancho Cucamonga | 91730 | San Bernardino County | 1. FVR | 34 - Ontario | Metro East | Pomona | [9 empty] | YES | 2023-06-28 |  |  |  | 2023-06-12 | 2023-06-12 |  |  | 1 | 1 | 2023-06-13 | 2023-06-15 | 2023-06-28 | 4 | 4 | 10 | 10
1859 | 22 Vista Point Dr | 22 Vista Point Dr | Lee Vining | 93541 | Mono County | 6. Requirements (permit, easment, etc.) | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2024-08-01 | 12 | YES | [6 empty] | 2023-06-12 | 2024-03-04 |  |  | 183 | 183 | 2024-03-11
1860 | Stanton Motel 6 | 7450 Katella Ave | Stanton | 90680 | Orange County | 6. Requirements (permit, easment, etc.) | 48 - Fullerton | Orange | Saddleback |  |  | 3565428 | 2154838 | 2154837 | 2024-06-28 |  | YES | Level 3 | YES |  |  |  |  | 2023-06-13 | 2023-06-13 |  |  | 1 | 1 | 2023-06-14 | 2023-06-20 | 2023-06-25 | 6 | 6 | 4 | 4 | 2023-07-13 | 22 | 22 | 2023-07-14 | 2023-07-17 | 2023-08-28 | 2023-08-11 | 22 | 22 | 2023-08-11 | 2023-08-17 | 5 | 5 | 2023-09-14 | 2023-09-19 | 23 | 23 | 2023-09-26 | 6 | 6 | 2023-09-26 | 2024-01-18 | 2023-09-26 | 2023-09-27 | 6 | 6 | 29 | 29 | 2 | 2 | 2023-08-29 | 2023-09-20 | 2023-10-16 | -15 |  | 19 | 19 | 34 | 34 | [6 empty] | 2023-09-20 |  | 2023-10-16
1861 | Rule 29 Huntington Park Autozone | 2901 E Florence Ave EV | Huntington Park | 90255 | Los Angeles County | 4. Preliminary Design | 32 - Compton | Metro West | Alhambra |  |  | 3584821 | 2204928 | 2204927 | 2024-08-25 | 6 | YES | Level 2 | YES | 2023-07-03 | 2023-08-11 | 29 | 29 | 2023-06-13 | 2023-06-13 | 43 | 43 | 1 | 1 | 2023-06-16 | 2023-06-19 | 2023-07-01 | 5 | 5 | 10 | 10 | 2023-07-03 | 15 | 15 | 2023-08-30 | 2023-08-31 | 2023-10-13 | 2023-10-02 | 64 | 64 | 2023-10-02 | 2023-11-15 | 33 | 33 | 2023-12-11 | 2024-01-16 | 40 | 40 | 2024-01-12 | -2 |  | 2024-01-17 |  | 2024-01-17 | 2024-01-19 | 2 | 2 | 43 | 43 | 3 | 3 | 2023-12-07 | 2024-01-11 |  | -26 | [11 empty] | 2024-01-11
1862 | Tuttle Click Irvine | 43.5 Auto Center Drive | Irvine | 92618 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3680773 |  |  | 2023-12-23 | 44 | YES | Level 3 | NO | 2023-07-05 | 2023-08-15 | 30 | 30 | 2023-06-14 | 2023-06-14 | 44 | 44 | 1 | 1 | 2023-06-14 | 2023-06-20 | 2023-06-25 | 5 | 5 | 4 | 4 | 2024-02-20 | 172 | 172 | 2024-02-20 | 2024-03-14 | 2024-04-25
1864 | Diamond Bar | 21660 Copley Drive | Diamond Bar | 91765 | Los Angeles County | 11. Cancelled | 26 - Covina | Metro East | Pomona | [6 empty] | 4 |  |  | NO |  |  |  |  | 2023-06-19 | 2023-06-19 |  |  | 1 | 1 | 2023-06-20 | 2023-06-21 | 2023-07-06 | 3 | 3 | 11 | 11
1865 |  | 21700 Copley Drive | Diamond Bar | 91765 | Los Angeles County | 4. Preliminary Design | 26 - Covina | Metro East | Pomona | [6 empty] | 4 |  |  | YES |  |  |  |  | 2023-06-19 | 2023-06-19 |  |  | 1 | 1 | 2023-06-20 | 2023-06-21 | 2023-07-06 | 3 | 3 | 11 | 11
1866 | 1475 S Harbor Blvd, Fullerton, CA | 1455 S Harbor Blvd EV | Fullerton | 92832 | Orange County | 4. Preliminary Design | 48 - Fullerton | Orange | Saddleback |  |  | 3670809 |  |  | 2024-06-30 | 12 | YES | Level 2 | NO | 2023-07-06 | 2024-01-23 | 138 | 138 | 2023-06-21 | 2023-06-21 | 148 | 148 | 1 | 1 | 2023-06-22 | 2023-07-30 | 2023-06-30 | 27 | 27 | -20 |  | 2024-01-24 | 149 | 149 | 2024-01-30 | 2024-01-30 | 2024-03-01
1867 | Costa Mesa Robins Ford | 2060 A Harbor Blvd | Costa Mesa | 92627 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback |  |  | 3669799 |  |  | 2024-06-15 | 5 | YES | Level 3 | YES |  |  |  |  | 2023-08-01 | 2023-08-01 |  |  | 1 | 1 | 2023-08-03 | 2023-08-03 | 2023-08-09 | 3 | 3 | 5 | 5 | 2024-01-25 | 122 | 122 | 2024-01-29 | 2024-01-31 | 2024-03-12 | 2024-03-21 | 40 | 40 | 2024-03-21
1868 | R29 BOA - South Pasadena | 929 S Fair Oaks Ave | South Pasadena | 91030 | Los Angeles County | 3. Active | 27 - Monrovia | Metro East | Pomona |  |  | 3239419 | 2169239 | 1967602 | 2024-07-08 |  | YES | Level 2 | YES | 2022-01-04 | 2022-01-18 | 10 | 10 | 2021-12-17 | 2021-12-17 | 21 | 21 | 1 | 1 | 2021-12-21 |  | 2022-01-03 |  |  |  |  | 2023-06-23 | 384 | 384 | 2023-06-23 | [10 empty] | 2023-05-23 |  |  | 2023-09-06 | 74 | 74 | 2023-10-10 | 2023-10-10 | 2023-10-10 | 2023-10-10 | 98 | 98 |  |  | 1 | 1 | 2023-10-10 | 2023-11-30 | 2024-02-02 | 98 | 98 | 44 | 44 | 79 | 79 | 2023-10-16 | 29 | 29 | 2023-11-06 | 16 | 16 | 2023-10-10 | 2023-10-10 | 2024-02-02 | 2024-02-02 | 79 | 79 | 102 | 102
1869 | Temecula | 42188 Winchester Rd | Temecula | 92590 | Riverside County | 6. Requirements (permit, easment, etc.) | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-12-01 | 4 | YES | Level 2 | YES | 2023-08-09 | 2023-09-20 | 30 | 30 | 2023-06-23 | 2023-06-23 | 62 | 62 | 1 | 1 | 2023-06-27 | 2023-07-10 | 2023-08-09 | 11 | 11 | 23 | 23
1870 | R29 Village at Century R2 | 3380 W Century Blvd | Inglewood | 90303 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra |  |  | 3359574 | 2201156 | 2198239 | 2024-08-25 | 3 | YES | Level 3 | YES | 2023-07-28 | 2023-08-01 | 3 | 3 | 2023-06-22 | 2023-06-22 | 28 | 28 | 1 | 1 | 2023-06-26 | 2023-06-28 | 2023-07-18 | 5 | 5 | 14 | 14 | 2023-08-04 | 31 | 31 | 2023-08-04 | 2023-08-09 | 2023-09-22 | 2023-10-02 | 41 | 41 | 2023-10-02 | 2023-10-03 | 2 | 2 | 2023-10-27 | 2023-10-30 | 20 | 20 | 2023-10-30 | 1 | 1 | 2023-12-18 | 2023-12-18 | 2023-12-18 | 2023-12-19 | 34 | 34 | 54 | 54 | 2 | 2 | 2023-11-27 | 2023-12-13 | 2024-02-22 | 19 | 19 | 48 | 48 | 60 | 60 | [6 empty] | 2023-12-13 |  | 2024-02-22
1871 | Santa Ana | 2000 E Wilshire Ave | Santa Ana | 92705 | Orange County | 4. Preliminary Design | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-10-01 | 8 | YES | Level 3 | NO | 2023-07-17 | 2023-08-25 | 30 | 30 | 2023-06-23 | 2023-06-23 | 45 | 45 | 1 | 1 | 2023-06-26 | 2023-07-07 | 2023-07-14 | 10 | 10 | 6 | 6
1872 | 4755 E Philadelphia St | 4755 E Philadelphia St | Ontario | 91761 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO |  |  | 3585529 | 2167075 |  | 2024-12-01 | 5 | YES | Level 2 | NO |  |  |  |  | 2023-06-27 | 2023-06-27 |  |  | 1 | 1 | 2023-06-27 | 2023-06-28 | 2023-07-03 | 2 | 2 | 4 | 4 | 2023-08-16 | 36 | 36 | 2024-01-23 | 2024-01-23 | 2024-03-08 | 2024-03-01 | 136 | 136 | 2024-03-01
1873 |  | 5001 E Philadelphia St | Ontario | 91761 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO |  |  | 3583809 | 2165896 |  | 2024-12-01 | 4 | YES | Level 3 | [5 empty] | 2023-06-27 | 2023-06-27 |  |  | 1 | 1 | 2023-06-27 | 2023-06-28 | 2023-07-03 | 2 | 2 | 4 | 4 | 2023-08-14 | 34 | 34 | 2023-08-14 | 2023-08-16 | 2023-09-27 | 2023-10-05 | 38 | 38 | 2023-10-05 | 2023-12-04 | 41 | 41
1874 |  | 14245 Toyota Way | Ontario | 91761 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-07-01 |  |  |  | YES |  |  |  |  | 2023-06-27 | 2023-06-27 |  |  | 1 | 1 | 2023-06-27 | 2023-07-06 | 2023-07-08 | 7 | 7 | 2 | 2
1875 | 9714 Van Buren Boulevard | 9714 Van Buren Boulevard | Riverside | 92345 | Riverside County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-01 | 24 | [7 empty] | 2023-06-26 | 2023-06-27 |  |  | 2 | 2 | 2023-06-29 |  | 2023-07-18
1878 | Pomona | 2420 S Reservoir St | Pomona | 91766 | Los Angeles County | 4. Preliminary Design | 26 - Covina | Metro East | Pomona | [9 empty] | YES |  |  |  |  | 2023-06-29 | 2023-06-29 |  |  | 1 | 1 | 2023-07-05 | 2023-07-06 | 2023-07-20 | 5 | 5 | 11 | 11
1879 | Jamboree Road | 13672 Jamboree Road | Irvine | 92602 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback |  |  | 3659254 | 2223607 |  | 2024-10-11 | 6 | YES | Level 3 | YES | 2023-11-20 | 2024-01-02 | 28 | 28 | 2023-06-30 | 2023-07-05 | 125 | 125 | 3 | 3 | 2023-07-05 | 2023-07-11 | 2023-07-14 | 5 | 5 | 4 | 4 | 2024-01-03 | 128 | 128 | 2024-01-08 | 2024-01-10 | 2024-02-21 | 2024-02-21 | 34 | 34 | 2024-02-21
1881 | Beverly Hills Hub | 8567 Wilshire Blvd | Beverly Hills | 90211 | Los Angeles County | 4. Preliminary Design | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-01-22 |  | YES |  | YES |  |  |  |  | 2023-06-30 | 2023-06-30 |  |  | 1 | 1 | 2023-07-05 | 2023-07-11 | 2023-07-15 | 7 | 7 | 4 | 4
1882 | Rove Palm Desert | 73320 Dinah Shore Dr. | Palm Desert | 92211 | Riverside County | 2. Engineering | 79 - Palm Springs | Desert | SBRO |  |  | 3674336 |  |  | 2024-12-01 | 40 |  | Level 3 | YES | 2023-09-19 | 2023-10-27 | 29 | 29 | 2023-07-03 | 2023-07-03 | 83 | 83 | 1 | 1 | 2023-07-06 | 2023-07-17 | 2023-07-24 | 10 | 10 | 6 | 6 |  |  |  | 2024-02-06 | 2024-02-10 | 2024-03-26
1883 | Diamond Plaza | 1370 Fullerton Rd | Rowland Heights | 91748 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-05-01 | 8 | YES | Level 3 | YES | 2023-09-28 | 2023-11-01 | 25 | 25 | 2023-07-03 | 2023-07-03 | 86 | 86 | 1 | 1 | 2023-07-05 | 2023-07-06 | 2023-07-20 | 3 | 3 | 11 | 11
1884 | Arcadia Hub | 1201 S Baldwin Ave | Arcadia | 91007 | Los Angeles County | 3. Active | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2024-05-01 | 12 | YES | Level 2 | YES | 2023-09-27 | 2023-10-31 | 25 | 25 | 2023-07-03 | 2023-07-03 | 85 | 85 | 1 | 1 | 2023-07-05 | 2023-07-06 | 2023-07-20 | 3 | 3 | 11 | 11
1885 | Camarillo | 2360 Las Posa Rd | Camarillo | 93010 | Ventura County | 11. Cancelled | 39 - Ventura | North Coast | Ventura | [5 empty] | 2024-07-01 | 30 |  |  | YES |  |  |  |  | 2023-07-03 | 2023-08-21 |  |  | 35 | 35 | 2023-08-21 | 2023-08-22 | 2023-09-01 | 2 | 2 | 9 | 9
1886 | Ruby Inn Bridgeport | 333 Main St - EV | Bridgeport | 93537 | Mono County | 5. Final Design | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2024-05-26 | 4 | YES |  | YES |  |  |  |  | 2023-07-07 | 2023-07-07 |  |  | 1 | 1 | 2023-07-11 | 2023-07-13 | 2023-07-18 | 5 | 5 | 4 | 4
1887 | 2011 E Donlon St | 2100 E Donlon St | Blythe | 92225 | Riverside County | 6. Requirements (permit, easment, etc.) | 87 - Blythe | Rurals | SBRO |  |  | 3649271 | 2220118 |  | 2024-06-01 | 30 | YES | Level 3 | YES | 2023-08-21 | 2023-12-12 | 79 | 79 | 2023-07-13 | 2023-07-13 | 106 | 106 | 1 | 1 | 2023-07-19 | 2023-07-31 | 2023-08-20 | 13 | 13 | 15 | 15 | 2023-12-15 | 109 | 109 | 2023-12-13 | 2023-12-15 | 2024-01-29 | 2024-03-08 | 57 | 57 | 2024-03-08 | 2024-03-11 | 2 | 2 | 2024-03-29 | [16 empty] | 2024-03-14
1888 | 73448 1/2 Dinah Shore Drive | 73448 1/2 Dinah Shore Drive | Palm Desert | 92211 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO |  |  | 3622591 | 2212017 |  | 2024-06-01 | 22 | NO |  |  | 2023-11-29 | 2023-12-07 | 7 | 7 | 2023-07-12 | 2023-07-13 | 103 | 103 | 2 | 2 | 2023-07-13 |  | 2023-08-02 | [7 empty] | 2023-12-08 |  | 2024-01-12 | 2024-01-09 |  |  | 2024-01-22 | 2024-01-23 | 2 | 2 | 2024-02-13 | 2024-02-01 | 8 | 8 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-03-04 | 2024-02-01 |  | 1 | 1 |  |  |  |  | 2024-02-01 |  |  | 1 | 1 |  |  |  |  | 2024-03-04 | 22 | 22 | [9 empty] | 22 | 22
1889 | 691 S Sanderson Ave | 691 S Sanderson Ave | San Jacinto | 92582 | Riverside County | 6. Requirements (permit, easment, etc.) | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-11-01 |  | YES |  | NO |  |  |  |  | 2023-07-13 | 2023-07-13 |  |  | 1 | 1
1890 | 906 South Riverside Avenue Local planning is the planner | 914 South Riverside Avenue | Rialto | 92376 | San Bernardino County | 10. Customer Hold | 30 - Foothill | Desert | Saddleback |  |  | 3649346 | 2209198 | 2209197 |  | 4 | YES | Level 3 | [23 empty] | 2023-09-22 | 2023-08-29 |  |  | 2023-09-26 | 2023-10-13 | 14 | 14 | 2023-12-11 | 2024-02-28 | 93 | 93 | 2024-03-04 | 4 | 4 | 2024-03-04 |  | 2024-03-04 | 2024-03-07 | 4 | 4 | 99 | 99 | 4 | 4
1891 | Santa Fe Springs DLX1 | 11811 E Florence Ave | Santa Fe Springs | 90670 | Los Angeles County | 2. Engineering | 47 - Whittier | Metro West | Alhambra | [9 empty] | YES |  |  |  |  | 2023-07-14 | 2023-07-14 |  |  | 1 | 1 | 2023-07-19 | 2023-07-20 | 2023-08-07 | 5 | 5 | 13 | 13
1892 | Victorville DFX4 | 15272 Bear Valley Rd | Victorville | 92395 | San Bernardino County | 11. Cancelled | 73 - Victorville | Rurals | SBRO | [7 empty] | NO |  | NO | 2024-03-04 |  |  |  | 2023-07-17 | 2023-07-17 |  |  | 1 | 1 | 2023-07-19 | 2023-07-27 |  | 9 | 9
1893 | Villa Coronado Gated Community | 100 Ambazar | Irvine | 92614 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2023-09-10 | 1 |  |  | YES |  |  |  |  | 2023-07-17 | 2023-07-17 |  |  | 1 | 1 | 2023-07-19 | 2023-07-20 | 2023-07-24 | 4 | 4 | 3 | 3
1895 | Amtrak | 35 W Montecito St | Santa Barbara | 93101 | Santa Barbara County | 4. Preliminary Design | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-01-30 | 4 | YES | Level 2 | YES | 2023-07-25 | 2023-08-02 | 7 | 7 | 2023-07-17 | 2023-07-17 | 13 | 13 | 1 | 1 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 4 | 4 | 2 | 2
1896 | Eastvale | 14940 Limonite Ave | Eastvale | 91752 | Riverside County | 3. Active | 34 - Ontario | Metro East | Pomona |  |  | 3659188 | 2220195 |  | 2024-01-01 | 49 | YES | Level 3 | YES | 2023-11-17 | 2023-12-27 | 26 | 26 | 2023-07-17 | 2023-07-17 | 114 | 114 | 1 | 1 | 2023-07-19 | 2023-07-20 | 2023-07-24 | 4 | 4 | 3 | 3 | 2023-12-27 | 114 | 114 | 2024-01-08 | 2024-01-08 | 2024-02-21 | 2024-02-28 | 43 | 43 | 2024-02-29
1897 | High Noon Advisors | 14130 Bear Valley Road | Victorville | 92392 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2024-03-01 | 20 | YES | Level 3 | YES | 2023-07-31 | 2023-09-14 | 33 | 33 | 2023-07-17 | 2024-02-06 | -99 |  | 141 | 141 | 2024-02-06 | 2023-07-27 | 2023-07-30 | -133 |  | 2 | 2
1898 |  | 1590 Industrial Park Ave | Redlands | 92374 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-07-19 | 10 |  |  | YES |  |  |  |  | 2023-07-19 | 2023-07-19 |  |  | 1 | 1 | 2023-07-20 | 2023-07-25 | 2023-07-28 | 5 | 5 | 4 | 4
1899 | 3495 Walnut Ave | 3495 Walnut Ave | Chino | 91710 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-08-01 | 36 | YES | Level 3 | YES | 2023-09-26 | 2023-10-17 | 16 | 16 | 2023-07-24 | 2023-07-24 | 61 | 61 | 1 | 1 | 2023-07-25 | 2023-07-28 | 2023-08-09 | 5 | 5 | 9 | 9
1900 |  | 360 E Rialto St | San Bernardino | 92408 | San Bernardino County | 2. Engineering | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-06-25 | 108 | YES | Level 3 | YES | 2023-08-18 |  |  |  | 2023-07-25 | 2023-07-25 |  |  | 1 | 1 | 2023-08-01 | 2023-08-01 | 2023-08-18 | 6 | 6 | 14 | 14
1901 | 580 W Mill St | 580 W Mill St | San Bernardino | 92410 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-06-01 | 120 | YES | Level 3 | YES | 2023-08-14 | 2023-09-26 | 31 | 31 | 2023-07-25 | 2023-07-25 | 45 | 45 | 1 | 1 | 2023-07-25 | 2023-08-01 | 2024-01-29 | 6 | 6 | 124 | 124
1902 | 4400 N Varsity Ave., EV1 | 4400 N Varsity Ave., EV1 | San Bernardino | 92407 | San Bernardino County | 2. Engineering | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-05-29 | 12 | YES | Level 3 | YES |  | 2023-08-10 |  |  | 2024-02-12 | 2024-01-30 | -118 |  | -10 |  | 2024-02-01 | 2024-02-12 | 2024-02-12 | 10 | 10 | 1 | 1
1903 | 1675 W Lacey Blvd | 1675 W Lacey Blvd | Hanford | 93230 | Kings County | 2. Engineering | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-12-20 |  |  |  | YES | 2023-08-10 |  |  |  | 2023-07-25 | 2023-07-25 |  |  | 1 | 1 | 2023-07-26 | 2023-08-08 | 2023-08-05 | 11 | 11 | -2
1904 | 120 W Valley Blvd., EV1 | 120 W Valley Blvd., EV1 | Rialto | 92376 | San Bernardino County | 4. Preliminary Design | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-06-02 | 12 | YES |  | YES | 2023-08-31 | 2023-10-10 | 28 | 28 | 2023-07-26 | 2023-07-26 | 54 | 54 | 1 | 1 | 2023-07-27 | 2023-07-02 | 2023-08-09 | -17 |  | 27 | 27
1905 | Cosa Mesa Robins Ford | 2096 A Harbor Blvd | Costa Mesa | 92627 | Orange County | 4. Preliminary Design | 33 - Huntington Beach | Orange | Saddleback |  |  | 3669885 |  |  | 2024-06-05 | 16 | YES | Level 2 | YES | 2024-01-04 | 2024-01-24 | 14 | 14 | 2023-06-22 | 2023-06-22 | 148 | 148 | 1 | 1 | 2023-06-26 | 2023-07-05 | 2023-07-06 | 9 | 9 | 2 | 2 | 2024-01-25 | 149 | 149 | 2024-01-29 | 2024-01-31 | 2024-03-12 | 2024-02-28 | 24 | 24 | 2024-02-28
1906 | Valley Blvd - Bloomington | 18434 Valley Blvd | Bloomington | 92316 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO |  |  | 3677492 | 2239693 | 2239694 | 2025-01-01 | 217 | YES | Level 3 |  | 2023-08-09 | 2023-09-19 | 29 | 29 | 2023-07-31 | 2023-07-31 | 36 | 36 | 1 | 1 | 2023-08-01 | 2023-08-03 | 2023-08-09 | 4 | 4 | 5 | 5 | 2024-02-12 | 135 | 135 | 2024-02-13 | 2024-02-15 | 2024-03-29
1907 | Bimbo - El Segundo | 140 N Aviation Blvd | El Segundo | 90245 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-06-22 | 26 |  |  | NO |  |  |  |  | 2023-08-01 | 2023-08-01 |  |  | 1 | 1 | 2023-08-01 | 2023-08-03 | 2023-08-16 | 3 | 3 | 10 | 10
1908 | Grab N Go | 20572 Lake Forest Dr | Lake Forest | 92630 | Orange County | 11. Cancelled | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-04-01 | 4 | YES | Level 3 | [5 empty] | 2023-08-01 | 2023-08-01 |  |  | 1 | 1 | 2023-08-01 | 2023-08-04 | 2023-08-10 | 4 | 4 | 5 | 5
1909 | Newbury Park | 1714 Newbury Rd | Newbury Park | 91320 | Ventura County | 10. Customer Hold | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2023-04-01 | 4 |  |  | NO |  |  |  |  | 2023-08-01 | 2023-08-01 |  |  | 1 | 1 | 2023-08-01 | 2023-08-07 | 2023-08-12 | 5 | 5 | 5 | 5
1910 |  | 30875 Rancho Vista Rd | Temecula | 92592 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-12-01 | 16 |  |  | NO |  |  |  |  | 2023-08-01 | 2023-08-01 |  |  | 1 | 1 | 2023-08-01 | 2023-08-08 | 2023-08-28 | 6 | 6 | 15 | 15
1911 | Costa Mesa Robins Ford 2054 Site 2 | 2060B Harbor Blvd | Costa Mesa | 92627 | Orange County | 6. Requirements (permit, easment, etc.) | 33 - Huntington Beach | Orange | Saddleback |  |  | 3669851 |  |  | 2024-06-15 | 7 | YES | Level 3 | YES | 2023-07-14 | 2023-08-14 | 22 | 22 | 2023-08-01 | 2023-08-01 | 10 | 10 | 1 | 1 | 2023-08-03 | 2023-08-03 | 2023-08-09 | 3 | 3 | 5 | 5 | 2024-01-25 | 122 | 122 | 2024-01-29 | 2024-01-31 | 2024-03-12 | 2024-03-21 | 40 | 40 | 2024-03-21
1912 | Porterville - Tuleriver | 31071 Highway 190 | Porterville | 93257 | Tulare County | 6. Requirements (permit, easment, etc.) | 51 - Tulare | San Joaquin | Ventura |  |  | 3626151 | 2207443 |  | 2024-10-13 | 4 | YES | Level 3 | YES | 2023-08-16 | 2023-10-25 | 50 | 50 | 2023-08-07 | 2023-08-07 | 57 | 57 | 1 | 1 | 2023-08-07 | 2023-08-10 | 2023-08-16 | 4 | 4 | 5 | 5 | 2023-10-30 | 60 | 60 | 2023-10-30 | 2023-10-31 | 2024-01-16 | 2024-01-17 | 53 | 53 | 2024-01-17 | 2024-01-19 | 3 | 3 | 2024-02-26 | 2024-03-13 | 38 | 38 | 2024-03-13 | 1 | 1 | 2024-03-13 |  | 2024-03-13 |  | 1 | 1 |  |  |  |  | 2024-02-23 |  |  | -14
1913 | Non EV - Lounge | 4600 W Century Blvd | Inglewood | 90304 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra |  |  | 3580277 | 2181367 |  | 2024-04-09 | 0 | NO |  | YES | 2022-10-17 | 2022-10-21 | 5 | 5 | 2022-08-24 | 2022-08-24 | 42 | 42 | 1 | 1 | 2022-08-31 | 2022-09-08 | 2022-10-01 | 11 | 11 | 17 | 17 | 2023-08-07 | 241 | 241 | 2023-08-08 | 2023-08-09 | 2023-09-27 | 2023-09-27 | 37 | 37 | 2023-09-27 | 2023-10-26 | 22 | 22 | 2023-11-16 | 2024-01-24 | 60 | 60 | 2024-01-25 | 2 | 2 | 2024-01-25 | 2024-02-20 | 2024-01-25 | 2024-01-29 | 2 | 2 | 63 | 63 | 3 | 3 | 2024-03-08 |  |  | 32 | 32 |  |  |  |  | 2024-03-20 | 39 | 39 | [9 empty] | 40 | 40
1914 | 7055 Market Pl Dr | 7055 Market Pl Dr | Goleta | 93117 | Ventura County | 3. Active | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2025-04-08 |  | YES | [6 empty] | 2023-08-09 | 2023-08-09 |  |  | 1 | 1 | 2023-08-09 | 2023-08-19 | 2023-08-19 | 8 | 8 | 0
1915 | South Coast Winery Hotel | 34843 Rancho California Rd | TEMECULA | 92592 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2023-08-31 | 6 | YES | [7 empty] | 2023-07-14 |  |  |  |  | 2023-07-19 | 2023-07-27 | 2023-07-28 | 10 | 10 | 2 | 2
1916 | 1630 W Valley Blvd | 1630 W Valley Blvd | Colton | 92324 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-03-27 | [8 empty] | 2023-08-09 | 2023-08-09 |  |  | 1 | 1
1917 | 616 N New Ave | 616 N New Ave | Monterey Park | 91755 | Los Angeles County | 1. FVR | 22 - Montebello | Metro East | Pomona | [5 empty] | 2025-01-01 |  | YES | [6 empty] | 2023-08-09 | 2023-08-09 |  |  | 1 | 1 | 2023-08-10 | 2023-08-22 | 2023-08-22 | 10 | 10 | 1 | 1
1918 | 4300 Green River Rd | 4300 Green River Rd | Corona | 92880 | Riverside County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-01-01 |  | YES |  | YES |  |  |  |  | 2023-08-09 | 2023-08-09 |  |  | 1 | 1 | 2023-08-10 | 2023-08-25 | 2023-08-25 | 13 | 13 | 1 | 1
1919 | Cathedral City | 69200A E Palm Canyon Dr | Catedral City | 92234 | Riverside County | 10. Customer Hold | 79 - Palm Springs | Desert | SBRO | [6 empty] | 18 |  | Level 2 | YES |  |  |  |  | 2023-08-14 | 2023-08-14 |  |  | 1 | 1 | 2023-08-14 | 2023-08-18 | 2023-09-24 | 5 | 5 | 25 | 25
1920 | N Terminal - Phase 2 | North Terminal Warf West SP Phase 2 | Port Hueneme | 93041 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3550288 |  |  |  |  | YES | Level 3 | NO | 2023-08-03 | 2023-09-20 | 34 | 34 | 2023-05-08 | 2023-05-08 | 95 | 95 | 1 | 1 | 2023-05-09 | 2023-05-11 | 2023-05-16 | 4 | 4 | 4 | 4
1921 | Adelanto New Expressway | 11600 Air Expressway | Adelanto | 92301 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2024-04-15 | 8 | YES | Level 2 | YES |  |  |  |  | 2023-08-15 | 2023-08-15 |  |  | 1 | 1 | 2023-08-15 | 2023-08-21 | 2023-08-28 | 5 | 5 | 6 | 6
1922 | Stadium Way | 12000 Stadium Way | Adelanto | 92301 | San Bernardino County | 4. Preliminary Design | 73 - Victorville | Rurals | SBRO | [5 empty] | 2024-05-15 | 10 | YES | Level 2 | NO | 2023-12-18 |  |  |  | 2023-08-15 | 2023-08-15 |  |  | 1 | 1 | 2023-08-15 | 2023-08-21 | 2023-08-28 | 5 | 5 | 6 | 6
1923 | Bellflower | 13110 Lakewood Blvd | Bellflower | 90706 | Los Angeles County | 1. FVR | 32 - Compton | Metro West | Alhambra |  |  | 3636433 |  |  | 2024-12-01 | 4 | YES | Level 3 | YES |  |  |  |  | 2023-08-15 | 2023-08-15 |  |  | 1 | 1 | 2023-08-16 | 2023-08-21 | 2023-09-08 | 5 | 5 | 14 | 14 | 2023-11-16 | 67 | 67 | 2023-11-29 | 2023-12-13 | 2024-04-10 | 2024-03-13 | 79 | 79 | 2024-03-13
1924 | Vinfast Ventura EV | 6660 AUTO CENTER DR | Ventura | 93003 | Ventura County | 5. Final Design | 39 - Ventura | North Coast | Ventura | [6 empty] | 20 |  | Level 3 | NO |  |  |  |  | 2023-08-03 | 2023-08-14 |  |  | 8 | 8 | 2023-08-21 | 2023-08-17 | 2023-08-17 | 4 | 4 | 1 | 1
1925 | Lounge - Santa Monica | 1003 Olympic Blvd | Santa Monica | 90404 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 42 - Santa Monica | Metro West | Alhambra |  |  | 3585815 | 2183942 |  | 2024-11-29 | 0 | NO |  | YES |  |  |  |  | 2022-10-11 | 2021-11-05 |  |  | -234 |  | 2021-11-05 | 2021-11-19 | 2021-12-10 | 10 | 10 | 14 | 14 | 2023-08-16 | 215 | 215 | 2023-08-16 | 2023-08-21 | 2023-09-29 | 2023-10-04 | 35 | 35 | 2023-10-04 |  |  |  |  | 2024-03-04
1926 | Hybrid Site Signal Hill | 1800 E Willow St EV1 | Signal Hill | 90755 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2025-04-16 | 28 | YES | Level 2 | NO | 2024-03-21 |  |  |  | 2023-08-16 | 2023-08-16 |  |  | 1 | 1 | 2023-08-17 | 2023-08-22 | 2023-09-08 | 5 | 5 | 13 | 13
1927 | Artesia - 37052 | 12202 South St | Artesia | 90701 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra |  |  | 3609144 |  |  | 2025-01-05 | 4 | YES | Level 3 | YES |  |  |  |  | 2023-08-17 | 2023-08-17 |  |  | 1 | 1 | 2023-08-21 | 2023-08-22 | 2023-09-14 | 4 | 4 | 17 | 17 | 2023-10-02 | 32 | 32 | 2023-12-08 | 2023-12-20
1928 | Home Depot Thousand Oaks | 2745 Teller Road | Thousand Oaks | 91320 | Ventura County | 3. Active | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-07-01 | [8 empty] | 2023-08-18 | 2023-08-18 |  |  | 1 | 1 | 2023-08-21 | 2023-08-22 | 2023-08-26 | 3 | 3 | 4 | 4
1929 | 871 N Main St, Bishop, CA, 93514 | 871 N Main St | Bishop | 93514 | Inyo County | 3. Active | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2024-06-20 |  | YES |  | YES |  |  |  |  | 2023-08-21 | 2023-08-21 |  |  | 1 | 1 | 2023-08-22 | 2023-08-24 | 2023-09-01 | 4 | 4 | 7 | 7
1930 | Fontana | 15436 Valley Blvd | Fontana | 92335 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-04-01 | 18 | YES | Level 3 |  | 2023-08-28 | 2023-09-08 | 9 | 9 | 2023-08-22 | 2023-08-22 | 13 | 13 | 1 | 1 | 2023-08-22 | 2023-08-23 | 2023-08-28 | 2 | 2 | 4 | 4
1931 | 3835 E Thousand Oaks Blvd | 3835 E Thousand Oaks Blvd | Thousand Oaks | 91362 | Ventura County | 3. Active | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-08-23 |  | YES |  | YES |  |  |  |  | 2023-08-22 | 2023-08-22 |  |  | 1 | 1
1932 | Mira Loma | 3777 De Forest Circle | Mira Loma | 91752 | Riverside County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-01 | 16 | YES | Level 2 | YES | 2023-09-25 | 2023-10-30 | 26 | 26 | 2023-08-22 | 2023-08-22 | 49 | 49 | 1 | 1 | 2023-08-23 | 2023-08-24 | 2023-09-19 | 3 | 3 | 18 | 18
1933 | La Puente | 14804 Valley Blvd | La Puente | 91745 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-12-01 | 4 | YES | Level 3 | YES | 2023-09-25 | 2023-10-27 | 25 | 25 | 2023-08-22 | 2023-08-23 | 47 | 47 | 2 | 2 | 2023-08-30 | 2023-09-05 | 2023-09-22 | 9 | 9 | 14 | 14
1934 | Visalia | 99 Bradham Dr | Visalia | 93291 | Tulare County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2025-03-01 | 16 | YES | Level 1 |  | 2023-09-10 | 2023-10-23 | 31 | 31 | 2023-08-23 | 2023-08-23 | 43 | 43 | 1 | 1 |  | 2023-09-09 | 2023-09-09 | 12 | 12 | 0
1935 |  | 17340 Gale Ave | City of Industry | 91708 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2023-09-01 | 6 |  |  | YES
1936 | Carson ePort | 18937 S Main St | Carson | 90248 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [6 empty] | 205 |  | Level 3 | YES |  |  |  |  | 2023-08-24 | 2023-08-24 |  |  | 1 | 1 | 2023-08-25 | 2023-08-29 |  | 4 | 4
1937 | City of Industry | 18305 E Arenth Ave | City of Industry | 91748 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-12-01 | 6 | YES | Level 3 | YES | 2023-09-15 | 2023-10-26 | 30 | 30 | 2023-08-24 | 2023-08-24 | 45 | 45 | 1 | 1 | 2023-08-25 | 2023-08-28 | 2023-09-15 | 3 | 3 | 14 | 14
1938 | Moreno Valley | 21839 Allesandro Blvd | Moreno Valley | 92553 | Riverside County | 11. Cancelled | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-04-01 | 12 | YES | Level 3 |  | 2023-09-27 | 2023-11-21 | 40 | 40 | 2023-08-24 | 2023-08-24 | 63 | 63 | 1 | 1 | 2023-08-25 | 2023-09-07 | 2023-09-26 | 10 | 10 | 14 | 14
1940 | Porsche Experience Center | 19800 S Main St | Carson | 90745 | Los Angeles County | 1. FVR | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-02-15 |  |  |  | YES |  |  |  |  | 2023-08-25 | 2023-08-25 |  |  | 1 | 1
1941 | Fountain Valley Hyundai | 10550 Talbert Ave | Fountain Valley | 92708 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-01-31 | 10 | NO |  | YES | 2023-11-14 |  |  |  | 2023-08-29 | 2023-08-29 |  |  | 1 | 1 | 2023-08-29 | 2023-08-30 | 2023-09-14 | 2 | 2 | 11 | 11
1942 | Slover Cypress | 16515 Slover Ave | Fontana | 92337 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-01 | 46 | NO |  | YES | 2024-02-13 | 2024-03-19 | 25 | 25 | 2023-08-30 | 2023-08-30 | 138 | 138 | 1 | 1 | 2023-08-31 | 2023-09-06 | 2023-09-11 | 5 | 5 | 4 | 4
1943 | Slover & Riverside Ave | 2150 S Riverside Ave | Rialto | 92376 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-01 | 35 | NO |  | YES | 2023-08-28 | 2023-11-08 | 52 | 52 | 2023-08-30 | 2023-08-30 | 50 | 50 | 1 | 1 | 2023-08-31 | 2023-09-05 | 2023-09-11 | 4 | 4 | 5 | 5
1944 | Calabash and Santa Ana | 10988 Calabash Ave - EV | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-01-15 | 35 | NO |  | YES | 2023-09-19 | 2023-11-03 | 34 | 34 | 2023-08-30 | 2023-08-30 | 47 | 47 | 1 | 1 | 2023-08-31 | 2023-09-06 | 2023-09-11 | 5 | 5 | 4 | 4
1945 | Rancho Cucamonga | Napa St & Etiwanda Ave | Rancho Cucamonga | 91739 | San Bernardino County | 11. Cancelled | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-02-01 | 46 | NO |  |  | 2023-09-19 | 2023-11-03 | 34 | 34 | 2023-08-30 | 2023-08-30 | 47 | 47 | 1 | 1 | 2023-08-31 | 2023-09-06 | 2023-09-11 | 5 | 5 | 4 | 4
1946 | Signal Hill - EV1 | 18715 S Western Ave - EV1 | Torrance | 90248 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-03-01 | 36 | [7 empty] | 2023-08-31 | 2023-08-31 |  |  | 1 | 1 | 2023-09-05 | 2023-09-06 | 2023-09-25 | 4 | 4 | 14 | 14
1947 | Signal Hill - EV2 | 18715 S Western Ave - EV2 | Torrance | 90248 | Los Angeles County | 4. Preliminary Design | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-03-01 | 66 |  |  | YES |  |  |  |  | 2023-08-31 | 2023-08-31 |  |  | 1 | 1 | 2023-09-05 | 2023-09-06 | 2023-09-25 | 4 | 4 | 14 | 14
1948 | 19700 S Figueroa St | 19700 S Figueroa St, Unit #EV | Carson | 90745 | Los Angeles County | 1. FVR | 32 - Compton | Metro West | Alhambra |  |  | 3669843 |  |  | 2024-06-01 | 14 | NO | Level 3 |  | 2023-12-19 | 2024-01-29 | 27 | 27 | 2023-09-01 | 2023-09-01 | 101 | 101 | 1 | 1 | 2023-09-05 | 2024-01-29 | 2024-01-29 | 101 | 101 | 1 | 1 | 2024-01-29 | 101 | 101 | 2024-01-29 | 2024-01-30 | 2024-03-13 | 2024-03-04 | 25 | 25 | 2024-03-04 | 2024-03-06 | 3 | 3
1949 | 3055 California Ave | 3055 California Ave EV1 | Signal Hill | 90755 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2025-06-02 | [8 empty] | 2023-09-01 | 2023-09-01 |  |  | 1 | 1 | 2023-09-05 | 2023-10-25 | 2023-10-25 | 38 | 38 | 1 | 1
1950 | Albertsons Ridgecrest | 927 S China Blvd EV | Ridgecrest | 93555 | Kern County | 4. Preliminary Design | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-08-25 | 6 | NO |  | YES |  |  |  |  | 2023-09-06 | 2023-09-06 |  |  | 1 | 1 | 2023-09-07 | 2023-09-11 | 2023-09-16 | 4 | 4 | 5 | 5
1951 | Capital Hills-Holiday Inn | 901 Capital Hills Pkwy | Tehachapi | 93561 | Kern County | 1. FVR | 52 - Tehachapi | San Joaquin | Ventura |  |  | 3682249 |  |  | 2023-12-21 | 8 | NO |  | YES | 2023-12-14 | 2023-12-14 | 1 | 1 | 2023-09-06 | 2023-09-06 | 70 | 70 | 1 | 1 | 2023-09-07 | 2023-09-12 | 2023-09-22 | 5 | 5 | 9 | 9 | 2023-12-14 | 70 | 70 | 2024-02-22 | 2024-02-22 | 2024-04-08
1952 | 19800 S Main Street | 19800 S Main Street | Carson | 90745 | Los Angeles County | 2. Engineering | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-02-15 | 28 | YES | Level 3 | YES |  |  |  |  | 2023-09-06 | 2023-09-06 |  |  | 1 | 1 | 2023-09-07 | 2023-09-29 | 2023-09-29 | 18 | 18 | 1 | 1
1953 | Marriott Ontario Hotels - 2200 E Holt Blvd | 2200 E Holt Blvd | Ontario | 91761 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2023-12-01 | 17 |  |  | YES | 2023-11-15 | 2023-12-27 | 28 | 28 | 2023-08-11 | 2023-09-07 | 77 | 77 | 19 | 19 | 2023-09-11 | 2023-09-12 | 2023-09-26 | 4 | 4 | 11 | 11
1954 | 16701 Trojan Way | 16701 Trojan Way | La Mirada | 90638 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-06-01 | 82 | NO |  | NO | 2024-01-29 |  |  |  | 2023-09-06 | 2023-09-06 |  |  | 1 | 1 | 2023-09-07 | 2023-09-19 | 2023-09-19 | 10 | 10 | 1 | 1
1955 | 300 S Highway 173 | 300 S Highway 173 | Lake Arrowhead | 92352 | Orange County | 4. Preliminary Design | 40 - Arrowhead | Desert | SBRO | [5 empty] | 2024-09-30 |  | YES | Level 2 | YES |  |  |  |  | 2023-09-06 | 2023-09-06 |  |  | 1 | 1 | 2023-09-07 | 2023-09-26 | 2023-09-26 | 15 | 15 | 1 | 1
1956 | 14600 Proctor Avenue | 14600 Proctor Avenue | City of Industry | 91746 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona |  |  | 3688987 |  |  | 2024-06-01 | 82 | NO |  |  | 2024-03-04 |  |  |  | 2023-09-06 | 2023-09-06 |  |  | 1 | 1 |  | 2023-09-19 | 2023-09-19 | 10 | 10 | 1 | 1 | 2024-03-06 | 125 | 125 | 2024-03-06 | 2024-03-08 | 2024-04-19
1957 | America West Properties Inc - 9062 Adams Ave | 9062 Adams Ave | Huntington Beach | 92646 | Orange County | 1. FVR | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-01-15 | 15 | [7 empty] | 2023-08-15 | 2023-09-07 |  |  | 17 | 17 | 2023-09-11 | 2023-09-14 | 2023-09-19 | 6 | 6 | 4 | 4
1958 | Fountain Valley Costco - 17880 Newhope St | 17880 Newhope St | Fountain Valley | 92708 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-01-15 | 20 |  |  | YES |  |  |  |  | 2023-08-15 | 2023-09-07 |  |  | 17 | 17
1959 | 22500 Town Cir., EV1 | 22500 Town Cir., EV1 | Moreno Valley | 92553 | Riverside County | 1. FVR | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-08-15 | 20 | YES |  | YES | 2023-10-11 | 2023-12-18 | 47 | 47 | 2023-09-08 | 2023-09-08 | 70 | 70 | 1 | 1 | 2023-09-11 | 2023-09-14 |  | 5 | 5
1960 | 23872 Alicia Pkwy # G-A | 23872 Alicia Pkwy | Mission Viejo | 92691 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-08-01 | 16 | YES |  | YES |  |  |  |  | 2023-09-11 | 2023-09-12 |  |  | 2 | 2 | 2023-09-14 | 2023-09-20 | 2023-09-26 | 7 | 7 | 5 | 5
1961 | 21572 Plano Trabuco Rd | 21572 Plano Trabuco Rd | Trabuco Canyon | 92679 | Orange County | 2. Engineering | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-08-01 | 20 | YES |  | YES | 2023-10-04 | 2023-11-15 | 31 | 31 | 2023-09-11 | 2023-09-11 | 48 | 48 | 1 | 1 | 2023-09-14 | 2023-09-20 | 2023-09-25 | 8 | 8 | 4 | 4
1962 | 36891 Cook St, (EV1) | 36891 Cook St | Palm Desert | 92211 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-12-12 | 16 | YES | Level 2 | YES | 2024-03-05 |  |  |  | 2023-09-12 | 2023-09-12 |  |  | 1 | 1 | 2023-09-14 | 2023-09-20 | 2023-10-19 | 7 | 7 | 22 | 22
1963 | Vine at Castaic | 31783 Castaic Rd | Castaic | 91384 | Ventura County | 1. FVR | 59 - Valencia | North Valley | Ventura | [5 empty] | 2024-12-24 |  | NO |  | YES | 2024-03-20 |  |  |  | 2023-09-13 | 2023-09-13 |  |  | 1 | 1 | 2023-09-14 | 2023-09-18 | 2023-09-23 | 4 | 4 | 5 | 5
1964 | 101 E Chapman Ave | 101 E Chapman Ave | Orange | 92866 | Orange County | 5. Final Design | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-07-01 | 16 | YES |  | YES |  |  |  |  | 2023-09-13 | 2023-09-13 |  |  | 1 | 1 | 2023-09-14 | 2023-09-21 | 2023-09-27 | 7 | 7 | 5 | 5
1965 | Oxnard Grocery Outlet | 920 N Ventura Rd | Oxnard | 93030 | Ventura County | 6. Requirements (permit, easment, etc.) | 39 - Ventura | North Coast | Ventura |  |  | 3632598 | 2209080 | 2209081 | 2024-09-28 | 8 | YES | Level 2 | YES | 2023-10-12 | 2023-11-09 | 21 | 21 | 2023-09-14 | 2023-09-14 | 41 | 41 | 1 | 1 | 2023-09-18 | 2023-09-19 | 2023-09-24 | 4 | 4 | 4 | 4 | 2023-10-12 | 21 | 21 | 2023-11-09 | 2023-11-09 | 2023-12-27 | 2024-01-17 | 65 | 65 | 2024-01-17 | 2024-03-01 | 32 | 32 | 2024-03-25
1966 | 26895 Ynez Road | 26895 Ynez Road | Temecula | 92591 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar |  |  | 3696158 |  |  | 2024-01-15 | 8 | YES | Level 3 | YES | 2024-01-02 | 2024-02-13 | 30 | 30 | 2023-09-14 | 2023-09-14 | 104 | 104 | 1 | 1 | 2023-09-18 | 2023-09-21 | 2023-09-18 | 6 | 6 | -4 |  | 2024-03-19 | 128 | 128 | 2024-03-19 | 2024-03-19 | 2024-04-30
1967 | 240 S Glenn Dr | 240 S Glenn Dr | Camarillo | 93010 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura | [6 empty] | 6 | YES | Level 2 | YES | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-09-11 | 2023-09-11 | 70 | 70 | 1 | 1 | 2023-09-14 | 2023-09-18 | 2023-09-22 | 6 | 6 | 5 | 5
1968 | Blythe-13241 N. Neighbours Blvd | 13241 N. Neighbours Blvd | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Rurals | SBRO | [5 empty] | 2025-02-01 | 108 | NO |  | YES | 2023-10-17 | 2023-12-27 | 49 | 49 | 2023-09-15 | 2023-09-15 | 71 | 71 | 1 | 1 | 2023-09-18 | 2023-09-26 | 2023-10-11 | 8 | 8 | 12 | 12
1969 | 24440 Alicia Pkwy, Mission Viejo, CA 92691 | 24440 Alicia Pkwy | Mission Viejo | 92691 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-12-31 | 24 | YES | Level 3 | YES | 2023-10-11 | 2023-11-27 | 32 | 32 | 2023-09-18 | 2023-09-18 | 49 | 49 | 1 | 1 | 2023-09-25 | 2023-09-29 | 2023-10-02 | 10 | 10 | 2 | 2
1970 | 47330 Zenobia Road | 47330 Zenobia Road | Lebec | 93243 | Kern County | 3. Active | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-10-31 |  | YES | Level 3 |  | 2023-09-19 | 2023-11-09 | 38 | 38 | 2023-09-18
1971 | 2501 East Ave P, Bldg 531 | 2501 East Ave P, Bldg 531 | Palmdale | 93535 | Los Angeles County | 4. Preliminary Design | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-02-01 |  | YES |  | NO |  |  |  |  | 2023-09-18 | 2023-09-18 |  |  | 1 | 1 | 2023-09-19
1972 | 2501 East Ave P, Bldg 552 | 2501 East Ave P, Bldg 552 | Palmdale | 93535 | Los Angeles County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura |  |  | 3699560 |  |  | 2024-02-01 |  | NO | Level 2 | YES |  |  |  |  | 2023-09-18 | 2023-09-18 |  |  | 1 | 1 | 2023-09-19 | 2023-09-26 | 2023-09-29 | 7 | 7 | 4 | 4 | 2024-03-26 | 131 | 131 | 2024-03-26 | 2024-03-26 | 2024-05-09
1973 | Valley Blvd - Fontana | 16005 Valley Blvd | Fontana | 92335 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2023-12-01 | 26 | YES | Level 3 | YES | 2024-02-07 |  |  |  | 2023-09-20 | 2023-09-20 |  |  | 1 | 1 | 2023-09-20 | 2023-09-25 | 2023-09-26 | 4 | 4 | 2 | 2
1974 | 1050 E Holt Blvd | 1050 E Holt Blvd | Ontario | CA 91761 | Los Angeles County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-03-01 |  | YES | Level 3 |  | 2023-10-02 | 2023-11-14 | 32 | 32 | 2023-09-20 | 2023-09-20 | 40 | 40 | 1 | 1 | 2023-09-21 |  | 2023-09-28
1975 | 1260 W Redondo Beach Blvd | 1260 W Redondo Beach Blvd | Gardena | 90247 | Los Angeles County | 1. FVR | 44 - South Bay | Metro West | Alhambra | [7 empty] | YES | [6 empty] | 2023-09-21 | 2023-09-21 |  |  | 1 | 1 | 2023-09-22 | 2023-09-28 | 2023-10-16 | 6 | 6 | 13 | 13
1976 | 4155 Tweedy Blvd | 4155 Tweedy Blvd | South Gate | 90280 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-04-25 | 12 | [7 empty] | 2024-03-22 | 2024-03-25 |  |  | 2 | 2 | 2024-03-26
1977 | 10923 Atlantic Ave., EV1 | 10923 Atlantic Ave., EV1 | Lynwood | 90262 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-11-08 |  | YES |  | YES |  |  |  |  | 2023-09-21 | 2023-09-21 |  |  | 1 | 1 | 2023-09-22 | 2023-09-28 | 2023-10-16 | 6 | 6 | 13 | 13
1978 | Oxnard Hotel | 701 Town Center Dr | Oxnard | 93036 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura |  |  | 3622855 | 2209827 |  | 2024-09-25 | 10 | NO |  | NO | 2023-11-14 |  |  |  | 2023-09-21 | 2023-09-21 |  |  | 1 | 1 | 2023-09-25 | 2023-09-27 | 2023-10-01 | 5 | 5 | 3 | 3 | 2023-10-19 | 21 | 21 | 2023-10-30 | 2023-10-30 | 2023-12-14 | 2024-01-09 | 55 | 55 | 2024-01-09 | 2024-01-30 | 15 | 15 | 2024-02-21 | 2024-03-08 | 28 | 28 | 2024-03-08 | 1 | 1 | 2024-03-12 |  | 2024-03-12 |  | 3 | 3
1979 | Store 25922 South El Monte | 1533 Peck Rd | South El Monte | 91733 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona |  |  | 3650432 |  |  | 2025-03-20 | 4 | YES |  | YES |  |  |  |  | 2023-09-26 | 2023-09-26 |  |  | 1 | 1 | 2023-09-26 | 2023-09-27 | 2023-10-30 | 2 | 2 | 24 | 24 | 2023-12-12 | 54 | 54
1980 | Store 18040 Huntington Beach | 8492 Warner Ave | Huntington Beach | 92647 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback |  |  | 3649737 |  |  | 2025-01-20 | 4 | YES | Level 1 | NO |  |  |  |  | 2023-09-26 | 2023-09-26 |  |  | 1 | 1 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2 | 2 | 2 | 2 | 2023-12-12 | 54 | 54
1981 | Store 38168 Rialto | 1130 W Renaissance Pkwy | Rialto | 92376 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO |  |  | 3650346 |  |  | 2025-03-20 | 4 | YES |  | NO |  |  |  |  | 2023-09-26 | 2023-09-26 |  |  | 1 | 1 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2 | 2 | 2 | 2 | 2023-12-12 | 54 | 54
1982 | Store 43209 Temecula | 29750 Rancho California Rd | Temecula | 92591 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-03-20 | 4 | YES |  | YES |  |  |  |  | 2023-09-26 | 2023-09-26 |  |  | 1 | 1 | 2023-09-27 | 2023-10-03 |  | 6 | 6 |  |  | 2023-12-12 | 54 | 54
1983 | 73091 Country Club Dr | 73091 Country Club Dr | Palm Desert | 92260 | Riverside County | 1. FVR | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-12-20 |  |  |  | YES |  |  |  |  | 2023-09-26 | 2023-09-26 |  |  | 1 | 1 | 2023-09-28 | 2023-10-05 | 2023-11-07 | 8 | 8 | 24 | 24
1984 | 36101 Bob Hope Dr | 36101 Bob Hope Dr | Rancho Mirage | 92270 | Riverside County | 3. Active | 79 - Palm Springs | Desert | Ventura | [5 empty] | 2025-01-20 | 24 | YES |  | NO |  |  |  |  | 2023-09-26 | 2024-03-26 |  |  | 125 | 125 | 2024-03-27 | 2024-04-01 |  | 5 | 5
1985 | 610 Ilex St | 610 Ilex St | San Fernando | 91340 | Los Angeles County | 11. Cancelled | 59 - Valencia | North Valley | Ventura |  |  | 3652353 |  |  | 2024-10-18 | 7 | YES | Level 1 | [5 empty] | 2023-09-27 | 2023-09-27 |  |  | 1 | 1 | 2023-09-28 | 2023-10-02 | 2023-10-05 | 4 | 4 | 4 | 4 | 2023-12-19 | 58 | 58 | 2023-12-19 | 2023-12-19
1986 | N China Lake Blvd Shopping Center | 1110 N China Lake Blvd | Ridgecrest | 93555 | Kern County | 3. Active | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-06-18 | 6 | YES | Level 1 | YES |  |  |  |  | 2023-09-28 | 2023-09-29 |  |  | 2 | 2 | 2023-10-02 | 2023-10-12 |  | 10 | 10
1987 | Tivoli Centre | 1400 N Norma EV St | Ridgecrest | 93555 | Kern County | 3. Active | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-12-26 | 6 | YES |  |  | 2024-01-29 | 2024-03-14 | 33 | 33 | 2023-09-28 | 2023-09-29 | 114 | 114 | 2 | 2 | 2023-10-02 | 2023-10-04 | 2023-11-09 | 4 | 4 | 27 | 27
1988 | 2780 Cabot Dr | 2780 Cabot Dr | Corona | 92883 | Los Angeles County | 12. System Upgrade | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-12-16 |  | YES |  | YES |  |  |  |  | 2023-10-02 | 2023-10-02 |  |  | 1 | 1 | 2023-10-02
1989 | Stovepipe Wells Village - Death Valley | 51880 Highway 190 | Death Valley | 92328 | Inyo County | 3. Active | 86 - Ridgecrest | Rurals | Ventura | [5 empty] | 2024-02-15 | 8 | YES |  | NO | 2023-10-17 | 2023-12-22 | 47 | 47 | 2023-10-03 | 2023-10-03 | 57 | 57 | 1 | 1 | 2023-10-04 | 2023-10-09 | 2023-10-13 | 5 | 5 | 5 | 5
1990 | Non EV Solver & Riverside Ave | 2150 S Riverside Ave | Rialto | 92376 | San Bernardino County | 1. FVR | 30 - Foothill | Desert | SBRO | [7 empty] | NO |  | YES |  |  |  |  | 2023-08-30 | 2023-08-30 |  |  | 1 | 1 | 2023-08-31 | 2023-09-05 | 2023-09-11 | 4 | 4 | 5 | 5
1991 | 8775 Sunset Blvd, Phase 2 | 8775 Sunset Blvd, Phase 2 | West Hollywood | 90069 | Los Angeles County | 4. Preliminary Design | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-03-01 |  | YES |  | NO | 2023-11-17 | 2023-11-28 | 6 | 6 | 2023-10-04 | 2024-10-04 | -217 |  | 254 | 254 | 2023-10-04 |  | 2023-10-10
1992 | 4359 Lennox Blvd | 4359 Lennox Blvd | Lennox | 90304 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra |  |  | 3692650 |  |  |  | 10 | YES |  | YES |  |  |  |  | 2023-10-04 | 2023-10-05 |  |  | 2 | 2 | 2023-10-05 | 2023-10-12 | 2023-11-06 | 6 | 6 | 18 | 18 | 2024-03-13 | 110 | 110 | 2024-03-25 | 2026-03-26 | 2024-04-23
1993 | Baldwin Park OLAM 13057-13065 | 13061 Garvey Blvd | Baldwin Park | 91706 | Los Angeles County | 4. Preliminary Design | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2024-12-15 |  | NO |  | YES | 2023-10-31 | 2023-12-19 | 34 | 34 | 2023-10-06 | 2023-10-06 | 51 | 51 | 1 | 1 | 2023-10-09 | 2023-10-10 | 2023-10-31 | 3 | 3 | 16 | 16
1994 | Los Jardines Bell Gardens | 7100 Eastern Ave | Bell Gardens | 90201 | Los Angeles County | 1. FVR | 32 - Compton | Metro West | Alhambra |  |  | 3679302 |  |  | 2024-12-26 | 8 | YES | Level 2 |  | 2024-01-17 | 2024-02-14 | 21 | 21 | 2023-10-09 | 2023-10-09 | 88 | 88 | 1 | 1 | 2023-10-10 | 2023-10-17 | 2023-11-06 | 7 | 7 | 15 | 15 | 2024-01-10 | 64 | 64 | 2024-02-15 | 2024-02-16 | 2024-04-02 | 2024-03-14 | 45 | 45 | 2024-03-14
1995 | 639 S Tustin St | 639 S Tustin St | Orange | 92866 | Orange County | 6. Requirements (permit, easment, etc.) | 29 - Santa Ana | Orange | Saddleback | [9 empty] | YES |  |  |  |  | 2023-10-06 | 2023-10-06 |  |  | 1 | 1 | 2023-12-07 | 2023-12-14 | 2023-12-14 | 48 | 48 | 1 | 1
1996 | Non EV Lounge | 2015 University Drive | Compton | 90220 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra |  |  | 3615571 | 2202767 |  | 2024-06-28 | 0 | NO |  | YES | 2022-10-19 | 2022-10-25 | 5 | 5 | 2022-08-11 | 2022-08-11 | 53 | 53 | 1 | 1 | 2022-08-15 | 2022-08-18 | 2022-09-10 | 6 | 6 | 16 | 16 | 2023-10-09 | 294 | 294 | 2023-10-10 | 2023-10-11 | 2023-11-22 | 2024-01-19 | 70 | 70 | 2024-01-19 | 2024-02-06 | 13 | 13 | 2024-02-29 | 2024-03-04 | 19 | 19 | 2024-03-06 | 3 | 3 | 2024-03-06 |  | 2024-03-06 |  | 3 | 3
1997 | Phase 2 - PSPC 2570 Riverside Ave Rialto | 10940 S Riverside Ave | Rialto | 92501 | San Bernardino County | 2. Engineering | 30 - Foothill | Desert | SBRO | [7 empty] | NO |  | YES | 2023-09-08 | 2023-10-10 | 23 | 23 | 2023-03-14 | 2023-03-14 | 148 | 148 | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 3 | 3 | 2 | 2 | 2023-11-08 | 169 | 169 | 2023-11-08 | 2023-11-09
1998 | Phase 3 - PSPC 2570 Riverside Ave Rialto | 10940 S Riverside | Rialto | 92501 | San Bernardino County | 1. FVR | 30 - Foothill | Desert | SBRO | [10 empty] | 2023-10-11 |  |  |  | 2023-03-14 | 2023-03-14 |  |  | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 3 | 3 | 2 | 2
1999 | 22220 Bundy Canyon Rd | 22220 Bundy Canyon Rd | Wildomar, CA, 92595 | 92595 | Riverside County | 6. Requirements (permit, easment, etc.) | 88 - Wildomar | San Jacinto | Wildomar | [5 empty] | 2024-12-30 |  |  |  | YES |  |  |  |  | 2023-09-13 | 2023-09-13 |  |  | 1 | 1 | 2023-09-14 |  | 2023-10-11
2000 | R29 - Margarita Plaza Huntington Park | 7000 Santa Fe Ave EV | Huntington Park | 90255 | Los Angeles County | 2. Engineering | 32 - Compton | Metro West | Alhambra |  |  | 3368960 | 2196922 | 2196929 | 2025-01-10 | 6 | YES | Level 3 | YES | 2022-05-20 | 2022-05-23 | 2 | 2 | 2022-04-20 | 2022-04-20 | 24 | 24 | 1 | 1 | 2022-04-25 | 2022-05-06 | 2022-05-06 | 13 | 13 | 1 | 1 | 2023-10-11 | 375 | 375 | 2023-10-12 | 2023-10-18 | 2023-12-01 | 2023-11-27 | 32 | 32 | 2023-11-27 | 2023-12-19 | 17 | 17 | 2024-01-15 | 2024-02-09 | 36 | 36 | 2024-01-12 | -20 |  | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-13 | 1 | 1 | 38 | 38 | 3 | 3 | 2024-01-10 | 2024-01-23 |  | -22 | [11 empty] | 2024-01-23
2002 | Ridgecrest - 154 N China Lake Blvd - Phase 2 | 154 N China Lake Blvd Phase 2 | Ridgecrest | 93555 | Kern County | 1. FVR | 86 - Ridgecrest | Rurals | Ventura | [10 empty] | 2023-11-13 | 2023-12-26 | 29 | 29 | 2022-05-04 | 2022-05-04 | 416 | 416 | 1 | 1 | 2022-05-04 | 2022-05-16 | 2022-05-16 | 9 | 9 | 1 | 1
2003 | 5412 Carpinteria Ave | 5412 Carpinteria Ave | Carpinteria | 93013 | Ventura County | 10. Customer Hold | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2024-10-01 |  | YES |  | YES |  |  |  |  | 2023-10-16 | 2023-10-16 |  |  | 1 | 1 |  | 2023-11-03 | 2023-11-03 | 15 | 15 | 1 | 1
2004 | 4004 Grand Ave, EV1 | 4004 Grand Ave, EV1 | Chino | 91710 | Los Angeles County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-11-28 |  | YES |  | YES | 2023-11-17 | 2024-01-02 | 29 | 29 | 2023-10-18 | 2023-10-18 | 51 | 51 | 1 | 1 | 2023-10-24 | 2023-10-31 | 2023-10-31 | 10 | 10 | 1 | 1
2005 | 14071 Springdale St | 14071 Springdale St | Westminster | 82683 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-09-10 | 15 | YES | Level 2 | YES | 2024-01-24 | 2024-01-24 | 1 | 1 | 2023-10-19 | 2023-10-19 | 65 | 65 | 1 | 1 | 2023-10-24 | 2023-11-06 | 2023-11-06 | 13 | 13 | 1 | 1
2006 | 876 W Donlon St | 876 W Donlon St | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Rurals | SBRO | [5 empty] | 2024-09-30 | 6 | YES |  | YES |  |  |  |  | 2023-10-19 | 2023-10-19 |  |  | 1 | 1 | 2023-10-24 | 2024-01-05 | 2024-01-05 | 53 | 53 | 1 | 1
2007 | 18700 S Broadway | 18700 S Broadway | Gardena | 90248 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-03-01 | 72 | YES | Level 3 | YES | 2023-11-15 | 2023-12-06 | 14 | 14 | 2023-10-19 | 2023-10-23 | 31 | 31 | 3 | 3 | 2023-10-23 | 2023-11-14 | 2023-11-14 | 17 | 17 | 1 | 1
2008 | 1442 Edinger Ave | 1442 Edinger Ave | Tustin | 92780 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2025-03-01 | 72 | YES | Level 3 |  | 2023-11-13 | 2023-12-22 | 28 | 28 | 2023-10-19 | 2023-10-23 | 43 | 43 | 3 | 3 | 2023-10-24 | 2023-11-06 | 2023-11-06 | 11 | 11 | 1 | 1
2009 | Balboa Island | 410 South Bay Front | Balboa Island | 92662 | Orange County | 2. Engineering | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2025-01-01 | 4 |  |  | YES |  |  |  |  | 2023-10-23 | 2023-10-23 |  |  | 1 | 1 | 2023-10-24 | 2023-11-01 | 2023-11-07 | 8 | 8 | 5 | 5
2011 | 1136 E Montecito St | 1136 E Montecito St | Santa Barbara | 93101 | Santa Barbara County | 3. Active | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2024-02-28 |  |  |  |  | 2024-03-07 |  |  |  | 2023-10-25 | 2023-10-25 |  |  | 1 | 1 | 2023-10-26 | 2023-10-30 | 2023-11-03 | 4 | 4 | 5 | 5
2012 | Chase Bank - 16120 Foothill | 16120 Foothill Blvd - EV | Fontana | 92335 | San Bernardino County | 2. Engineering | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-05-02 | 6 |  |  | YES |  |  |  |  | 2023-10-25 | 2023-10-25 |  |  | 1 | 1 | 2023-10-26 | 2023-10-31 | 2023-11-03 | 5 | 5 | 4 | 4
2013 | Kohls Beaumont Parking Lot | 1479 East 2nd Street | Beaumont | 92223 | Riverside County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-09-30 | 16 | YES |  | YES | 2023-12-14 | 2024-01-19 | 24 | 24 | 2023-10-26 | 2023-10-26 | 57 | 57 | 1 | 1 | 2023-10-27 | 2023-10-31 | 2023-11-14 | 4 | 4 | 11 | 11
2014 | 47993 Morongo Trail | 47993 Morongo Trail | Cabazon | 92230 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-10-01 | 40 | YES | [6 empty] | 2023-10-27 | 2023-10-27 |  |  | 1 | 1 | 2023-10-30
2015 | 1850 S Parco Ave | 1850 S Parco Ave | Ontario | 91761 | Los Angeles County | 4. Preliminary Design | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-06-01 |  |  |  | YES | [5 empty] | 2023-10-31 |  |  |  |  | 2023-10-31
2016 | Joshua Tree | 61142 29 Palms Highway | Joshua Tree | 92252 | San Bernardino County | 3. Active | 84 - Yucca Valley | Rurals | SBRO |  |  | 3661557 | 2224744 | 2224745 | 2024-07-24 | 12 | YES | Level 2 | YES | 2023-11-27 | 2024-01-09 | 30 | 30 | 2023-11-02 | 2023-11-02 | 45 | 45 | 1 | 1 | 2023-11-06 | 2023-11-14 | 2023-11-22 | 9 | 9 | 7 | 7 | 2024-01-10 | 46 | 46 | 2024-01-11 | 2024-01-16 | 2024-02-26 | 2024-03-12 | 43 | 43
2017 | Orange - 2550 Tustin | 2550 N Tustin St | Orange | 92865 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2025-02-17 | 27 | YES |  | YES | 2024-01-24 | 2024-03-04 | 28 | 28 | 2023-11-02 | 2023-11-03 | 81 | 81 | 2 | 2 | 2023-11-06 | 2023-11-07 | 2023-11-22 | 3 | 3 | 12 | 12
2018 | N La Brea Ave Shopping Center | 250 N La Brea Ave | Inglewood | 90301 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2025-01-14 | 8 | YES | [6 empty] | 2023-11-01 | 2023-11-02 |  |  | 2 | 2 | 2023-11-06 | 2023-11-07 | 2023-11-22 | 4 | 4 | 12 | 12
2019 | Tri- City Shopping Center | 1380 Industrial Park Ave - EV | Redlands | 92374 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-12-27 | 8 | YES |  | YES |  |  |  |  | 2023-11-01 | 2023-11-02 |  |  | 2 | 2 | 2023-11-06 | 2023-11-08 | 2023-11-09 | 5 | 5 | 2 | 2
2020 | Buena Park | 7051 Valley View St | Buena Park | 90620 | Orange County | 2. Engineering | 48 - Fullerton | Orange | Saddleback | [6 empty] | 40 |  |  | YES | 2023-12-04 | 2024-01-18 | 31 | 31 | 2023-11-06 | 2023-11-06 | 49 | 49 | 1 | 1 | 2023-11-06 | 2023-11-07 | 2023-11-09 | 2 | 2 | 3 | 3
2021 | 19307 Golden Valley Rd, Kohls | 19307 Golden Valley Rd | Santa Clarita | 91387 | Los Angeles County | 3. Active | 59 - Valencia | North Coast | Ventura | [5 empty] | 2024-09-30 |  | YES |  | YES | 2023-12-12 | 2024-01-30 | 33 | 33 | 2023-11-06 | 2023-11-06 | 57 | 57 | 1 | 1 | 2023-11-08 | 2023-11-15 | 2023-11-15 | 8 | 8 | 1 | 1
2022 | 730 Woollomes Ave | 730 Woollomes Ave | Delano | 93215 | Kern County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-07-01 | 8 | YES | Level 3 | YES | 2023-12-04 | 2024-01-10 | 26 | 26 | 2023-08-24 | 2023-11-27 | 31 | 31 | 65 | 65 | 2023-11-28 | 2023-12-02 | 2023-12-02 | 5 | 5 | 0
2023 | 1320 N Lassen Street | 1320 N Lassen Street | San Bernardino | 92410 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-04-01 |  | YES | Level 2 |  | 2023-11-27 | 2023-12-01 | 5 | 5 | 2023-11-07 | 2023-11-07 | 17 | 17 | 1 | 1 | 2023-11-07 | 2023-11-08 | 2023-11-22 | 2 | 2 | 11 | 11
2024 | Newport Beach | 4023 Birch Street | Newport Beach | 92660 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-05-01 | 4 |  |  | YES |  |  |  |  | 2023-11-07 | 2023-11-07 |  |  | 1 | 1 | 2023-11-08 | 2023-11-13 | 2023-11-22 | 5 | 5 | 8 | 8
2025 | Palmdale DAX8 | 600 Technology Drive | Palmdale | 93551 | Los Angeles County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura | [6 empty] | 119 |  |  |  | 2024-01-25 | 2024-03-08 | 31 | 31 | 2023-11-08 | 2023-11-08 | 82 | 82 | 1 | 1 | 2023-11-13 | 2023-11-16 | 2023-12-04 | 7 | 7 | 11 | 11
2026 | Camarillo - DOT4 | 3175 Mission Oaks Blvd | Camarillo | 93012 | Ventura County | 2. Engineering | 39 - Ventura | North Coast | Ventura | [6 empty] | 273 |  |  | YES |  |  |  |  | 2023-11-08 | 2023-11-08 |  |  | 1 | 1 | 2023-11-13 | 2023-11-14 | 2023-11-17 | 5 | 5 | 4 | 4
2027 | Cathedral City - DJW8 | 35750 Date Palm Drive | Cathedral City | 92234 | Riverside County | 1. FVR | 79 - Palm Springs | Desert | SBRO | [6 empty] | 119 | NO |  |  | 2024-01-09 | 2024-02-23 | 32 | 32 | 2023-11-08 | 2023-11-08 | 72 | 72 | 1 | 1 | 2023-11-13 | 2023-11-16 | 2023-11-30 | 7 | 7 | 9 | 9
2028 | Beaumont, CA - Desert Lawn Drive | Desert Lawn Drive and Oak Valley Pkwy (Beaumont) | Beaumont | 92320 | Riverside County | 1. FVR | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-09-02 |  |  |  | YES |  |  |  |  | 2023-11-08 | 2023-11-08 |  |  | 1 | 1 | 2023-11-13 | 2023-11-14 |  | 5 | 5
2029 | Yucaipa, CA - Yucaipa Blvd | 31495 Yucaipa Blvd | Yucaipa | 92399 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-09-01 | 20 |  |  | YES |  |  |  |  | 2023-11-08 | 2023-11-08 |  |  | 1 | 1 | 2023-11-13 | 2023-11-14 | 2024-01-08 | 5 | 5 | 36 | 36
2030 | Mammoth Lakes | 70 Hillside Dr | Mammoth Lakes | 93546 | Mono County | 4. Preliminary Design | 85 - Bishop/Mammoth | Rurals | Ventura | [5 empty] | 2024-05-27 | 8 | YES | Level 3 | NO | 2023-12-04 | 2024-01-12 | 28 | 28 | 2023-11-13 | 2023-11-13 | 41 | 41 | 1 | 1 | 2023-11-21 | 2023-12-02 | 2023-12-02 | 13 | 13 | 0
2031 | Rialto PSPC 2570 Riverside Ave - Non EV | 10940 S Riverside Ave - Non EV | Rialto | 92501 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [6 empty] | 0 | NO |  | YES |  |  |  |  | 2023-03-14 | 2023-03-14 |  |  | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 3 | 3 | 2 | 2 | 2023-11-14 | 173 | 173 | 2023-11-14 | 2023-11-15 | 2024-04-19
2032 | 6186 Crusher Dr | 6186 Crusher Dr | Jurupa Valley | 92509 | Riverside County | 1. FVR | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-12-31 |  |  |  | YES |  |  |  |  | 2023-11-14 | 2023-11-27 |  |  | 8 | 8 | 2023-11-27 | 2023-12-18 | 2023-12-18 | 16 | 16 | 1 | 1
2033 | Palmdale Target Phase 2 | 39440 10th St W | Palmdale | 93551 | Los Angeles County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-09-30 |  | YES |  | NO | 2023-12-06 | 2023-12-22 | 13 | 13 | 2023-11-16 | 2023-11-16 | 25 | 25 | 1 | 1 | 2023-11-16 | 2023-11-20 | 2023-11-26 | 3 | 3 | 3 | 3
2034 | 4903 Torrance Blvd | 4903 Torrance Blvd | Torrance | 90503 | Los Angeles County | 1. FVR | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-12-25 | 10 | YES |  |  | 2024-03-05 |  |  |  |  | 2023-11-13 |  |  |  |  | 2023-11-16 |  | 2023-11-29
2035 | 12402 Washington Place | 12402 Washington Place | Los Angeles | 90066 | Los Angeles County | 4. Preliminary Design | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2024-12-25 |  |  |  | NO |  |  |  |  | 2023-11-15 | 2023-11-18 |  |  | 3 | 3 | 2023-11-27 | 2023-12-05 | 2023-12-05 | 10 | 10 | 1 | 1
2036 | 134 N Mill St | 134 N Mill St | Santa Paula | 93601 | Ventura County | 2. Engineering | 39 - Ventura | North Coast | Ventura |  |  | 3689354 |  |  | 2024-09-30 | 4 | YES |  | YES |  |  |  |  | 2023-11-15 | 2023-11-16 |  |  | 2 | 2 | 2023-11-22 | 2023-12-02 | 2023-12-02 | 10 | 10 | 0 |  | 2024-03-06 | 75 | 75 | 2024-03-06 | 2024-03-07 | 2024-04-22
2037 | 6237 Pats Ranch Rd | 6237 Pats Ranch Rd, EV1 | Jurupa Valley | 91752 | Riverside County | 1. FVR | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-09-05 | 16 | YES | Level 3 | YES | 2024-01-11 |  |  |  | 2023-10-27 | 2023-10-27 |  |  | 1 | 1 | 2023-11-01 | 2023-11-01 | 2024-01-03 | 4 | 4 | 42 | 42
2038 | 12989 Park Plaza Dr, Cerritos, CA 90703 | 12989 Park Plaza Dr | Cerritos | 90703 | Los Angeles County | 2. Engineering | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-12-20 | 20 | YES |  | YES |  |  |  |  | 2023-11-16 | 2023-11-16 |  |  | 1 | 1 | 2023-11-20 | 2023-11-27 | 2023-12-06 | 6 | 6 | 8 | 8
2039 | 31884 Castaic Rd | 31884 Castaic Rd | Castaic | 91384 | Los Angeles County | 3. Active | 59 - Valencia | North Coast | Ventura | [5 empty] | 2024-12-20 | 32 | NO | Level 3 | YES | 2024-03-26 |  |  |  | 2023-11-20 | 2024-01-23 |  |  | 42 | 42 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 10 | 10 | 1 | 1
2040 | 1670 Devore Rd. San Bernardino, CA 92407 | 1670 Devore Rd. San Bernardino, CA 92407 | San Bernardino | 92407 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-06-30 | 40 | YES | [6 empty] | 2023-11-21 | 2023-11-21 |  |  | 1 | 1 | 2023-11-22 | 2023-11-27 | 2023-12-18 | 3 | 3 | 16 | 16
2041 | 18745 Conard Ave | 18745 Conard Ave | Lake Elsinore | 92532 | Riverside County | 2. Engineering | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-01-01 |  |  |  | YES | [5 empty] | 2023-11-27 |  |  |  |  | 2023-11-28 | 2023-12-18 | 2023-12-18 | 16 | 16 | 1 | 1
2042 | 1660 E Eucalyptus Ave | 1660 E Eucalyptus Ave | Ontario | 91762 | Los Angeles County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2025-06-30 | 108 | YES |  | YES | 2023-12-21 |  |  |  | 2023-11-07 | 2023-11-28 |  |  | 14 | 14 | 2023-11-29 | 2023-12-12 | 2023-12-12 | 11 | 11 | 1 | 1
2043 | Long Beach | 6346 E Pacific Coast Hwy - EV | Long Beach | 90803 | Los Angeles County | 3. Active | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-11-14 | 16 | YES | Level 2 | YES | 2024-01-08 | 2024-02-20 | 30 | 30 | 2023-11-30 | 2023-12-04 | 53 | 53 | 3 | 3 | 2023-12-04 | 2023-12-13 | 2023-12-22 | 8 | 8 | 8 | 8
2044 | Palm Springs | 2901 N Palm Canyon Dr | Palm Springs | 92262 | Riverside County | 11. Cancelled | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2024-02-20 | 16 |  |  | YES |  |  |  |  | 2023-11-30 | 2023-11-30 |  |  | 1 | 1 | 2023-11-30 | 2023-12-06 | 2024-01-10 | 5 | 5 | 24 | 24
2045 | Carson - Perry St MS2 | 21611 S Perry St | Carson | 90745 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2024-07-01 |  | YES |  |  | 2023-11-30 |  |  |  | 2023-10-12 | 2023-10-12 |  |  | 1 | 1 | 2023-10-16 | 2023-10-18 | 2023-11-02 | 5 | 5 | 12 | 12
2046 | Inglewood - Ralphs Centinela | 950 N La Brea Ave - EV | Inglewood | 90302 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2025-03-28 | 8 | YES | [6 empty] | 2023-11-30 | 2023-11-30 |  |  | 1 | 1 | 2023-12-04 | 2023-12-13 | 2023-12-21 | 10 | 10 | 7 | 7
2047 | Ken Garff Auto - Cathedral City | 68-025 Kyle Rd | Cathedral City | 92234 | Riverside County | 1. FVR | 79 - Palm Springs | Desert | SBRO | [6 empty] | 4 | [7 empty] | 2023-12-04 | 2023-12-04 |  |  | 1 | 1 | 2023-12-05 | 2023-12-07 | 2024-01-17 | 4 | 4 | 27 | 27
2048 | Prologis Mira Loma (11905 Landon Dr) | 11905 Landon Dr | Mira Loma | 91752 | Los Angeles County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-08-30 |  |  |  | YES | [5 empty] | 2023-12-05 |  |  |  |  | 2023-12-06 | 2023-12-14 | 2023-12-14 | 8 | 8 | 1 | 1
2049 | 63755 Orr Way, Desert Hot Springs, CA | 63755 Orr Way | Desert Hot Springs | 92240 | Riverside County | 2. Engineering | 79 - Palm Springs | Desert | SBRO | [6 empty] | 128 | YES | Level 3 | YES | 2024-03-18 |  |  |  | 2023-11-09 | 2023-11-09 |  |  | 1 | 1 | 2023-11-13 | 2023-11-16 | 2023-12-04 | 6 | 6 | 11 | 11
2050 | 7250 Cajon Blvd | 7250 Cajon Blvd | San Bernardino | 92407 | San Bernardino County | 2. Engineering | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-05-10 | 12 | YES | Level 3 | YES | 2024-01-10 |  |  |  |  | 2023-12-04 |  |  |  |  | 2023-12-04 | 2023-12-11 | 2023-12-11 | 6 | 6 | 1 | 1
2051 | Lenwood and Agate Roads | Lenwood and Agate Roads | Lenwood | 92311 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [9 empty] | YES | 2023-12-28 | 2024-03-01 | 44 | 44 | 2023-11-16 | 2023-11-16 | 71 | 71 | 1 | 1 | 2023-11-20 | 2023-11-22 | 2023-12-25 | 5 | 5 | 21 | 21
2054 | Long Beach - Cherry Ave | 3520 Cherry Ave | Long Beach | 90807 | Los Angeles County | 10. Customer Hold | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-12-10 | 9 | [7 empty] | 2023-12-05 | 2023-12-05 |  |  | 1 | 1 | 2023-12-06 | 2023-12-13 | 2024-01-03 | 7 | 7 | 14 | 14
2055 | 11010 Santa Fe Ave | 11010 Santa Fe Ave | Lynwood | 90262 | Los Angeles County | 10. Customer Hold | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-12-15 | [9 empty] | 2023-12-06 |  |  |  |  | 2023-12-07 | 2023-12-11 |  | 4 | 4
2056 | Bear Valley Road and Hwy 395 | Bear Valley Road and Hwy 395 | Victorville | 92392 | San Bernardino County | 3. Active | 73 - Victorville | Rurals | SBRO | [5 empty] | 2025-03-31 | [9 empty] | 2023-12-06 |  |  |  |  | 2023-12-07 | 2023-12-12 |  | 5 | 5
2057 | DUR9 - Temecula | 27711 Diaz Rd | Temecula | 92590 | Riverside County | 4. Preliminary Design | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-12-12 | 216 |  |  | YES |  |  |  |  | 2023-12-11 | 2023-12-11 |  |  | 1 | 1 | 2023-12-12 | 2023-12-14 | 2024-01-10 | 4 | 4 | 18 | 18
2058 | PSPC Blythe East - Phase 2 | 2088 E Hobsonway | Blythe | 92225 | Riverside County | 4. Preliminary Design | 87 - Blythe | Rurals | SBRO |  |  | 3665136 |  |  | 2026-03-15 | 8 | NO |  | YES | 2023-08-31 | 2023-12-12 | 71 | 71 | 2023-03-23 | 2023-03-23 | 184 | 184 | 1 | 1 | 2023-03-27 | 2023-04-06 | 2023-05-09 | 11 | 11 | 24 | 24 | 2023-08-31 | 114 | 114 | 2024-01-18 | 2024-01-22 | 2024-02-12
2059 | PSPC Blythe East - Non EV | 2088 E Hobsonway | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Rurals | SBRO |  |  | 3665125 |  |  | 2025-03-15 | 0 | NO |  | YES | 2023-08-31 | 2023-12-12 | 71 | 71 | 2023-03-23 | 2023-03-23 | 184 | 184 | 1 | 1 | 2023-03-27 | 2023-04-06 | 2023-05-09 | 11 | 11 | 24 | 24 | 2023-08-21 | 106 | 106 | 2024-01-18 | 2024-01-22 | 2024-02-12
2060 | Hemet Shopping Center | 2255 E Florida Ave | Hemet | 92545 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-02-16 | 8 | YES | [6 empty] | 2023-12-12 | 2023-12-12 |  |  | 1 | 1 | 2023-12-13 | 2023-12-20 | 2024-01-16 | 7 | 7 | 17 | 17
2061 | Mission Playhouse Parking Lot | 320 S Mission Dr | San Gabriel | 91776 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona | [5 empty] | 2024-06-30 | 4 | [7 empty] | 2023-12-14 | 2023-12-14 |  |  | 1 | 1 | 2023-12-14 | 2023-12-18 | 2024-01-10 | 3 | 3 | 16 | 16
2062 | Canyon Country | 27134 Furnivall Ave | Canyon Country | 91351 | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura | [5 empty] | 2026-09-01 | 62 |  |  | YES |  |  |  |  | 2023-12-15 | 2023-12-15 |  |  | 1 | 1 | 2023-12-18 | 2023-12-19 | 2023-12-27 | 3 | 3 | 6 | 6
2063 | Westminster, CA - 14731 Goldenwest St | Westminster, CA - 14731 Goldenwest St | Westminster | 92683 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2025-03-30 | 16 | YES |  |  | 2024-01-17 | 2024-01-24 | 6 | 6 | 2023-12-08 | 2023-12-08 | 31 | 31 | 1 | 1 | 2023-12-08 | 2023-12-11 | 2023-12-18 | 2 | 2 | 6 | 6
2064 | Lowes Corona | 1285 Magnolia Ave EV | Corona | 92879 | Riverside County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-12-01 | 8 | [7 empty] | 2023-12-18 | 2023-12-18 |  |  | 1 | 1 | 2023-12-19 | 2023-12-20 |  | 3 | 3
2065 | Ontario | 700 S Etiwanda Ave | Ontario | 91761 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-02-28 | 10 |  |  | YES |  |  |  |  | 2023-12-18 | 2023-12-18 |  |  | 1 | 1 | 2023-12-19 | 2023-12-20 | 2023-12-27 | 3 | 3 | 5 | 5
2066 | 27532 Sierra Hwy, EV1 | 27532 Sierra Hwy, EV1 | Santa Clarita | 91351 | Los Angeles County | 2. Engineering | 59 - Valencia | North Coast | Ventura | [5 empty] | 2025-06-27 | 16 | YES |  | YES | [5 empty] | 2023-12-18 |  |  |  |  | 2023-12-19 | 2023-12-20 | 2023-12-21 | 3 | 3 | 2 | 2
2067 | DPS5 - Santa Clarita | 28820 Chase Place | Santa Clarita | 91355 | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura | [5 empty] | 2024-09-02 | 297 |  |  | YES | 2024-02-29 |  |  |  | 2023-12-19 | 2023-12-19 |  |  | 1 | 1 | 2023-12-19 | 2023-12-20 | 2023-12-22 | 2 | 2 | 3 | 3
2068 | DLX8- Santa Ana | 515 E Dyer Road | Santa Ana | 92707 | Orange County | 2. Engineering | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-09-02 | 276 |  |  | YES |  |  |  |  | 2023-12-19 | 2023-12-19 |  |  | 1 | 1 | 2023-12-19 | 2023-12-20 | 2023-12-28 | 2 | 2 | 6 | 6
2069 | DFX9- Huntington Beach | 14952 Bolsa Chica St | Huntington Beach | 92647 | Orange County | 2. Engineering | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-09-20 | 287 |  |  | YES | 2024-02-29 |  |  |  | 2023-12-19 | 2023-12-19 |  |  | 1 | 1 | 2023-12-19 | 2023-12-20 | 2023-12-29 | 2 | 2 | 7 | 7
2070 | DDO6 - Torrance | 2751 Skypark Dr | Torrance | 90505 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-09-02 | 226 |  |  | NO |  |  |  |  | 2023-12-19 | 2023-12-19 |  |  | 1 | 1 | 2023-12-19 | 2023-12-21 | 2024-01-16 | 3 | 3 | 16 | 16
2071 | 2400 Elden Avenue | 2400 Elden Avenue | Costa Mesa | 92627 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2024-07-01 | 2 | YES | Level 1 | YES | [5 empty] | 2023-12-19 |  |  |  |  | 2023-12-20 | 2023-12-29 | 2023-12-29 | 8 | 8 | 1 | 1
2072 | Tercero Torrance | 4000 Redondo Beach Blvd | Torrance | 90504 | Los Angeles County | 3. Active | 44 - South Bay | Metro West | Alhambra | [6 empty] | 8 | YES | [6 empty] | 2023-12-19 | 2023-12-19 |  |  | 1 | 1 | 2023-12-20 | 2023-12-20 | 2024-01-11 | 2 | 2 | 15 | 15
2073 | Chino Hills Costco | 13111 Peyton Dr | Chino Hills | 91709 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-09-03 | 10 | YES | [6 empty] | 2023-12-20 | 2023-12-20 |  |  | 1 | 1 | 2023-12-21 | 2023-12-26 | 2023-12-29 | 4 | 4 | 4 | 4
2074 |  | 2831 E. Coast Hwy | Corona Del Mar | 92623 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [9 empty] | NO |  |  |  |  | 2023-12-06 | 2023-12-07 |  |  | 2 | 2 | 2023-12-15 | 2023-12-15 | 2023-12-21 | 7 | 7 | 5 | 5
2075 |  | 501 Ninos Drive | Santa Barbara | 93103 | Santa Barbara County | 11. Cancelled | 49 - Santa Barbara | North Coast | Ventura | [7 empty] | YES | [6 empty] | 2023-12-21 | 2023-12-21 |  |  | 1 | 1 | 2023-12-26 | 2023-12-29 | 2023-12-29 | 6 | 6 | 1 | 1
2076 | Orangefair Marketplace - Fullerton | 246 E Orangethorpe Ave | Fullerton | 92832 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-12-31 | 16 |  |  | YES |  |  |  |  | 2023-12-21 | 2023-12-21 |  |  | 1 | 1 | 2023-12-22 | 2023-12-29 | 2023-12-29 | 6 | 6 | 1 | 1
2078 | 670 Garnet Rd | 670 Garnet Rd | Palm Springs | 92262 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2025-07-31 |  |  |  | YES | 2023-12-22 | 2024-02-27 | 44 | 44
2079 | 2601 Lincoln Blvd | 2601 Lincoln Blvd | Santa Monica | 90405 | Los Angeles County | 2. Engineering | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2024-08-31 | 32 |  |  |  | 2024-02-16 | 2024-03-19 | 22 | 22 | 2023-12-26 | 2023-12-27 | 57 | 57 | 2 | 2 | 2023-12-28 | 2024-01-02 | 2024-01-29 | 4 | 4 | 19 | 19
2080 | 4015 E Guasti Rd, Phase 3 | 4015 E Guasti Rd, Phase 3 | Ontario | 91761 | San Bernardino County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [7 empty] | YES |  | YES | 2023-12-28
2081 | 23700 Malibu Rd | 23700 Malibu Rd | Malibu | 90265 | Los Angeles County | 11. Cancelled | 35 - Thousand Oaks | North Coast | Ventura | [5 empty] | 2024-12-01 |  |  |  | YES | 2023-12-29 |  |  |  | 2024-01-09 | 2024-01-09 |  |  | 1 | 1 | 2024-01-10 | 2024-01-11 | 2024-01-19 | 3 | 3 | 6 | 6
2082 | Palm Desert | 74836 Technology Drive | Palm Desert | 92211 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2025-02-17 | 16 |  | Level 3 | YES | 2024-01-22 | 2024-03-07 | 33 | 33 | 2024-01-08 | 2024-01-08 | 42 | 42 | 1 | 1 | 2024-01-08 | 2024-01-11 | 2024-01-22 | 4 | 4 | 7 | 7
2083 | OLAM 275 E Mill Street | 265 E Mill Street | San Bernardino | 92408 | San Bernardino County | 2. Engineering | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-05-01 | 35 |  |  | YES | 2024-01-22 | 2024-03-15 | 39 | 39 | 2024-01-05 | 2024-01-08 | 48 | 48 | 2 | 2 | 2024-01-09 | 2024-01-10 | 2024-01-17 | 3 | 3 | 5 | 5
2084 | Fontana - 13866 Slover | 13866 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-11-30 | 18 |  |  |  | 2024-02-26 |  |  |  | 2024-01-09 | 2024-01-09 |  |  | 1 | 1 | 2024-01-10 | 2024-01-11 | 2024-01-15 | 3 | 3 | 2 | 2
2085 | Huntington Beach, CA - 19640 Beach Blvd | 19640 Beach Blvd | Huntington Beach | 92648 | Orange County | 2. Engineering | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2025-08-01 | 24 | [8 empty] | 2024-01-09 |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-17 | 6 | 6 | 1 | 1
2086 | Best Western Palm Desert | 74695 Highway 111 | Palm Desert | 92260 | Riverside County | 2. Engineering | 79 - Palm Springs | Desert | SBRO | [6 empty] | 6 | YES |  | YES | [5 empty] | 2024-01-09 |  |  |  |  | 2024-01-09 | 2024-02-14 | 2024-02-14 | 26 | 26 | 1 | 1
2087 | 11081 Cherry Ave | 11081 Cherry Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-07-01 | 57 | YES | Level 3 |  | 2024-01-23 |  |  |  |  | 2024-01-11 |  |  |  |  | 2024-01-12 | 2024-01-16 | 2024-01-19 | 3 | 3 | 4 | 4
2088 | 2080 Rosamond Blvd, EV-1 | 2080 Rosamond Blvd, EV-1 | Rosamond | 93560 | Kern County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2025-01-31 | 24 | YES |  | YES |  |  |  |  | 2024-01-18 | 2024-01-18 |  |  | 1 | 1 | 2024-01-23 | 2024-01-26 | 2024-01-26 | 7 | 7 | 1 | 1
2089 | 73 Frazier Mountain Park Rd, EV1 | 73 Frazier Mountain Park Rd, EV1 | Lebec | 93243 | Kern County | 3. Active | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-11-01 | 16 | YES | Level 3 |  | 2024-03-11 |  |  |  |  | 2024-01-17 |  |  |  |  | 2024-01-18 | 2024-01-22 | 2024-02-06 | 4 | 4 | 12 | 12
2090 | 49669 Gorman Post Rd | 49669 Gorman Post Rd | Gorman | 93243 | Kern County | 1. FVR | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-11-01 | 16 | YES |  | YES |  |  |  |  | 2024-01-17 | 2024-01-17 |  |  | 1 | 1 | 2024-01-18 | 2024-01-22 | 2024-01-29 | 4 | 4 | 6 | 6
2091 | Westlake Valley | 3810 Thousand Oaks Blvd | Westlake Valley | 91362 | Ventura County | 4. Preliminary Design | 35 - Thousand Oaks | North Coast | Ventura | [6 empty] | 5 |  |  | YES |  |  |  |  | 2024-01-18 | 2024-01-18 |  |  | 1 | 1 | 2024-01-29 | 2024-02-05 | 2024-02-11 | 13 | 13 | 5 | 5
2092 | Non EV - PSPC North Palm Springs Indian Canyon | 6550 N Indian Canyon Dr | Palm Springs | 92262 | Riverside County | 3. Active | 79 - Palm Springs | Desert | SBRO |  |  | 3665599 |  |  | 2024-05-15 |  | NO |  | YES | 2023-05-05 | 2023-06-16 | 30 | 30 | 2023-06-28 | 2023-06-28 | -9 |  | 1 | 1 | 2023-06-29 | 2023-07-13 | 2023-08-21 | 11 | 11 | 28 | 28 | 2024-01-19 | 141 | 141 | 2024-03-07 |  | 2024-04-04
2093 | Phase 2 - Commerce - Tanager | 2810 Tanager Ave | Commerce | 90040 | Los Angeles County | 4. Preliminary Design | 32 - Compton | Metro West | Alhambra | [9 empty] | YES | 2023-09-25 | 2023-12-04 | 49 | 49 | 2023-04-13 | 2023-04-13 | 163 | 163 | 1 | 1 | 2023-04-17 | 2023-04-26 | 2023-04-28 | 10 | 10 | 3 | 3
2094 | Non EV - Commerce - Tanager | 2810 Tanager Ave | Commerce | 90040 | Los Angeles County | 12. System Upgrade | 32 - Compton | Metro West | Alhambra |  |  | 3666526 |  |  |  | 0 |  |  | YES | 2023-09-25 | 2023-12-04 | 49 | 49 | 2023-04-13 | 2023-04-13 | 163 | 163 | 1 | 1 | 2023-04-17 | 2023-04-26 | 2023-04-28 | 10 | 10 | 3 | 3 | 2024-01-18 | 193 | 193 | 2024-01-22 | 2024-01-26 | 2024-02-26
2095 | Phase 2 - Slover Almond | 14311 Slover Ave | Fontana | 92337 | San Bernardino County | 4. Preliminary Design | 30 - Foothill | Desert | SBRO | [9 empty] | YES | 2023-09-25 | 2023-11-30 | 47 | 47 | 2023-05-26 | 2023-05-26 | 130 | 130 | 1 | 1 | 2023-05-30 | 2023-06-01 | 2023-06-06 | 4 | 4 | 4 | 4 | 2024-01-18 | 162 | 162
2096 | Non EV - Slover Almond | 14311 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO |  |  | 3667812 |  |  |  | 0 |  |  |  | 2023-09-25 | 2023-11-30 | 47 | 47 | 2023-05-26 | 2023-05-26 | 130 | 130 | 1 | 1 | 2023-05-30 | 2023-06-01 | 2023-06-06 | 4 | 4 | 4 | 4 | 2024-01-18 | 162 | 162 | 2024-01-24 | 2024-01-29 | 2024-02-22
2097 | 14895 Bear Valley Rd | 14895 Bear Valley Rd | Hesperia | 92345 | San Bernardino County | 2. Engineering | 73 - Victorville | Rurals | SBRO | [5 empty] | 2025-12-31 | 16 |  |  | YES |  |  |  |  | 2024-01-23 | 2024-01-23 |  |  | 1 | 1 | 2024-01-24 | 2024-01-24 | 2024-01-29 | 2 | 2 | 4 | 4
2098 | Carson-OLAM 21611 S Perry St | 21611 S Perry St | Carson | 90745 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-01-15 | 14 |  |  | YES | 2024-02-14 |  |  |  | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-24 | 2024-01-30 | 2024-02-13 | 5 | 5 | 11 | 11
2099 | Fontana - Slover - Oak Harbor Freight | 14235 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-07-30 | 10 |  |  | YES |  |  |  |  | 2024-01-23 | 2024-01-23 |  |  | 1 | 1 | 2024-01-24 | 2024-01-29 | 2024-02-08 | 5 | 5 | 9 | 9
2100 | San Bernardino- 711 West 2nd St | 711 West 2nd St - EV | San Bernardino | 92410 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-10-03 | 8 | YES |  | YES |  |  |  |  | 2024-01-09 | 2024-01-24 |  |  | 11 | 11 | 2024-01-25 | 2024-01-29 | 2024-02-02 | 4 | 4 | 5 | 5
2101 | Fullerton- East Mall Site | 246 E Orangethorpe Ave | Fullerton | 92832 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-12-31 | 8 |  |  | YES |  |  |  |  | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-25 | 2024-01-26 | 2024-02-09 | 3 | 3 | 11 | 11
2102 | Fullerton- North Lemon Site-Part 2 | 246 E Orangethorpe Ave | Fullerton | 92832 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-12-31 | 8 | [7 empty] | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-25 | 2024-01-26 | 2024-02-08 | 3 | 3 | 10 | 10
2103 | Lounge Non-EV service | 9150 EV4 Aviation Blvd | Inglewood | 90301 | Los Angeles County | 11. Cancelled | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-12-31 | [8 empty] | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-25 | 2024-01-31 | 2024-02-19 | 6 | 6 | 13 | 13
2104 | Studio Village Shopping Center | 11096 Jefferson Blvd - EV | Culver City | 90230 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-01-20 | 4 | YES |  | NO |  |  |  |  | 2024-01-25 | 2024-01-25 |  |  | 1 | 1 | 2024-01-26 | 2024-02-01 |  | 6 | 6
2105 | 330 W Maple Ave | 330 W Maple Ave | Monrovia | 91016 | Los Angeles County | 3. Active | 27 - Monrovia | Metro East | Pomona | [5 empty] | 2024-08-31 | 10 | YES |  | YES | [5 empty] | 2024-01-26 |  |  |  |  | 2024-01-26 | 2024-01-30 | 2024-02-12 | 3 | 3 | 10 | 10
2106 | 3697 Santa Claus Lane | 3697 Santa Claus Lane | Carpinteria | 93013 | Ventura County | 2. Engineering | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2024-12-30 | 4 | YES |  | YES |  |  |  |  | 2024-01-12 | 2024-01-25 |  |  | 9 | 9 | 2024-01-26 | 2024-02-12 | 2024-02-18 | 13 | 13 | 5 | 5
2107 | 49744 Gorman Post Rd | 49744 Gorman Post Rd | Lebec | 93243 | Kern County | 3. Active | 36 - Antelope Valley | North Valley | Ventura | [6 empty] | 16 | YES | Level 3 |  | 2024-03-21 |  |  |  | 2024-01-19 | 2024-01-19 |  |  | 1 | 1 | 2024-01-25 | 2024-01-28 | 2024-01-29 | 6 | 6 | 1 | 1
2108 | Renaissance Pkwy - Rialto | 1135 W Renaissance Pkwy EV1 | Rialto | 92376 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2024-04-01 | 2 |  |  | NO |  |  |  |  | 2024-01-26 | 2024-01-26 |  |  | 1 | 1 | 2024-01-29 | 2024-01-30 | 2024-02-08 | 3 | 3 | 8 | 8
2109 | Culver City- 10361 Jefferson | 10361 Jefferson Blvd | Culver City | 90232 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2025-01-29 | 32 | [7 empty] | 2024-01-26 | 2024-01-26 |  |  | 1 | 1 | 2024-01-29 | 2024-02-01 | 2024-02-19 | 5 | 5 | 12 | 12
2110 | Stevenson Ranch, CA - 25720 The Old Road | 25720 The Old Road | Stevenson Ranch | 91381 | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura | [5 empty] | 2025-06-02 | 12 | [7 empty] | 2024-01-22 | 2024-01-22 |  |  | 1 | 1 | 2024-01-25 | 2024-01-29 | 2024-02-09 | 6 | 6 | 10 | 10
2111 | Santa Fe Springs, CA- 10621 Carmenita Rd | 10621 Carmenita Rd | Santa Fe Springs | 90670 | Los Angeles County | 3. Active | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2025-09-21 | 12 | [7 empty] | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-24 | 2024-01-29 | 2024-02-15 | 4 | 4 | 14 | 14
2112 | Brea, CA- 1639 E. Imperial Highway EV1 | 1639 E. Imperial Highway | Brea | 92821 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2025-01-10 | 12 |  |  | YES |  |  |  |  | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-24 | 2024-01-25 | 2024-02-02 | 2 | 2 | 7 | 7
2113 | Long Beach, CA- 2600 Long Beach Blvd | 2600 Long Beach Blvd | Long Beach | 90806 | Los Angeles County | 11. Cancelled | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2025-04-18 | 12 |  |  | YES |  |  |  |  | 2024-01-24 | 2024-01-24 |  |  | 1 | 1 | 2024-01-24 | 2024-01-30 | 2024-02-19 | 5 | 5 | 14 | 14
2114 | WattEV CA7 | 10444 Citrus Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-06-30 | 15 | YES | Level 3 | YES | 2024-02-27 |  |  |  |  | 2024-01-29 |  |  |  |  | 2024-01-30
2115 | 12241 Seal Beach Blvd | 12241 Seal Beach Blvd | Seal Beach | 90740 | Orange County | 3. Active | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2025-08-31 | 10 | [8 empty] | 2024-01-30 |  |  |  |  | 2024-01-30 | 2024-02-26 | 2024-02-26 | 19 | 19 | 1 | 1
2116 | 31515 Yucaipa Blvd | 31515 Yucaipa Blvd | Yucaipa | 92399 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-11-01 | 4 | NO |  | YES | [5 empty] | 2024-01-29 |  |  |  |  | 2024-01-30 | 2024-02-27 | 2024-02-27 | 21 | 21 | 1 | 1
2117 | 325 Luis Estrada Rd | 325 Luis Estrada Rd | Beaumont | 92223 | Riverside County | 2. Engineering | 31 - Redlands | Desert | SBRO | [5 empty] | 2025-03-31 |  | NO |  | YES |  |  |  |  | 2024-01-30 | 2024-01-30 |  |  | 1 | 1 | 2024-02-01 | 2024-02-12 | 2024-02-12 | 10 | 10 | 1 | 1
2118 | 2305 Wallace Ave | 2305 Wallace Ave | Summerland | 93067 | Ventura County | 2. Engineering | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2024-12-15 | 4 | YES |  | YES | 2024-02-19 |  |  |  | 2024-01-30 | 2024-01-30 |  |  | 1 | 1 | 2024-02-12 | 2024-02-12 | 2024-02-18 | 10 | 10 | 5 | 5
2119 | WattEV CA 6 | 1173 Harley Knox Blvd | Perris |  | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-12-01 | 30 | YES | Level 3 | NO | 2024-02-20 |  |  |  | 2024-01-30 | 2024-01-30 |  |  | 1 | 1 | 2024-01-31 | 2024-02-14 | 2024-02-14 | 12 | 12 | 1 | 1
2121 | S/E corner of Bristol x I-405 | S/E corner of Bristol x I-405 | Costa Mesa | 92626 | Orange County | 3. Active | 33 - Huntington Beach | Orange | Saddleback | [6 empty] | 33 |  |  | YES |  |  |  |  | 2024-02-01 | 2024-02-02 |  |  | 2 | 2 | 2024-02-06 | 2024-02-08 | 2024-02-13 | 5 | 5 | 4 | 4
2122 | Gateway Plaza Santa Fe Springs | 10639 Carmenita Rd | Santa Fe Springs | 90670 | Los Angeles County | 2. Engineering | 47 - Whittier | Metro West | Alhambra |  |  | 3280719 |  |  | 2025-07-16 | 3 | YES |  | YES |  |  |  |  | 2024-01-23 | 2024-01-24 |  |  | 2 | 2 | 2024-01-24 | 2024-01-29 | 2024-02-15 | 4 | 4 | 14 | 14
2123 | 1550 E Katella Ave | 1550 E Katella Ave | Orange | 92867 | Orange County | 2. Engineering | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-08-25 | 8 | YES |  | YES | 2024-02-20 |  |  |  | 2024-02-05 | 2024-02-06 |  |  | 2 | 2 | 2024-02-06 | 2024-02-08 | 2024-02-16 | 3 | 3 | 7 | 7
2124 | 6631 Stephens Ranch Rd | 6631 Stephens Ranch Rd | La Verne | 91750 | Los Angeles County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-11-01 | 22 | YES |  | YES | 2024-03-05 |  |  |  | 2024-02-05 | 2024-02-06 |  |  | 2 | 2 | 2024-02-07 | 2024-02-08 | 2024-02-28 | 3 | 3 | 14 | 14
2125 | Lake Elsinore Ford | 31500 Auto Center Dr | Lake Elsinore | 92530 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-02-06 | 6 |  |  | NO |  |  |  |  | 2024-02-07 | 2024-02-07 |  |  | 1 | 1 | 2024-02-07 | 2024-02-08 | 2024-03-06 | 2 | 2 | 19 | 19
2126 | Performance Ford of West Covina | 2000 E Garvey Ave | West Covina | 91791 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2025-02-06 | 3 |  |  | NO |  |  |  |  | 2024-02-07 | 2024-02-07 |  |  | 1 | 1 | 2024-02-09 | 2024-02-12 | 2024-03-06 | 4 | 4 | 17 | 17
2127 | Carson | 23315 Main St HM | Carson | 90745 | Los Angeles County | 2. Engineering | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-02-07 | 4 |  |  | YES |  |  |  |  | 2024-02-07 | 2024-02-07 |  |  | 1 | 1 | 2024-02-08 | 2024-02-13 | 2024-03-04 | 5 | 5 | 14 | 14
2128 | Magic Mountain Six Flags | 26101 Magic Mountain Parkway | Valencia | 91355 | Los Angeles County | 1. FVR | 59 - Valencia | North Valley | Ventura | [5 empty] | 2025-02-07 | 35 |  |  | YES | 2024-02-29 |  |  |  | 2024-02-08 | 2024-02-08 |  |  | 1 | 1 | 2024-02-08 | 2024-02-13 | 2024-02-19 | 4 | 4 | 4 | 4
2129 | 4063 N Webster Ave | 4063 N Webster Ave | Perris | 92571 | Riverside County | 2. Engineering | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-03-31 |  | NO |  | YES | [5 empty] | 2024-02-09 |  |  |  |  | 2024-02-12 | 2024-02-12 | 2024-03-06 | 2 | 2 | 17 | 17
2130 | 5565 Sierra Ave | 5565 Sierra Ave | Fontana | 92336 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [5 empty] | 2025-01-31 |  |  |  | NO | 2024-03-01 |  |  |  |  | 2024-02-09 |  |  |  |  | 2024-02-12 | 2024-02-29 | 2024-02-29 | 14 | 14 | 1 | 1
2131 | Compton-Gateway Towne Center | 230 Towne Center Dr | Compton | 90220 | Los Angeles County | 3. Active | 32 - Compton | Metro West | Alhambra | [5 empty] | 2025-02-12 | 6 |  |  | NO |  |  |  |  | 2024-02-09 | 2024-02-09 |  |  | 1 | 1 | 2024-02-12 | 2024-02-14 | 2024-03-11 | 4 | 4 | 18 | 18
2132 | 67670 Carey Rd | 67670 Carey Rd | Cathedral City | 92075 | Riverside County | 2. Engineering | 79 - Palm Springs | Desert | SBRO | [9 empty] | YES | [5 empty] | 2024-02-12 |  |  |  |  | 2024-02-13 | 2024-03-13 | 2024-03-13 | 22 | 22 | 1 | 1
2133 | Bob Hope Dr | Bob Hope Dr | Cathedral City | 92234 | Riverside County | 2. Engineering | 79 - Palm Springs | Desert | SBRO | [6 empty] | 12 | YES |  | YES | 2024-03-21 |  |  |  | 2024-02-08 | 2024-02-12 |  |  | 3 | 3 | 2024-02-13 | 2024-02-15 | 2024-02-21 | 4 | 4 | 4 | 4
2134 | 401 Shoreline Dr | 401 Shoreline Dr | Santa Barbara | 93101 | Ventura County | 1. FVR | 49 - Santa Barbara | North Coast | Ventura | [5 empty] | 2024-03-31 | 4 | YES |  |  | 2024-03-07 |  |  |  |  | 2024-02-13 |  |  |  |  | 2024-02-14 | 2024-03-29 | 2024-03-05 | 33 | 33 | -19
2135 | 1900 Sycamore Canyon Rd | 1900 Sycamore Canyon Rd | San Dimas | 91773 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [5 empty] | 2024-11-01 | 12 | YES | [6 empty] | 2024-02-08 | 2024-02-14 |  |  | 5 | 5 | 2024-03-19
2136 | Gorman, CA - 49717 Ralphs Ranch Rd | 49717 Ralphs Ranch Rd | Gorman | 93243 | Los Angeles County | 2. Engineering | 36 - Antelope Valley | North Valley | Ventura | [5 empty] | 2024-11-25 | 132 | NO |  | YES |  |  |  |  | 2024-02-01 | 2024-01-19 |  |  | -10 |  | 2024-01-25 | 2024-01-25 | 2024-02-01 | 5 | 5 | 6 | 6
2137 | 20825 Currier Road | 20825 Currier Road | City of Industry | 91789 | Los Angeles County | 3. Active | 26 - Covina | Metro East | Pomona | [6 empty] | 12 |  |  | NO | [5 empty] | 2024-02-15 |  |  |  |  | 2024-02-20 | 2024-03-13 | 2024-03-13 | 19 | 19 | 1 | 1
2138 | 2637 Elden Ave | 2637 Elden Ave | Costa Mesa | 92627 | Orange County | 11. Cancelled | 33 - Huntington Beach | Orange | Saddleback | [6 empty] | 4 | YES | [6 empty] | 2024-02-16 | 2024-02-16 |  |  | 1 | 1 | 2024-02-16 | 2024-02-21 | 2024-02-21 | 3 | 3 | 1 | 1
2139 | Mountain View Ave/ Ayers Ave | 916 Mountain View Ave | Ojai | 93023 | Ventura County | 2. Engineering | 39 - Ventura | North Coast | Ventura | [9 empty] | YES |  |  |  |  | 2024-02-05 | 2024-02-05 |  |  | 1 | 1 | 2024-02-06 | 2024-02-12 | 2024-02-18 | 6 | 6 | 5 | 5
2140 | Lake Forest | 26845 Vista Terrace | Lake Forest | 92630 | Orange County | 10. Customer Hold | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-05-03 | 25 | YES |  |  | 2024-03-04 |  |  |  | 2024-02-20 | 2024-02-20 |  |  | 1 | 1 | 2024-02-20 | 2024-02-22 | 2024-02-26 | 3 | 3 | 3 | 3
2141 | Valley Blvd - Bloomington | 18434 Valley Blvd | Bloomington | 92316 | San Bernardino County | 2. Engineering | 30 - Foothill | Desert | SBRO |  |  | 3677492 |  |  |  |  | NO | Level 3 | YES | [17 empty] | 2024-02-20 |  |  | 2024-02-20 | 2024-02-20
2142 | 56 Fairbanks | 56 Fairbanks | Irvine | 92618 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-12-30 |  | YES |  | NO | 2024-03-15 |  |  |  | 2024-02-19 | 2024-02-20 |  |  | 1 | 1 | 2024-02-21 | 2024-02-21 | 2024-03-01 | 2 | 2 | 8 | 8
2143 | Knotts Berry Farm | 8039 Beach Blvd EV | Buena Park | 90620 | Orange County | 2. Engineering | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-09-01 | 20 |  |  | YES |  |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-21 | 2024-02-22 | 2024-02-26 | 2 | 2 | 3 | 3
2144 | Barstow Power Capacity | High Desert Rd & Lenwood | Barstow | 92311 | San Bernardino County | 3. Active | 72 - Barstow | Rurals | SBRO | [5 empty] | 2025-09-16 | 25 |  |  | NO | 2024-03-04 |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-21 | 2024-02-22 | 2024-02-28 | 2 | 2 | 5 | 5
2145 | Delano | 1031 Lexington Street | Delano | 93215 | Kern County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-12-31 | 12 | [7 empty] | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-22 | 2024-02-28 | 2024-03-04 | 6 | 6 | 4 | 4
2146 | Gardena - 2900 Rosecrans Avenue | 2900 West Rosecrans Avenue | Gardena | 90249 | Los Angeles County | 1. FVR | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-12-09 | 24 |  | Level 3 | YES |  |  |  |  | 2024-02-08 | 2024-02-12 |  |  | 3 | 3 | 2024-02-14 | 2024-03-11 | 2024-03-11 | 20 | 20 | 1 | 1
2147 | 550 Deep Valley Dr | 550 Deep Valley Dr | Rolling Hills Estate | 90274 | Los Angeles County | 2. Engineering | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2026-08-31 | 10 |  |  | YES |  |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-22 | 2024-02-26 | 2024-03-14 | 4 | 4 | 14 | 14
2148 | In N Out Redlands | 1301 W Lugonia Ave | Redlands | 92374 | San Bernardino County | 3. Active | 31 - Redlands | Desert | SBRO | [5 empty] | 2024-06-30 | 6 |  |  | YES | 2024-03-13 |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-22 | 2024-02-26 | 2024-02-26 | 4 | 4 | 1 | 1
2149 | Lithia Temecula Honda | 27655 Ynez Rd | Temecula | 92591 | Riverside County | 3. Active | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2024-12-30 | 12 |  |  | NO |  |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-22 | 2024-02-27 | 2024-03-21 | 5 | 5 | 18 | 18
2150 | Los Angeles | 5028 E Olympic Blvd Suite A | Los Angeles | 90022 | Los Angeles County | 3. Active | 22 - Montebello | Metro East | Pomona | [5 empty] | 2024-12-30 | 3 |  |  | YES |  |  |  |  | 2024-02-21 | 2024-02-21 |  |  | 1 | 1 | 2024-02-22 | 2024-02-27 | 2024-03-18 | 5 | 5 | 15 | 15
2151 | Lake Forest, CA - 22441 El Toro Rd | 22441 El Toro Rd | Lake Forest | 92630 | Orange County | 3. Active | 43 - Saddleback | Orange | Saddleback | [5 empty] | 2024-12-01 | 28 | YES |  | YES | 2024-03-10 |  |  |  | 2024-02-13 | 2024-02-13 |  |  | 1 | 1 | 2024-02-15 | 2024-02-19 | 2024-02-19 | 4 | 4 | 0
2152 | 20388 Harvill Ave | 20388 Harvill Ave | Perris | 92570 | San Bernardino County | 2. Engineering | 77 - Menifee | San Jacinto | Wildomar | [5 empty] | 2025-01-27 | 19 |  |  | YES | [5 empty] | 2024-02-26 |  |  |  |  | 2024-02-26 | 2024-03-13 | 2024-03-13 | 13 | 13 | 1 | 1
2153 | 13718 - 13738 Slover Ave | 13700 Slover Ave | Fontana | 92337 | San Bernardino County | 3. Active | 30 - Foothill | Desert | SBRO | [10 empty] | 2024-03-04 |  |  |  | 2024-02-25 | 2024-02-26 |  |  | 1 | 1 | 2024-02-27
2154 | Santa Monica, CA - 1933 Pico Blvd | 1933 Pico Blvd | Santa Monica | 90405 | Los Angeles County | 3. Active | 42 - Santa Monica | Metro West | Alhambra | [5 empty] | 2024-12-13 | 16 | YES | Level 3 | [5 empty] | 2024-02-12 | 2024-02-12 |  |  | 1 | 1 | 2024-02-15 | 2024-02-22 | 2024-02-22 | 8 | 8 | 1 | 1
2155 | Tustin, CA - 15071 Newport Ave | 15071 Newport Ave | Tustin | 92780 | Orange County | 2. Engineering | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-12-01 | 8 |  |  | YES |  |  |  |  | 2024-02-13 | 2024-02-13 |  |  | 1 | 1 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 3 | 3 | 2 | 2
2156 | City Hall | 401 E Chapman Ave | Placentia | 92870 | Orange County | 3. Active | 48 - Fullerton | Orange | Saddleback | [5 empty] | 2024-07-01 | 19 | YES |  |  | 2024-03-15 |  |  |  |  | 2024-02-26 |  |  |  |  | 2024-02-27 | 2024-03-05 | 2024-03-05 | 7 | 7 | 1 | 1
2157 | Tustin, CA - 2300 Park Ave | 2300 Park Ave | Tustin | 92782 | Orange County | 3. Active | 29 - Santa Ana | Orange | Saddleback | [5 empty] | 2024-12-01 | 40 | [7 empty] | 2024-02-13 | 2024-02-13 |  |  | 1 | 1 | 2024-02-15 | 2024-02-15 | 2024-02-19 | 3 | 3 | 2 | 2
2158 | 740 Ventura Blvd | 740 Ventura Blvd - EV | Camarillo | 93010 | Ventura County | 2. Engineering | 39 - Ventura | North Coast | Ventura | [9 empty] | YES
2159 | 401 Newport Center Drive EV3 | 401 Newport Center Drive EV3 | Newport Beach | 92660 | Orange County | 2. Engineering | 33 - Huntington Beach | Orange | Saddleback | [5 empty] | 2025-10-31 | 20 |  |  | YES | [5 empty] | 2024-02-28 |  |  |  |  | 2024-02-29 | 2024-03-09 | 2024-03-11 | 8 | 8 | 1 | 1
2160 | OLAM Marquardt Ave | 14930 Marquardt Ave | Santa Fe Springs | 90670 | Los Angeles County | 3. Active | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2026-01-01 | 50 |  |  |  | 2024-03-20 |  |  |  | 2024-02-27 | 2024-02-29 |  |  | 3 | 3 | 2024-03-04 | 2024-03-06 | 2024-03-20 | 5 | 5 | 11 | 11
2161 | Castaic, CA - 29607 The Old Rd, EV1 | 29607 The Old Rd, EV1 | Castaic |  | Los Angeles County | 3. Active | 59 - Valencia | North Valley | Ventura | [5 empty] | 2024-11-21 | 16 | NO | Level 3 | [5 empty] | 2024-02-29 | 2024-02-29 |  |  | 1 | 1 | 2024-03-06 | 2024-03-09 | 2024-03-11 | 7 | 7 | 1 | 1
2162 | Los Angeles, CA - 11407 S Western Ave | 11407 S Western Ave | Los Angeles | 90047 | Los Angeles County | 2. Engineering | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2024-02-28 | 20 | YES |  | YES |  |  |  |  | 2024-02-27 | 2024-02-29 |  |  | 3 | 3 | 2024-03-04 | 2024-03-20 | 2024-03-21 | 15 | 15 | 2 | 2
2163 | 1711 E Harbor Ave | 1711 E Harbor Ave | Long Beach | 94601 | Los Angeles County | 4. Preliminary Design | 46 - Long Beach | Metro West | Alhambra | [5 empty] | 2024-11-01 |  | YES |  | YES | 2024-03-25 |  |  |  |  | 2024-03-01 |  |  |  |  | 2024-03-04 | 2024-03-22 | 2024-03-22 | 16 | 16 | 1 | 1
2164 | Slover Almond - Pole Relo | 14311 Slover Ave | Fontana | 92337 | San Bernardino County | 1. FVR | 30 - Foothill | Desert | SBRO |  |  | 3667788 |  |  |  |  | NO |  |  | 2023-09-25 | 2023-11-30 | 47 | 47 | 2023-05-26 | 2023-05-26 | 130 | 130 | 1 | 1 | 2023-05-30 | 2023-06-01 | 2023-06-06 | 4 | 4 | 4 | 4 | 2024-01-18 | 162 | 162 | 2024-03-05 |  | 2024-04-22
2165 | 18715 S Western Ave | 18715 S Western Ave | Torrance | 90248 | Los Angeles County | 2. Engineering | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2025-09-01 | 40 |  |  | YES | [5 empty] | 2024-03-04 |  |  |  |  | 2024-03-05
2166 | WattEV CA11 | Carnegie St & E Vineyard Ave | Oxnard | 93036 | Ventura County | 3. Active | 39 - Ventura | North Coast | Ventura | [5 empty] | 2024-05-30 | 10 | YES | Level 3 | YES | 2024-03-14 |  |  |  | 2024-03-04 | 2024-03-05 |  |  | 2 | 2 | 2024-03-06 | 2024-03-07 | 2024-03-14 | 3 | 3 | 6 | 6
2167 | Pole Relo | 10940 S Riverside Ave | Rialto | 92501 | San Bernardino County | 1. FVR | 30 - Foothill | Desert | SBRO | [7 empty] | NO |  |  | 2023-09-08 | 2023-10-10 | 23 | 23 | 2023-03-14 | 2023-03-14 | 148 | 148 | 1 | 1 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 3 | 3 | 2 | 2 | 2023-11-08 | 169 | 169 | 2023-11-08 | 2023-11-09
2168 | Pixley, CA - 12250 Avenue 120 | 12250 Avenue 120 | Pixley | 93256 | Tulare County | 3. Active | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-12-21 | 20 |  |  | NO |  |  |  |  | 2024-02-29 | 2024-02-29 |  |  | 1 | 1 | 2024-03-07
2169 | Eastvale - Hamner Rd | 12578 Schleisman Rd | Eastvale | 91752 | Riverside County | 2. Engineering | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-09-01 | 4 |  |  | YES |  |  |  |  | 2024-03-06 | 2024-03-06 |  |  | 1 | 1 | 2024-03-07 | 2024-03-12 | 2024-03-25 | 5 | 5 | 10 | 10
2170 | 8690 E Hobsonway | 8690 E Hobsonway | Blythe | 92225 | Riverside County | 3. Active | 87 - Blythe | Desert | SBRO | [5 empty] | 2025-01-31 |  |  |  | NO | 2024-03-06
2172 | Ontario JCDR - Jeep Chrysler Dodge Ram | 1202 Auto Center Drive | Ontario | 91761 | San Bernardino County | 3. Active | 34 - Ontario | Metro East | Pomona | [5 empty] | 2024-12-06 | 8 |  |  | NO |  |  |  |  | 2024-03-11 | 2024-03-11 |  |  | 1 | 1 | 2024-03-11 | 2024-03-12 | 2024-03-25 | 2 | 2 | 10 | 10
2173 | 11142 Garey Ave. El Monte, CA. 91733 | 11142 Garey Ave | El Monte | 91733 | Los Angeles County | 6. Requirements (permit, easment, etc.) | 22 - Montebello | Metro East | Pomona | [5 empty] | 2024-07-18 | 10 | [7 empty] | 2024-03-11 | 2024-03-11 |  |  | 1 | 1 | 2024-03-11 | 2024-03-14 | 2024-03-15 | 4 | 4 | 2 | 2
2174 | Rancho Mirage - 69930 CA-111 | 69930 CA-111 | Rancho Mirage | 92270 | Riverside County | 1. FVR | 79 - Palm Springs | Desert | SBRO | [5 empty] | 2025-02-01 | 28 | YES | Level 3 | YES |  |  |  |  | 2024-02-29 | 2024-03-10 |  |  | 7 | 7 | 2024-03-18 | 2024-03-18 | 2024-03-25 | 6 | 6 | 6 | 6
2175 | 701 W Manchester Blvd | 701 W Manchester Blvd | Inglewood | 90301 | Los Angeles County | 1. FVR | 44 - South Bay | Metro West | Alhambra | [5 empty] | 2025-03-25 | 22 |  |  |  | 2024-03-12 |  |  |  |  | 2024-03-12 |  |  |  |  | 2024-03-12
2176 | Michelson Irvine | 3151 Michelson Dr | Irvine | 92612 | Orange County | 1. FVR | 43 - Saddleback | Orange | Saddleback | [6 empty] | 150 | [7 empty] | 2024-03-12 | 2024-03-12 |  |  | 1 | 1 | 2024-03-12 | 2024-03-20 |  | 7 | 7
2177 | Tulare - 621 E Prosperity Avenue | 621 E Prosperity Avenue | Tulare | 93274 | Tulare County | 1. FVR | 51 - Tulare | San Joaquin | Ventura | [5 empty] | 2024-12-21 | 16 | [7 empty] | 2024-02-29 | 2024-02-29 |  |  | 1 | 1 | 2024-03-07
2178 | 9961 Freeman Ave | 9961 Freeman Ave | Santa Fe Springs | 90670 | Los Angeles County | 1. FVR | 47 - Whittier | Metro West | Alhambra | [5 empty] | 2025-10-01 | [9 empty] | 2024-03-13 |  |  |  |  | 2024-03-14
Formulas:
Eng = IF(OR([Engineering Feasibility Request]="",[Engineering Complete]=""),"",NETWORKDAYS([Engineering Feasibility Request],[Engineering Complete],[1]Holidays!$C3:C62))
Project Received = IF([1]query!AK2="","",[1]query!AK2)
Site Visit Requested = IF([1]query!AM2="","",[1]query!AM2)
PA = IF(OR([Site Visit Requested]="",[Engineering Complete]=""),"",NETWORKDAYS([Site Visit Requested],[Engineering Complete],[1]Holidays!$C3:C52))
PA = IF(OR([Preliminary Design to Customer]="",[Preliminary Design Approved]=""),"",NETWORKDAYS([Preliminary Design to Customer],[Preliminary Design Approved],[1]Holidays!$C3:C52))
SI = IF(OR([Project Received]="",[Site Visit Requested]=""),"",NETWORKDAYS([Project Received],[Site Visit Requested],[1]Holidays!$C3:C52))
Site Visit Scheduled = IF([1]query!AN2="","",[1]query!AN2)
Site Visit Complete = IF([1]query!AO2="","",[1]query!AO2)
FVR Received = IF([1]query!AQ2="","",[1]query!AQ2)
SV = IF(OR([Site Visit Requested]="",[Site Visit Complete]=""),"",NETWORKDAYS([Site Visit Requested],[Site Visit Complete],[1]Holidays!$C3:C52))
FVR = IF(OR([Site Visit Complete]="",[FVR Received]=""),"",NETWORKDAYS([Site Visit Complete],[FVR Received],[1]Holidays!$C3:C52))
Submittal Complete = IF([1]query!AR2="","",[1]query!AR2)
S = IF(OR([Project Received]="",[Submittal Complete]=""),"",NETWORKDAYS([Project Received],[Submittal Complete],[1]Holidays!$C3:C52))
Sent to Design Hub = IF([1]query!AT2="","",[1]query!AT2)
Preliminary Planned Received = IF([1]query!AY2="","",[1]query!AY2)
P = IF(OR([Submittal Complete]="",[Preliminary Design Received]=""),"",NETWORKDAYS([Submittal Complete],[Preliminary Design Received],[1]Holidays!$C3:C52))
P = IF(OR([Permit Requested]="",[Permit Received]=""),"",NETWORKDAYS([Permit Requested],[Permit Received],[1]Holidays!$C3:C52))
F = IF(OR([Preliminary Design Approved]="",[Final Design Received]=""),"",NETWORKDAYS([Preliminary Design Approved],[Final Design Received],[1]Holidays!$C3:C52))
FC = IF(OR([Final Design Received]="",[Final Design to Customer]=""),"",NETWORKDAYS([Final Design Received],[Final Design to Customer],[1]Holidays!$C3:C52))
Invoice Sent = IF([1]query!BO2="","",[1]query!BO2)
Contract Sent = IF([1]query!BQ2="","",[1]query!BQ2)
C = IF(OR([Final Design Received]="",[Contract Sent]=""),"",NETWORKDAYS([Final Design Received],[Contract Sent],[1]Holidays!$C3:C52))
F-C = IF(OR([Preliminary Design Approved]="",[Contract Received]=""),"",NETWORKDAYS([Preliminary Design Approved],[Contract Received],[1]Holidays!$C3:C52))
SC = IF(OR([Contract Sent]="",[Contract Received]=""),"",NETWORKDAYS([Contract Sent],[Contract Received],[1]Holidays!$C3:C52))
SC = IF(OR([Submittal Complete]="",[Project Completed]=""),"",NETWORKDAYS([Submittal Complete],[Project Completed],[1]Holidays!$C3:C52))
Easement Requested = IF([1]query!BX2="","",[1]query!BX2)
Easement Sent to Property Owner = IF([1]query!BY2="","",[1]query!BY2)
Easement Executed = IF([1]query!BZ2="","",[1]query!BZ2)
ES = IF(OR([Final Design Received]="",[Easement Requested]=""),"",NETWORKDAYS([Final Design Received],[Easement Requested],[1]Holidays!$C3:C52))
ES2 = IF(OR([Easement Sent to Property Owner]="",[Easement Executed]=""),"",NETWORKDAYS([Easement Sent to Property Owner],[Easement Executed],[1]Holidays!$C3:C52))
E = IF(OR([Easement Requested]="",[Easement Executed]=""),"",NETWORKDAYS([Easement Requested],[Easement Executed],[1]Holidays!$C3:C52))
PR = IF(OR([Final Design to Customer]="",[Permit Requested]=""),"",NETWORKDAYS([Final Design to Customer],[Permit Requested],[1]Holidays!$C3:C52))
PR = IF(OR([Project Received]="",[Project Completed]=""),"",NETWORKDAYS([Project Received],[Project Completed],[1]Holidays!$C3:C52))
CR = IF(OR([Contract Sent]="",[Easement Sent to Property Owner]=""),"",IF([Contract Sent]<[Easement Sent to Property Owner],[Contract Sent],[Easement Sent to Property Owner]))
CR4 = IF(OR([CR1]="",[CR3]=""),"",NETWORKDAYS([CR1],[CR3],[1]Holidays!$C3:C52))
E-P = IF(OR([Final Design Received]="",[Permit Requested]=""),"",NETWORKDAYS([Final Design Received],[Permit Requested],[1]Holidays!$C3:C52))
CC = IF(OR([PWRD Submitted to Civil]="",[Civil Complete]=""),"",NETWORKDAYS([PWRD Submitted to Civil],[Civil Complete],[1]Holidays!$C3:C52))
CC = IF(OR([Precon Requested]="",[Final Inspection Complete]=""),"",NETWORKDAYS([Precon Requested],[Final Inspection Complete],[1]Holidays!$C3:C52))
Trench Requested = IF([1]query!CO2="","",[1]query!CO2)
PC = IF(OR([Precon Requested]="",[Precon Completed ?]=""),"",NETWORKDAYS([Precon Requested],[Precon Completed ?],[1]Holidays!$C3:C52))
Tr = IF(OR([Precon Completed ?]="",[Trench Inspection Complete]=""),"",NETWORKDAYS([Precon Completed ?],[Trench Inspection Complete],[1]Holidays!$C3:C52))
Tr = IF(OR([Trench Requested]="",[Trench Inspection Complete]=""),"",NETWORKDAYS([Trench Requested],[Trench Inspection Complete],[1]Holidays!$C3:C52))
Mn = IF(OR([Mandrel Requested]="",[Mandrel Inspection Complete]=""),"",NETWORKDAYS([Mandrel Requested],[Mandrel Inspection Complete],[1]Holidays!$C3:C52))
FI = IF(OR([Final Inspection Requested]="",[Final Inspection Complete]=""),"",NETWORKDAYS([Final Inspection Requested],[Final Inspection Complete],[1]Holidays!$C3:C52))
ReS = IF(OR([Submitted to Regional Scheduling]="",[Electrical Started]=""),"",NETWORKDAYS([Submitted to Regional Scheduling],[Electrical Started],[1]Holidays!$C3:C52))
ReC = IF(OR([Submitted to Regional Scheduling]="",[Electrical Completed]=""),"",NETWORKDAYS([Submitted to Regional Scheduling],[Electrical Completed],[1]Holidays!$C3:C52))
CL = IF(OR([Project Completed]="",[Commissioning Letter]=""),"",NETWORKDAYS([Project Completed],[Commissioning Letter],[1]Holidays!$C3:C52))
Confirmed = IF([1]query!AU3="","",[1]query!AU3)
Preliminary Design Received = IF([1]query!AZ3="","",[1]query!AZ3)
Preliminary Design to Customer = IF([1]query!BA3="","",[1]query!BA3)
Preliminary Design Approved = IF([1]query!BB3="","",[1]query!BB3)
Final Received Planned = IF([1]query!BD3="","",[1]query!BD3)
Final Design Received = IF([1]query!BE3="","",[1]query!BE3)
Final Design to Customer = IF([1]query!BF3="","",[1]query!BF3)
Payment Received = IF([1]query!BP3="","",[1]query!BP3)
Contract Received = IF([1]query!BR3="","",[1]query!BR3)
CR2 = IF(OR([Contract Received]="",[Easement Executed]=""),"",IF([Contract Received]>[Easement Executed],[Contract Received],[Easement Executed]))
PWRD Submitted to Civil = IF([1]query!CI3="","",[1]query!CI3)
Civil Started = IF([1]query!CJ3="","",[1]query!CJ3)
Civil Complete = IF([1]query!CK3="","",[1]query!CK3)
Precon Requested = IF([1]query!CN3="","",[1]query!CN3)
Mandrel Requested = IF([1]query!CP3="","",[1]query!CP3)
Precon Completed ? = IF([1]query!CQ3="","",[1]query!CQ3)
Trench Inspection Complete = IF([1]query!CR3="","",[1]query!CR3)
Mandrel Inspection Complete = IF([1]query!CS3="","",[1]query!CS3)
Final Inspection Requested = IF([1]query!CU3="","",[1]query!CU3)
Final Inspection Complete = IF([1]query!CV3="","",[1]query!CV3)
Submitted to Regional Scheduling = IF([1]query!CZ3="","",[1]query!CZ3)
Electrical Completed = IF([1]query!DB3="","",[1]query!DB3)
Project Completed = IF([1]query!DE3="","",[1]query!DE3)
Electrical Started = IF([1]query!DA7="","",[1]query!DA7)
Permit Requested = IF([1]query!CB22="","",[1]query!CB22)
CR1 = IF(OR([Permit Requested]="",[CR]=""),"",IF([Permit Requested]<[CR],[Permit Requested],[CR]))
Permit Received = IF([1]query!CC24="","",[1]query!CC24)
CR3 = IF(OR([Permit Received]="",[CR2]=""),"",IF([Permit Received]>[CR2],[Permit Received],[CR2]))
Engineering Feasibility Request = IF([1]query!T26="","",[1]query!T26)
Engineering Complete = IF([1]query!U26="","",[1]query!U26)
Customer Want Date = IF([1]query!AE115="","",[1]query!AE115)
Commissioning Letter = IF([1]query!EG625="","",[1]query!EG625)