## D.12-05-035 Report (12-2015)
SDG&E 399.20(m) Report for the Re-MAT Feed-in Tariff
December 2015
Contract Effective Date | Seller Name & Project Name | FiT PPA | Status | IOU | Contract Capacity (MW) | Average Annual Expected Generation (GWh/yr) | Technology | Vintage | Contract Term (years) | Location (city, county) | Contract Commercial Operations Date | Actual Commercial Operations Date | 6-month Regulatory Delay | Reason for Regulatory Delay | Interconnection Agreement Signed (Y/N) | Interconnection Agreement Application Completed (Y/N) | Stage in Interconnection Process | Full Buy/Sell or Excess Sales | Product Category | Full Capacity Deliverability Status, or Energy Only
2014-01-09 | Axio Power Holdings, LLC. Sun Edison - Cameron |  | Terminated | SDG&E | 2.4 | 6701 | Solar PV |  | 20 | Unincorporated Area, County of San Diego | 2015-11-30 |  |  |  | No | No | Study | Full Buy/Sell | Peaking | Energy Only
2014-03-07 | Sycamore Energy 2, LLC. |  | Operational | SDG&E | 2.25 | 13403 | Landfill Gas |  | 10 | Santee, County of San Diego | 2014-03-30 | 2014-03-30 |  |  | Yes | Yes | Completion | Full Buy/Sell | Baseload | Energy Only
2014-03-28 | OCI Solar Lakeside, LLC. |  | Terminated | SDG&E | 2 | 7033 | Solar PV |  | 20 | Lakeside, County of San Diego | 2015-09-01 |  |  |  | No | No | Study | Full Buy/Sell | Peaking | Energy Only
2014-03-28 | NLP Granger A82 |  | Operational | SDG&E | 3 | 8086 | Solar PV |  | 20 | Valley Center, County of San Diego | 2015-12-31 | 2016-09-17 |  |  | Yes | Yes | Completion | Full Buy/Sell | Peaking | FCDS
2014-06-16 | SEPV Boulevard , LLC. |  | Terminated | SDG&E | 2.9 | 8847 | Solar PV |  | 20 | Boulevard, CA | 2016-05-15 |  |  |  | No | No | Study | Full Buy/Sell | Peaking | Energy Only
2014-06-16 | NLP Valley Center Solar |  | Operational | SDG&E | 2.33 | 7090 | Solar PV |  | 20 | Valley Center, County of San Diego | 2017-07-20 | 2016-12-07 |  |  | Yes | Yes | Completion | Full Buy/Sell | Peaking | Energy Only
2015-12-22 | Pristine Sun Fund CA Llc- 2226 Marsaglia |  | Terminated | SDG&E | 0.8 | 2550 | Solar PV |  | 20 | Ramona, County of San Diego | 2017-12-22 |  |  |  | No | No | Study | Full Buy/Sell | Peaking | Energy Only
2015-12-22 | Pristine Sun Fund CA Llc- 2273 Saltus |  | Terminated | SDG&E | 1.5 | 3950 | Solar PV |  | 20 | Ramona, County of San Diego | 2017-12-22 |  |  |  | No | No | Study | Full Buy/Sell | Peaking | Energy Only

## Menus
Menus
| On-Schedule | Solar PV | Existing | 10 | Yes | Site | Yes | Yes | Study | Full Buy/Sell | Baseload | FCDS
| Delayed | Solar Thermal | New | 15 | No | Permit | No | No | Agreement | Excess Sale | Peaking | Energy Only
| Operational | Geothermal |  | 20 |  | Interconnection |  |  | Construction |  | Non-Peaking
| Terminated | Biogas |  |  |  | Transmission |  |  | Completion
Biomass
Small Hydro
Landfill Gas
Wave
Tidal
Wind